## Sheet1
ID | Name | Start | Predecessors | Summary | Outline_Number | Outline_Level | Percent_Complete | Text1_Unitname | Number1 | Actual_Start | Actual_Finish | Duration | Constraint_Type | Constraint_Date | Task_Mode | Actual_Duration
1 | E1 BUILDING |  |  | 1 | 1 | 0 | 0.000000 |  | 15555 |  |  | 7 |  |  | As Soon As Possible | 0
2 | EARTH WORK |  |  | 1 | 2 | 1 | 0.000000 |  | 15557 |  |  | 10 |  |  | As Soon As Possible | 0
3 | EARTH WORK EXCAVATION IN SOFT MURUM / SOIL | 13-01-2024 |  | 0 | 3 | 2 | 1.000000 |  | 15605 | 13-01-2024 |  | 25 | Must Start On | 09-05-2025 | As Soon As Possible | -45302
4 | EARTH WORK EXCAVATION IN HARD ROCK | 13-01-2024 |  | 0 | 3 | 2 | 1.000000 |  | 15606 | 13-01-2024 |  | 10 | Must Start On | 10-05-2025 | As Soon As Possible | -45302
5 | EARTH WORK EXCAVATION IN EXTRA HARD ROCK | 13-01-2024 |  | 0 | 3 | 2 | 1.000000 |  | 15607 | 13-01-2024 |  | 5 | Must Start On | 11-05-2025 | As Soon As Possible | -45302
6 | EARTH WORK MINI ROLLER | 23-04-2024 |  | 0 | 3 | 2 | 0.100000 |  | 15785 | 23-04-2024 |  | 1 | Must Start On | 12-05-2025 | As Soon As Possible | -45403
7 | RCC WORK |  |  | 1 | 2 | 1 | 0.000000 |  | 15608 |  |  | 0 |  |  | As Soon As Possible | 0
8 | E1 Building Indent no 757 Footing PCC M15 RMC | 13-01-2024 |  | 0 | 3 | 2 | 0.100000 |  | 15609 | 13-01-2024 |  | 0 | Must Start On | 04-01-2024 | As Soon As Possible | -45302
9 | RCC WORK Box Type W/P with Ghotai-Sft. | 13-01-2024 |  | 0 | 3 | 2 | 0.100000 |  | 15628 | 13-01-2024 |  | 0 | Must Start On | 04-01-2024 | As Soon As Possible | -45302
10 | RCC WORK Borewell water Tanker | 01-04-2024 |  | 0 | 3 | 2 | 0.100000 |  | 15762 | 01-04-2024 |  | 0 | Must Start On | 04-01-2024 | As Soon As Possible | -45381
11 | E1 BLDG RCC WORK - PODIUM SLAB EXPANSION SHEET | 15-04-2024 |  | 0 | 3 | 2 | 0.100000 |  | 15774 | 15-04-2024 |  | 0 | Must Start On | 04-01-2024 | As Soon As Possible | -45395
12 | RCC WORK SOLLING | 28-05-2024 |  | 0 | 3 | 2 | 0.100000 |  | 15943 | 28-05-2024 |  | 0 | Must Start On | 04-01-2024 | As Soon As Possible | -45438
13 | Up to Plinth |  |  | 1 | 3 | 2 | 0.000000 |  | 15964 |  |  | 0 |  |  | As Soon As Possible | 0
14 | E1 BUILDING RETAINING WALL | 13-06-2024 |  | 0 | 4 | 3 | 0.100000 |  | 16107 | 13-06-2024 |  | 0 | Must Start On | 04-01-2024 | As Soon As Possible | -45454
15 | Up to Plinth E-1 Bldg Column Lift & St.case Upto 1st | 01-04-2024 |  | 0 | 4 | 3 | 0.000000 |  | 16296 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
16 | 1st Slab & Above Coln |  |  | 1 | 3 | 2 | 0.000000 |  | 15965 |  |  | 0 |  |  | As Soon As Possible | 0
17 | UP TO 1st Slab & Above Coln Indent no 988 E1 Building column | 25-05-2024 |  | 0 | 4 | 3 | 0.100000 |  | 15968 | 25-05-2024 |  | 0 | Must Start On | 04-01-2024 | As Soon As Possible | -45435
18 | E1-Bldg 1st Slab Concrete | 25-05-2024 |  | 0 | 4 | 3 | 0.100000 |  | 15969 | 25-05-2024 |  | 0 | Must Start On | 04-01-2024 | As Soon As Possible | -45435
19 | INDENT-963/E-1 Bldg Column Lift & Staircase Upto 1st Slab | 29-05-2024 |  | 0 | 4 | 3 | 0.100000 |  | 15983 | 29-05-2024 |  | 0 | Must Start On | 04-01-2024 | As Soon As Possible | -45439
20 | UP TO 1st Slab & Above Coln E1-Bldg 1st Slab Steel Reinforce | 01-04-2024 |  | 0 | 4 | 3 | 0.100000 |  | 16112 | 01-04-2024 |  | 0 | Must Start On | 04-01-2024 | As Soon As Possible | -45381
21 | UP TO 1st Slab & Above Coln E1building 1st slab levelling by | 20-07-2024 |  | 0 | 4 | 3 | 0.000000 |  | 17236 | 20-07-2024 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45491
22 | 2nd Slab & above Coln |  |  | 1 | 3 | 2 | 0.000000 |  | 15966 |  |  | 0 |  |  | As Soon As Possible | 0
23 | E1 Building 2nd Slab & above Coln E1 2nd SLAB | 20-07-2024 |  | 0 | 4 | 3 | 0.000000 |  | 16285 | 20-07-2024 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45491
24 | 3rd Slab & Above Coln |  |  | 1 | 3 | 2 | 0.000000 |  | 15967 |  |  | 0 |  |  | As Soon As Possible | 0
25 | Up To 3rd Slab & Above Coln E1 Bldg. 3rd slab &above column | 01-09-2024 |  | 0 | 4 | 3 | 0.000000 |  | 17603 | 01-09-2024 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45534
26 | Up To 3rd Slab & Above Coln E1 bldg.3rd slab reinforcement | 01-09-2024 |  | 0 | 4 | 3 | 0.000000 |  | 17604 | 01-09-2024 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45534
27 | RCC WORK E1 BUILDING RETAINING WALL LABOUR | 15-07-2024 |  | 0 | 3 | 2 | 0.000000 |  | 17719 | 15-07-2024 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45486
28 | 4TH SLAB & ABOVE COLUMN |  |  | 1 | 3 | 2 | 0.000000 |  | 18059 |  |  | 0 |  |  | As Soon As Possible | 0
29 | 4TH SLAB & ABOVE COLUMN TYPICAL SLAB & ABOVE COLUMN | 29-10-2024 |  | 0 | 4 | 3 | 0.000000 |  | 18060 | 29-10-2024 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45592
30 | 5TH SLAB & ABOVE COL. |  |  | 1 | 3 | 2 | 0.000000 |  | 18077 |  |  | 0 |  |  | As Soon As Possible | 0
31 | E1 BLDG 5TH SLAB & ABOVE COL. TYPICAL SLAB & ABOVE COLUMN | 29-11-2024 |  | 0 | 4 | 3 | 0.000000 |  | 18078 | 29-11-2024 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45623
32 | E1 BLDG AC SLEEVE FOR WATER DRAIN | 29-11-2024 |  | 0 | 3 | 2 | 0.000000 |  | 18244 | 29-11-2024 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45623
33 | E1 BLDG |  |  | 1 | 3 | 2 | 0.000000 |  | 18249 |  |  | 0 |  |  | As Soon As Possible | 0
34 | E1 BLDG FOOTING TESTING OF CUBE AND REINFORCEMENT | 25-11-2024 |  | 0 | 4 | 3 | 0.000000 |  | 18250 | 25-11-2024 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45619
35 | E1 BLDG 1ST SLAB MT FOR CUBE AND REINFORCEMENT | 25-11-2024 |  | 0 | 4 | 3 | 0.000000 |  | 18251 | 25-11-2024 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45619
36 | E1 BLDG 2ND SLAB MATERIAL TESTING FOR CUBE AND REINFORCEM | 25-11-2024 |  | 0 | 4 | 3 | 0.000000 |  | 18252 | 25-11-2024 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45619
37 | E1 BLDG 3RD SLAB MATERIAL TESTING FOR CUBE AND REINFORCEM | 25-11-2024 |  | 0 | 4 | 3 | 0.000000 |  | 18253 | 25-11-2024 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45619
38 | E1 BLDG 4TH SLAB MATERIAL TESTING FOR CUBE AND REINFORCEM | 25-11-2024 |  | 0 | 4 | 3 | 0.000000 |  | 18254 | 25-11-2024 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45619
39 | E1 BLDG 5TH SLAB MATERIAL TESTING FOR CUBE AND REINFORCEM | 25-11-2024 |  | 0 | 4 | 3 | 0.000000 |  | 18255 | 25-11-2024 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45619
40 | E1 BLDG 6TH MATERIAL TESTING FOR CUBE AND REINFORCEM | 03-03-2025 |  | 0 | 4 | 3 | 0.000000 |  | 18256 | 03-03-2025 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45717
41 | E1 BLDG 7TH SLAB MATERIAL TESTING FOR CUBE AND REINFORCEM | 03-03-2025 |  | 0 | 4 | 3 | 0.000000 |  | 18257 | 03-03-2025 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45717
42 | E1 BLDG 8TH SLAB MATERIAL TESTING FOR CUBE AND REINFORCEM | 01-02-2025 |  | 0 | 4 | 3 | 0.000000 |  | 18258 | 01-02-2025 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45687
43 | E1 BLDG 9TH SLAB MATERIAL TESTING FOR CUBE AND REINFORCEM | 01-05-2025 |  | 0 | 4 | 3 | 0.000000 |  | 18259 | 01-05-2025 | 01-05-2025 | 1 | Must Start On | 01-04-2024 | As Soon As Possible | 1
44 | E1 BLDG 10TH SLAB MATERIAL TESTING FOR CUBE AND REINFORCEM | 01-04-2024 |  | 0 | 4 | 3 | 0.000000 |  | 18260 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
45 | E1 BLDG 11th Slab MATERIAL TESTING FOR CUBE AND REINFORCEM | 01-04-2024 |  | 0 | 4 | 3 | 0.000000 |  | 18261 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
46 | E1 BLDG 12TH SLAB MATERIAL TESTING FOR CUBE AND REINFORCEM | 01-04-2024 |  | 0 | 4 | 3 | 0.000000 |  | 18262 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
47 | E1 BLDG 13TH SLAB MATERIAL TESTING FOR CUBE AND REINFORCEM | 01-04-2024 |  | 0 | 4 | 3 | 0.000000 |  | 18263 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
48 | E1 BLDG 14th SLAB MATERIAL TESTING FOR CUBE AND REINFORCEM | 01-04-2024 |  | 0 | 4 | 3 | 0.000000 |  | 18264 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
49 | E1 BLDG OHWT AND ABV MATERIAL TESTING FOR CUBE AND REINFORCE | 01-04-2024 |  | 0 | 4 | 3 | 0.000000 |  | 18265 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
50 | E1 BLDG RCC WORK ORDER |  |  | 1 | 3 | 2 | 0.000000 |  | 18432 |  |  | 0 |  |  | As Soon As Possible | 0
51 | SAKSHI CONS. & SNEHA ENTERPRISES |  |  | 1 | 4 | 3 | 0.000000 |  | 18433 |  |  | 0 |  |  | As Soon As Possible | 0
52 | E1 BLDG RCC : PLINTH COMP - FOOTING, COL. UPTO PLINTH | 15-10-2024 |  | 0 | 5 | 4 | 0.000000 |  | 18434 | 15-10-2024 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45578
53 | E1 BLDG RCC : PLINTH COMP - PLINTH BEAM PARKING | 15-10-2024 |  | 0 | 5 | 4 | 0.000000 |  | 18435 | 15-10-2024 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45578
54 | E1 BLDG RCC : PLINTH COMP - SOLING | 15-10-2024 |  | 0 | 5 | 4 | 0.000000 |  | 18436 | 15-10-2024 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45578
55 | E1 BLDG RCC : PLINTH COMP - PCC | 15-10-2024 |  | 0 | 5 | 4 | 0.000000 |  | 18437 | 15-10-2024 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45578
56 | E1 BLDG RCC : 1ST SLAB - PARKING-SHUT.,REINF. & CAST. OF COL | 15-10-2024 |  | 0 | 5 | 4 | 0.000000 |  | 18438 | 15-10-2024 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45578
57 | E1 BLDG RCC : 1ST SLAB - CASTING OF SLAB | 15-10-2024 |  | 0 | 5 | 4 | 0.000000 |  | 18439 | 15-10-2024 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45578
58 | E1 BLDG RCC : 2ND SLAB - SHUTT.,REINF. & CAST. OF SLAB | 15-10-2024 |  | 0 | 5 | 4 | 0.000000 |  | 18440 | 15-10-2024 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45578
59 | E1 BLDG RCC : 3RD SLAB - SHUTT.,REINF. & CAST. OF SLAB | 15-10-2024 |  | 0 | 5 | 4 | 0.000000 |  | 18441 | 15-10-2024 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45578
60 | E1 BLDG RCC : 4TH SLAB - SHUTT.,REINF. & CAST. OF SLAB | 15-10-2024 |  | 0 | 5 | 4 | 0.000000 |  | 18442 | 15-10-2024 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45578
61 | E1 BLDG RCC : 5TH SLAB - SHUTT.,REINF. & CAST. OF SLAB | 01-11-2024 |  | 0 | 5 | 4 | 0.000000 |  | 18443 | 01-11-2024 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45595
62 | E1 BLDG RCC : 6TH SLAB - SHUTT.,REINF. & CAST. OF SLAB | 01-12-2024 |  | 0 | 5 | 4 | 0.000000 |  | 18444 | 01-12-2024 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45625
63 | E1 BLDG RCC : 7TH SLAB - SHUTT.,REINF. & CAST. OF SLAB | 15-01-2025 |  | 0 | 5 | 4 | 0.000000 |  | 18445 | 15-01-2025 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45670
64 | E1 BLDG RCC : 8TH SLAB - SHUTT.,REINF. & CAST. OF SLAB | 01-03-2025 |  | 0 | 5 | 4 | 0.000000 |  | 18446 | 01-03-2025 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45715
65 | E1 BLDG RCC : 9TH SLAB - SHUTT.,REINF. & CAST. OF SLAB | 01-05-2025 |  | 0 | 5 | 4 | 0.000000 |  | 18447 | 01-05-2025 | 01-05-2025 | 1 | Must Start On | 01-04-2024 | As Soon As Possible | 1
66 | E1 BLDG RCC : 10TH SLAB - SHUTT.,REINF. & CAST. OF SLAB | 01-04-2024 |  | 0 | 5 | 4 | 0.000000 |  | 18448 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
67 | E1 BLDG RCC : 11TH SLAB - SHUTT.,REINF. & CAST. OF SLAB | 01-04-2024 |  | 0 | 5 | 4 | 0.000000 |  | 18449 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
68 | E1 BLDG RCC : HACKING,DESHUTT. - 1ST, 2ND & 3RD SLAB | 01-03-2025 |  | 0 | 5 | 4 | 0.000000 |  | 18450 | 01-03-2025 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45715
69 | E1 BLDG RCC : HACKING,DESHUTT. - 4TH, 5TH, & 6TH SLAB | 01-03-2025 |  | 0 | 5 | 4 | 0.000000 |  | 18451 | 01-03-2025 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45715
70 | E1 BLDG RCC : HACKING,DESHUTT. - 7TH, 8TH, & 9TH SLAB | 01-05-2025 |  | 0 | 5 | 4 | 0.000000 |  | 18452 | 01-05-2025 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45776
71 | E1 BLDG RCC : HACKING,DESHUTT. - 10TH, 11TH, & 12TH SLAB | 01-04-2024 |  | 0 | 5 | 4 | 0.000000 |  | 18453 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
72 | E1 BLDG RCC : HACKING,DESHUTT. - 13TH, 14TH, & OHWT | 01-04-2024 |  | 0 | 5 | 4 | 0.000000 |  | 18454 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
73 | E1 BLDG RCC : RETENTION | 01-04-2024 |  | 0 | 5 | 4 | 0.000000 |  | 18455 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
74 | SHREE SWAMI SAMARTH CONSTRUCTION & DEVELOPERS |  |  | 1 | 4 | 3 | 0.000000 |  | 18456 |  |  | 0 |  |  | As Soon As Possible | 0
75 | E1 BLDG RCC : PLINTH COMP - FOOTING, COL. UPTO PLINTH | 15-10-2024 |  | 0 | 5 | 4 | 0.000000 |  | 18457 | 15-10-2024 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45578
76 | E1 BLDG RCC : 1ST SLAB - PARKING-SHUT.,REINF. & CAST. OF COL | 15-10-2024 |  | 0 | 5 | 4 | 0.000000 |  | 18458 | 15-10-2024 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45578
77 | E1 BLDG RCC : 1ST SLAB - CASTING OF SLAB | 15-10-2024 |  | 0 | 5 | 4 | 0.000000 |  | 18459 | 15-10-2024 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45578
78 | E1 BLDG RCC : 2ND SLAB - SHUTT.,REINF. & CAST. OF SLAB | 15-10-2024 |  | 0 | 5 | 4 | 0.000000 |  | 18460 | 15-10-2024 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45578
79 | E1 BLDG RCC : 3RD SLAB - SHUTT.,REINF. & CAST. OF SLAB | 15-10-2024 |  | 0 | 5 | 4 | 0.000000 |  | 18461 | 15-10-2024 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45578
80 | E1 BLDG RCC : 4TH SLAB - SHUTT.,REINF. & CAST. OF SLAB | 15-10-2024 |  | 0 | 5 | 4 | 0.000000 |  | 18462 | 15-10-2024 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45578
81 | E1 BLDG RCC : 5TH SLAB - SHUTT.,REINF. & CAST. OF SLAB | 15-11-2024 |  | 0 | 5 | 4 | 0.000000 |  | 18463 | 15-11-2024 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45609
82 | E1 BLDG RCC : 6TH SLAB - SHUTT.,REINF. & CAST. OF SLAB | 01-12-2024 |  | 0 | 5 | 4 | 0.000000 |  | 18464 | 01-12-2024 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45625
83 | E1 BLDG RCC : 7TH SLAB - SHUTT.,REINF. & CAST. OF SLAB | 14-01-2025 |  | 0 | 5 | 4 | 0.000000 |  | 18465 | 14-01-2025 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45669
84 | E1 BLDG RCC : 8TH SLAB - SHUTT.,REINF. & CAST. OF SLAB | 01-02-2025 |  | 0 | 5 | 4 | 0.000000 |  | 18466 | 01-02-2025 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45687
85 | E1 BLDG RCC : 9TH SLAB - SHUTT.,REINF. & CAST. OF SLAB | 20-03-2025 |  | 0 | 5 | 4 | 0.000000 |  | 18467 | 20-03-2025 | 01-05-2025 | 42 | Must Start On | 01-04-2024 | As Soon As Possible | 42
86 | E1 BLDG RCC : 10TH SLAB - SHUTT.,REINF. & CAST. OF SLAB | 01-04-2024 |  | 0 | 5 | 4 | 0.000000 |  | 18468 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
87 | E1 BLDG RCC : 11TH SLAB - SHUTT.,REINF. & CAST. OF SLAB | 01-04-2024 |  | 0 | 5 | 4 | 0.000000 |  | 18469 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
88 | E1 BLDG RCC : 12TH SLAB - SHUTT.,REINF. & CAST. OF SLAB | 01-04-2024 |  | 0 | 5 | 4 | 0.000000 |  | 18470 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
89 | E1 BLDG RCC : 13TH SLAB - SHUTT.,REINF. & CAST. OF SLAB | 01-04-2024 |  | 0 | 5 | 4 | 0.000000 |  | 18471 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
90 | E1 BLDG RCC : 14TH SLAB - SHUTT.,REINF. & CAST. OF SLAB | 01-04-2024 |  | 0 | 5 | 4 | 0.000000 |  | 18472 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
91 | E1 BLDG RCC : LMR & OHWT - LMR & OHWT COMPLETION | 01-04-2024 |  | 0 | 5 | 4 | 0.000000 |  | 18473 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
92 | E1 BLDG RCC : MISC.WORK - COMP. OF STAIR PARDI,LINTEL,LOFT | 01-04-2024 |  | 0 | 5 | 4 | 0.000000 |  | 18474 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
93 | E1 BLDG RCC : PF - 3 MONTH AFTER COMP. OF ALL WORK | 01-04-2024 |  | 0 | 5 | 4 | 0.000000 |  | 18475 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
94 | E1 BLDG RCC : CLEANING - CLEANING UPTO 7TH SLAB | 01-04-2024 |  | 0 | 5 | 4 | 0.000000 |  | 18476 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
95 | E1 BLDG RCC : CLEANING - UPTO 14TH SLAB & OHWT,TOP TERR. | 01-04-2024 |  | 0 | 5 | 4 | 0.000000 |  | 18477 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
96 | E1 BLDG RCC : HACKING,DESHUTT. - 1ST, 2ND & 3RD SLAB | 01-03-2025 |  | 0 | 5 | 4 | 0.000000 |  | 18478 | 01-03-2025 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45715
97 | E1 BLDG RCC : HACKING,DESHUTT. - 4TH, 5TH, & 6TH SLAB | 01-03-2025 |  | 0 | 5 | 4 | 0.000000 |  | 18479 | 01-03-2025 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45715
98 | E1 BLDG RCC : HACKING,DESHUTT. - 7TH, 8TH, & 9TH SLAB | 01-04-2024 |  | 0 | 5 | 4 | 0.000000 |  | 18480 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
99 | E1 BLDG RCC : HACKING,DESHUTT. - 10TH, 11TH, & 12TH SLAB | 01-04-2024 |  | 0 | 5 | 4 | 0.000000 |  | 18481 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
100 | E1 BLDG RCC : HACKING,DESHUTT. - 13TH, 14TH, & OHWT | 01-04-2024 |  | 0 | 5 | 4 | 0.000000 |  | 18482 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
101 | E1 BLDG RCC : WORK COMPLETION AS PER SCHEDULE | 01-04-2024 |  | 0 | 5 | 4 | 0.000000 |  | 18483 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
102 | 6TH SLAB & ABOVE COLUMN RCC WORK |  |  | 1 | 3 | 2 | 0.000000 |  | 18685 |  |  | 0 |  |  | As Soon As Possible | 0
103 | E1 BLDG 6TH SLAB ABOVE COLUMN-RAW MATERIALS | 10-12-2024 |  | 0 | 4 | 3 | 0.000000 |  | 18686 | 10-12-2024 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45634
104 | E1 BLDG 6TH SLAB & ABOVE RCC WORK-STEEL | 10-12-2024 |  | 0 | 4 | 3 | 0.000000 |  | 18687 | 10-12-2024 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45634
105 | E1 BLDG 6TH SLAB CONCRETING WORK (RMC-M30) | 10-12-2024 |  | 0 | 4 | 3 | 0.000000 |  | 18688 | 10-12-2024 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45634
106 | 7TH SLAB & ABOVE COLUMN RCC WORK |  |  | 1 | 3 | 2 | 0.000000 |  | 18701 |  |  | 0 |  |  | As Soon As Possible | 0
107 | E1 BLDG 7TH SLAB & ABOVE RCC WORK-STEEL & RAW MATERIALS | 28-12-2024 |  | 0 | 4 | 3 | 0.000000 |  | 18702 | 28-12-2024 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45652
108 | 8TH SLAB & ABOVE COLUMN RCC WORK |  |  | 1 | 3 | 2 | 0.000000 |  | 18952 |  |  | 0 |  |  | As Soon As Possible | 0
109 | E1 BLDG 8TH SLAB & ABOVE RCC WORK-STEEL & RAW MATERIALS | 12-02-2025 |  | 0 | 4 | 3 | 0.000000 |  | 18954 | 12-02-2025 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45698
110 | 9TH SLAB & ABOVE COLUMN RCC WORK |  |  | 1 | 3 | 2 | 0.000000 |  | 18953 |  |  | 0 |  |  | As Soon As Possible | 0
111 | E1 BLDG 9TH SLAB & ABOVE RCC WORK-STEEL & RAW MATERIALS | 15-03-2025 |  | 0 | 4 | 3 | 0.000000 |  | 18955 | 15-03-2025 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45729
112 | 10th SLAB AND ABOVE COLUMN |  |  | 1 | 3 | 2 | 0.000000 |  | 19435 |  |  | 0 |  |  | As Soon As Possible | 0
113 | E1 BLDG 10th SLAB & ABOVE COLUMN TYPICAL SLAB & ABOVE COLUMN | 13-04-2025 |  | 0 | 4 | 3 | 0.000000 |  | 19436 | 13-04-2025 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45758
114 | 11th SLAB AND ABOVE COLUMN |  |  | 1 | 3 | 2 | 0.000000 |  | 19538 |  |  | 0 |  |  | As Soon As Possible | 0
115 | E1 BLDG 11TH SLAB & ABOVE RCC WORK-STEEL & RAW MATERIALS | 01-04-2024 |  | 0 | 4 | 3 | 0.000000 |  | 19539 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
116 | 12TH SLAB & ABOVE COLUMNS |  |  | 1 | 3 | 2 | 0.000000 |  | 19802 |  |  | 0 |  |  | As Soon As Possible | 0
117 | 12TH SLAB & ABOVE COLUMNS | 01-04-2024 |  | 0 | 4 | 3 | 0.000000 |  | 19834 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
118 | 13TH SLAB & ABOVE COLUMNS |  |  | 1 | 3 | 2 | 0.000000 |  | 19805 |  |  | 0 |  |  | As Soon As Possible | 0
119 | 13TH SLAB AND ABOVE COLUMNS | 01-04-2024 |  | 0 | 4 | 3 | 0.000000 |  | 19835 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
120 | 14TH SLAB |  |  | 1 | 3 | 2 | 0.000000 |  | 19807 |  |  | 0 |  |  | As Soon As Possible | 0
121 | 14TH SLAB | 01-04-2024 |  | 0 | 4 | 3 | 0.000000 |  | 19836 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
122 | CAR POLICY |  |  | 1 | 2 | 1 | 0.000000 |  | 17866 |  |  | 0 |  |  | As Soon As Possible | 0
123 | E1 BUILDING CONTRACTOR ALL RISK POLICY | 24-09-2024 |  | 0 | 3 | 2 | 0.000000 |  | 17867 | 24-09-2024 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45557
124 | DEVLOPMENT |  |  | 1 | 2 | 1 | 0.000000 |  | 18103 |  |  | 0 |  |  | As Soon As Possible | 0
125 | DEVLOPMENT E1 UG SERVICES | 07-11-2024 |  | 0 | 3 | 2 | 0.000000 |  | 18104 | 07-11-2024 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45601
126 | DEVLOPMENT E1 BLDG Safety Work Devlopment | 02-12-2024 |  | 0 | 3 | 2 | 0.000000 |  | 18640 | 02-12-2024 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45626
127 | E1 Building SAFETY NET FIXING MATERIAL | 01-02-2025 |  | 0 | 3 | 2 | 0.000000 |  | 18790 | 01-02-2025 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45687
128 | SAFETY MATERIAL E1 Building 2nd Level Safety Net | 01-02-2025 |  | 0 | 3 | 2 | 0.000000 |  | 19252 | 01-02-2025 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45687
129 | E1 BUILDING ESTIMATION | 28-12-2024 |  | 0 | 2 | 1 | 0.000000 |  | 18282 | 28-12-2024 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45652
130 | PLUMBING WORK |  |  | 1 | 2 | 1 | 0.000000 |  | 18322 |  |  | 0 |  |  | As Soon As Possible | 0
131 | E1 BLDG GROUND FLOOR PLUMBING MATERIAL | 01-10-2024 |  | 0 | 3 | 2 | 0.000000 |  | 18323 | 01-10-2024 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45564
132 | E1 BLDG Under Ground Plumbing Labour | 01-10-2024 |  | 0 | 3 | 2 | 0.000000 |  | 18694 | 01-10-2024 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45564
133 | Electrical Work |  |  | 1 | 2 | 1 | 0.000000 |  | 18717 |  |  | 0 |  |  | As Soon As Possible | 0
134 | E1 ELECTRICAL WO |  |  | 1 | 3 | 2 | 0.000000 |  | 19294 |  |  | 0 |  |  | As Soon As Possible | 0
135 | E1 Building Electrical work1ST, 2ND AND 3RD FLOOR | 02-04-2024 |  | 0 | 4 | 3 | 0.000000 |  | 18718 | 02-04-2024 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45382
136 | E1 Building Electrical Work 4th,5th and 6th Floor | 02-04-2024 |  | 0 | 4 | 3 | 0.000000 |  | 18719 | 02-04-2024 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45382
137 | E1 Building Electrical Work 7th, 8th and 9th Floor | 02-04-2024 |  | 0 | 4 | 3 | 0.000000 |  | 18720 | 02-04-2024 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45382
138 | E1 Building Electrical Work 10th, 11th and 12th Floor | 02-04-2024 |  | 0 | 4 | 3 | 0.000000 |  | 18721 | 02-04-2024 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45382
139 | MATERIAL |  |  | 1 | 3 | 2 | 0.000000 |  | 19295 |  |  | 0 |  |  | As Soon As Possible | 0
140 | E1 BLDG ST CASE LIGHTING-4TH TO 12TH FLOOR - MATERIAL | 26-03-2025 |  | 0 | 4 | 3 | 0.000000 |  | 19296 | 26-03-2025 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45740
141 | WALL PIPING |  |  | 1 | 3 | 2 | 0.000000 |  | 19848 |  |  | 0 |  |  | As Soon As Possible | 0
142 | WALL PIPING E1 BLDG 1st 2nd and 3rd Floor | 02-04-2025 |  | 0 | 4 | 3 | 0.000000 |  | 19849 | 02-04-2025 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45747
143 | WALL PIPING E1 BLDG 4th,5th AND 6th Floor | 01-04-2025 |  | 0 | 4 | 3 | 0.000000 |  | 19850 | 01-04-2025 | 01-04-2025 | 1 | Must Start On | 01-04-2024 | As Soon As Possible | 1
144 | WALL PIPING E1 BLDG 7th , 8th and 9th Floor | 01-04-2025 |  | 0 | 4 | 3 | 0.000000 |  | 19851 | 01-04-2025 | 01-04-2025 | 1 | Must Start On | 01-04-2024 | As Soon As Possible | 1
145 | WALL PIPING E1 BLDG 10th, 11th and 12th Floor | 01-04-2024 |  | 0 | 4 | 3 | 0.000000 |  | 19852 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
146 | BBM WORK |  |  | 1 | 2 | 1 | 0.000000 |  | 18949 |  |  | 0 |  |  | As Soon As Possible | 0
147 | MATERIAL |  |  | 1 | 3 | 2 | 0.000000 |  | 19107 |  |  | 0 |  |  | As Soon As Possible | 0
148 | E1 BUILDING 1ST FLOOR BRICK WORK & ST-CASE BLOCK WORK | 01-02-2025 |  | 0 | 4 | 3 | 0.000000 |  | 19109 | 01-02-2025 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45687
149 | E1 BUILDING 2ND FLOOR BRICK WORK & ST-CASE BLOCK WORK | 27-03-2025 |  | 0 | 4 | 3 | 0.000000 |  | 19545 | 27-03-2025 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45741
150 | E1 BUILDING 3RD FLOOR BRICK WORK & ST-CASE BLOCK WORK | 12-04-2025 |  | 0 | 4 | 3 | 0.000000 |  | 19816 | 12-04-2025 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45757
151 | E1 BUILDING 4TH FLOOR BRICK WORK & ST-CASE BLOCK WORK | 01-04-2024 |  | 0 | 4 | 3 | 0.000000 |  | 19817 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
152 | LOWER GROUND FLOOR | 01-04-2024 |  | 0 | 4 | 3 | 0.000000 |  | 19837 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
153 | UPPER GROUND FLOOR | 01-04-2024 |  | 0 | 4 | 3 | 0.000000 |  | 19838 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
154 | 5TH FLOOR | 01-04-2024 |  | 0 | 4 | 3 | 0.000000 |  | 19839 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
155 | 6TH FLOOR | 01-04-2024 |  | 0 | 4 | 3 | 0.000000 |  | 19840 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
156 | 8TH FLOOR | 01-04-2024 |  | 0 | 4 | 3 | 0.000000 |  | 19841 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
157 | 7TH FLOOR (REFUGE FLOOR) | 01-04-2024 |  | 0 | 4 | 3 | 0.000000 |  | 19842 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
158 | 9TH FLOOR | 01-04-2024 |  | 0 | 4 | 3 | 0.000000 |  | 19843 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
159 | 10TH FLOOR | 01-04-2024 |  | 0 | 4 | 3 | 0.000000 |  | 19844 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
160 | 11TH FLOOR | 01-04-2024 |  | 0 | 4 | 3 | 0.000000 |  | 19845 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
161 | 12TH FLOOR | 01-04-2024 |  | 0 | 4 | 3 | 0.000000 |  | 19846 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
162 | LABOUR |  |  | 1 | 3 | 2 | 0.000000 |  | 19108 |  |  | 0 |  |  | As Soon As Possible | 0
163 | BBM AND PLSTR-NON GST |  |  | 1 | 4 | 3 | 0.000000 |  | 19569 |  |  | 0 |  |  | As Soon As Possible | 0
164 | BBM AT E1 BLDG AT PART B 1,2,3,4 FLR | 14-02-2025 |  | 0 | 5 | 4 | 0.000000 |  | 19570 | 14-02-2025 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45700
165 | BBM AT E1 PART B AT 9,10,11 FLOOR | 14-02-2025 |  | 0 | 5 | 4 | 0.000000 |  | 19571 | 14-02-2025 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45700
166 | BBM AT E1 PART B MISC AND ELEV. PIN | 01-04-2024 |  | 0 | 5 | 4 | 0.000000 |  | 19572 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
167 | INT PLASTER E1 PART B 1,2,3,4 FLR | 01-04-2024 |  | 0 | 5 | 4 | 0.000000 |  | 19573 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
168 | INT PLASTER E1 PART B 9,10,11,12 FLR | 01-04-2024 |  | 0 | 5 | 4 | 0.000000 |  | 19574 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
169 | INT PLSTR E1 PART B ST, LIFT, MISC, BUTT | 01-04-2024 |  | 0 | 5 | 4 | 0.000000 |  | 19575 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
170 | EXT PLSTR E1 PART B F 04,05 B BED, TERR | 01-04-2024 |  | 0 | 5 | 4 | 0.000000 |  | 19576 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
171 | EXT PLSTR E1 SW81 to 82, 06 LVN TERR | 01-04-2024 |  | 0 | 5 | 4 | 0.000000 |  | 19577 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
172 | EXT PLSTR E1 F 06,07,08 BED , TERR | 01-04-2024 |  | 0 | 5 | 4 | 0.000000 |  | 19578 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
173 | EXT PLSTR E1 DUCT 8 B, C,9 A D | 01-04-2024 |  | 0 | 5 | 4 | 0.000000 |  | 19579 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
174 | EXT PLSTR E1 DUCT 12 A,B Duct 10 SW FAC | 01-04-2024 |  | 0 | 5 | 4 | 0.000000 |  | 19580 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
175 | EXT PLSTR E1 Parapet, Refuse, MISC, Podi | 01-04-2024 |  | 0 | 5 | 4 | 0.000000 |  | 19581 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
176 | EXT PLSTR E1 CLEANING AND MISC | 01-04-2024 |  | 0 | 5 | 4 | 0.000000 |  | 19582 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
177 | BBM AND PLSTR RETENTION FOR E1 BLDG PART B | 01-04-2024 |  | 0 | 5 | 4 | 0.000000 |  | 19583 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
178 | BBM AND PLSTR-GST |  |  | 1 | 4 | 3 | 0.000000 |  | 19662 |  |  | 0 |  |  | As Soon As Possible | 0
179 | BBM AT E1 BLDG AT PART B L.G & U.G FLOOR | 01-04-2024 |  | 0 | 5 | 4 | 0.000000 |  | 19664 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
180 | BBM AT E1 BLDG AT PART B 5,6,7,8,12 FLOOR | 01-04-2024 |  | 0 | 5 | 4 | 0.000000 |  | 19665 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
181 | BBM AT E1 BLDG AT PART B TOP TERRACE & OHWT | 01-04-2024 |  | 0 | 5 | 4 | 0.000000 |  | 19666 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
182 | BBM AT E1 BLDG AT PART B LIFT 8 PASS & 13 PASS | 01-04-2024 |  | 0 | 5 | 4 | 0.000000 |  | 19667 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
183 | INT PLASTER E1 PART B 5,6,7,8 FLOOR | 01-04-2024 |  | 0 | 5 | 4 | 0.000000 |  | 19668 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
184 | INT PLASTER E1 PART B L.G & U.G FLOOR | 01-04-2024 |  | 0 | 5 | 4 | 0.000000 |  | 19669 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
185 | INT PLASTER E1 PART B PASSAGE UPTO 12TH FLOOR | 01-04-2024 |  | 0 | 5 | 4 | 0.000000 |  | 19670 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
186 | INT PLASTER E1 PART B STAIRCASE PLASTER UPTO 12TH FLOOR | 01-04-2024 |  | 0 | 5 | 4 | 0.000000 |  | 19671 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
187 | EXT PLSTR E1 PART B F 03,04 B BED ,TERR & DUCT 7B | 01-04-2024 |  | 0 | 5 | 4 | 0.000000 |  | 19672 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
188 | EXT PLSTR E1 PART B F 05 TERR,LIV.TERR & SW 81 TO SW 82 NSW | 01-04-2024 |  | 0 | 5 | 4 | 0.000000 |  | 19673 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
189 | EXT PLSTR E1 PART B F 06 TERR,TERR OUT SIDE,B.BED UP 6TH WS | 01-04-2024 |  | 0 | 5 | 4 | 0.000000 |  | 19674 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
190 | EXT PLSTR E1 PART B F 08 B.BED,DUCT 7A UPTH 12 & 8A UPTO 6TH | 01-04-2024 |  | 0 | 5 | 4 | 0.000000 |  | 19675 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
191 | EXT PLSTR E1 PART B DUCT 9B,9C,11B,11C UPTO 12TH & 12A,12B | 01-04-2024 |  | 0 | 5 | 4 | 0.000000 |  | 19676 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
192 | EXT PLSTR E1 PART B DUCT 10,ELE DUCT 13A,13B,FIRE 14B | 01-04-2024 |  | 0 | 5 | 4 | 0.000000 |  | 19677 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
193 | EXT PLSTR E1 PART B OHWT OUTER | 01-04-2024 |  | 0 | 5 | 4 | 0.000000 |  | 19678 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
194 | EXT PLSTR E1 PART B PARKING PODIUM SIDE,UPPER & LOWER | 01-04-2024 |  | 0 | 5 | 4 | 0.000000 |  | 19679 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
195 | EXT PLSTR E1 PART B CLEANING & MISCELLANEOUS | 01-04-2024 |  | 0 | 5 | 4 | 0.000000 |  | 19680 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
196 | BBM AND PLSTR RETENTION FOR E1 BLDG PART B | 01-04-2024 |  | 0 | 5 | 4 | 0.000000 |  | 19681 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
197 | PLASTER WORK |  |  | 1 | 2 | 1 | 0.000000 |  | 19909 |  |  | 0 |  |  | As Soon As Possible | 0
198 | INTERNAL PLASTER |  |  | 1 | 3 | 2 | 0.000000 |  | 19910 |  |  | 0 |  |  | As Soon As Possible | 0
199 | 1ST FLOOR INTERNAL PLASTER | 26-04-2025 |  | 0 | 4 | 3 | 0.000000 |  | 19960 | 26-04-2025 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45771
200 | 2ND FLOOR INTERNAL PLASTER | 26-04-2025 |  | 0 | 4 | 3 | 0.000000 |  | 19961 | 26-04-2025 |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | -45771
201 | 3RD FLOOR INTERNAL PLASTER | 01-04-2024 |  | 0 | 4 | 3 | 0.000000 |  | 19962 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
202 | 4TH FLOOR INTERNAL PLASTER | 01-04-2024 |  | 0 | 4 | 3 | 0.000000 |  | 19963 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
203 | 5TH FLOOR INTERNAL PLASTER | 01-04-2024 |  | 0 | 4 | 3 | 0.000000 |  | 19964 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
204 | 6TH FLOOR INTERNAL PLASTER | 01-04-2024 |  | 0 | 4 | 3 | 0.000000 |  | 19965 |  |  | 0 | Must Start On | 01-04-2024 | As Soon As Possible | 0
205 | EXTERNAL PLASTER |  |  | 1 | 3 | 2 | 0.000000 |  | 19911 |  |  | 0 |  |  | As Soon As Possible | 0