## MatLabCategoryVarianceDetails63
Material/Labour Category Variance Details
Project Name : DESTINATION 24 AVENUE
Task Name : All Task
Page 1 of 1
Total Records: 3640 Records 1 to 3640
Sr_No | Task | Task_Completion | Task_Status | Item_Type | Item_Name | Unit | Estimated_Qty_1 | Estimated_Rate | Estimated_Amount_1 | Req_Approved_Qty | Req_Rate | Req_Amount | EstQty_CompWork_2 | EstRate_WorkComp | EstAmount_CompWork_2 | PO_WO_Qty_2 | PO_WO_Rate | PO_WO_Amount_2 | Issue_RABil_Qty_3 | Issue_RABil_Rate | Issue_RABill_Amount_3 | QtyDiff(1-2) | QtyDiff(1-3) | AmtDiff(1-2) | AmtDiff(1-3) | Task_Identification1 | Task_Identification2 | Task_Identification3
1 | EARTH WORK BLOCK EXCAVATION WORK | 0 | Started | Labour | (L)Labour for Block Excavation | CUM | 2902.71 | 78.76 | 228617.44 | 2902.71 | 78.76 | 228617.44 | 0 | 78.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2902.71 | 2902.71 | 228617.44 | 228617.4396 | Building
2 | EARTH WORK BLOCK METALING | 0 | Started | Labour | (L)BLOCK METALLING (Mat+Lab) | SQFT | 8602.62 | 42 | 361310.04 | 8602.62 | 42 | 361310.04 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8602.62 | 8602.62 | 361310.04 | 361310.04 | Building
3 | EARTH WORK MACHINERY ROLLER | 0 | Started | Labour | (L)Compaction For Back Filling Murum | DAY | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | Building
4 | A WING RAFT PCC M15 | 100 | Started | Material | (M)CEMENT PPC 50KG | BAG | 522 | 320 | 167040 | 522 | 320 | 167040 | 522 | 320 | 167040 | 200 | 309.99 | 61998.08 | 0 | 0 | 0 | 0 | 522 | 0 | 167040 | Building
5 | A WING RAFT PCC M15 | 100 | Started | Material | (M)Crush Sand | BRASS | 26.64 | 3675 | 97902 | 26.64 | 3675 | 97902 | 27 | 3675 | 99225 | 26.64 | 3675 | 97902 | 0 | 0 | 0 | -0.36 | 26.64 | -1323 | 97902 | Building
6 | A WING RAFT PCC M15 | 100 | Started | Material | (M)Metal No.III 20MM | BRASS | 39.69 | 3045 | 120856.05 | 39.69 | 3045 | 120856.05 | 40 | 3045 | 121800 | 0 | 0 | 0 | 0 | 0 | 0 | -0.31 | 39.69 | -943.95 | 120856.05 | Building
7 | A WING RAFT FOOTING RMC-M25 | 100 | Started | Material | (M)RMC M-25 | CUM | 404 | 4600 | 1858400 | 404 | 4600 | 1858400 | 404 | 4600 | 1858400 | 404 | 4600 | 1858400 | 0 | 0 | 0 | 0 | 404 | 0 | 1858400 | Building
8 | A WING COL.(UP TO PLINTH) CONCRETE-M30 | 100 | Started | Material | (M)CEMENT OPC 43 | BAG | 407 | 378.88 | 154204.16 | 407 | 378.88 | 154204.16 | 407 | 378.88 | 154204.16 | 407 | 365 | 148555 | 0 | 0 | 0 | 0 | 407 | 0 | 154204.16 | Building
9 | A WING COL.(UP TO PLINTH) CONCRETE-M30 | 100 | Started | Material | (M)Crush Sand | BRASS | 9.46 | 3675 | 34765.5 | 9.46 | 3675 | 34765.5 | 9 | 3675 | 33075 | 0 | 0 | 0 | 0 | 0 | 0 | 0.46 | 9.46 | 1690.5 | 34765.5 | Building
10 | A WING COL.(UP TO PLINTH) CONCRETE-M30 | 100 | Started | Material | (M)Metal No.III 20MM | BRASS | 14.19 | 3045 | 43208.55 | 14.19 | 3045 | 43208.55 | 14 | 3045 | 42630 | 0 | 0 | 0 | 0 | 0 | 0 | 0.19 | 14.19 | 578.55 | 43208.55 | Building
11 | A WING PLINTH BEAM CONCRETE-M25 | 100 | Started | Material | (M)CEMENT OPC 43 | BAG | 279.36 | 378.88 | 105843.92 | 279.36 | 378.88 | 105843.92 | 279 | 378.88 | 105707.52 | 193 | 365 | 70445 | 0 | 0 | 0 | 0.36 | 279.36 | 136.397 | 105843.9168 | Building
12 | A WING PLINTH BEAM CONCRETE-M25 | 100 | Started | Material | (M)Crush Sand | BRASS | 10.864 | 3675 | 39925.2 | 10.864 | 3675 | 39925.2 | 11 | 3675 | 40425 | 0 | 0 | 0 | 0 | 0 | 0 | -0.136 | 10.864 | -499.8 | 39925.2 | Building
13 | A WING PLINTH BEAM CONCRETE-M25 | 100 | Started | Material | (M)Metal No.III 20MM | BRASS | 16.8004 | 3045 | 51157.22 | 16.8004 | 3045 | 51157.22 | 17 | 3045 | 51765 | 0 | 0 | 0 | 0 | 0 | 0 | -0.1996 | 16.8004 | -607.782 | 51157.218 | Building
14 | A WING PLINTH BEAM RMC-M30 | 100 | Started | Material | (M)RMC M-30 | CUM | 17 | 4000 | 68000 | 17 | 4000 | 68000 | 17 | 4000 | 68000 | 17 | 5200 | 88400 | 0 | 0 | 0 | 0 | 17 | 0 | 68000 | Building
15 | A WING FOOTING STEEL-8MM STEEL | 100 | Started | Material | (M)T.M.T.Bar 8mm (Fe 500, 0.395 KGS/Rm) | KG | 100 | 59 | 5900 | 100 | 59 | 5900 | 100 | 59 | 5900 | 100 | 61.54 | 6154.36 | 0 | 0 | 0 | 0 | 100 | 0 | 5900 | Building
16 | A WING FOOTING STEEL-10MM STEEL | 100 | Started | Material | (M)T.M.T.Bar 10mm (Fe 500, 0.617 KGS/Rm) | KG | 2700 | 59 | 159300 | 2700 | 59 | 159300 | 2700 | 59 | 159300 | 2700 | 59.92 | 161795.47 | 4153.644 | 59.36 | 246548.68 | 0 | -1453.644 | 0 | -87248.68 | Building
17 | A WING FOOTING STEEL-12MM STEEL | 100 | Started | Material | (M)T.M.T.Bar 12mm (Fe 500, 0.888 KGS/Rm) | KG | 4300 | 59 | 253700 | 4300 | 59 | 253700 | 4300 | 59 | 253700 | 4000 | 60.36 | 241422 | 0 | 0 | 0 | 0 | 4300 | 0 | 253700 | Building
18 | A WING COL.(UP TP PLINTH) STEEL 8MM STEEL | 100 | Started | Material | (M)T.M.T.Bar 8mm (Fe 500, 0.395 KGS/Rm) | KG | 5800 | 59 | 342200 | 5800 | 59 | 342200 | 5800 | 59 | 342200 | 5800 | 61.54 | 356952.88 | 0 | 0 | 0 | 0 | 5800 | 0 | 342200 | Building
19 | A WING COL.(UP TP PLINTH) STEEL 10MM STEEL | 100 | Started | Material | (M)T.M.T.Bar 10mm (Fe 500, 0.617 KGS/Rm) | KG | 100 | 59 | 5900 | 100 | 59 | 5900 | 100 | 59 | 5900 | 100 | 58.69 | 5869.21 | 0 | 0 | 0 | 0 | 100 | 0 | 5900 | Building
20 | A WING COL.(UP TP PLINTH) STEEL 12MM STEEL | 100 | Started | Material | (M)T.M.T.Bar 12mm (Fe 500, 0.888 KGS/Rm) | KG | 150 | 59 | 8850 | 150 | 59 | 8850 | 150 | 59 | 8850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 8850 | Building
21 | A WING COL.(UP TP PLINTH) STEEL 16MM STEEL | 100 | Started | Material | (M)T.M.T.Bar 16mm (Fe 500, 1.58 KGS/Rm) | KG | 3600 | 59 | 212400 | 3600 | 59 | 212400 | 3600 | 59 | 212400 | 2000 | 60.36 | 120711 | 0 | 0 | 0 | 0 | 3600 | 0 | 212400 | Building
22 | A WING COL.(UP TP PLINTH) STEEL-20MM STEEL | 100 | Started | Material | (M)T.M.T.Bar 20mm (Fe 500, 2.47 KGS/Rm) | KG | 7800 | 59 | 460200 | 7800 | 59 | 460200 | 7800 | 59 | 460200 | 7800 | 59.33 | 462788.58 | 0 | 0 | 0 | 0 | 7800 | 0 | 460200 | Building
23 | A WING COL.(UP TP PLINTH) STEEL-25MM STEEL | 100 | Started | Material | (M)T.M.T.Bar 25mm (Fe 500, 3.85 KGS/Rm) | KG | 6900 | 59 | 407100 | 6900 | 59 | 407100 | 6900 | 59 | 407100 | 5000 | 60.36 | 301777.5 | 0 | 0 | 0 | 0 | 6900 | 0 | 407100 | Building
24 | A WING COL.(UP TP PLINTH) STEEL-BINDING WIRE | 100 | Started | Material | (M)MS Binding Wire 18G | KG | 400 | 50 | 20000 | 400 | 50 | 20000 | 400 | 50 | 20000 | 400 | 80.79 | 32316.32 | 0 | 0 | 0 | 0 | 400 | 0 | 20000 | Building
25 | A WING PLINTH BEAM STEEL 8MM STEEL | 100 | Started | Material | (M)T.M.T.Bar 8mm (Fe 500, 0.395 KGS/Rm) | KG | 1500 | 59 | 88500 | 1500 | 59 | 88500 | 1500 | 59 | 88500 | 1500 | 61.54 | 92315.4 | 0 | 0 | 0 | 0 | 1500 | 0 | 88500 | Building
26 | A WING PLINTH BEAM STEEL 10MM STEEL | 100 | Started | Material | (M)T.M.T.Bar 10mm (Fe 500, 0.617 KGS/Rm) | KG | 200 | 59 | 11800 | 200 | 59 | 11800 | 200 | 59 | 11800 | 200 | 58.69 | 11738.42 | 0 | 0 | 0 | 0 | 200 | 0 | 11800 | Building
27 | A WING PLINTH BEAM STEEL 12MM STEEL | 100 | Started | Material | (M)T.M.T.Bar 12mm (Fe 500, 0.888 KGS/Rm) | KG | 2100 | 59 | 123900 | 2100 | 59 | 123900 | 2100 | 59 | 123900 | 2100 | 58.69 | 123253.41 | 0 | 0 | 0 | 0 | 2100 | 0 | 123900 | Building
28 | A WING PLINTH BEAM STEEL 16MM STEEL | 100 | Started | Material | (M)T.M.T.Bar 16mm (Fe 500, 1.58 KGS/Rm) | KG | 650 | 59 | 38350 | 650 | 59 | 38350 | 650 | 59 | 38350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 0 | 38350 | Building
29 | A WING PLINTH BEAM STEEL 20MM STEEL | 100 | Started | Material | (M)T.M.T.Bar 20mm (Fe 500, 2.47 KGS/Rm) | KG | 850 | 59 | 50150 | 850 | 59 | 50150 | 850 | 59 | 50150 | 200 | 58.69 | 11738.42 | 0 | 0 | 0 | 0 | 850 | 0 | 50150 | Building
30 | A WING PLINTH BEAM STEEL 25MM STEEL | 100 | Started | Material | (M)T.M.T.Bar 25mm (Fe 500, 3.85 KGS/Rm) | KG | 2000 | 59 | 118000 | 2000 | 59 | 118000 | 2000 | 59 | 118000 | 2000 | 58.69 | 117384.2 | 0 | 0 | 0 | 0 | 2000 | 0 | 118000 | Building
31 | A WING PLINTH BEAM STEEL 32MM STEEL | 100 | Started | Material | (M)T.M.T.Bar 32mm (Fe 500, 6.31 KGS/Rm) | KG | 800 | 59 | 47200 | 800 | 59 | 47200 | 800 | 59 | 47200 | 800 | 61.54 | 49234.88 | 0 | 0 | 0 | 0 | 800 | 0 | 47200 | Building
32 | A WING PLINTH BEAM STEEL BINDING WIRE | 100 | Started | Material | (M)MS Binding Wire 18G | KG | 150 | 50 | 7500 | 150 | 50 | 7500 | 150 | 50 | 7500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 7500 | Building
33 | COLUMN & LIFT ABOVE PLINTH-8MM STEEL | 100 | Started | Material | (M)T.M.T.Bar 8mm (Fe 500, 0.395 KGS/Rm) | KG | 4500 | 59 | 265500 | 4500 | 59 | 265500 | 4500 | 59 | 265500 | 4500 | 59.92 | 269627.24 | 0 | 0 | 0 | 0 | 4500 | 0 | 265500 | Building
34 | COLUMN & LIFT ABOVE PLINTH-12MM STEEL | 100 | Started | Material | (M)T.M.T.Bar 12mm (Fe 500, 0.888 KGS/Rm) | KG | 500 | 59 | 29500 | 500 | 59 | 29500 | 500 | 59 | 29500 | 500 | 58.69 | 29346.05 | 0 | 0 | 0 | 0 | 500 | 0 | 29500 | Building
35 | COLUMN & LIFT ABOVE PLINTH-16MM STEEL | 100 | Started | Material | (M)T.M.T.Bar 16mm (Fe 500, 1.58 KGS/Rm) | KG | 2000 | 59 | 118000 | 2000 | 59 | 118000 | 2000 | 59 | 118000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 118000 | Building
36 | COLUMN & LIFT ABOVE PLINTH-20MM STEEL | 100 | Started | Material | (M)T.M.T.Bar 20mm (Fe 500, 2.47 KGS/Rm) | KG | 4500 | 59 | 265500 | 4500 | 59 | 265500 | 4500 | 59 | 265500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | 0 | 265500 | Building
37 | COLUMN & LIFT ABOVE PLINTH-25MM STEEL | 100 | Started | Material | (M)T.M.T.Bar 25mm (Fe 500, 3.85 KGS/Rm) | KG | 3500 | 59 | 206500 | 3500 | 59 | 206500 | 3500 | 59 | 206500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 0 | 206500 | Building
38 | COLUMN & LIFT ABOVE PLINTH-BINDING WIRE | 100 | Started | Material | (M)MS Binding Wire 18G | KG | 220 | 50 | 11000 | 220 | 50 | 11000 | 220 | 50 | 11000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 0 | 11000
39 | COLUMN & LIFT ABOVE PLINTH-CONCRETE-M30 | 100 | Started | Material | (M)CEMENT OPC 43 | BAG | 441.188 | 378.88 | 167157.31 | 441.188 | 378.88 | 167157.31 | 441 | 378.88 | 167086.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0.188 | 441.188 | 71.229 | 167157.3094 | Building
40 | COLUMN & LIFT ABOVE PLINTH-CONCRETE-M30 | 100 | Started | Material | (M)Crush Sand | BRASS | 10.2546 | 3675 | 37685.66 | 10.2546 | 3675 | 37685.66 | 10 | 3675 | 36750 | 0 | 0 | 0 | 0 | 0 | 0 | 0.2546 | 10.2546 | 935.655 | 37685.655 | Building
41 | COLUMN & LIFT ABOVE PLINTH-CONCRETE-M30 | 100 | Started | Material | (M)Metal No.III 20MM | BRASS | 15.382 | 3045 | 46838.19 | 15.382 | 3045 | 46838.19 | 15 | 3045 | 45675 | 0 | 0 | 0 | 0 | 0 | 0 | 0.382 | 15.382 | 1163.19 | 46838.19 | Building
42 | 1ST SLAB (BEAM,SLAB & ST CASE)-8MM STEEL | 100 | Started | Material | (M)T.M.T.Bar 8mm (Fe 500, 0.395 KGS/Rm) | KG | 3000 | 59 | 177000 | 3000 | 59 | 177000 | 3000 | 59 | 177000 | 3000 | 59.88 | 179640.6 | 0 | 0 | 0 | 0 | 3000 | 0 | 177000 | Building
43 | 1ST SLAB (BEAM,SLAB & ST CASE)-10MM STEEL | 100 | Started | Material | (M)T.M.T.Bar 10mm (Fe 500, 0.617 KGS/Rm) | KG | 800 | 59 | 47200 | 800 | 59 | 47200 | 800 | 59 | 47200 | 800 | 58.69 | 46953.68 | 0 | 0 | 0 | 0 | 800 | 0 | 47200 | Building
44 | 1ST SLAB (BEAM,SLAB & ST CASE)-12MM STEEL | 100 | Started | Material | (M)T.M.T.Bar 12mm (Fe 500, 0.888 KGS/Rm) | KG | 2000 | 59 | 118000 | 2000 | 59 | 118000 | 2000 | 59 | 118000 | 2000 | 58.69 | 117384.2 | 0 | 0 | 0 | 0 | 2000 | 0 | 118000 | Building
45 | 1ST SLAB (BEAM,SLAB & ST CASE)-16MM STEEL | 100 | Started | Material | (M)T.M.T.Bar 16mm (Fe 500, 1.58 KGS/Rm) | KG | 2000 | 59 | 118000 | 2000 | 59 | 118000 | 2000 | 59 | 118000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 118000 | Building
46 | 1ST SLAB (BEAM,SLAB & ST CASE)-20MM STEEL | 100 | Started | Material | (M)T.M.T.Bar 20mm (Fe 500, 2.47 KGS/Rm) | KG | 2000 | 59 | 118000 | 2000 | 59 | 118000 | 2000 | 59 | 118000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 118000 | Building
47 | 1ST SLAB (BEAM,SLAB & ST CASE)-25MM STEEL | 100 | Started | Material | (M)T.M.T.Bar 25mm (Fe 500, 3.85 KGS/Rm) | KG | 1000 | 59 | 59000 | 1000 | 59 | 59000 | 1000 | 59 | 59000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 59000 | Building
48 | 1ST SLAB (BEAM,SLAB & ST CASE)-BINDING WIRE | 100 | Started | Material | (M)MS Binding Wire 18G | KG | 140 | 50 | 7000 | 140 | 50 | 7000 | 140 | 50 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140 | 0 | 7000 | Building
49 | 1ST SLAB (BEAM,SLAB & ST CASE)-CONCRETE-M25 | 100 | Started | Material | (M)CEMENT OPC 43 | BAG | 670.032 | 378.88 | 253861.72 | 670.032 | 378.88 | 253861.72 | 670 | 378.88 | 253849.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0.032 | 670.032 | 12.124 | 253861.7242 | Building
50 | 1ST SLAB (BEAM,SLAB & ST CASE)-CONCRETE-M25 | 100 | Started | Material | (M)Crush Sand | BRASS | 26.0568 | 3675 | 95758.74 | 26.0568 | 3675 | 95758.74 | 26 | 3675 | 95550 | 0 | 0 | 0 | 0 | 0 | 0 | 0.0568 | 26.0568 | 208.74 | 95758.74 | Building
51 | 1ST SLAB (BEAM,SLAB & ST CASE)-CONCRETE-M25 | 100 | Started | Material | (M)Metal No.III 20MM | BRASS | 40.295 | 3045 | 122698.28 | 40.295 | 3045 | 122698.28 | 40 | 3045 | 121800 | 0 | 0 | 0 | 0 | 0 | 0 | 0.295 | 40.295 | 898.275 | 122698.275 | Building
52 | COLUMN & LIFT ABOVE 1ST SLAB-8MM STEEL | 100 | Started | Material | (M)T.M.T.Bar 8mm (Fe 500, 0.395 KGS/Rm) | KG | 4500 | 59 | 265500 | 4500 | 59 | 265500 | 4500 | 59 | 265500 | 2100 | 59.03 | 123966.27 | 0 | 0 | 0 | 0 | 4500 | 0 | 265500 | Building
53 | COLUMN & LIFT ABOVE 1ST SLAB-10MM STEEL | 100 | Started | Material | (M)T.M.T.Bar 10mm (Fe 500, 0.617 KGS/Rm) | KG | 700 | 59 | 41300 | 700 | 59 | 41300 | 700 | 59 | 41300 | 700 | 58.69 | 41084.47 | 0 | 0 | 0 | 0 | 700 | 0 | 41300 | Building
54 | COLUMN & LIFT ABOVE 1ST SLAB-12MM STEEL | 100 | Started | Material | (M)T.M.T.Bar 12mm (Fe 500, 0.888 KGS/Rm) | KG | 500 | 59 | 29500 | 500 | 59 | 29500 | 500 | 59 | 29500 | 500 | 58.69 | 29346.05 | 0 | 0 | 0 | 0 | 500 | 0 | 29500 | Building
55 | COLUMN & LIFT ABOVE 1ST SLAB-16MM STEEL | 100 | Started | Material | (M)T.M.T.Bar 16mm (Fe 500, 1.58 KGS/Rm) | KG | 2000 | 59 | 118000 | 2000 | 59 | 118000 | 2000 | 59 | 118000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 118000 | Building
56 | COLUMN & LIFT ABOVE 1ST SLAB-20MM STEEL | 100 | Started | Material | (M)T.M.T.Bar 20mm (Fe 500, 2.47 KGS/Rm) | KG | 3500 | 59 | 206500 | 3500 | 59 | 206500 | 3500 | 59 | 206500 | 3000 | 58.69 | 176076.3 | 0 | 0 | 0 | 0 | 3500 | 0 | 206500 | Building
57 | COLUMN & LIFT ABOVE 1ST SLAB-25MM STEEL | 100 | Started | Material | (M)T.M.T.Bar 25mm (Fe 500, 3.85 KGS/Rm) | KG | 2500 | 59 | 147500 | 2500 | 59 | 147500 | 2500 | 59 | 147500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 147500 | Building
58 | COLUMN & LIFT ABOVE 1ST SLAB-BINDING WIRE | 100 | Started | Material | (M)MS Binding Wire 18G | KG | 190 | 50 | 9500 | 190 | 50 | 9500 | 190 | 50 | 9500 | 150 | 80.79 | 12118.62 | 0 | 0 | 0 | 0 | 190 | 0 | 9500 | Building
59 | COLUMN & LIFT ABOVE 1ST SLAB-CONCRETE-M30 | 100 | Started | Material | (M)CEMENT OPC 43 | BAG | 393.754 | 378.88 | 149185.52 | 393.754 | 378.88 | 149185.52 | 394 | 378.88 | 149278.72 | 0 | 0 | 0 | 0 | 0 | 0 | -0.246 | 393.754 | -93.204 | 149185.5155 | Building
60 | COLUMN & LIFT ABOVE 1ST SLAB-CONCRETE-M30 | 100 | Started | Material | (M)Crush Sand | BRASS | 9.1521 | 3675 | 33633.97 | 9.1521 | 3675 | 33633.97 | 9 | 3675 | 33075 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1521 | 9.1521 | 558.968 | 33633.9675 | Building
61 | COLUMN & LIFT ABOVE 1ST SLAB-CONCRETE-M30 | 100 | Started | Material | (M)Metal No.III 20MM | BRASS | 13.7282 | 3045 | 41802.37 | 13.7282 | 3045 | 41802.37 | 14 | 3045 | 42630 | 0 | 0 | 0 | 0 | 0 | 0 | -0.2718 | 13.7282 | -827.631 | 41802.369 | Building
62 | A BLDG.1ST SLAB | 0 | Tentative | Labour | (L)SHUTTERING, R/F & CASTING OF SLAB | SQFT | 3478.3413 | 197.06 | 685441.94 | 0 | 0 | 0 | 0 | 197.06 | 0 | 3478.3413 | 197.06 | 685441.9371 | 0 | 0 | 0 | 3478.3413 | 3478.3413 | 685441.937 | 685441.9366
63 | 2ND SLAB (BEAM,SLAB & ST CASE)-8MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 8mm (Fe 500, 0.395 KGS/Rm) | KG | 4000 | 59 | 236000 | 4000 | 59 | 236000 | 400 | 59 | 23600 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 4000 | 212400 | 236000 | Building
64 | 2ND SLAB (BEAM,SLAB & ST CASE)-10MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 10mm (Fe 500, 0.617 KGS/Rm) | KG | 850 | 59 | 50150 | 850 | 59 | 50150 | 85 | 59 | 5015 | 850 | 58.69 | 49888.285 | 0 | 0 | 0 | 765 | 850 | 45135 | 50150 | Building
65 | 2ND SLAB (BEAM,SLAB & ST CASE)-12MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 12mm (Fe 500, 0.888 KGS/Rm) | KG | 2100 | 59 | 123900 | 2100 | 59 | 123900 | 210 | 59 | 12390 | 0 | 0 | 0 | 0 | 0 | 0 | 1890 | 2100 | 111510 | 123900 | Building
66 | 2ND SLAB (BEAM,SLAB & ST CASE)-16MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 16mm (Fe 500, 1.58 KGS/Rm) | KG | 1800 | 59 | 106200 | 1800 | 59 | 106200 | 180 | 59 | 10620 | 1800 | 58.69 | 105645.78 | 0 | 0 | 0 | 1620 | 1800 | 95580 | 106200 | Building
67 | 2ND SLAB (BEAM,SLAB & ST CASE)-20MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 20mm (Fe 500, 2.47 KGS/Rm) | KG | 1400 | 59 | 82600 | 1400 | 59 | 82600 | 140 | 59 | 8260 | 1000 | 58.69 | 58692.1 | 0 | 0 | 0 | 1260 | 1400 | 74340 | 82600 | Building
68 | 2ND SLAB (BEAM,SLAB & ST CASE)-25MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 25mm (Fe 500, 3.85 KGS/Rm) | KG | 1800 | 59 | 106200 | 1800 | 59 | 106200 | 180 | 59 | 10620 | 1800 | 58.69 | 105645.78 | 0 | 0 | 0 | 1620 | 1800 | 95580 | 106200 | Building
69 | 2ND SLAB (BEAM,SLAB & ST CASE)-BINDING WIRE | 10 | Started | Material | (M)MS Binding Wire 18G | KG | 250 | 50 | 12500 | 250 | 50 | 12500 | 25 | 50 | 1250 | 250 | 80.79 | 20197.7 | 0 | 0 | 0 | 225 | 250 | 11250 | 12500 | Building
70 | 2ND SLAB (BEAM,SLAB & ST CASE)-CONCRETE-M25 | 10 | Started | Material | (M)CEMENT OPC 43 | BAG | 850.032 | 378.88 | 322060.12 | 850.032 | 378.88 | 322060.12 | 85 | 378.88 | 32204.8 | 0 | 0 | 0 | 0 | 0 | 0 | 765.032 | 850.032 | 289855.324 | 322060.1242 | Building
71 | 2ND SLAB (BEAM,SLAB & ST CASE)-CONCRETE-M25 | 10 | Started | Material | (M)Crush Sand | BRASS | 33.0568 | 3675 | 121483.74 | 33.0568 | 3675 | 121483.74 | 3 | 3675 | 11025 | 0 | 0 | 0 | 0 | 0 | 0 | 30.0568 | 33.0568 | 110458.74 | 121483.74 | Building
72 | 2ND SLAB (BEAM,SLAB & ST CASE)-CONCRETE-M25 | 10 | Started | Material | (M)Metal No.III 20MM | BRASS | 51.12 | 3045 | 155660.4 | 51.12 | 3045 | 155660.4 | 5 | 3045 | 15225 | 0 | 0 | 0 | 0 | 0 | 0 | 46.12 | 51.12 | 140435.4 | 155660.4 | Building
73 | COLUMN & LIFT ABOVE 2ND SLAB-8MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 8mm (Fe 500, 0.395 KGS/Rm) | KG | 4000 | 59 | 236000 | 4000 | 59 | 236000 | 400 | 59 | 23600 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 4000 | 212400 | 236000 | Building
74 | COLUMN & LIFT ABOVE 2ND SLAB-10MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 10mm (Fe 500, 0.617 KGS/Rm) | KG | 650 | 59 | 38350 | 650 | 59 | 38350 | 65 | 59 | 3835 | 150 | 58.69 | 8803.815 | 0 | 0 | 0 | 585 | 650 | 34515 | 38350 | Building
75 | COLUMN & LIFT ABOVE 2ND SLAB-12MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 12mm (Fe 500, 0.888 KGS/Rm) | KG | 900 | 59 | 53100 | 900 | 59 | 53100 | 90 | 59 | 5310 | 900 | 58.69 | 52822.89 | 0 | 0 | 0 | 810 | 900 | 47790 | 53100 | Building
76 | COLUMN & LIFT ABOVE 2ND SLAB-16MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 16mm (Fe 500, 1.58 KGS/Rm) | KG | 2200 | 59 | 129800 | 2200 | 59 | 129800 | 220 | 59 | 12980 | 2200 | 58.69 | 129122.62 | 0 | 0 | 0 | 1980 | 2200 | 116820 | 129800 | Building
77 | COLUMN & LIFT ABOVE 2ND SLAB-20MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 20mm (Fe 500, 2.47 KGS/Rm) | KG | 4600 | 59 | 271400 | 4600 | 59 | 271400 | 460 | 59 | 27140 | 0 | 0 | 0 | 0 | 0 | 0 | 4140 | 4600 | 244260 | 271400 | Building
78 | COLUMN & LIFT ABOVE 2ND SLAB-25MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 25mm (Fe 500, 3.85 KGS/Rm) | KG | 3200 | 59 | 188800 | 3200 | 59 | 188800 | 320 | 59 | 18880 | 3200 | 58.69 | 187814.72 | 0 | 0 | 0 | 2880 | 3200 | 169920 | 188800 | Building
79 | COLUMN & LIFT ABOVE 2ND SLAB-BINDING WIRE | 10 | Started | Material | (M)MS Binding Wire 18G | KG | 200 | 50 | 10000 | 200 | 50 | 10000 | 20 | 50 | 1000 | 200 | 80.79 | 16158.16 | 0 | 0 | 0 | 180 | 200 | 9000 | 10000 | Building
80 | COLUMN & LIFT ABOVE 2ND SLAB-CONCRETE-M30 | 10 | Started | Material | (M)CEMENT OPC 43 | BAG | 379.472 | 378.88 | 143774.35 | 379.472 | 378.88 | 143774.35 | 38 | 378.88 | 14397.44 | 0 | 0 | 0 | 0 | 0 | 0 | 341.472 | 379.472 | 129376.911 | 143774.3514 | Building
81 | COLUMN & LIFT ABOVE 2ND SLAB-CONCRETE-M30 | 10 | Started | Material | (M)Crush Sand | BRASS | 8.8202 | 3675 | 32414.24 | 8.8202 | 3675 | 32414.24 | 1 | 3675 | 3675 | 0 | 0 | 0 | 0 | 0 | 0 | 7.8202 | 8.8202 | 28739.235 | 32414.235 | Building
82 | COLUMN & LIFT ABOVE 2ND SLAB-CONCRETE-M30 | 10 | Started | Material | (M)Metal No.III 20MM | BRASS | 13.2302 | 3045 | 40285.96 | 13.2302 | 3045 | 40285.96 | 1 | 3045 | 3045 | 0 | 0 | 0 | 0 | 0 | 0 | 12.2302 | 13.2302 | 37240.959 | 40285.959 | Building
83 | A BLDG.2ND SLAB | 0 | Tentative | Labour | (L)SHUTTERING, R/F & CASTING OF SLAB | SQFT | 4013.4731 | 197.06 | 790895.01 | 0 | 0 | 0 | 0 | 197.06 | 0 | 4013.4731 | 197.06 | 790895.0077 | 0 | 0 | 0 | 4013.4731 | 4013.4731 | 790895.009 | 790895.0091
84 | PERMA BOND SBR (A WING 6TH & 7TH SLAB-RCC WORK) | 0 | Started | Material | (M)Perma Bond Sbr - 25 Lit | BUCKET | 2 | 5500 | 11000 | 0 | 0 | 0 | 0 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 11000 | 11000
85 | PERMA BOND SBR (A WING UP 1ST & 2ND SLAB-RCC WORK) | 0 | Started | Material | (M)Perma Bond Sbr - 25 Lit | BUCKET | 2 | 5500 | 11000 | 0 | 0 | 0 | 0 | 5500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 11000 | 11000
86 | A WING 3RD SLAB-STELL 8MM | 10 | Started | Material | (M)T.M.T.Bar 8mm (Fe 500, 0.395 KGS/Rm) | KG | 6000 | 59 | 354000 | 6000 | 59 | 354000 | 600 | 59 | 35400 | 6000 | 58.69 | 352152.6 | 0 | 0 | 0 | 5400 | 6000 | 318600 | 354000 | Building
87 | A WING 3RD SLAB-STELL 10MM | 10 | Started | Material | (M)T.M.T.Bar 10mm (Fe 500, 0.617 KGS/Rm) | KG | 1500 | 59 | 88500 | 1500 | 59 | 88500 | 150 | 59 | 8850 | 0 | 0 | 0 | 0 | 0 | 0 | 1350 | 1500 | 79650 | 88500 | Building
88 | A WING 3RD SLAB-STELL 12MM | 10 | Started | Material | (M)T.M.T.Bar 12mm (Fe 500, 0.888 KGS/Rm) | KG | 3000 | 59 | 177000 | 3000 | 59 | 177000 | 300 | 59 | 17700 | 0 | 0 | 0 | 0 | 0 | 0 | 2700 | 3000 | 159300 | 177000 | Building
89 | A WING 3RD SLAB-STELL 16MM | 10 | Started | Material | (M)T.M.T.Bar 16mm (Fe 500, 1.58 KGS/Rm) | KG | 2000 | 59 | 118000 | 2000 | 59 | 118000 | 200 | 59 | 11800 | 2000 | 58.69 | 117384.2 | 0 | 0 | 0 | 1800 | 2000 | 106200 | 118000 | Building
90 | A WING 3RD SLAB-STELL 20MM | 10 | Started | Material | (M)T.M.T.Bar 20mm (Fe 500, 2.47 KGS/Rm) | KG | 2000 | 59 | 118000 | 2000 | 59 | 118000 | 200 | 59 | 11800 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 2000 | 106200 | 118000 | Building
91 | A WING 3RD SLAB-STELL 25MM | 10 | Started | Material | (M)T.M.T.Bar 25mm (Fe 500, 3.85 KGS/Rm) | KG | 1600 | 59 | 94400 | 1600 | 59 | 94400 | 160 | 59 | 9440 | 1600 | 58.69 | 93907.36 | 0 | 0 | 0 | 1440 | 1600 | 84960 | 94400 | Building
92 | A WING 3RD SLAB-STELL BINDING WIRE | 10 | Started | Material | (M)MS Binding Wire 18G | KG | 200 | 50 | 10000 | 200 | 50 | 10000 | 20 | 50 | 1000 | 200 | 80.79 | 16158.16 | 200 | 80.24 | 16048 | 180 | 0 | 9000 | -6048 | Building
93 | A WING 3RD SLAB CONCRETE-M25 | 10 | Started | Material | (M)CEMENT OPC 43 | BAG | 850 | 378.88 | 322048 | 850 | 378.88 | 322048 | 85 | 378.88 | 32204.8 | 0 | 0 | 0 | 0 | 0 | 0 | 765 | 850 | 289843.2 | 322048 | Building
94 | A WING 3RD SLAB CONCRETE-M25 | 10 | Started | Material | (M)Crush Sand | BRASS | 25.8 | 3675 | 94815 | 25.8 | 3675 | 94815 | 3 | 3675 | 11025 | 25.8 | 3675 | 94815 | 0 | 0 | 0 | 22.8 | 25.8 | 83790 | 94815 | Building
95 | A WING 3RD SLAB CONCRETE-M25 | 10 | Started | Material | (M)Metal No.III 20MM | BRASS | 31.8 | 3045 | 96831 | 31.8 | 3045 | 96831 | 3 | 3045 | 9135 | 0 | 0 | 0 | 0 | 0 | 0 | 28.8 | 31.8 | 87696 | 96831 | Building
96 | A WING COL.ABV 3RD SLAB-STEEL 8MM | 10 | Started | Material | (M)T.M.T.Bar 8mm (Fe 500, 0.395 KGS/Rm) | KG | 4000 | 59 | 236000 | 4000 | 59 | 236000 | 400 | 59 | 23600 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 4000 | 212400 | 236000 | Building
97 | A WING COL.ABV 3RD SLAB-STEEL 12MM | 10 | Started | Material | (M)T.M.T.Bar 12mm (Fe 500, 0.888 KGS/Rm) | KG | 1000 | 59 | 59000 | 1000 | 59 | 59000 | 100 | 59 | 5900 | 1000 | 58.69 | 58692.1 | 0 | 0 | 0 | 900 | 1000 | 53100 | 59000 | Building
98 | A WING COL.ABV 3RD SLAB-STEEL 16MM | 10 | Started | Material | (M)T.M.T.Bar 16mm (Fe 500, 1.58 KGS/Rm) | KG | 2500 | 59 | 147500 | 2500 | 59 | 147500 | 250 | 59 | 14750 | 0 | 0 | 0 | 0 | 0 | 0 | 2250 | 2500 | 132750 | 147500 | Building
99 | A WING COL.ABV 3RD SLAB-STEEL 20MM | 10 | Started | Material | (M)T.M.T.Bar 20mm (Fe 500, 2.47 KGS/Rm) | KG | 3000 | 59 | 177000 | 3000 | 59 | 177000 | 300 | 59 | 17700 | 0 | 0 | 0 | 0 | 0 | 0 | 2700 | 3000 | 159300 | 177000 | Building
100 | A WING COL.ABV 3RD SLAB-STEEL 25MM | 10 | Started | Material | (M)T.M.T.Bar 25mm (Fe 500, 3.85 KGS/Rm) | KG | 1400 | 59 | 82600 | 1400 | 59 | 82600 | 140 | 59 | 8260 | 1400 | 58.69 | 82168.94 | 0 | 0 | 0 | 1260 | 1400 | 74340 | 82600 | Building
101 | A WING COL.ABV 3RD SLAB-STEEL BINDING WIRE | 10 | Started | Material | (M)MS Binding Wire 18G | KG | 175 | 50 | 8750 | 175 | 50 | 8750 | 18 | 50 | 900 | 0 | 0 | 0 | 175 | 80.24 | 14042 | 157 | 0 | 7850 | -5292 | Building
102 | A WING COL.ABV 3RD SLAB-CONCRETE M30 | 10 | Started | Material | (M)CEMENT OPC 43 | BAG | 350 | 378.88 | 132608 | 350 | 378.88 | 132608 | 35 | 378.88 | 13260.8 | 0 | 0 | 0 | 0 | 0 | 0 | 315 | 350 | 119347.2 | 132608 | Building
103 | A WING COL.ABV 3RD SLAB-CONCRETE M30 | 10 | Started | Material | (M)Crush Sand | BRASS | 9.541 | 3675 | 35063.18 | 9.541 | 3675 | 35063.18 | 1 | 3675 | 3675 | 0 | 0 | 0 | 0 | 0 | 0 | 8.541 | 9.541 | 31388.175 | 35063.175 | Building
104 | A WING COL.ABV 3RD SLAB-CONCRETE M30 | 10 | Started | Material | (M)Metal No.III 20MM | BRASS | 12.37 | 3045 | 37666.65 | 12.37 | 3045 | 37666.65 | 1 | 3045 | 3045 | 0 | 0 | 0 | 0 | 0 | 0 | 11.37 | 12.37 | 34621.65 | 37666.65 | Building
105 | A BLDG.3RD SLAB | 0 | Tentative | Labour | (L)SHUTTERING, R/F & CASTING OF SLAB | SQFT | 3478.3413 | 197.06 | 685441.94 | 0 | 0 | 0 | 0 | 197.06 | 0 | 3478.3413 | 197.06 | 685441.9371 | 0 | 0 | 0 | 3478.3413 | 3478.3413 | 685441.937 | 685441.9366
106 | INDENT-805/A BLDG/RCC-4TH SLAB & ABV.COLUMN | 0 | Started | Material | (M)CEMENT OPC 43 | BAG | 1250 | 378.88 | 473600 | 1250 | 378.88 | 473600 | 0 | 378.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250 | 1250 | 473600 | 473600 | Building
107 | INDENT-805/A BLDG/RCC-4TH SLAB & ABV.COLUMN | 0 | Started | Material | (M)Crush Sand | BRASS | 35.5 | 3675 | 130462.5 | 35.5 | 3675 | 130462.5 | 0 | 3675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35.5 | 35.5 | 130462.5 | 130462.5 | Building
108 | INDENT-805/A BLDG/RCC-4TH SLAB & ABV.COLUMN | 0 | Started | Material | (M)Metal No.III 20MM | BRASS | 44.2 | 3045 | 134589 | 44.2 | 3045 | 134589 | 0 | 3045 | 0 | 44.2 | 3205.35 | 141676.5065 | 0 | 0 | 0 | 44.2 | 44.2 | 134589 | 134589 | Building
109 | INDENT-805/A BLDG/RCC-4TH SLAB & ABV.COLUMN | 0 | Started | Material | (M)MS Binding Wire 18G | KG | 400 | 50 | 20000 | 400 | 50 | 20000 | 0 | 50 | 0 | 0 | 0 | 0 | 400 | 80.24 | 32096 | 400 | 0 | 20000 | -12096 | Building
110 | INDENT-805/A BLDG/RCC-4TH SLAB & ABV.COLUMN | 0 | Started | Material | (M)PERMA BOND SBR 25 LTR BUCKET | BUCKET | 1 | 4491.75 | 4491.75 | 1 | 4491.75 | 4491.75 | 0 | 4491.75 | 0 | 1 | 5300 | 5300 | 0 | 0 | 0 | 1 | 1 | 4491.75 | 4491.75 | Building
111 | INDENT-805/A BLDG/RCC-4TH SLAB & ABV.COLUMN | 0 | Started | Material | (M)T.M.T.Bar 10mm (Fe 500, 0.617 KGS/Rm) | KG | 1500 | 59 | 88500 | 1500 | 59 | 88500 | 0 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1500 | 88500 | 88500 | Building
112 | INDENT-805/A BLDG/RCC-4TH SLAB & ABV.COLUMN | 0 | Started | Material | (M)T.M.T.Bar 12mm (Fe 500, 0.888 KGS/Rm) | KG | 3000 | 59 | 177000 | 3000 | 59 | 177000 | 0 | 59 | 0 | 0 | 0 | 0 | 727.41 | 60.06 | 43686.21 | 3000 | 2272.59 | 177000 | 133313.79 | Building
113 | INDENT-805/A BLDG/RCC-4TH SLAB & ABV.COLUMN | 0 | Started | Material | (M)T.M.T.Bar 16mm (Fe 500, 1.58 KGS/Rm) | KG | 4000 | 59 | 236000 | 4000 | 59 | 236000 | 0 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 4000 | 236000 | 236000 | Building
114 | INDENT-805/A BLDG/RCC-4TH SLAB & ABV.COLUMN | 0 | Started | Material | (M)T.M.T.Bar 20mm (Fe 500, 2.47 KGS/Rm) | KG | 5000 | 59 | 295000 | 5000 | 59 | 295000 | 0 | 59 | 0 | 0 | 0 | 0 | 289.04 | 60.47 | 17479.26 | 5000 | 4710.96 | 295000 | 277520.74 | Building
115 | INDENT-805/A BLDG/RCC-4TH SLAB & ABV.COLUMN | 0 | Started | Material | (M)T.M.T.Bar 25mm (Fe 500, 3.85 KGS/Rm) | KG | 2500 | 59 | 147500 | 2500 | 59 | 147500 | 0 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 2500 | 147500 | 147500 | Building
116 | INDENT-805/A BLDG/RCC-4TH SLAB & ABV.COLUMN | 0 | Started | Material | (M)T.M.T.Bar 8mm (Fe 500, 0.395 KGS/Rm) | KG | 9000 | 59 | 531000 | 9000 | 59 | 531000 | 0 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | 9000 | 531000 | 531000 | Building
117 | INDENT-847/A BLDG/RCC-5TH SLAB & ABV.COLUMN | 0 | Started | Material | (M)CEMENT OPC 43 | BAG | 1250 | 378.88 | 473600 | 1250 | 378.88 | 473600 | 0 | 378.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250 | 1250 | 473600 | 473600 | Building
118 | INDENT-847/A BLDG/RCC-5TH SLAB & ABV.COLUMN | 0 | Started | Material | (M)Crush Sand | BRASS | 37.2 | 3675 | 136710 | 37.2 | 3675 | 136710 | 0 | 3675 | 0 | 37.2 | 3675 | 136710 | 0 | 0 | 0 | 37.2 | 37.2 | 136710 | 136710 | Building
119 | INDENT-847/A BLDG/RCC-5TH SLAB & ABV.COLUMN | 0 | Started | Material | (M)Metal No.III 20MM | BRASS | 46 | 3045 | 140070 | 46 | 3045 | 140070 | 0 | 3045 | 0 | 46 | 3360 | 154560 | 0 | 0 | 0 | 46 | 46 | 140070 | 140070 | Building
120 | INDENT-847/A BLDG/RCC-5TH SLAB & ABV.COLUMN | 0 | Started | Material | (M)T.M.T.Bar 10mm (Fe 500, 0.617 KGS/Rm) | KG | 1500 | 59 | 88500 | 1500 | 59 | 88500 | 0 | 59 | 0 | 0 | 0 | 0 | 407.22 | 59.36 | 24171.44 | 1500 | 1092.78 | 88500 | 64328.56 | Building
121 | INDENT-847/A BLDG/RCC-5TH SLAB & ABV.COLUMN | 0 | Started | Material | (M)T.M.T.Bar 12mm (Fe 500, 0.888 KGS/Rm) | KG | 3500 | 59 | 206500 | 3500 | 59 | 206500 | 0 | 59 | 0 | 0 | 0 | 0 | 3499.3 | 60.06 | 210157.92 | 3500 | 0.7 | 206500 | -3657.92 | Building
122 | INDENT-847/A BLDG/RCC-5TH SLAB & ABV.COLUMN | 0 | Started | Material | (M)T.M.T.Bar 16mm (Fe 500, 1.58 KGS/Rm) | KG | 4500 | 59 | 265500 | 4500 | 59 | 265500 | 0 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | 4500 | 265500 | 265500 | Building
123 | INDENT-847/A BLDG/RCC-5TH SLAB & ABV.COLUMN | 0 | Started | Material | (M)T.M.T.Bar 20mm (Fe 500, 2.47 KGS/Rm) | KG | 3500 | 59 | 206500 | 3500 | 59 | 206500 | 0 | 59 | 0 | 0 | 0 | 0 | 3500 | 60.47 | 211657.25 | 3500 | 0 | 206500 | -5157.25 | Building
124 | INDENT-847/A BLDG/RCC-5TH SLAB & ABV.COLUMN | 0 | Started | Material | (M)T.M.T.Bar 25mm (Fe 500, 3.85 KGS/Rm) | KG | 1500 | 59 | 88500 | 1500 | 59 | 88500 | 0 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 1500 | 88500 | 88500 | Building
125 | INDENT-847/A BLDG/RCC-5TH SLAB & ABV.COLUMN | 0 | Started | Material | (M)T.M.T.Bar 8mm (Fe 500, 0.395 KGS/Rm) | KG | 9000 | 59 | 531000 | 9000 | 59 | 531000 | 0 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9000 | 9000 | 531000 | 531000 | Building
126 | A WING 6TH SLAB-STELL 8MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 8mm (Fe 500, 0.395 KGS/Rm) | KG | 5500 | 59 | 324500 | 5500 | 59 | 324500 | 550 | 59 | 32450 | 5500 | 61.95 | 340725 | 3626.34 | 62.18 | 225479.94 | 4950 | 1873.66 | 292050 | 99020.06
127 | A WING 6TH SLAB-STELL 12MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 12mm (Fe 500, 0.888 KGS/Rm) | KG | 2000 | 59 | 118000 | 2000 | 59 | 118000 | 200 | 59 | 11800 | 2000 | 60.18 | 120360 | 1998.2 | 60.06 | 120006.3 | 1800 | 1.8 | 106200 | -2006.3
128 | A WING 6TH SLAB-STELL 16MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 16mm (Fe 500, 1.58 KGS/Rm) | KG | 2500 | 59 | 147500 | 2500 | 59 | 147500 | 250 | 59 | 14750 | 2500 | 60.18 | 150450 | 2500 | 60.83 | 152074.75 | 2250 | 0 | 132750 | -4574.75
129 | A WING 6TH SLAB-STELL 20MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 20mm (Fe 500, 2.47 KGS/Rm) | KG | 750 | 59 | 44250 | 750 | 59 | 44250 | 75 | 59 | 4425 | 750 | 60.18 | 45135 | 750 | 60.47 | 45355.13 | 675 | 0 | 39825 | -1105.13
130 | A WING 6TH SLAB-STELL 25MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 25mm (Fe 500, 3.85 KGS/Rm) | KG | 1500 | 59 | 88500 | 1500 | 59 | 88500 | 150 | 59 | 8850 | 1500 | 60.18 | 90270 | 1500 | 58.91 | 88369.65 | 1350 | 0 | 79650 | 130.35
131 | A WING 6TH SLAB-STELL PERMA BOND SBR | 10 | Started | Material | (M)PERMA BOND SBR | LITRE | 25 | 291.08 | 7277 | 25 | 291.08 | 7277 | 3 | 291.08 | 873.24 | 25 | 212.01 | 5300.27 | 0 | 0 | 0 | 22 | 25 | 6403.76 | 7277
132 | A WING 6TH SLAB CONCRETE-M25 CONCRETE-M25 | 10 | Started | Material | (M)CEMENT OPC 43 | BAG | 967 | 378.88 | 366376.96 | 967 | 378.88 | 366376.96 | 97 | 378.88 | 36751.36 | 967 | 364.99 | 352947.264 | 855 | 345 | 294975 | 870 | 112 | 329625.6 | 71401.96
133 | A WING 6TH SLAB CONCRETE-M25 CONCRETE-M25 | 10 | Started | Material | (M)Crush Sand | BRASS | 27.65 | 3675 | 101613.75 | 27.65 | 3675 | 101613.75 | 3 | 3675 | 11025 | 27.65 | 3675 | 101613.75 | 0 | 0 | 0 | 24.65 | 27.65 | 90588.75 | 101613.75
134 | A WING 6TH SLAB CONCRETE-M25 CONCRETE-M25 | 10 | Started | Material | (M)Metal No.III 20MM | BRASS | 32.7 | 3045 | 99571.5 | 32.7 | 3045 | 99571.5 | 3 | 3045 | 9135 | 32.7 | 3360 | 109872 | 0 | 0 | 0 | 29.7 | 32.7 | 90436.5 | 99571.5
135 | A WING COL.ABV 6TH SLAB-CONCRETE M25 CONCRETE-M25 | 10 | Started | Material | (M)CEMENT OPC 43 | BAG | 333 | 378.88 | 126167.04 | 333 | 378.88 | 126167.04 | 33 | 378.88 | 12503.04 | 233 | 364.99 | 85043.136 | 260 | 345 | 89700 | 300 | 73 | 113664 | 36467.04
136 | A WING COL.ABV 6TH SLAB-CONCRETE M25 CONCRETE-M25 | 10 | Started | Material | (M)Crush Sand | BRASS | 9.5 | 3675 | 34912.5 | 9.5 | 3675 | 34912.5 | 1 | 3675 | 3675 | 9.5 | 3675 | 34912.5 | 0 | 0 | 0 | 8.5 | 9.5 | 31237.5 | 34912.5
137 | A WING COL.ABV 6TH SLAB-CONCRETE M25 CONCRETE-M25 | 10 | Started | Material | (M)Metal No.III 20MM | BRASS | 11.5 | 3045 | 35017.5 | 11.5 | 3045 | 35017.5 | 1 | 3045 | 3045 | 11.5 | 3360 | 38640 | 0 | 0 | 0 | 10.5 | 11.5 | 31972.5 | 35017.5
138 | A WING 7TH SLAB-STELL 8MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 8mm (Fe 500, 0.395 KGS/Rm) | KG | 5500 | 59 | 324500 | 5500 | 59 | 324500 | 550 | 59 | 32450 | 5500 | 64.07 | 352407 | 7735.68 | 61.77 | 477860.03 | 4950 | -2235.68 | 292050 | -153360.03
139 | A WING 7TH SLAB-STELL 12MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 12mm (Fe 500, 0.888 KGS/Rm) | KG | 2000 | 59 | 118000 | 2000 | 59 | 118000 | 200 | 59 | 11800 | 2000 | 62.3 | 124608 | 2131.2 | 60.06 | 127993.9 | 1800 | -131.2 | 106200 | -9993.9
140 | A WING 7TH SLAB-STELL 16MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 16mm (Fe 500, 1.58 KGS/Rm) | KG | 2500 | 59 | 147500 | 2500 | 59 | 147500 | 250 | 59 | 14750 | 2500 | 62.3 | 155760 | 2500 | 60.83 | 152074.75 | 2250 | 0 | 132750 | -4574.75
141 | A WING 7TH SLAB-STELL 20MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 20mm (Fe 500, 2.47 KGS/Rm) | KG | 750 | 59 | 44250 | 750 | 59 | 44250 | 75 | 59 | 4425 | 750 | 62.3 | 46728 | 750 | 60.47 | 45355.13 | 675 | 0 | 39825 | -1105.13
142 | A WING 7TH SLAB-STELL 25MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 25mm (Fe 500, 3.85 KGS/Rm) | KG | 1500 | 59 | 88500 | 1500 | 59 | 88500 | 150 | 59 | 8850 | 1500 | 62.3 | 93456 | 1500 | 58.91 | 88369.8 | 1350 | 0 | 79650 | 130.2
143 | A WING 7TH SLAB CONCRETE-M25 CONCRETE-M25 | 10 | Started | Material | (M)CEMENT OPC 43 | BAG | 967 | 378.88 | 366376.96 | 967 | 378.88 | 366376.96 | 97 | 378.88 | 36751.36 | 967 | 350 | 338453.0944 | 918 | 345 | 316710 | 870 | 49 | 329625.6 | 49666.96 | Swimming Pool
144 | A WING 7TH SLAB CONCRETE-M25 CONCRETE-M25 | 10 | Started | Material | (M)Crush Sand | BRASS | 27.65 | 3675 | 101613.75 | 27.65 | 3675 | 101613.75 | 3 | 3675 | 11025 | 27.65 | 3675 | 101613.75 | 0 | 0 | 0 | 24.65 | 27.65 | 90588.75 | 101613.75 | Swimming Pool
145 | A WING 7TH SLAB CONCRETE-M25 CONCRETE-M25 | 10 | Started | Material | (M)Metal No.III 20MM | BRASS | 32.7 | 3045 | 99571.5 | 32.7 | 3045 | 99571.5 | 3 | 3045 | 9135 | 32.7 | 3360 | 109872 | 0 | 0 | 0 | 29.7 | 32.7 | 90436.5 | 99571.5 | Swimming Pool
146 | A WING COL.ABV 7TH SLAB-CONCRETE M25 CONCRETE-M25 | 10 | Started | Material | (M)CEMENT OPC 43 | BAG | 333 | 378.88 | 126167.04 | 333 | 378.88 | 126167.04 | 33 | 378.88 | 12503.04 | 233 | 350 | 81550.7456 | 247 | 345 | 85215 | 300 | 86 | 113664 | 40952.04
147 | A WING COL.ABV 7TH SLAB-CONCRETE M25 CONCRETE-M25 | 10 | Started | Material | (M)Crush Sand | BRASS | 9.5 | 3675 | 34912.5 | 9.5 | 3675 | 34912.5 | 1 | 3675 | 3675 | 9.5 | 3675 | 34912.5 | 0 | 0 | 0 | 8.5 | 9.5 | 31237.5 | 34912.5
148 | A WING COL.ABV 7TH SLAB-CONCRETE M25 CONCRETE-M25 | 10 | Started | Material | (M)Metal No.III 20MM | BRASS | 11.5 | 3045 | 35017.5 | 11.5 | 3045 | 35017.5 | 1 | 3045 | 3045 | 11.5 | 3360 | 38640 | 0 | 0 | 0 | 10.5 | 11.5 | 31972.5 | 35017.5
149 | INDENT-23/A WING/RCC-8TH SLAB & ABOVE COLUMN R/F & RAW MATER | 10 | Started | Material | (M)CEMENT OPC 43 | BAG | 1250 | 378.88 | 473600 | 1250 | 378.88 | 473600 | 125 | 378.88 | 47360 | 1200 | 355 | 426000.12 | 1212 | 345 | 418140 | 1125 | 38 | 426240 | 55460
150 | INDENT-23/A WING/RCC-8TH SLAB & ABOVE COLUMN R/F & RAW MATER | 10 | Started | Material | (M)Crush Sand | BRASS | 37.2 | 3675 | 136710 | 37.2 | 3675 | 136710 | 4 | 3675 | 14700 | 37.2 | 3370.27 | 125374.2 | 0 | 0 | 0 | 33.2 | 37.2 | 122010 | 136710
151 | INDENT-23/A WING/RCC-8TH SLAB & ABOVE COLUMN R/F & RAW MATER | 10 | Started | Material | (M)Metal No.III 20MM | BRASS | 44.2 | 3045 | 134589 | 44.2 | 3045 | 134589 | 4 | 3045 | 12180 | 44.2 | 3063.96 | 135426.9048 | 0 | 0 | 0 | 40.2 | 44.2 | 122409 | 134589
152 | INDENT-23/A WING/RCC-8TH SLAB & ABOVE COLUMN R/F & RAW MATER | 10 | Started | Material | (M)T.M.T.Bar 12mm (Fe 500, 0.888 KGS/Rm) | KG | 1250 | 59 | 73750 | 1250 | 59 | 73750 | 125 | 59 | 7375 | 1250 | 61.71 | 77142.5 | 1250 | 60.06 | 75071.5 | 1125 | 0 | 66375 | -1321.5
153 | INDENT-23/A WING/RCC-8TH SLAB & ABOVE COLUMN R/F & RAW MATER | 10 | Started | Material | (M)T.M.T.Bar 16mm (Fe 500, 1.58 KGS/Rm) | KG | 3000 | 59 | 177000 | 3000 | 59 | 177000 | 300 | 59 | 17700 | 3000 | 61.71 | 185142 | 3191.8 | 60.83 | 194156.87 | 2700 | -191.8 | 159300 | -17156.87
154 | INDENT-23/A WING/RCC-8TH SLAB & ABOVE COLUMN R/F & RAW MATER | 10 | Started | Material | (M)T.M.T.Bar 20mm (Fe 500, 2.47 KGS/Rm) | KG | 1000 | 59 | 59000 | 1000 | 59 | 59000 | 100 | 59 | 5900 | 1000 | 61.71 | 61714 | 1000 | 60.47 | 60473.5 | 900 | 0 | 53100 | -1473.5
155 | INDENT-23/A WING/RCC-8TH SLAB & ABOVE COLUMN R/F & RAW MATER | 10 | Started | Material | (M)T.M.T.Bar 25mm (Fe 500, 3.85 KGS/Rm) | KG | 500 | 59 | 29500 | 500 | 59 | 29500 | 50 | 59 | 2950 | 500 | 61.71 | 30857 | 500 | 58.91 | 29456.6 | 450 | 0 | 26550 | 43.4
156 | INDENT-23/A WING/RCC-8TH SLAB & ABOVE COLUMN R/F & RAW MATER | 10 | Started | Material | (M)T.M.T.Bar 32mm (Fe 500, 6.31 KGS/Rm) | KG | 900 | 59 | 53100 | 900 | 59 | 53100 | 90 | 59 | 5310 | 900 | 63.48 | 57135.6 | 900 | 64.31 | 57879 | 810 | 0 | 47790 | -4779
157 | INDENT-23/A WING/RCC-8TH SLAB & ABOVE COLUMN R/F & RAW MATER | 10 | Started | Material | (M)T.M.T.Bar 8mm (Fe 500, 0.395 KGS/Rm) | KG | 3000 | 59 | 177000 | 3000 | 59 | 177000 | 300 | 59 | 17700 | 3000 | 63.48 | 190452 | 7977.42 | 61.77 | 492793.15 | 2700 | -4977.42 | 159300 | -315793.15
158 | INDENT-23/A WING/RCC-9TH SLAB & ABOVE COLUMN R/F & RAW MATER | 10 | Started | Material | (M)CEMENT OPC 43 | BAG | 1250 | 378.88 | 473600 | 1250 | 378.88 | 473600 | 125 | 378.88 | 47360 | 1250 | 348 | 435000 | 1120 | 345 | 386400 | 1125 | 130 | 426240 | 87200
159 | INDENT-23/A WING/RCC-9TH SLAB & ABOVE COLUMN R/F & RAW MATER | 10 | Started | Material | (M)Crush Sand | BRASS | 37.2 | 3675 | 136710 | 37.2 | 3675 | 136710 | 4 | 3675 | 14700 | 37.2 | 3570 | 132804 | 0 | 0 | 0 | 33.2 | 37.2 | 122010 | 136710
160 | INDENT-23/A WING/RCC-9TH SLAB & ABOVE COLUMN R/F & RAW MATER | 10 | Started | Material | (M)Metal No.III 20MM | BRASS | 44.2 | 3045 | 134589 | 44.2 | 3045 | 134589 | 4 | 3045 | 12180 | 44.2 | 3255 | 143871.0088 | 0 | 0 | 0 | 40.2 | 44.2 | 122409 | 134589
161 | INDENT-23/A WING/RCC-9TH SLAB & ABOVE COLUMN R/F & RAW MATER | 10 | Started | Material | (M)T.M.T.Bar 12mm (Fe 500, 0.888 KGS/Rm) | KG | 1250 | 59 | 73750 | 1250 | 59 | 73750 | 125 | 59 | 7375 | 1250 | 61.71 | 77142.5 | 1249.9 | 60.06 | 75065.49 | 1125 | 0.1 | 66375 | -1315.49
162 | INDENT-23/A WING/RCC-9TH SLAB & ABOVE COLUMN R/F & RAW MATER | 10 | Started | Material | (M)T.M.T.Bar 16mm (Fe 500, 1.58 KGS/Rm) | KG | 3000 | 59 | 177000 | 3000 | 59 | 177000 | 300 | 59 | 17700 | 3000 | 61.71 | 185142 | 3000 | 60.83 | 182489.85 | 2700 | 0 | 159300 | -5489.85
163 | INDENT-23/A WING/RCC-9TH SLAB & ABOVE COLUMN R/F & RAW MATER | 10 | Started | Material | (M)T.M.T.Bar 20mm (Fe 500, 2.47 KGS/Rm) | KG | 1000 | 59 | 59000 | 1000 | 59 | 59000 | 100 | 59 | 5900 | 1000 | 61.71 | 61714 | 1000 | 60.47 | 60473.5 | 900 | 0 | 53100 | -1473.5
164 | INDENT-23/A WING/RCC-9TH SLAB & ABOVE COLUMN R/F & RAW MATER | 10 | Started | Material | (M)T.M.T.Bar 25mm (Fe 500, 3.85 KGS/Rm) | KG | 500 | 59 | 29500 | 500 | 59 | 29500 | 50 | 59 | 2950 | 500 | 61.71 | 30857 | 500 | 58.91 | 29456.55 | 450 | 0 | 26550 | 43.45
165 | INDENT-23/A WING/RCC-9TH SLAB & ABOVE COLUMN R/F & RAW MATER | 10 | Started | Material | (M)T.M.T.Bar 32mm (Fe 500, 6.31 KGS/Rm) | KG | 900 | 59 | 53100 | 900 | 59 | 53100 | 90 | 59 | 5310 | 900 | 63.48 | 57135.6 | 337.6 | 64.31 | 21711.06 | 810 | 562.4 | 47790 | 31388.94
166 | INDENT-23/A WING/RCC-9TH SLAB & ABOVE COLUMN R/F & RAW MATER | 10 | Started | Material | (M)T.M.T.Bar 8mm (Fe 500, 0.395 KGS/Rm) | KG | 3000 | 59 | 177000 | 3000 | 59 | 177000 | 300 | 59 | 17700 | 3000 | 63.48 | 190452 | 8541.48 | 61.77 | 527637.61 | 2700 | -5541.48 | 159300 | -350637.61
167 | A BLDG. PLINTH COMPLETION | 0 | Tentative | Labour | (L)FOOTING, COL. UP TO PLINTH | SQFT | 2211.3713 | 197.06 | 435772.83 | 0 | 0 | 0 | 0 | 197.06 | 0 | 2211.3713 | 197.06 | 435772.8271 | 0 | 0 | 0 | 2211.3713 | 2211.3713 | 435772.828 | 435772.8284 | PLINTH BEAM
168 | A BLDG.4TH SLAB | 0 | Tentative | Labour | (L)SHUTTERING, R/F & CASTING OF SLAB | SQFT | 3478.3413 | 197.06 | 685441.94 | 0 | 0 | 0 | 0 | 197.06 | 0 | 3478.3413 | 197.06 | 685441.9371 | 0 | 0 | 0 | 3478.3413 | 3478.3413 | 685441.937 | 685441.9366
169 | A BLDG.5TH SLAB | 0 | Started | Labour | (L)SHUTTERING, R/F & CASTING OF SLAB | SQFT | 3478.3413 | 197.06 | 685441.94 | 0 | 0 | 0 | 0 | 197.06 | 0 | 3478.3413 | 197.06 | 685441.9371 | 3478.3413 | 197.06 | 685441.94 | 3478.3413 | 0 | 685441.937 | -0.0034
170 | A BLDG.6TH SLAB | 0 | Started | Labour | (L)SHUTTERING, R/F & CASTING OF SLAB | SQFT | 3612.1258 | 197.06 | 711805.51 | 0 | 0 | 0 | 0 | 197.06 | 0 | 3612.1258 | 197.06 | 711805.5086 | 3612.1258 | 197.06 | 711805.51 | 3612.1258 | 0 | 711805.51 | 0.0001
171 | A BLDG.7TH SLAB | 0 | Started | Labour | (L)SHUTTERING, R/F & CASTING OF SLAB | SQFT | 3612.1258 | 197.06 | 711805.51 | 0 | 0 | 0 | 0 | 197.06 | 0 | 3612.1258 | 197.06 | 711805.5086 | 3612.1258 | 197.06 | 711805.51 | 3612.1258 | 0 | 711805.51 | 0.0001
172 | A BLDG.8TH SLAB | 0 | Started | Labour | (L)SHUTTERING, R/F & CASTING OF SLAB | SQFT | 3612.1258 | 197.06 | 711805.51 | 0 | 0 | 0 | 0 | 197.06 | 0 | 3612.1258 | 197.06 | 711805.5086 | 3612.1258 | 197.06 | 711805.51 | 3612.1258 | 0 | 711805.51 | 0.0001
173 | A BLDG.9TH SLAB | 0 | Started | Labour | (L)SHUTTERING, R/F & CASTING OF SLAB | SQFT | 4682.3832 | 197.06 | 922710.43 | 0 | 0 | 0 | 0 | 197.06 | 0 | 4682.3832 | 197.06 | 922710.4344 | 4682.3832 | 197.06 | 922710.43 | 4682.3832 | 0 | 922710.433 | 0.0034
174 | A BLDG.10TH SLAB | 0 | Started | Labour | (L)SHUTTERING, R/F & CASTING OF SLAB | SQFT | 4682.3832 | 197.06 | 922710.43 | 0 | 0 | 0 | 0 | 197.06 | 0 | 4682.3832 | 197.06 | 922710.4344 | 4682.3832 | 197.06 | 922710.43 | 4682.3832 | 0 | 922710.433 | 0.0034
175 | A BLDG.11TH SLAB | 0 | Started | Labour | (L)SHUTTERING, R/F & CASTING OF SLAB | SQFT | 4849.6108 | 197.06 | 955664.3 | 0 | 0 | 0 | 0 | 197.06 | 0 | 4849.6108 | 197.06 | 955664.3036 | 4849.6108 | 197.06 | 955664.3 | 4849.6108 | 0 | 955664.304 | 0.0042
176 | A BLDG.12TH SLAB | 0 | Started | Labour | (L)SHUTTERING, R/F & CASTING OF SLAB | SQFT | 4849.6108 | 197.06 | 955664.3 | 0 | 0 | 0 | 0 | 197.06 | 0 | 4849.6108 | 197.06 | 955664.3036 | 4849.6108 | 197.06 | 955664.3 | 4849.6108 | 0 | 955664.304 | 0.0042
177 | A BLDG.13TH SLAB | 0 | Started | Labour | (L)SHUTTERING, R/F & CASTING OF SLAB | SQFT | 4849.6108 | 197.06 | 955664.3 | 0 | 0 | 0 | 0 | 197.06 | 0 | 4849.6108 | 197.06 | 955664.3036 | 4849.6108 | 197.06 | 955664.3 | 4849.6108 | 0 | 955664.304 | 0.0042
178 | A BLDG.LMR & OHWT | 0 | Tentative | Labour | (L)LMR & OHWT COMPLETION | SQFT | 602.018 | 197.06 | 118633.67 | 0 | 0 | 0 | 0 | 197.06 | 0 | 602.018 | 197.06 | 118633.666 | 0 | 0 | 0 | 602.018 | 602.018 | 118633.667 | 118633.6671
179 | A BLDG.PF | 0 | Tentative | Labour | (L)AFTER COMP. OF 6TH SLAB | SQFT | 253.485 | 197.06 | 49951.75 | 0 | 0 | 0 | 0 | 197.06 | 0 | 253.485 | 197.06 | 49951.755 | 0 | 0 | 0 | 253.485 | 253.485 | 49951.754 | 49951.7541
180 | A BLDG.PF | 0 | Tentative | Labour | (L)AFTER COMP. OF RCC WORK | SQFT | 337.9716 | 197.06 | 66600.68 | 0 | 0 | 0 | 0 | 197.06 | 0 | 337.9716 | 197.06 | 66600.6772 | 0 | 0 | 0 | 337.9716 | 337.9716 | 66600.684 | 66600.6835
181 | A BLDG.RETENTION | 0 | Tentative | Labour | (L)RETENTION-RCC WORK | SQFT | 1867.6886 | 197.06 | 368046.72 | 0 | 0 | 0 | 0 | 197.06 | 0 | 1867.6886 | 197.06 | 368046.7162 | 0 | 0 | 0 | 1867.6886 | 1867.6886 | 368046.716 | 368046.7155
182 | A BLDG. PLINTH COMP. | 0 | Tentative | Labour | (L)Plinth Beam, Soling, PCC | SQFT | 2189.3713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2189.3713 | 167 | 365625.0071 | 0 | 0 | 0 | 2189.3713 | 2189.3713 | 0 | 0
183 | A BLDG .1ST SLAB | 0 | Started | Labour | (L)Hacking & Deshuttering | SQFT | 1098.4251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1098.4251 | 167 | 183436.9917 | 228.8383 | 167 | 38216 | 1098.4251 | 869.5868 | 0 | -38216
184 | A BLDG. 2ND SLAB | 0 | Started | Labour | (L)Hacking & Deshuttering | SQFT | 1267.4072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1267.4072 | 167 | 211657.0024 | 264.0419 | 167 | 44095 | 1267.4072 | 1003.3653 | 0 | -44095
185 | A BLDG. 3RD SLAB | 0 | Started | Labour | (L)Hacking & Deshuttering | SQFT | 1098.4251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1098.4251 | 167 | 183436.9917 | 228.8383 | 167 | 38216 | 1098.4251 | 869.5868 | 0 | -38216
186 | A BLDG. 4TH SLAB | 0 | Started | Labour | (L)Hacking & Deshuttering | SQFT | 1098.4251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1098.4251 | 167 | 183436.9917 | 228.8383 | 167 | 38216 | 1098.4251 | 869.5868 | 0 | -38216
187 | A BLDG. 5TH SLAB | 0 | Started | Labour | (L)Hacking & Deshuttering | SQFT | 1098.4251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1098.4251 | 167 | 183436.9917 | 1098.4251 | 167 | 183436.99 | 1098.4251 | 0 | 0 | -183436.99
188 | A BLDG. 6TH SLAB | 0 | Started | Labour | (L)Hacking & Deshuttering | SQFT | 1140.6707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1140.6707 | 167 | 190492.0069 | 1140.6707 | 167 | 190492.01 | 1140.6707 | 0 | 0 | -190492.01
189 | A BLDG. 7TH SLAB | 0 | Started | Labour | (L)Hacking & Deshuttering | SQFT | 1140.6707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1140.6707 | 167 | 190492.0069 | 1140.6707 | 167 | 190492.01 | 1140.6707 | 0 | 0 | -190492.01
190 | A BLDG. 8TH SLAB | 0 | Started | Labour | (L)Hacking & Deshuttering | SQFT | 1140.6707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1140.6707 | 167 | 190492.0069 | 1140.6707 | 167 | 190492.01 | 1140.6707 | 0 | 0 | -190492.01
191 | A BLDG. 9TH SLAB | 0 | Started | Labour | (L)Hacking & Deshuttering | SQFT | 246.4431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 246.4431 | 167 | 41155.9977 | 246.4431 | 167 | 41156 | 246.4431 | 0 | 0 | -41156
192 | A BLDG. 10TH SLAB | 0 | Tentative | Labour | (L)Hacking & Deshuttering | SQFT | 246.4431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 246.4431 | 167 | 41155.9977 | 0 | 0 | 0 | 246.4431 | 246.4431 | 0 | 0
193 | A BLDG. 11TH SLAB | 0 | Tentative | Labour | (L)Hacking & Deshuttering | SQFT | 255.2455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255.2455 | 167 | 42625.9985 | 0 | 0 | 0 | 255.2455 | 255.2455 | 0 | 0
194 | A BLDG. 12TH SLAB | 0 | Tentative | Labour | (L)Hacking & Deshuttering | SQFT | 255.2455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255.2455 | 167 | 42625.9985 | 0 | 0 | 0 | 255.2455 | 255.2455 | 0 | 0
195 | A BLDG. 13TH SLAB | 0 | Tentative | Labour | (L)Hacking & Deshuttering | SQFT | 255.2455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255.2455 | 167 | 42625.9985 | 0 | 0 | 0 | 255.2455 | 255.2455 | 0 | 0
196 | A BLDG LMR & OHWT | 0 | Tentative | Labour | (L)Hacking & Deshuttering | SQFT | 665.3892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 665.3892 | 167 | 111119.9964 | 0 | 0 | 0 | 665.3892 | 665.3892 | 0 | 0
197 | A BLDG. MISC. WORK | 0 | Tentative | Labour | (L)ST-CASE PARDI,LINTEL & LOFT | SQFT | 880.1497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 880.1497 | 167 | 146984.9999 | 0 | 0 | 0 | 880.1497 | 880.1497 | 0 | 0
198 | A BLDG PF | 0 | Tentative | Labour | (L)AFTER COMP.OF 6MONTH OF WORK | SQFT | 253.485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 253.485 | 167 | 42331.995 | 0 | 0 | 0 | 253.485 | 253.485 | 0 | 0
199 | A BLDG CLEANING | 0 | Tentative | Labour | (L)UPTO 7TH & UPTO TOP TERR. | SQFT | 560.3053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 560.3053 | 167 | 93570.9851 | 0 | 0 | 0 | 560.3053 | 560.3053 | 0 | 0
200 | A BLDG RETENTION | 0 | Tentative | Labour | (L)Retention Amount | SQFT | 1867.6886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1867.6886 | 167 | 311903.9962 | 0 | 0 | 0 | 1867.6886 | 1867.6886 | 0 | 0
201 | INDENT-89/A WING/RCC-10th SLAB & ABV.COLUMN. | 0 | Started | Material | (M)CEMENT OPC 43 | BAG | 1250 | 378.88 | 473600 | 1250 | 378.88 | 473600 | 0 | 378.88 | 0 | 1200 | 345 | 414000 | 1136 | 347.77 | 395070 | 1250 | 114 | 473600 | 78530
202 | INDENT-89/A WING/RCC-10th SLAB & ABV.COLUMN. | 0 | Started | Material | (M)Crush Sand | BRASS | 37.2 | 3675 | 136710 | 37.2 | 3675 | 136710 | 0 | 3675 | 0 | 37.2 | 3780 | 140616 | 0 | 0 | 0 | 37.2 | 37.2 | 136710 | 136710
203 | INDENT-89/A WING/RCC-10th SLAB & ABV.COLUMN. | 0 | Started | Material | (M)Metal No.III 20MM | BRASS | 44.2 | 3045 | 134589 | 44.2 | 3045 | 134589 | 0 | 3045 | 0 | 44.2 | 3570 | 157794 | 0 | 0 | 0 | 44.2 | 44.2 | 134589 | 134589
204 | INDENT-89/A WING/RCC-10th SLAB & ABV.COLUMN. | 0 | Started | Material | (M)MS Binding Wire 18G | KG | 400 | 50 | 20000 | 400 | 50 | 20000 | 0 | 50 | 0 | 400 | 80.24 | 32096 | 400 | 80.24 | 32096 | 400 | 0 | 20000 | -12096
205 | INDENT-89/A WING/RCC-10th SLAB & ABV.COLUMN. | 0 | Started | Material | (M)T.M.T.Bar 10mm (Fe 500, 0.617 KGS/Rm) | KG | 5500 | 59 | 324500 | 5500 | 59 | 324500 | 0 | 59 | 0 | 5500 | 55.93 | 307626 | 2362.92 | 59.36 | 140256.32 | 5500 | 3137.08 | 324500 | 184243.68
206 | INDENT-89/A WING/RCC-10th SLAB & ABV.COLUMN. | 0 | Started | Material | (M)T.M.T.Bar 12mm (Fe 500, 0.888 KGS/Rm) | KG | 4000 | 59 | 236000 | 4000 | 59 | 236000 | 0 | 59 | 0 | 4000 | 55.93 | 223728 | 3999.6 | 60.06 | 240204.61 | 4000 | 0.4 | 236000 | -4204.61
207 | INDENT-89/A WING/RCC-10th SLAB & ABV.COLUMN. | 0 | Started | Material | (M)T.M.T.Bar 16mm (Fe 500, 1.58 KGS/Rm) | KG | 4209 | 59 | 248331 | 4209 | 59 | 248331 | 0 | 59 | 0 | 4209 | 56.74 | 238804.27 | 4205.75 | 60.83 | 255835.58 | 4209 | 3.25 | 248331 | -7504.58
208 | INDENT-89/A WING/RCC-10th SLAB & ABV.COLUMN. | 0 | Started | Material | (M)T.M.T.Bar 20mm (Fe 500, 2.47 KGS/Rm) | KG | 2400 | 59 | 141600 | 2400 | 59 | 141600 | 0 | 59 | 0 | 2400 | 55.93 | 134236.8 | 2400 | 60.47 | 145136.4 | 2400 | 0 | 141600 | -3536.4
209 | INDENT-89/A WING/RCC-10th SLAB & ABV.COLUMN. | 0 | Started | Material | (M)T.M.T.Bar 25mm (Fe 500, 3.85 KGS/Rm) | KG | 4600 | 59 | 271400 | 4600 | 59 | 271400 | 0 | 59 | 0 | 4600 | 55.93 | 257287.2 | 2343.1 | 58.91 | 138039.37 | 4600 | 2256.9 | 271400 | 133360.63
210 | INDENT-89/A WING/RCC-10th SLAB & ABV.COLUMN. | 0 | Started | Material | (M)T.M.T.Bar 8mm (Fe 500, 0.395 KGS/Rm) | KG | 8500 | 59 | 501500 | 8500 | 59 | 501500 | 0 | 59 | 0 | 8500 | 57.7 | 490467 | 10075.2 | 61.77 | 622380.81 | 8500 | -1575.2 | 501500 | -120880.81
211 | INDENT-90/A WING/RCC-11th SLAB & ABV.COLUMN. | 0 | Started | Material | (M)CEMENT OPC 43 | BAG | 1250 | 378.88 | 473600 | 1250 | 378.88 | 473600 | 0 | 378.88 | 0 | 1200 | 360 | 432000 | 788 | 360 | 283680 | 1250 | 462 | 473600 | 189920
212 | INDENT-90/A WING/RCC-11th SLAB & ABV.COLUMN. | 0 | Started | Material | (M)Crush Sand | BRASS | 37.2 | 3675 | 136710 | 37.2 | 3675 | 136710 | 0 | 3675 | 0 | 37.2 | 3570 | 132804 | 0 | 0 | 0 | 37.2 | 37.2 | 136710 | 136710
213 | INDENT-90/A WING/RCC-11th SLAB & ABV.COLUMN. | 0 | Started | Material | (M)Metal No.III 20MM | BRASS | 44.2 | 3045 | 134589 | 44.2 | 3045 | 134589 | 0 | 3045 | 0 | 44.2 | 3255 | 143871 | 0 | 0 | 0 | 44.2 | 44.2 | 134589 | 134589
214 | INDENT-90/A WING/RCC-11th SLAB & ABV.COLUMN. | 0 | Started | Material | (M)MS Binding Wire 18G | KG | 400 | 50 | 20000 | 400 | 50 | 20000 | 0 | 50 | 0 | 400 | 80.24 | 32096 | 145.3 | 80.24 | 11658.87 | 400 | 254.7 | 20000 | 8341.13
215 | INDENT-90/A WING/RCC-11th SLAB & ABV.COLUMN. | 0 | Started | Material | (M)T.M.T.Bar 10mm (Fe 500, 0.617 KGS/Rm) | KG | 5500 | 59 | 324500 | 5500 | 59 | 324500 | 0 | 59 | 0 | 5500 | 54.87 | 301785 | 1222.2 | 59.36 | 72546.37 | 5500 | 4277.8 | 324500 | 251953.63
216 | INDENT-90/A WING/RCC-11th SLAB & ABV.COLUMN. | 0 | Started | Material | (M)T.M.T.Bar 12mm (Fe 500, 0.888 KGS/Rm) | KG | 4000 | 59 | 236000 | 4000 | 59 | 236000 | 0 | 59 | 0 | 4000 | 54.87 | 219480 | 4000 | 60.06 | 240228.62 | 4000 | 0 | 236000 | -4228.62
217 | INDENT-90/A WING/RCC-11th SLAB & ABV.COLUMN. | 0 | Started | Material | (M)T.M.T.Bar 16mm (Fe 500, 1.58 KGS/Rm) | KG | 4209 | 59 | 248331 | 4209 | 59 | 248331 | 0 | 59 | 0 | 4209 | 56.33 | 237105.07 | 2047.95 | 60.83 | 124576.68 | 4209 | 2161.05 | 248331 | 123754.32
218 | INDENT-90/A WING/RCC-11th SLAB & ABV.COLUMN. | 0 | Started | Material | (M)T.M.T.Bar 20mm (Fe 500, 2.47 KGS/Rm) | KG | 2400 | 59 | 141600 | 2400 | 59 | 141600 | 0 | 59 | 0 | 2400 | 54.87 | 131688 | 2400 | 60.47 | 145136.4 | 2400 | 0 | 141600 | -3536.4
219 | INDENT-90/A WING/RCC-11th SLAB & ABV.COLUMN. | 0 | Started | Material | (M)T.M.T.Bar 25mm (Fe 500, 3.85 KGS/Rm) | KG | 4600 | 59 | 271400 | 4600 | 59 | 271400 | 0 | 59 | 0 | 4600 | 54.87 | 252402 | 1574.2 | 58.91 | 92741.16 | 4600 | 3025.8 | 271400 | 178658.84
220 | INDENT-90/A WING/RCC-11th SLAB & ABV.COLUMN. | 0 | Started | Material | (M)T.M.T.Bar 8mm (Fe 500, 0.395 KGS/Rm) | KG | 8500 | 59 | 501500 | 8500 | 59 | 501500 | 0 | 59 | 0 | 8500 | 56.64 | 481440 | 5237.7 | 58.61 | 307004.97 | 8500 | 3262.3 | 501500 | 194495.03
221 | A WING 12TH SLAB & ABOVE COLUMN R/F & RAW MATERIAL | 0 | Started | Material | (M)CEMENT OPC 43 | BAG | 1250 | 378.88 | 473600 | 1250 | 378.88 | 473600 | 0 | 378.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250 | 1250 | 473600 | 473600
222 | A WING 12TH SLAB & ABOVE COLUMN R/F & RAW MATERIAL | 0 | Started | Material | (M)Crush Sand | BRASS | 37.2 | 3675 | 136710 | 37.2 | 3675 | 136710 | 0 | 3675 | 0 | 37.2 | 3675 | 136710 | 0 | 0 | 0 | 37.2 | 37.2 | 136710 | 136710
223 | A WING 12TH SLAB & ABOVE COLUMN R/F & RAW MATERIAL | 0 | Started | Material | (M)Metal No.III 20MM | BRASS | 44.52 | 3045 | 135563.4 | 44.52 | 3045 | 135563.4 | 0 | 3045 | 0 | 44.52 | 3373.25 | 150177.09 | 0 | 0 | 0 | 44.52 | 44.52 | 135563.4 | 135563.4
224 | A WING 12TH SLAB & ABOVE COLUMN R/F & RAW MATERIAL | 0 | Started | Material | (M)MS Binding Wire 18G | KG | 350 | 50 | 17500 | 350 | 50 | 17500 | 0 | 50 | 0 | 350 | 73.16 | 25606 | 0 | 0 | 0 | 350 | 350 | 17500 | 17500
225 | A WING 12TH SLAB & ABOVE COLUMN R/F & RAW MATERIAL | 0 | Started | Material | (M)RMC M-25 | CUM | 133 | 4600 | 611800 | 133 | 4600 | 611800 | 0 | 4600 | 0 | 128 | 5100 | 652800.0152 | 0 | 0 | 0 | 133 | 133 | 611800 | 611800
226 | A WING 12TH SLAB & ABOVE COLUMN R/F & RAW MATERIAL | 0 | Started | Material | (M)T.M.T.Bar 12mm (Fe 500, 0.888 KGS/Rm) | KG | 4000 | 59 | 236000 | 4000 | 59 | 236000 | 0 | 59 | 0 | 4000 | 59.94 | 239776 | 0 | 0 | 0 | 4000 | 4000 | 236000 | 236000
227 | A WING 12TH SLAB & ABOVE COLUMN R/F & RAW MATERIAL | 0 | Started | Material | (M)T.M.T.Bar 16mm (Fe 500, 1.58 KGS/Rm) | KG | 3000 | 59 | 177000 | 3000 | 59 | 177000 | 0 | 59 | 0 | 3000 | 59.94 | 179832 | 0 | 0 | 0 | 3000 | 3000 | 177000 | 177000
228 | A WING 12TH SLAB & ABOVE COLUMN R/F & RAW MATERIAL | 0 | Started | Material | (M)T.M.T.Bar 20mm (Fe 500, 2.47 KGS/Rm) | KG | 2000 | 59 | 118000 | 2000 | 59 | 118000 | 0 | 59 | 0 | 2000 | 60.53 | 121068 | 0 | 0 | 0 | 2000 | 2000 | 118000 | 118000
229 | A WING 12TH SLAB & ABOVE COLUMN R/F & RAW MATERIAL | 0 | Started | Material | (M)T.M.T.Bar 8mm (Fe 500, 0.395 KGS/Rm) | KG | 8000 | 59 | 472000 | 8000 | 59 | 472000 | 0 | 59 | 0 | 8000 | 61.71 | 493712 | 0 | 0 | 0 | 8000 | 8000 | 472000 | 472000
230 | A WING 13TH SLAB & OHWT R/F & RAW MATERIAL | 0 | Started | Material | (M)CEMENT OPC 43 | BAG | 474 | 378.88 | 179589.12 | 474 | 378.88 | 179589.12 | 0 | 378.88 | 0 | 91 | 358 | 32578 | 0 | 0 | 0 | 474 | 474 | 179589.12 | 179589.12
231 | A WING 13TH SLAB & OHWT R/F & RAW MATERIAL | 0 | Started | Material | (M)Crush Sand | BRASS | 14 | 3675 | 51450 | 14 | 3675 | 51450 | 0 | 3675 | 0 | 14 | 3675 | 51450 | 0 | 0 | 0 | 14 | 14 | 51450 | 51450
232 | A WING 13TH SLAB & OHWT R/F & RAW MATERIAL | 0 | Started | Material | (M)Metal No.III 20MM | BRASS | 18 | 3045 | 54810 | 18 | 3045 | 54810 | 0 | 3045 | 0 | 18 | 3360 | 60480 | 0 | 0 | 0 | 18 | 18 | 54810 | 54810
233 | A WING 13TH SLAB & OHWT R/F & RAW MATERIAL | 0 | Started | Material | (M)MS Binding Wire 18G | KG | 350 | 50 | 17500 | 350 | 50 | 17500 | 0 | 50 | 0 | 350 | 73.16 | 25606 | 0 | 0 | 0 | 350 | 350 | 17500 | 17500
234 | A WING 13TH SLAB & OHWT R/F & RAW MATERIAL | 0 | Started | Material | (M)RMC M-25 | CUM | 133 | 4600 | 611800 | 133 | 4600 | 611800 | 0 | 4600 | 0 | 133 | 5225 | 694924.9867 | 0 | 0 | 0 | 133 | 133 | 611800 | 611800
235 | A WING 13TH SLAB & OHWT R/F & RAW MATERIAL | 0 | Started | Material | (M)T.M.T.Bar 12mm (Fe 500, 0.888 KGS/Rm) | KG | 4000 | 59 | 236000 | 4000 | 59 | 236000 | 0 | 59 | 0 | 4000 | 59.94 | 239776 | 0 | 0 | 0 | 4000 | 4000 | 236000 | 236000
236 | A WING 13TH SLAB & OHWT R/F & RAW MATERIAL | 0 | Started | Material | (M)T.M.T.Bar 16mm (Fe 500, 1.58 KGS/Rm) | KG | 3000 | 59 | 177000 | 3000 | 59 | 177000 | 0 | 59 | 0 | 3000 | 59.94 | 179832 | 0 | 0 | 0 | 3000 | 3000 | 177000 | 177000
237 | A WING 13TH SLAB & OHWT R/F & RAW MATERIAL | 0 | Started | Material | (M)T.M.T.Bar 20mm (Fe 500, 2.47 KGS/Rm) | KG | 2000 | 59 | 118000 | 2000 | 59 | 118000 | 0 | 59 | 0 | 2000 | 60.53 | 121068 | 0 | 0 | 0 | 2000 | 2000 | 118000 | 118000
238 | A WING 13TH SLAB & OHWT R/F & RAW MATERIAL | 0 | Started | Material | (M)T.M.T.Bar 8mm (Fe 500, 0.395 KGS/Rm) | KG | 8000 | 59 | 472000 | 8000 | 59 | 472000 | 0 | 59 | 0 | 8000 | 61.71 | 493712 | 0 | 0 | 0 | 8000 | 8000 | 472000 | 472000
239 | A WING TERRACE FLOOR RCC PARAPET WALL (H=1.35 M) | 0 | Started | Material | (M)CEMENT OPC 43 | BAG | 209 | 378.88 | 79185.92 | 209 | 378.88 | 79185.92 | 0 | 378.88 | 0 | 209 | 358 | 74822 | 0 | 0 | 0 | 209 | 209 | 79185.92 | 79185.92
240 | A WING TERRACE FLOOR RCC PARAPET WALL (H=1.35 M) | 0 | Started | Material | (M)Crush Sand | BRASS | 6.5 | 3675 | 23887.5 | 6.5 | 3675 | 23887.5 | 0 | 3675 | 0 | 6.5 | 3675 | 23887.5 | 0 | 0 | 0 | 6.5 | 6.5 | 23887.5 | 23887.5
241 | A WING TERRACE FLOOR RCC PARAPET WALL (H=1.35 M) | 0 | Started | Material | (M)Metal No.III 20MM | BRASS | 8 | 3045 | 24360 | 8 | 3045 | 24360 | 0 | 3045 | 0 | 8 | 3360 | 26880 | 0 | 0 | 0 | 8 | 8 | 24360 | 24360
242 | A WING- STEEL TESTING-LAB (INDENT-549) | 0 | Started | Labour | (L)10MM STEEL TESTING-LAB. | NOS | 36 | 531 | 19116 | 0 | 0 | 0 | 0 | 531 | 0 | 36 | 531 | 19116 | 3 | 531 | 1593 | 36 | 33 | 19116 | 17523 | Building
243 | A WING- STEEL TESTING-LAB (INDENT-549) | 0 | Started | Labour | (L)12MM STEEL TESTING-LAB. | NOS | 36 | 531 | 19116 | 0 | 0 | 0 | 0 | 531 | 0 | 36 | 531 | 19116 | 6 | 531 | 3186 | 36 | 30 | 19116 | 15930 | Building
244 | A WING- STEEL TESTING-LAB (INDENT-549) | 0 | Started | Labour | (L)16MM STEEL TESTING-LAB. | NOS | 36 | 649 | 23364 | 0 | 0 | 0 | 0 | 649 | 0 | 36 | 649 | 23364 | 6 | 649 | 3894 | 36 | 30 | 23364 | 19470 | Building
245 | A WING- STEEL TESTING-LAB (INDENT-549) | 0 | Started | Labour | (L)20MM STEEL TESTING-LAB. | NOS | 36 | 649 | 23364 | 0 | 0 | 0 | 0 | 649 | 0 | 36 | 649 | 23364 | 6 | 649 | 3894 | 36 | 30 | 23364 | 19470 | Building
246 | A WING- STEEL TESTING-LAB (INDENT-549) | 0 | Started | Labour | (L)25MM STEEL TESTING-LAB. | NOS | 36 | 649 | 23364 | 0 | 0 | 0 | 0 | 649 | 0 | 36 | 649 | 23364 | 6 | 649 | 3894 | 36 | 30 | 23364 | 19470 | Building
247 | A WING- STEEL TESTING-LAB (INDENT-549) | 0 | Started | Labour | (L)32MM STEEL TESTING-LAB. | NOS | 36 | 826 | 29736 | 0 | 0 | 0 | 0 | 826 | 0 | 36 | 826 | 29736 | 0 | 0 | 0 | 36 | 36 | 29736 | 29736 | Building
248 | A WING- STEEL TESTING-LAB (INDENT-549) | 0 | Started | Labour | (L)8MM STEEL TESTING-LAB. | NOS | 36 | 531 | 19116 | 0 | 0 | 0 | 0 | 531 | 0 | 36 | 531 | 19116 | 6 | 531 | 3186 | 36 | 30 | 19116 | 15930 | Building
249 | A WING- CUBE TESTING-LAB (INDENT-549) | 0 | Started | Labour | (L)CONCRETE CUBE TEST (Compressive Strength) | NOS | 600 | 88.5 | 53100 | 0 | 0 | 0 | 0 | 88.5 | 0 | 600 | 88.5 | 53100 | 0 | 0 | 0 | 600 | 600 | 53100 | 53100
250 | Water Testing Charge for 24 Avenue Site | 0 | Started | Labour | (L)Water Testing for Drinking Purpose | NOS | 2 | 2076.8 | 4153.6 | 0 | 0 | 0 | 0 | 2076.8 | 0 | 2 | 2076.8 | 4153.6 | 2 | 2076.8 | 4153.6 | 2 | 0 | 4153.6 | 0
251 | INDENT-880/A BLDG/DPC & PATLI WORK UP TO 6TH FLOOR | 10 | Started | Material | (M)CEMENT PPC 50KG | BAG | 348 | 320 | 111360 | 315 | 320 | 100800 | 35 | 320 | 11200 | 300 | 309.99 | 92997.12 | 5 | 304.61 | 1523.04 | 313 | 343 | 100160 | 109836.96
252 | INDENT-880/A BLDG/DPC & PATLI WORK UP TO 6TH FLOOR | 10 | Started | Material | (M)Crush Sand | BRASS | 17.76 | 3675 | 65268 | 14.48 | 3675 | 53214 | 2 | 3675 | 7350 | 13.63 | 3675 | 50090.2536 | 0 | 0 | 0 | 15.76 | 17.76 | 57918 | 65268
253 | INDENT-880/A BLDG/DPC & PATLI WORK UP TO 6TH FLOOR | 10 | Started | Material | (M)Metal No.III 20MM | BRASS | 26.46 | 3045 | 80570.7 | 11.66 | 3045 | 35504.7 | 3 | 3045 | 9135 | 11.66 | 3454.19 | 40275.9 | 0 | 0 | 0 | 23.46 | 26.46 | 71435.7 | 80570.7
254 | BBM WORK INDENT-880/A BLDG/BBM WORK UPTO 6TH FLR | 10 | Started | Material | (M)AAC Block-125MM | CUM | 408 | 4200 | 1713600 | 408 | 4200 | 1713600 | 41 | 4200 | 172200 | 408 | 3936.14 | 1605943.377 | 0 | 0 | 0 | 367 | 408 | 1541400 | 1713600
255 | BBM WORK INDENT-880/A BLDG/BBM WORK UPTO 6TH FLR | 10 | Started | Material | (M)AAC Block-230MM | CUM | 9 | 4200 | 37800 | 9 | 4200 | 37800 | 1 | 4200 | 4200 | 9 | 3900 | 35100.0054 | 0 | 0 | 0 | 8 | 9 | 33600 | 37800
256 | BBM WORK INDENT-880/A BLDG/BBM WORK UPTO 6TH FLR | 10 | Started | Material | (M)BLOCK ADHESIEVE | 40 KG/BAG | 365 | 400 | 146000 | 365 | 400 | 146000 | 37 | 400 | 14800 | 365 | 350 | 127750 | 0 | 0 | 0 | 328 | 365 | 131200 | 146000
257 | A BLDG BLOCK 7TH TO TERR. FLOOR | 0 | Started | Material | (M)AAC Block-125MM | CUM | 441 | 4200 | 1852200 | 441 | 4200 | 1852200 | 0 | 4200 | 0 | 441 | 3900 | 1719899.9559 | 0 | 0 | 0 | 441 | 441 | 1852200 | 1852200
258 | A BLDG BLOCK 7TH TO TERR. FLOOR | 0 | Started | Material | (M)AAC Block-230MM | CUM | 8 | 4200 | 33600 | 8 | 4200 | 33600 | 0 | 4200 | 0 | 8 | 3900 | 31200.0024 | 0 | 0 | 0 | 8 | 8 | 33600 | 33600
259 | A BLDG BLOCK 7TH TO TERR. FLOOR | 0 | Started | Material | (M)BLOCK ADHESIEVE | 40 KG/BAG | 394 | 400 | 157600 | 394 | 400 | 157600 | 0 | 400 | 0 | 394 | 350 | 137900 | 0 | 0 | 0 | 394 | 394 | 157600 | 157600
260 | A BLDG DPC & PATALI 7TH TO TERR.FLOOR | 0 | Started | Material | (M)CEMENT PPC 50KG | BAG | 326 | 320 | 104320 | 326 | 320 | 104320 | 0 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 326 | 326 | 104320 | 104320
261 | A BLDG DPC & PATALI 7TH TO TERR.FLOOR | 0 | Started | Material | (M)Crush Sand | BRASS | 12 | 3675 | 44100 | 12 | 3675 | 44100 | 0 | 3675 | 0 | 12 | 3675 | 44100.006 | 0 | 0 | 0 | 12 | 12 | 44100 | 44100
262 | A BLDG DPC & PATALI 7TH TO TERR.FLOOR | 0 | Started | Material | (M)Metal No.III 20MM | BRASS | 15 | 3045 | 45675 | 15 | 3045 | 45675 | 0 | 3045 | 0 | 15 | 3570 | 53550 | 0 | 0 | 0 | 15 | 15 | 45675 | 45675
263 | FLAT:01-03, A BLDG BBM-PARKING & 1ST FLOOR | 0 | Started | Labour | (L)BBM WORK | SQFT | 902.4265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 902.4265 | 74 | 66779.561 | 699.6341 | 74 | 51772.92 | 902.4265 | 202.7924 | 0 | -51772.92
264 | FLAT:01-03, A BLDG BBM-2ND & 3RD FLOOR | 0 | Started | Labour | (L)BBM WORK | SQFT | 1419.5473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1419.5473 | 74 | 105046.5002 | 1419.5473 | 74 | 105046.5 | 1419.5473 | 0 | 0 | -105046.5
265 | FLAT:01-03, A BLDG BBM-4TH,5TH & 6TH FLOOR | 0 | Started | Labour | (L)BBM WORK | SQFT | 2190.1587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2190.1587 | 74 | 162071.7438 | 2190.1587 | 74 | 162071.74 | 2190.1587 | 0 | 0 | -162071.74
266 | FLAT:01-03, A BLDG BBM-7TH,8TH FLOOR | 0 | Started | Labour | (L)BBM WORK | SQFT | 1495.5945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1495.5945 | 74 | 110673.993 | 1495.5825 | 74 | 110673.11 | 1495.5945 | 0.012 | 0 | -110673.11
267 | FLAT:01-03, A BLDG BBM-9TH,10TH FLOOR | 0 | Started | Labour | (L)BBM WORK | SQFT | 1571.6416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1571.6416 | 74 | 116301.4784 | 1571.6416 | 74 | 116301.48 | 1571.6416 | 0 | 0 | -116301.48
268 | FLAT:01-03, A BLDG BBM-11TH,12TH FLOOR | 0 | Tentative | Labour | (L)BBM WORK | SQFT | 1647.6888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1647.6888 | 74 | 121928.9712 | 0 | 0 | 0 | 1647.6888 | 1647.6888 | 0 | 0
269 | FLAT:01-03, A BLDG BBM-TOP TERR. & ABOVE OHWT | 0 | Tentative | Labour | (L)BBM WORK | SQFT | 405.5849 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 405.5849 | 74 | 30013.2826 | 0 | 0 | 0 | 405.5849 | 405.5849 | 0 | 0
270 | FLAT:01-03, A BLDG BBM-LIFT,ELEV. & MISS. BBM | 0 | Started | Labour | (L)BBM WORK | SQFT | 506.9812 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 506.9812 | 74 | 37516.6088 | 0 | 0 | 0 | 506.9812 | 506.9812 | 0 | 0
271 | FLAT:01-03, A BLDG BBM-CLEANING | 0 | Started | Labour | (L)CLEANING WORK | SQFT | 58.3784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.3784 | 74 | 4320.0016 | 0 | 0 | 0 | 58.3784 | 58.3784 | 0 | 0
272 | FLAT:01-03, A BLDG INT.PLASTER-1,2,3,4 & 5TH FLOOR | 0 | Started | Labour | (L)INTERNAL PLASTER- | SQFT | 1896.4264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1896.4264 | 74 | 140335.5536 | 1896.422 | 74 | 140335.23 | 1896.4264 | 0.0044 | 0 | -140335.23
273 | FLAT:01-03, A BLDG INT.PLASTER-6,7,8,9 & 10TH FLOOR | 0 | Started | Labour | (L)INTERNAL PLASTER- | SQFT | 2162.5916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2162.5916 | 74 | 160031.7784 | 831.7568 | 74 | 61550 | 2162.5916 | 1330.8348 | 0 | -61550
274 | FLAT:01-03, A BLDG INT.PLASTER-11TH & 12TH FLOOR | 0 | Tentative | Labour | (L)INTERNAL PLASTER- | SQFT | 964.8485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 964.8485 | 74 | 71398.789 | 0 | 0 | 0 | 964.8485 | 964.8485 | 0 | 0
275 | FLAT:01-03, A BLDG INT.PLASTER-PASSAGE-1ST TO 12TH | 0 | Tentative | Labour | (L)INTERNAL PLASTER- | SQFT | 665.4128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 665.4128 | 74 | 49240.5472 | 0 | 0 | 0 | 665.4128 | 665.4128 | 0 | 0
276 | FLAT:01-03, A BLDG INT.PLASTER-ST CASE & PARDI 1ST TO 12TH | 0 | Started | Labour | (L)INTERNAL PLASTER- | SQFT | 465.7889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 465.7889 | 74 | 34468.3786 | 0 | 0 | 0 | 465.7889 | 465.7889 | 0 | 0
277 | FLAT:01-03, A BLDG INT.PLASTER-LIFT WITH SCAFFOLDING | 0 | Tentative | Labour | (L)INTERNAL PLASTER- | SQFT | 216.2592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216.2592 | 74 | 16003.1808 | 0 | 0 | 0 | 216.2592 | 216.2592 | 0 | 0
278 | FLAT:01-03, A BLDG INT.PLASTER-MISS.,JAMB & BUT FILLING | 0 | Started | Labour | (L)INTERNAL PLASTER- | SQFT | 282.8004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 282.8004 | 74 | 20927.2296 | 0 | 0 | 0 | 282.8004 | 282.8004 | 0 | 0
279 | FLAT:01-03, A BLDG INT.PLASTER-CLEANING 1ST TO 12TH | 0 | Tentative | Labour | (L)CLEANING WORK | SQFT | 58.3784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.3784 | 74 | 4320.0016 | 0 | 0 | 0 | 58.3784 | 58.3784 | 0 | 0
280 | FLAT:01-03, RETENTION | 0 | Started | Labour | (L)Retention Amount (BBM & PLASTER) | SQFT | 491.9414 | 89.68 | 44117.3 | 0 | 0 | 0 | 0 | 89.68 | 0 | 491.9414 | 74 | 36403.6636 | 0 | 0 | 0 | 491.9414 | 491.9414 | 44117.305 | 44117.3048
281 | FLAT:01-03, P.F2 | 0 | Started | Labour | (L)PF AMOUNT | SQFT | 192.4497 | 89.68 | 17258.89 | 0 | 0 | 0 | 0 | 89.68 | 0 | 192.4497 | 74 | 14241.2778 | 0 | 0 | 0 | 192.4497 | 192.4497 | 17258.889 | 17258.8891
282 | Flat: 01-03, Parking Plaster-100% | 0 | Tentative | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 521.24 | 89.68 | 46744.8 | 0 | 0 | 0 | 0 | 89.68 | 0 | 521.24 | 74 | 38571.76 | 0 | 0 | 0 | 521.24 | 521.24 | 46744.803 | 46744.8032
283 | Flat: 01-03, East Side Duct upto 12th Floor (B1+B2+B3) | 0 | Tentative | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 1764.603 | 89.68 | 158249.6 | 0 | 0 | 0 | 0 | 89.68 | 0 | 1764.603 | 74 | 130580.622 | 0 | 0 | 0 | 1764.603 | 1764.603 | 158249.597 | 158249.597
284 | Flat: 01-03, East Side Khata upto 12th Floor (B4) | 0 | Tentative | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 670.3862 | 89.68 | 60120.23 | 0 | 0 | 0 | 0 | 89.68 | 0 | 670.3862 | 74 | 49608.5788 | 0 | 0 | 0 | 670.3862 | 670.3862 | 60120.234 | 60120.2344
285 | Flat: 01-03, North Side Elev. upto 12th Floor (B5+B6+B7+B8) | 0 | Tentative | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 2490.6995 | 89.68 | 223365.93 | 0 | 0 | 0 | 0 | 89.68 | 0 | 2490.6995 | 74 | 184311.763 | 0 | 0 | 0 | 2490.6995 | 2490.6995 | 223365.931 | 223365.9312
286 | Flat: 01-03, North Side ST-Csae Elev. upto 12th floor (B9) | 0 | Tentative | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 643.3591 | 89.68 | 57696.44 | 0 | 0 | 0 | 0 | 89.68 | 0 | 643.3591 | 74 | 47608.5734 | 0 | 0 | 0 | 643.3591 | 643.3591 | 57696.444 | 57696.4441
287 | Flat: 01-03, North Side Elev. upto 12th Floor (B10 to B14) | 0 | Tentative | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 2485.5703 | 89.68 | 222905.94 | 0 | 0 | 0 | 0 | 89.68 | 0 | 2485.5703 | 74 | 183932.2022 | 0 | 0 | 0 | 2485.5703 | 2485.5703 | 222905.945 | 222905.9445
288 | Flat: 01-03, West Side Khata upto 12th floor (B15) | 0 | Tentative | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 561.45 | 89.68 | 50350.84 | 0 | 0 | 0 | 0 | 89.68 | 0 | 561.45 | 74 | 41547.3 | 0 | 0 | 0 | 561.45 | 561.45 | 50350.836 | 50350.836
289 | Flat: 01-03, West Side Duct upto 12th floor (B16+17+18) | 0 | Tentative | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 1766.259 | 89.68 | 158398.11 | 0 | 0 | 0 | 0 | 89.68 | 0 | 1766.259 | 74 | 130703.166 | 0 | 0 | 0 | 1766.259 | 1766.259 | 158398.107 | 158398.1071
290 | Flat: 01-03, Internal (Big lift) "DUCT B1" upto 12th Floor | 0 | Tentative | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 562.9392 | 89.68 | 50484.39 | 0 | 0 | 0 | 0 | 89.68 | 0 | 562.9392 | 74 | 41657.5008 | 0 | 0 | 0 | 562.9392 | 562.9392 | 50484.388 | 50484.3875
291 | Flat: 01-03, Fire "DUCT B2" Plaster upto 12th Floor | 0 | Tentative | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 562.9392 | 89.68 | 50484.39 | 0 | 0 | 0 | 0 | 89.68 | 0 | 562.9392 | 74 | 41657.5008 | 0 | 0 | 0 | 562.9392 | 562.9392 | 50484.388 | 50484.3875
292 | Flat: 01-03, Terrace Plaster upto 12th Floor | 0 | Tentative | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 844.4088 | 89.68 | 75726.58 | 0 | 0 | 0 | 0 | 89.68 | 0 | 844.4088 | 74 | 62486.2512 | 0 | 0 | 0 | 844.4088 | 844.4088 | 75726.581 | 75726.5812
293 | Flat: 01-03, Dry Terrace Plaster upto 12th Floor | 0 | Started | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 844.4088 | 89.68 | 75726.58 | 0 | 0 | 0 | 0 | 89.68 | 0 | 844.4088 | 80.66 | 68110.0912 | 281.4696 | 87.32 | 24577.93 | 844.4088 | 562.9392 | 75726.581 | 51148.6512
294 | Flat: 01-03, OHWT,Parapet & Terrace floor | 0 | Tentative | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 1058.4746 | 89.68 | 94924 | 0 | 0 | 0 | 0 | 89.68 | 0 | 1058.4746 | 74 | 78327.1204 | 0 | 0 | 0 | 1058.4746 | 1058.4746 | 94924.002 | 94924.0021
295 | Flat: 01-03, Miss.Plaster work-100% | 0 | Tentative | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 521.24 | 89.68 | 46744.8 | 0 | 0 | 0 | 0 | 89.68 | 0 | 521.24 | 74 | 38571.76 | 0 | 0 | 0 | 521.24 | 521.24 | 46744.803 | 46744.8032
296 | Flat: 01-03, Cleaning after plaster work | 0 | Tentative | Labour | (L)CLEANING WORK | SQFT | 54.059 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54.059 | 74 | 4000.366 | 0 | 0 | 0 | 54.059 | 54.059 | 0 | 0
297 | Flat: 01-03, "P.F Amount" | 0 | Started | Labour | (L)PF AMOUNT | SQFT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
298 | Flat: 01-03, "Retention" (After comp of 12th month) | 0 | Started | Labour | (L)Retention Amount (BBM & PLASTER) | SQFT | 1216.2162 | 89.68 | 109070.27 | 0 | 0 | 0 | 0 | 89.68 | 0 | 1216.2162 | 74 | 89999.9988 | 0 | 0 | 0 | 1216.2162 | 1216.2162 | 109070.269 | 109070.2688
299 | FLAT:04-06, A BLDG BBM-PARKING & 1ST FLOOR | 0 | Started | Labour | (L)BBM WORK | SQFT | 939.9876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939.9876 | 74 | 69559.0824 | 728.7545 | 74 | 53927.83 | 939.9876 | 211.2331 | 0 | -53927.83
300 | FLAT:04-06, A BLDG BBM-2ND & 3RD FLOOR | 0 | Started | Labour | (L)BBM WORK | SQFT | 1478.6322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1478.6322 | 74 | 109418.7828 | 1478.6322 | 74 | 109418.78 | 1478.6322 | 0 | 0 | -109418.78
301 | FLAT:04-06, A BLDG BBM-4TH,5TH & 6TH FLOOR | 0 | Started | Labour | (L)BBM WORK | SQFT | 2281.3183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2281.3183 | 74 | 168817.5542 | 2281.3183 | 74 | 168817.55 | 2281.3183 | 0 | 0 | -168817.55
302 | FLAT:04-06, A BLDG BBM-7TH,8TH FLOOR | 0 | Started | Labour | (L)BBM WORK | SQFT | 1557.8447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1557.8447 | 74 | 115280.5078 | 1557.8386 | 74 | 115280.06 | 1557.8447 | 0.0061 | 0 | -115280.06
303 | FLAT:04-06, A BLDG BBM-9TH,10TH FLOOR | 0 | Started | Labour | (L)BBM WORK | SQFT | 1637.0571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1637.0571 | 74 | 121142.2254 | 1637.0571 | 74 | 121142.23 | 1637.0571 | 0 | 0 | -121142.23
304 | FLAT:04-06, A BLDG BBM-11TH,12TH FLOOR | 0 | Tentative | Labour | (L)BBM WORK | SQFT | 1716.2696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1716.2696 | 74 | 127003.9504 | 0 | 0 | 0 | 1716.2696 | 1716.2696 | 0 | 0
305 | FLAT:04-06, A BLDG BBM-TOP TERR. & ABOVE OHWT | 0 | Tentative | Labour | (L)BBM WORK | SQFT | 422.4663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 422.4663 | 74 | 31262.5062 | 0 | 0 | 0 | 422.4663 | 422.4663 | 0 | 0
306 | FLAT:04-06, A BLDG BBM-LIFT,ELEV. & MISS. BBM | 0 | Tentative | Labour | (L)BBM WORK | SQFT | 528.0829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 528.0829 | 74 | 39078.1346 | 0 | 0 | 0 | 528.0829 | 528.0829 | 0 | 0
307 | FLAT:04-06, A BLDG BBM-CLEANING | 0 | Tentative | Labour | (L)CLEANING WORK | SQFT | 58.3784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.3784 | 74 | 4320.0016 | 0 | 0 | 0 | 58.3784 | 58.3784 | 0 | 0
308 | FLAT:04-06, A BLDG INT.PLASTER-1,2,3,4 & 5TH FLOOR | 0 | Started | Labour | (L)INTERNAL PLASTER- | SQFT | 1975.3603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1975.3603 | 74 | 146176.6622 | 415.8648 | 74 | 30774 | 1975.3603 | 1559.4955 | 0 | -30774
309 | FLAT:04-06, A BLDG INT.PLASTER-6,7,8,9 & 10TH FLOOR | 0 | Started | Labour | (L)INTERNAL PLASTER- | SQFT | 2252.6038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2252.6038 | 74 | 166692.6812 | 1316.9064 | 74 | 97451.07 | 2252.6038 | 935.6974 | 0 | -97451.07
310 | FLAT:04-06, A BLDG INT.PLASTER-11TH & 12TH FLOOR | 0 | Tentative | Labour | (L)INTERNAL PLASTER- | SQFT | 1005.0078 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1005.0078 | 74 | 74370.5772 | 0 | 0 | 0 | 1005.0078 | 1005.0078 | 0 | 0
311 | FLAT:04-06, A BLDG INT.PLASTER-PASSAGE-1ST TO 12TH | 0 | Started | Labour | (L)INTERNAL PLASTER- | SQFT | 693.1089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 693.1089 | 74 | 51290.0586 | 693.1089 | 74 | 51290.06 | 693.1089 | 0 | 0 | -51290.06
312 | FLAT:04-06, A BLDG INT.PLASTER-ST CASE & PARDI 1ST TO 12TH | 0 | Tentative | Labour | (L)INTERNAL PLASTER- | SQFT | 485.1762 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485.1762 | 74 | 35903.0388 | 0 | 0 | 0 | 485.1762 | 485.1762 | 0 | 0
313 | FLAT:04-06, A BLDG INT.PLASTER-LIFT WITH SCAFFOLDING | 0 | Tentative | Labour | (L)INTERNAL PLASTER- | SQFT | 225.2604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 225.2604 | 74 | 16669.2696 | 0 | 0 | 0 | 225.2604 | 225.2604 | 0 | 0
314 | FLAT:04-06, A BLDG INT.PLASTER-MISS.,JAMB & BUT FILLING | 0 | Tentative | Labour | (L)INTERNAL PLASTER- | SQFT | 294.5713 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 294.5713 | 74 | 21798.2762 | 0 | 0 | 0 | 294.5713 | 294.5713 | 0 | 0
315 | FLAT:04-06, A BLDG INT.PLASTER-CLEANING 1ST TO 12TH | 0 | Tentative | Labour | (L)CLEANING WORK | SQFT | 58.3784 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.3784 | 74 | 4320.0016 | 0 | 0 | 0 | 58.3784 | 58.3784 | 0 | 0
316 | FLAT:04-06, RETENTION | 0 | Tentative | Labour | (L)Retention Amount (BBM & PLASTER) | SQFT | 889.6276 | 89.68 | 79781.8 | 0 | 0 | 0 | 0 | 89.68 | 0 | 889.6276 | 74 | 65832.4424 | 0 | 0 | 0 | 889.6276 | 889.6276 | 79781.803 | 79781.8032
317 | FLAT:04-06, PF Amount | 0 | Tentative | Labour | (L)PF AMOUNT | SQFT | 311.3697 | 89.68 | 27923.63 | 0 | 0 | 0 | 0 | 89.68 | 0 | 311.3697 | 74 | 23041.3578 | 0 | 0 | 0 | 311.3697 | 311.3697 | 27923.635 | 27923.6347
318 | Flat:04-06, Parking Plaster 100% | 0 | Tentative | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 608.0875 | 89.68 | 54533.29 | 0 | 0 | 0 | 0 | 89.68 | 0 | 608.0875 | 87.32 | 53098.195 | 0 | 0 | 0 | 608.0875 | 608.0875 | 54533.287 | 54533.287
319 | Flat:04-06, East Side Duct upto 12th Floor (A1+A2+A3) | 0 | Tentative | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 1774.6227 | 89.68 | 159148.16 | 0 | 0 | 0 | 0 | 89.68 | 0 | 1774.6227 | 87.32 | 154960.0598 | 0 | 0 | 0 | 1774.6227 | 1774.6227 | 159148.164 | 159148.1637
320 | Flat:04-06, East Side Khata upto 12th floor (A4) | 0 | Tentative | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 670.1373 | 89.68 | 60097.91 | 0 | 0 | 0 | 0 | 89.68 | 0 | 670.1373 | 87.32 | 58516.3802 | 0 | 0 | 0 | 670.1373 | 670.1373 | 60097.913 | 60097.9131
321 | Flat:04-06, South Side Elev. upto 12th Floor (A5+A6+A7) | 0 | Tentative | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 1774.6227 | 89.68 | 159148.16 | 0 | 0 | 0 | 0 | 89.68 | 0 | 1774.6227 | 87.32 | 154960.0598 | 0 | 0 | 0 | 1774.6227 | 1774.6227 | 159148.164 | 159148.1637
322 | Flat:04-06, South Side ST-Csae & Garbage upto 12th floor(A8) | 0 | Tentative | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 670.1373 | 89.68 | 60097.91 | 0 | 0 | 0 | 0 | 89.68 | 0 | 670.1373 | 87.32 | 58516.3802 | 0 | 0 | 0 | 670.1373 | 670.1373 | 60097.913 | 60097.9131
323 | Flat:04-06, South Side Elev. upto 12th Floor (A9 to A13) | 0 | Tentative | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 2997.0027 | 89.68 | 268771.2 | 0 | 0 | 0 | 0 | 89.68 | 0 | 2997.0027 | 87.32 | 261698.2798 | 0 | 0 | 0 | 2997.0027 | 2997.0027 | 268771.202 | 268771.2021
324 | Flat:04-06, West Side Khata upto 12th floor (A14) | 0 | Tentative | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 670.1373 | 89.68 | 60097.91 | 0 | 0 | 0 | 0 | 89.68 | 0 | 670.1373 | 87.32 | 58516.3802 | 0 | 0 | 0 | 670.1373 | 670.1373 | 60097.913 | 60097.9131
325 | Flat:04-06, West Side Duct upto 12th floor (A15+16+17) | 0 | Tentative | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 1774.6227 | 89.68 | 159148.16 | 0 | 0 | 0 | 0 | 89.68 | 0 | 1774.6227 | 87.32 | 154960.0598 | 0 | 0 | 0 | 1774.6227 | 1774.6227 | 159148.164 | 159148.1637
326 | Flat:04-06, Internal (Small lift) "DUCT A1" upto 12th Floor | 0 | Tentative | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 608.0875 | 89.68 | 54533.29 | 0 | 0 | 0 | 0 | 89.68 | 0 | 608.0875 | 87.32 | 53098.195 | 0 | 0 | 0 | 608.0875 | 608.0875 | 54533.287 | 54533.287
327 | Flat:04-06, Elec. "DUCT A2" Plaster upto 12th Floor | 0 | Tentative | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 608.0875 | 89.68 | 54533.29 | 0 | 0 | 0 | 0 | 89.68 | 0 | 608.0875 | 87.32 | 53098.195 | 0 | 0 | 0 | 608.0875 | 608.0875 | 54533.287 | 54533.287
328 | Flat:04-06, Terrace Plaster upto 12th Floor | 0 | Tentative | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 912.1313 | 89.68 | 81799.94 | 0 | 0 | 0 | 0 | 89.68 | 0 | 912.1313 | 87.32 | 79647.2962 | 0 | 0 | 0 | 912.1313 | 912.1313 | 81799.935 | 81799.935
329 | Flat:04-06, Dry Terrace Plaster upto 12th Floor | 0 | Tentative | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 632.9074 | 89.68 | 56759.14 | 0 | 0 | 0 | 0 | 89.68 | 0 | 632.9074 | 87.32 | 55265.4676 | 0 | 0 | 0 | 632.9074 | 632.9074 | 56759.136 | 56759.1356
330 | Flat:04-06, OHWT,Parapet & Terrace floor | 0 | Tentative | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 1203.7651 | 89.68 | 107953.65 | 0 | 0 | 0 | 0 | 89.68 | 0 | 1203.7651 | 87.32 | 105112.7774 | 0 | 0 | 0 | 1203.7651 | 1203.7651 | 107953.654 | 107953.6542
331 | Flat:04-06, Miss.Plaster work-100% | 0 | Tentative | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 608.0875 | 89.68 | 54533.29 | 0 | 0 | 0 | 0 | 89.68 | 0 | 608.0875 | 87.32 | 53098.195 | 0 | 0 | 0 | 608.0875 | 608.0875 | 54533.287 | 54533.287
332 | Flat:04-06, Cleaning after plaster work | 0 | Tentative | Labour | (L)CLEANING WORK | SQFT | 61.1688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61.1688 | 87.32 | 5341.2512 | 0 | 0 | 0 | 61.1688 | 61.1688 | 0 | 0
333 | Flat:04-06, "P.F Amount" | 0 | Tentative | Labour | (L)PF AMOUNT | SQFT | 311.3697 | 89.68 | 27923.63 | 0 | 0 | 0 | 0 | 89.68 | 0 | 311.3697 | 87.32 | 27188.7978 | 0 | 0 | 0 | 311.3697 | 311.3697 | 27923.635 | 27923.6347
334 | Flat:04-06, "Retention" (After comp of 12th month) | 0 | Tentative | Labour | (L)Retention Amount (BBM & PLASTER) | SQFT | 889.6276 | 89.68 | 79781.8 | 0 | 0 | 0 | 0 | 89.68 | 0 | 889.6276 | 87.32 | 77682.2824 | 0 | 0 | 0 | 889.6276 | 889.6276 | 79781.803 | 79781.8032
335 | A WING FABRICATION INDENT-980/A WING/BALCONY RAILING | 10 | Started | Material | (M)MS Flat Patti 25mmx3mm (20ft long) | NOS | 26 | 310 | 8060 | 26 | 310 | 8060 | 3 | 310 | 930 | 26 | 373.02 | 9698.52 | 0 | 0 | 0 | 23 | 26 | 7130 | 8060
336 | A WING FABRICATION INDENT-980/A WING/BALCONY RAILING | 10 | Started | Material | (M)MS Square Pipe 25mm x 25mm x 20ft (16 gauge) Non coil | NOS | 227 | 442 | 100334 | 227 | 442 | 100334 | 23 | 442 | 10166 | 227 | 531.86 | 120732.22 | 0 | 0 | 0 | 204 | 227 | 90168 | 100334
337 | A WING FABRICATION INDENT-980/A WING/BALCONY RAILING | 10 | Started | Material | (M)MS Square Pipe 40mm x 40mm x 20ft (16 gauge) Non Coil | NOS | 26 | 700 | 18200 | 26 | 700 | 18200 | 3 | 700 | 2100 | 26 | 842.31 | 21900.06 | 0 | 0 | 0 | 23 | 26 | 16100 | 18200
338 | A WING FABRICATION INDENT-980/A WING/BALCONY RAILING | 10 | Started | Material | (M)ZINC OXIDE PRIMER | LTR | 10 | 250 | 2500 | 10 | 250 | 2500 | 1 | 250 | 250 | 10 | 283.2 | 2832 | 0 | 0 | 0 | 9 | 10 | 2250 | 2500
339 | A BLDG (F01-F04) RAILING ERECTION & FIXING WORK-1ST FLOOR | 0 | Started | Labour | (L)MS Railing Only Labour | SQFT | 404.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 404.04 | 28 | 11313.12 | 404.04 | 28 | 11313.12 | 404.04 | 0 | 0 | -11313.12
340 | A BLDG (F01-F06) RAILING ERECTION & FIXING WORK-2ND FLOOR | 0 | Started | Labour | (L)MS Railing Only Labour | SQFT | 485.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485.53 | 28 | 13594.84 | 485.53 | 28 | 13594.84 | 485.53 | 0 | 0 | -13594.84
341 | A BLDG (F01-F06) RAILING ERECTION & FIXING WORK-3RD FLOOR | 0 | Started | Labour | (L)MS Railing Only Labour | SQFT | 485.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485.53 | 28 | 13594.84 | 485.53 | 28 | 13594.84 | 485.53 | 0 | 0 | -13594.84
342 | A BLDG (F01-F06) RAILING ERECTION & FIXING WORK-4TH FLOOR | 0 | Started | Labour | (L)MS Railing Only Labour | SQFT | 485.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485.53 | 28 | 13594.84 | 485.53 | 28 | 13594.84 | 485.53 | 0 | 0 | -13594.84
343 | A BLDG (F01-F06) RAILING ERECTION & FIXING WORK-5TH FLOOR | 0 | Started | Labour | (L)MS Railing Only Labour | SQFT | 485.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485.53 | 28 | 13594.84 | 485.53 | 28 | 13594.84 | 485.53 | 0 | 0 | -13594.84
344 | A BLDG (F01-F06) RAILING ERECTION & FIXING WORK-6TH FLOOR | 0 | Started | Labour | (L)MS Railing Only Labour | SQFT | 485.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485.53 | 28 | 13594.84 | 485.53 | 28 | 13594.84 | 485.53 | 0 | 0 | -13594.84
345 | A BLDG (F01-F06) RAILING ERECTION & FIXING WORK-7TH FLOOR | 0 | Started | Labour | (L)MS Railing Only Labour | SQFT | 485.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485.53 | 28 | 13594.84 | 485.53 | 28 | 13594.84 | 485.53 | 0 | 0 | -13594.84
346 | A BLDG (F01-F06) RAILING ERECTION & FIXING WORK-8TH FLOOR | 0 | Started | Labour | (L)MS Railing Only Labour | SQFT | 485.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485.53 | 28 | 13594.84 | 485.53 | 28 | 13594.84 | 485.53 | 0 | 0 | -13594.84
347 | A BLDG (F01-F06) RAILING ERECTION & FIXING WORK-9TH FLOOR | 0 | Tentative | Labour | (L)MS Railing Only Labour | SQFT | 485.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485.53 | 28 | 13594.84 | 0 | 0 | 0 | 485.53 | 485.53 | 0 | 0
348 | A BLDG (F01-F06) RAILING ERECTION & FIXING WORK-10TH FLOOR | 0 | Started | Labour | (L)MS Railing Only Labour | SQFT | 485.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485.53 | 28 | 13594.84 | 0 | 0 | 0 | 485.53 | 485.53 | 0 | 0
349 | A BLDG (F01-F06) RAILING ERECTION & FIXING WORK-11TH FLOOR | 0 | Tentative | Labour | (L)MS Railing Only Labour | SQFT | 485.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485.53 | 28 | 13594.84 | 0 | 0 | 0 | 485.53 | 485.53 | 0 | 0
350 | A BLDG (F01-F06) RAILING ERECTION & FIXING WORK-12TH FLOOR | 0 | Tentative | Labour | (L)MS Railing Only Labour | SQFT | 485.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 485.53 | 28 | 13594.84 | 0 | 0 | 0 | 485.53 | 485.53 | 0 | 0
351 | A WING BALCONY RAILING-MATERIAL 4TH,5TH & 6TH FLOOR | 0 | Started | Material | (M)MS Flat Patti 25mmx3mm (20ft long) | NOS | 36 | 310 | 11160 | 36 | 310 | 11160 | 0 | 310 | 0 | 36 | 373.07 | 13430.5416 | 0 | 0 | 0 | 36 | 36 | 11160 | 11160
352 | A WING BALCONY RAILING-MATERIAL 4TH,5TH & 6TH FLOOR | 0 | Started | Material | (M)MS Square Pipe 25mm x 25mm x 20ft (16 gauge) Non coil | NOS | 227 | 442 | 100334 | 167 | 442 | 73814 | 0 | 442 | 0 | 167 | 518.95 | 86664.65 | 0 | 0 | 0 | 227 | 227 | 100334 | 100334
353 | A WING BALCONY RAILING-MATERIAL 4TH,5TH & 6TH FLOOR | 0 | Started | Material | (M)MS Square Pipe 40mm x 40mm x 20ft (16 gauge) Non Coil | NOS | 26 | 700 | 18200 | 26 | 700 | 18200 | 0 | 700 | 0 | 26 | 764.01 | 19864.26 | 0 | 0 | 0 | 26 | 26 | 18200 | 18200
354 | A WING BALCONY RAILING-MATERIAL 4TH,5TH & 6TH FLOOR | 0 | Started | Material | (M)ZINC OXIDE PRIMER | LTR | 10 | 250 | 2500 | 10 | 250 | 2500 | 0 | 250 | 0 | 10 | 283.2 | 2832 | 0 | 0 | 0 | 10 | 10 | 2500 | 2500
355 | A WING BALCONY RAILING-MATERIAL 7TH,8TH & 9TH FLOOR | 0 | Tentative | Material | (M)M.S. Holepass Patti- 2'' X 1'' | KG | 50 | 118 | 5900 | 50 | 118 | 5900 | 0 | 118 | 0 | 50 | 94.4 | 4720 | 0 | 0 | 0 | 50 | 50 | 5900 | 5900
356 | A WING BALCONY RAILING-MATERIAL 7TH,8TH & 9TH FLOOR | 0 | Tentative | Material | (M)MS Flat Patti 25mmx3mm (20ft long) | NOS | 30 | 310 | 9300 | 30 | 310 | 9300 | 0 | 310 | 0 | 30 | 226.94 | 6808.2 | 0 | 0 | 0 | 30 | 30 | 9300 | 9300
357 | A WING BALCONY RAILING-MATERIAL 7TH,8TH & 9TH FLOOR | 0 | Tentative | Material | (M)MS Square Pipe 25mm x 25mm x 20ft (16 gauge) Non coil | NOS | 197 | 442 | 87074 | 197 | 442 | 87074 | 0 | 442 | 0 | 197 | 493.7 | 97258.4469 | 0 | 0 | 0 | 197 | 197 | 87074 | 87074
358 | A WING BALCONY RAILING-MATERIAL 7TH,8TH & 9TH FLOOR | 0 | Tentative | Material | (M)MS Square Pipe 40mm x 40mm x 20ft (16 gauge) Non Coil | NOS | 26 | 700 | 18200 | 26 | 700 | 18200 | 0 | 700 | 0 | 26 | 731.84 | 19027.84 | 0 | 0 | 0 | 26 | 26 | 18200 | 18200
359 | A WING BALCONY RAILING-MATERIAL 7TH,8TH & 9TH FLOOR | 0 | Tentative | Material | (M)Plumbing Nails 1 1/2" | KG | 10 | 50 | 500 | 10 | 50 | 500 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 500 | 500
360 | A WING BALCONY RAILING-MATERIAL 7TH,8TH & 9TH FLOOR | 0 | Tentative | Material | (M)Plumbing Nails 3" | KG | 20 | 103.84 | 2076.8 | 20 | 103.84 | 2076.8 | 0 | 103.84 | 0 | 20 | 100.3 | 2006 | 0 | 0 | 0 | 20 | 20 | 2076.8 | 2076.8
361 | A WING BALCONY RAILING-MATERIAL 7TH,8TH & 9TH FLOOR | 0 | Tentative | Material | (M)ZINC OXIDE PRIMER | LTR | 10 | 250 | 2500 | 10 | 250 | 2500 | 0 | 250 | 0 | 10 | 283.2 | 2832 | 0 | 0 | 0 | 10 | 10 | 2500 | 2500
362 | A WING BALCONY RAILING-MATERIAL 10TH,11TH & 12TH FLOOR | 0 | Tentative | Material | (M)MS Flat Patti 25mmx3mm (20ft long) | NOS | 26 | 310 | 8060 | 0 | 0 | 0 | 0 | 310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 26 | 8060 | 8060
363 | A WING BALCONY RAILING-MATERIAL 10TH,11TH & 12TH FLOOR | 0 | Tentative | Material | (M)MS Square Pipe 25mm x 25mm x 20ft (16 gauge) Non coil | NOS | 227 | 442 | 100334 | 0 | 0 | 0 | 0 | 442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 227 | 227 | 100334 | 100334
364 | A WING BALCONY RAILING-MATERIAL 10TH,11TH & 12TH FLOOR | 0 | Tentative | Material | (M)MS Square Pipe 40mm x 40mm x 20ft (16 gauge) Non Coil | NOS | 26 | 700 | 18200 | 0 | 0 | 0 | 0 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 26 | 18200 | 18200
365 | A WING BALCONY RAILING-MATERIAL 10TH,11TH & 12TH FLOOR | 0 | Tentative | Material | (M)ZINC OXIDE PRIMER | LTR | 10 | 250 | 2500 | 10 | 250 | 2500 | 0 | 250 | 0 | 10 | 283.2 | 2832 | 0 | 0 | 0 | 10 | 10 | 2500 | 2500
366 | SAFETY WORK INDENT-03/A WING/SAFETY NET | 10 | Started | Material | (M)10MM SAFETY ROPE | KG | 26 | 180 | 4680 | 26 | 180 | 4680 | 3 | 180 | 540 | 26 | 212.4 | 5522.4 | 0 | 0 | 0 | 23 | 26 | 4140 | 4680
367 | SAFETY WORK INDENT-03/A WING/SAFETY NET | 10 | Started | Material | (M)SAFETY NET-10MX5M | NOS | 14 | 7965 | 111510 | 14 | 7965 | 111510 | 1 | 7965 | 7965 | 14 | 4130 | 57820 | 0 | 0 | 0 | 13 | 14 | 103545 | 111510
368 | INDENT-928/A BLDG 2ND SLAB/SAFETY NET LABOUR | 0 | Started | Labour | (L)Safety net fixing and removing (Labour) Duct | SQFT | 893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 893 | 3.5 | 3125.5 | 893 | 3.5 | 3125.5 | 893 | 0 | 0 | -3125.5 | Building
369 | INDENT-928/A BLDG 2ND SLAB/SAFETY NET LABOUR | 0 | Started | Labour | (L)Safety net fixing and removing (Labour) Outer side | SQFT | 10329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10329 | 3.65 | 37700.85 | 10329 | 3.65 | 37700.85 | 10329 | 0 | 0 | -37700.85 | Building
370 | SAFETY WORK A BLDG SAFETY NET WORK | 0 | Started | Material | (M)Anchor Fastners 10mm x 75mm | NOS | 100 | 23.6 | 2360 | 100 | 23.6 | 2360 | 0 | 23.6 | 0 | 100 | 23.6 | 2360 | 0 | 0 | 0 | 100 | 100 | 2360 | 2360
371 | SAFETY WORK A BLDG SAFETY NET WORK | 0 | Started | Material | (M)PP Rope 12MM (220mtr, 15kg/Bundle) | KG | 30 | 236 | 7080 | 30 | 236 | 7080 | 0 | 236 | 0 | 30 | 224.2 | 6726 | 0 | 0 | 0 | 30 | 30 | 7080 | 7080
372 | SAFETY WORK A BLDG SAFETY NET WORK | 0 | Started | Material | (M)SAFETY NET-10MX5M | NOS | 12 | 7965 | 95580 | 12 | 7965 | 95580 | 0 | 7965 | 0 | 12 | 8850 | 106200 | 0 | 0 | 0 | 12 | 12 | 95580 | 95580
373 | SAFETY WORK A BLDG SAFETY NET WORK | 0 | Started | Material | (M)SLAB BRACKET | NOS | 25 | 1062 | 26550 | 25 | 1062 | 26550 | 0 | 1062 | 0 | 25 | 1062 | 26550 | 0 | 0 | 0 | 25 | 25 | 26550 | 26550
374 | SAFETY WORK A BLDG SAFETY NET WORK | 0 | Started | Labour | (L)Anchor fastner - 10mm x 75 | NOS | 100 | 20 | 2000 | 0 | 0 | 0 | 0 | 20 | 0 | 100 | 20 | 2000 | 100 | 20 | 2000 | 100 | 0 | 2000 | 0
375 | SAFETY WORK A BLDG SAFETY NET WORK | 0 | Started | Labour | (L)SAFETY NET CLEANING WORK | SQFT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
376 | SAFETY WORK A BLDG SAFETY NET WORK | 0 | Started | Labour | (L)SAFETY NET FIXING | SQFT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
377 | SAFETY WORK A BLDG SAFETY NET WORK | 0 | Started | Labour | (L)SAFETY NET FIXING WITH SLAB/BEAM BRACKET | SQFT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
378 | SAFETY WORK A BLDG SAFETY NET WORK | 0 | Started | Labour | (L)SAFETY NET REMOVING WORK | SQFT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
379 | INDENT-35 & 36/A WING/SAFETY NET FIXING & REMOVING WORK | 0 | Started | Labour | (L)SAFETY NET CLEANING WORK | SQFT | 20658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20658 | 0.5 | 10329 | 14767 | 0.5 | 7383.5 | 20658 | 5891 | 0 | -7383.5
380 | INDENT-35 & 36/A WING/SAFETY NET FIXING & REMOVING WORK | 0 | Started | Labour | (L)SAFETY NET FIXING | SQFT | 9145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9145 | 2.25 | 20576.25 | 9145 | 2.25 | 20576.25 | 9145 | 0 | 0 | -20576.25
381 | INDENT-35 & 36/A WING/SAFETY NET FIXING & REMOVING WORK | 0 | Started | Labour | (L)SAFETY NET FIXING WITH SLAB/BEAM BRACKET | SQFT | 16785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16785 | 2.4 | 40284 | 15616.3965 | 2.4 | 37479.35 | 16785 | 1168.6035 | 0 | -37479.35
382 | INDENT-35 & 36/A WING/SAFETY NET FIXING & REMOVING WORK | 0 | Started | Labour | (L)SAFETY NET REMOVING WORK | SQFT | 25027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25027 | 1.25 | 31283.75 | 16059.384 | 1.25 | 20074.23 | 25027 | 8967.616 | 0 | -20074.23
383 | SAFETY WORK A BLDG SAFETY NET WORK-10TH SLAB | 0 | Tentative | Material | (M)Anchor Fastners 10mm x 75mm | NOS | 100 | 23.6 | 2360 | 100 | 23.6 | 2360 | 0 | 23.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 2360 | 2360
384 | A BLDG RCC- WORK ORDER (GST) | 0 | Started | Labour | (L)RCC WORK-LABOUR | SQFT | 57949 | 197.06 | 11419429.94 | 0 | 0 | 0 | 0 | 197.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57949 | 57949 | 11419429.94 | 11419429.94
385 | A BLDG RCC- WORK ORDER (GST) | 0 | Started | Labour | (L)SHUTTERING, R/F & CASTING OF SLAB | SQFT | 57949 | 197.06 | 11419429.94 | 0 | 0 | 0 | 0 | 197.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57949 | 57949 | 11419429.94 | 11419429.94
386 | A BLDG RCC-RCC WO A BLDG RCC WORK (NON GST) | 0 | Started | Labour | (L)RCC WORK-A BLDG (NON-GST) | SQFT | 16758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16758 | 16758 | 0 | 0
387 | A BLDG RCC-RCC WO A BLDG RCC WORK (NON GST) | 0 | Started | Labour | (L)SHUTTERING, R/F & CASTING OF SLAB | SQFT | 16758 | 197.06 | 3302331.48 | 0 | 0 | 0 | 0 | 197.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16758 | 16758 | 3302331.48 | 3302331.48
388 | INDENT-73/A BLDG/INTERNAL BACK COAT PLASTER-1ST TO 12TH FLOO | 10 | Started | Material | (M)Artificial Sand | BRASS | 52.64 | 5880 | 309523.2 | 52.64 | 5880 | 309523.2 | 5 | 5880 | 29400 | 52.64 | 5880 | 309523.2 | 0 | 0 | 0 | 47.64 | 52.64 | 280123.2 | 309523.2
389 | INDENT-73/A BLDG/INTERNAL BACK COAT PLASTER-1ST TO 12TH FLOO | 10 | Started | Material | (M)CEMENT PPC 50KG | BAG | 840 | 320 | 268800 | 840 | 320 | 268800 | 84 | 320 | 26880 | 500 | 310 | 155001.6 | 0 | 0 | 0 | 756 | 840 | 241920 | 268800
390 | INDENT-73/A BLDG/INTERNAL BACK COAT PLASTER-1ST TO 12TH FLOO | 10 | Started | Material | (M)PERMA PLASTO-O-PROOF CHEMICAL | LTR | 84 | 236 | 19824 | 84 | 236 | 19824 | 8 | 236 | 1888 | 0 | 0 | 0 | 0 | 0 | 0 | 76 | 84 | 17936 | 19824
391 | INDENT-73/A BLDG/INTERNAL SANLA PLASTER-1ST TO 12TH FLOOR | 10 | Started | Material | (M)Artificial Sand | BRASS | 32.9 | 5880 | 193452 | 32.9 | 5880 | 193452 | 3 | 5880 | 17640 | 32.9 | 6300 | 207270 | 0 | 0 | 0 | 29.9 | 32.9 | 175812 | 193452 | Building
392 | INDENT-73/A BLDG/INTERNAL SANLA PLASTER-1ST TO 12TH FLOOR | 10 | Started | Material | (M)CEMENT PPC 50KG | BAG | 525 | 320 | 168000 | 525 | 320 | 168000 | 53 | 320 | 16960 | 500 | 303 | 151500.05 | 0 | 0 | 0 | 472 | 525 | 151040 | 168000 | Building
393 | INDENT-73/A BLDG/INTERNAL SANLA PLASTER-1ST TO 12TH FLOOR | 10 | Started | Material | (M)PERMA PLASTO-O-PROOF CHEMICAL | LTR | 52.5 | 236 | 12390 | 52.5 | 236 | 12390 | 5 | 236 | 1180 | 0 | 0 | 0 | 0 | 0 | 0 | 47.5 | 52.5 | 11210 | 12390 | Building
394 | INDENT-73/A BLDG/INTERNAL SANLA PLASTER-1ST TO 12TH FLOOR | 10 | Started | Material | (M)SANLA-BADAM CHHAP | 12-15 KG/BAG | 612.5 | 120 | 73500 | 612.5 | 120 | 73500 | 61 | 120 | 7320 | 600 | 131.25 | 78750 | 0 | 0 | 0 | 551.5 | 612.5 | 66180 | 73500 | Building
395 | A BLDG PLASTER-NAILS,WISHOR,CHIKAN MESH,CHEMICAL ETC. | 10 | Started | Material | (M)CHIKAN MESH-6'' (20Mtr/Bundle) | BUNDLE | 22 | 153.4 | 3374.8 | 22 | 153.4 | 3374.8 | 2 | 153.4 | 306.8 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 22 | 3068 | 3374.8 | Building
396 | A BLDG PLASTER-NAILS,WISHOR,CHIKAN MESH,CHEMICAL ETC. | 10 | Started | Material | (M)MASTERBOND HACKAID (20 Ltr/Can) | LTR | 1340 | 4484 | 6008560 | 1340 | 4484 | 6008560 | 134 | 4484 | 600856 | 0 | 0 | 0 | 0 | 0 | 0 | 1206 | 1340 | 5407704 | 6008560 | Building
397 | A BLDG PLASTER-NAILS,WISHOR,CHIKAN MESH,CHEMICAL ETC. | 10 | Started | Material | (M)Nails 1 1/2" | KG | 210 | 100 | 21000 | 210 | 100 | 21000 | 21 | 100 | 2100 | 150 | 100.3 | 15045 | 0 | 0 | 0 | 189 | 210 | 18900 | 21000 | Building
398 | A BLDG PLASTER-NAILS,WISHOR,CHIKAN MESH,CHEMICAL ETC. | 10 | Started | Material | (M)White Recron 3s Fibers (125 Gram/Packet) | KG | 150 | 295 | 44250 | 150 | 295 | 44250 | 15 | 295 | 4425 | 80 | 47.5 | 3799.6 | 0 | 0 | 0 | 135 | 150 | 39825 | 44250 | Building
399 | A BLDG PLASTER-NAILS,WISHOR,CHIKAN MESH,CHEMICAL ETC. | 10 | Started | Material | (M)Wishor | KG | 105 | 118 | 12390 | 105 | 118 | 12390 | 11 | 118 | 1298 | 75 | 112.1 | 8407.5 | 0 | 0 | 0 | 94 | 105 | 11092 | 12390 | Building
400 | A BLDG REG.ST CASE SANLA PLASTER-1ST TO 12TH | 0 | Tentative | Material | (M)Artificial Sand | BRASS | 6 | 5880 | 35280 | 6 | 5880 | 35280 | 0 | 5880 | 0 | 6 | 6300 | 37800 | 0 | 0 | 0 | 6 | 6 | 35280 | 35280
401 | A BLDG REG.ST CASE SANLA PLASTER-1ST TO 12TH | 0 | Tentative | Material | (M)CEMENT PPC 50KG | BAG | 94 | 320 | 30080 | 94 | 320 | 30080 | 0 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94 | 94 | 30080 | 30080
402 | A BLDG REG.ST CASE SANLA PLASTER-1ST TO 12TH | 0 | Tentative | Material | (M)PERMA PLASTO-O-PROOF CHEMICAL | LTR | 9 | 236 | 2124 | 9 | 236 | 2124 | 0 | 236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9 | 2124 | 2124
403 | A BLDG REG.ST CASE SANLA PLASTER-1ST TO 12TH | 0 | Tentative | Material | (M)SANLA-BADAM CHHAP | 12-15 KG/BAG | 105 | 120 | 12600 | 105 | 120 | 12600 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105 | 105 | 12600 | 12600
404 | A BLDG ALL TERR,FIRE ST & SERV.DUCT SC PLASTER-1ST TO12TH | 0 | Tentative | Material | (M)Artificial Sand | BRASS | 50 | 5880 | 294000 | 50 | 5880 | 294000 | 0 | 5880 | 0 | 50 | 6300 | 315000 | 0 | 0 | 0 | 50 | 50 | 294000 | 294000
405 | A BLDG ALL TERR,FIRE ST & SERV.DUCT SC PLASTER-1ST TO12TH | 0 | Tentative | Material | (M)CEMENT PPC 50KG | BAG | 945 | 320 | 302400 | 945 | 320 | 302400 | 0 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 945 | 945 | 302400 | 302400
406 | A BLDG ALL TERR,FIRE ST & SERV.DUCT SC PLASTER-1ST TO12TH | 0 | Tentative | Material | (M)Perma Plasto-O-Proof | BUCKET | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
407 | A BLDG ALL TERR,FIRE ST & SERV.DUCT SC PLASTER-1ST TO12TH | 0 | Tentative | Material | (M)PERMA PLASTO-O-PROOF CHEMICAL | LTR | 94 | 236 | 22184 | 0 | 0 | 0 | 0 | 236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94 | 94 | 22184 | 22184
408 | A BLDG ALL TERR,FIRE ST & SERV.DUCT SC PLASTER-1ST TO12TH | 0 | Tentative | Labour | (L)Single Coat plaster (Ghotai plaster) | SQFT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
409 | A BLDG ALL EXT.ELE-4 NOS & OPEN DUCT-2NOS DC PLASTER-UPTO 12 | 0 | Tentative | Material | (M)Artificial Sand | BRASS | 105 | 5880 | 617400 | 105 | 5880 | 617400 | 0 | 5880 | 0 | 105 | 6300 | 661500 | 0 | 0 | 0 | 105 | 105 | 617400 | 617400
410 | A BLDG ALL EXT.ELE-4 NOS & OPEN DUCT-2NOS DC PLASTER-UPTO 12 | 0 | Tentative | Material | (M)CEMENT PPC 50KG | BAG | 1883 | 320 | 602560 | 1883 | 320 | 602560 | 0 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1883 | 1883 | 602560 | 602560
411 | A BLDG ALL EXT.ELE-4 NOS & OPEN DUCT-2NOS DC PLASTER-UPTO 12 | 0 | Tentative | Material | (M)Perma Plasto-O-Proof | BUCKET | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
412 | A BLDG ALL EXT.ELE-4 NOS & OPEN DUCT-2NOS DC PLASTER-UPTO 12 | 0 | Tentative | Material | (M)PERMA PLASTO-O-PROOF CHEMICAL | LTR | 188 | 236 | 44368 | 188 | 236 | 44368 | 0 | 236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 188 | 188 | 44368 | 44368
413 | INDENT-890/A BLDG/INT.ELEC.SUPPLY | 0 | Started | Material | (M)10 sq.mm x 4 core Aluminium Armoured Cable | RMT | 80 | 121.54 | 9723.2 | 80 | 121.54 | 9723.2 | 0 | 121.54 | 0 | 80 | 123.44 | 9875.2 | 0 | 0 | 0 | 80 | 80 | 9723.2 | 9723.2 | Building
414 | INDENT-890/A BLDG/INT.ELEC.SUPPLY | 0 | Started | Material | (M)40 Amp 4 Pole MCB Schneider with Box | NOS | 6 | 3009 | 18054 | 6 | 3009 | 18054 | 0 | 3009 | 0 | 6 | 1760.58 | 10563.48 | 0 | 0 | 0 | 6 | 6 | 18054 | 18054 | Building
415 | INDENT-890/A BLDG/INT.ELEC.SUPPLY | 0 | Started | Material | (M)63 Amp 4 Pole MCB Schneider with Box | NOS | 2 | 1866.76 | 3733.52 | 2 | 1866.76 | 3733.52 | 0 | 1866.76 | 0 | 2 | 2106.95 | 4213.9 | 0 | 0 | 0 | 2 | 2 | 3733.52 | 3733.52 | Building
416 | INDENT-890/A BLDG/INT.ELEC.SUPPLY | 0 | Started | Material | (M)Flexible Cable 2.5 sq.mm x 2 core | RMT | 100 | 100 | 10000 | 100 | 100 | 10000 | 0 | 100 | 0 | 100 | 13.78 | 1378 | 0 | 0 | 0 | 100 | 100 | 10000 | 10000 | Building
417 | INDENT-890/A BLDG/INT.ELEC.SUPPLY | 0 | Started | Material | (M)Industrial Socket 20 Amp 3 Pin | NOS | 18 | 123.9 | 2230.2 | 18 | 123.9 | 2230.2 | 0 | 123.9 | 0 | 18 | 125.84 | 2265.12 | 0 | 0 | 0 | 18 | 18 | 2230.2 | 2230.2 | Building
418 | INDENT-890/A BLDG/INT.ELEC.SUPPLY | 0 | Started | Material | (M)Insulation Tape | NOS | 5 | 11.8 | 59 | 5 | 11.8 | 59 | 0 | 11.8 | 0 | 5 | 11.98 | 59.9 | 0 | 0 | 0 | 5 | 5 | 59 | 59 | Building
419 | INDENT-890/A BLDG/INT.ELEC.SUPPLY | 0 | Started | Material | (M)LED Tubelight Fitting 10W x 2' long | NOS | 14 | 129.8 | 1817.2 | 14 | 129.8 | 1817.2 | 0 | 129.8 | 0 | 14 | 131.83 | 1845.62 | 0 | 0 | 0 | 14 | 14 | 1817.2 | 1817.2 | Building
420 | INDENT-890/A BLDG/INT.ELEC.SUPPLY | 0 | Started | Material | (M)MS Saddle 1" | NOS | 100 | 2.31 | 231 | 100 | 2.31 | 231 | 0 | 2.31 | 0 | 100 | 2.34 | 234.1 | 0 | 0 | 0 | 100 | 100 | 231 | 231 | Building
421 | INDENT-890/A BLDG/INT.ELEC.SUPPLY | 0 | Started | Material | (M)Screw 8 x 35mm | NOS | 200 | 0.77 | 154 | 200 | 0.77 | 154 | 0 | 0.77 | 0 | 200 | 0.78 | 155.4 | 0 | 0 | 0 | 200 | 200 | 154 | 154 | Building
422 | A BLDG ELEC.WORK (MAT.)- SLAB PIPING 2ND TO 13TH SLAB | 0 | Started | Labour | (L)SLAB PIPING | Slab | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 38466.03 | 461592.408 | 9 | 38466.03 | 346194.31 | 12 | 3 | 0 | -346194.31
423 | A BLDG ELEC.WORK (MAT.)- WALL PIPING 1ST & 2ND FLOOR | 0 | Started | Labour | (L)WALL PIPING | FLOORS | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 26656.79 | 53313.58 | 2 | 26656.79 | 53313.58 | 2 | 0 | 0 | -53313.58
424 | A BLDG ELEC.WORK (MAT.)- WALL PIPING 3RD TO 12TH FLOOR | 0 | Started | Labour | (L)WALL PIPING | FLOORS | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 29500 | 295000 | 6 | 29500 | 177000 | 10 | 4 | 0 | -177000
425 | A BLDG ELEC.WORK (MAT.)- DB FIXING 1ST TO 12TH FLOOR | 0 | Tentative | Labour | (L)DB FIXING | FLOORS | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 9440 | 113280 | 0 | 0 | 0 | 12 | 12 | 0 | 0
426 | A BLDG ELEC.WORK (MAT.)- WIRING 1ST TO 12TH FLOOR | 0 | Tentative | Labour | (L)WIRING | FLOORS | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 102576.22 | 1230914.64 | 0 | 0 | 0 | 12 | 12 | 0 | 0
427 | A BLDG ELEC.WORK (MAT.)- PLATES & SWITCHES 1ST TO 12TH FLOOR | 0 | Tentative | Labour | (L)PLATES & SWITCHES | FLOORS | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 85480.38 | 1025764.56 | 0 | 0 | 0 | 12 | 12 | 0 | 0
428 | A BLDG ELEC.WORK (MAT.)- TESTING ALL FLOOR FLATS | 0 | Tentative | Labour | (L)ELECTRICAL WORK. | NOS | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 34191.68 | 68383.36 | 0 | 0 | 0 | 2 | 2 | 0 | 0
429 | A BLDG ELEC.WORK (MAT.)-RETENTION AFTER COMP. OF RET. PERIOD | 0 | Tentative | Labour | (L)ELECTRICAL WORK. | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 118722.16 | 118722.16 | 0 | 0 | 0 | 1 | 1 | 0 | 0
430 | A BLDG ELEC.WORK (LAB.)- SLAB PIPING 2ND TO 13TH SLAB | 0 | Started | Labour | (L)SLAB PIPING | Slab | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12677 | 152124 | 9 | 12677 | 114093 | 12 | 3 | 0 | -114093
431 | A BLDG ELEC.WORK (LAB.)- WALL PIPING 1ST & 2ND FLOOR | 0 | Started | Labour | (L)WALL PIPING | FLOORS | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 8063 | 16126 | 2 | 8063 | 16126 | 2 | 0 | 0 | -16126
432 | A BLDG ELEC.WORK (LAB.)- WALL PIPING 3RD TO 12TH FLOOR | 0 | Started | Labour | (L)WALL PIPING | FLOORS | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10000 | 100000 | 6 | 10000 | 60000 | 10 | 4 | 0 | -60000
433 | A BLDG ELEC.WORK (LAB.)- DB FIXING 1ST TO 12TH FLOOR | 0 | Tentative | Labour | (L)DB FIXING | FLOORS | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 3000 | 36000 | 0 | 0 | 0 | 12 | 12 | 0 | 0
434 | A BLDG ELEC.WORK (LAB.)- WIRING 1ST TO 12TH FLOOR | 0 | Tentative | Labour | (L)WIRING | FLOORS | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 33805.67 | 405668.004 | 0 | 0 | 0 | 12 | 12 | 0 | 0
435 | A BLDG ELEC.WORK (LAB.)- PLATES & SWITCHES 1ST TO 12TH FLOOR | 0 | Tentative | Labour | (L)PLATES & SWITCHES | FLOORS | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 28171.33 | 338056.008 | 0 | 0 | 0 | 12 | 12 | 0 | 0
436 | A BLDG ELEC.WORK (LAB.)- TESTING ALL FLOOR FLATS | 0 | Tentative | Labour | (L)ELECTRICAL WORK. | NOS | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 11269 | 22538 | 0 | 0 | 0 | 2 | 2 | 0 | 0
437 | A BLDG ELEC.WORK (LAB.)-RETENTION AFTER COMP. OF RET. PERIOD | 0 | Tentative | Labour | (L)ELECTRICAL WORK. | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 100612 | 100612 | 0 | 0 | 0 | 1 | 1 | 0 | 0
438 | A BLDG ELECTRICAL MOTOR STARTER-MATERIAL | 0 | Tentative | Material | (M)3-PHASE DIGITAL STARTER-KDM222 | NOS | 1 | 4720 | 4720 | 1 | 4720 | 4720 | 0 | 4720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 4720 | 4720
439 | A Wing CAR Policy: 1st Installments (at policy inception) | 0 | Started | Labour | (L)CAR Policy-Premium | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 85899.28 | 85899.28 | 1 | 85899.28 | 85899.28 | 1 | 0 | 1.18 | -85898.1
440 | A Wing CAR Policy: 2nd Installments | 0 | Tentative | Labour | (L)CAR Policy-Premium | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 34005.24 | 34005.24 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
441 | A Wing CAR Policy: 3rd Installments | 0 | Tentative | Labour | (L)CAR Policy-Premium | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 34005.24 | 34005.24 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
442 | A Wing CAR Policy: 4th Installments | 0 | Tentative | Labour | (L)CAR Policy-Premium | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 34005.24 | 34005.24 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
443 | A Wing CAR Policy: 5th Installments | 0 | Tentative | Labour | (L)CAR Policy-Premium | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 34005.24 | 34005.24 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
444 | A Wing CAR Policy: 6th Installments | 0 | Tentative | Labour | (L)CAR Policy-Premium | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 34005.24 | 34005.24 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
445 | A Wing CAR Policy: 7th Installments | 0 | Tentative | Labour | (L)CAR Policy-Premium | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 34005.24 | 34005.24 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
446 | A Wing CAR Policy: 8th Installments | 0 | Tentative | Labour | (L)CAR Policy-Premium | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 34005.24 | 34005.24 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
447 | A Wing CAR Policy: 9th Installments | 0 | Tentative | Labour | (L)CAR Policy-Premium | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 34005.24 | 34005.24 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
448 | A BLDG DEBRIS DRUM CHUTES GR+12 FLOOR | 0 | Tentative | Material | (M)DEBRIS DRUM CHUTES | RMT | 39 | 2360 | 92040 | 39 | 2360 | 92040 | 0 | 2360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 39 | 92040 | 92040
449 | CPVC-A WING PLUMBING WORK-INTERNAL CONSEALED | 0 | Tentative | Material | (M)CPVC Brass Elbow 1/2" | NOS | 1600 | 35.4 | 56640 | 1600 | 35.4 | 56640 | 0 | 35.4 | 0 | 1600 | 38.63 | 61805.44 | 0 | 0 | 0 | 1600 | 1600 | 56640 | 56640
450 | CPVC-A WING PLUMBING WORK-INTERNAL CONSEALED | 0 | Tentative | Material | (M)CPVC BRASS MTA 1 1/4" | NOS | 54 | 54 | 2916 | 54 | 54 | 2916 | 0 | 54 | 0 | 54 | 354 | 19116.0972 | 0 | 0 | 0 | 54 | 54 | 2916 | 2916
451 | CPVC-A WING PLUMBING WORK-INTERNAL CONSEALED | 0 | Tentative | Material | (M)CPVC BRASS MTA 1'' | NOS | 125 | 106.2 | 13275 | 125 | 106.2 | 13275 | 0 | 106.2 | 0 | 125 | 170.83 | 21354.075 | 0 | 0 | 0 | 125 | 125 | 13275 | 13275
452 | CPVC-A WING PLUMBING WORK-INTERNAL CONSEALED | 0 | Tentative | Material | (M)CPVC CONSEALED STOP COCK-1/2'' (ALD-CHR-083) | NOS | 70 | 2065 | 144550 | 70 | 2065 | 144550 | 0 | 2065 | 0 | 70 | 650.19 | 45513.013 | 0 | 0 | 0 | 70 | 70 | 144550 | 144550
453 | CPVC-A WING PLUMBING WORK-INTERNAL CONSEALED | 0 | Tentative | Material | (M)CPVC Elbow 1 1/4" (90 degree) | NOS | 182 | 47.2 | 8590.4 | 182 | 47.2 | 8590.4 | 0 | 47.2 | 0 | 182 | 43.36 | 7890.7374 | 0 | 0 | 0 | 182 | 182 | 8590.4 | 8590.4
454 | CPVC-A WING PLUMBING WORK-INTERNAL CONSEALED | 0 | Tentative | Material | (M)CPVC Elbow 1" (90 degree) | NOS | 420 | 44.84 | 18832.8 | 420 | 44.84 | 18832.8 | 0 | 44.84 | 0 | 420 | 19.85 | 8336.328 | 0 | 0 | 0 | 420 | 420 | 18832.8 | 18832.8
455 | CPVC-A WING PLUMBING WORK-INTERNAL CONSEALED | 0 | Tentative | Material | (M)CPVC Elbow 1/2 (90 degree) | NOS | 715 | 35.4 | 25311 | 715 | 35.4 | 25311 | 0 | 35.4 | 0 | 715 | 8 | 5718.284 | 0 | 0 | 0 | 715 | 715 | 25311 | 25311
456 | CPVC-A WING PLUMBING WORK-INTERNAL CONSEALED | 0 | Tentative | Material | (M)CPVC End Cap 1 1/4" | NOS | 64 | 35.4 | 2265.6 | 64 | 35.4 | 2265.6 | 0 | 35.4 | 0 | 64 | 23.35 | 1494.112 | 0 | 0 | 0 | 64 | 64 | 2265.6 | 2265.6
457 | CPVC-A WING PLUMBING WORK-INTERNAL CONSEALED | 0 | Tentative | Material | (M)CPVC End Cap 1" | NOS | 54 | 29.5 | 1593 | 54 | 29.5 | 1593 | 0 | 29.5 | 0 | 54 | 11.37 | 613.7154 | 0 | 0 | 0 | 54 | 54 | 1593 | 1593
458 | CPVC-A WING PLUMBING WORK-INTERNAL CONSEALED | 0 | Tentative | Material | (M)CPVC End Cap 1/2" | NOS | 360 | 5.9 | 2124 | 360 | 5.9 | 2124 | 0 | 5.9 | 0 | 360 | 4.66 | 1678.5 | 0 | 0 | 0 | 360 | 360 | 2124 | 2124
459 | CPVC-A WING PLUMBING WORK-INTERNAL CONSEALED | 0 | Tentative | Material | (M)CPVC End Plug Threaded 1/2'' (Long) | NOS | 1395 | 11.8 | 16461 | 1395 | 11.8 | 16461 | 0 | 11.8 | 0 | 1395 | 5.18 | 7227.0765 | 0 | 0 | 0 | 1395 | 1395 | 16461 | 16461
460 | CPVC-A WING PLUMBING WORK-INTERNAL CONSEALED | 0 | Tentative | Material | (M)CPVC Pipe 1 1/4" X 3m long (SDR-11) | NOS | 12 | 944 | 11328 | 12 | 944 | 11328 | 0 | 944 | 0 | 12 | 476.36 | 5716.35 | 0 | 0 | 0 | 12 | 12 | 11328 | 11328
461 | CPVC-A WING PLUMBING WORK-INTERNAL CONSEALED | 0 | Tentative | Material | (M)CPVC Pipe 1" X 3m long (SDR-11) | NOS | 35 | 826 | 28910 | 35 | 826 | 28910 | 0 | 826 | 0 | 35 | 303.26 | 10614.2295 | 0 | 0 | 0 | 35 | 35 | 28910 | 28910
462 | CPVC-A WING PLUMBING WORK-INTERNAL CONSEALED | 0 | Tentative | Material | (M)CPVC Pipe 1/2 X 3m long (SDR-11) | NOS | 318 | 531 | 168858 | 318 | 531 | 168858 | 0 | 531 | 0 | 318 | 132.88 | 42257.1438 | 0 | 0 | 0 | 318 | 318 | 168858 | 168858
463 | CPVC-A WING PLUMBING WORK-INTERNAL CONSEALED | 0 | Tentative | Material | (M)CPVC Step Over Bend 1/2" | NOS | 105 | 35.4 | 3717 | 105 | 35.4 | 3717 | 0 | 35.4 | 0 | 105 | 28.23 | 2964.6435 | 0 | 0 | 0 | 105 | 105 | 3717 | 3717
464 | CPVC-A WING PLUMBING WORK-INTERNAL CONSEALED | 0 | Tentative | Material | (M)CPVC Tee 1/2" | NOS | 800 | 17.7 | 14160 | 800 | 17.7 | 14160 | 0 | 17.7 | 0 | 800 | 10.98 | 8781.2 | 0 | 0 | 0 | 800 | 800 | 14160 | 14160
465 | CPVC-A WING PLUMBING WORK-INTERNAL CONSEALED | 0 | Tentative | Material | (M)Teflon Tape | NOS | 280 | 19.48 | 5454.4 | 280 | 19.48 | 5454.4 | 0 | 19.48 | 0 | 280 | 19.47 | 5451.6 | 0 | 0 | 0 | 280 | 280 | 5454.4 | 5454.4
466 | UPVC-A WING PLUMBING WORK-INTERNAL CONSEALED | 0 | Tentative | Material | (M)CP Flush Valve 32mm (1085-N) | NOS | 72 | 3599 | 259128 | 72 | 3599 | 259128 | 0 | 3599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 72 | 259128 | 259128
467 | UPVC-A WING PLUMBING WORK-INTERNAL CONSEALED | 0 | Tentative | Material | (M)HALF TURN COCK-1'' (ALD-CHR-081) | NOS | 63 | 944 | 59472 | 63 | 944 | 59472 | 0 | 944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | 63 | 59472 | 59472
468 | UPVC-A WING PLUMBING WORK-INTERNAL CONSEALED | 0 | Tentative | Material | (M)M SEAL - 250 GM | NOS | 32 | 100 | 3200 | 32 | 100 | 3200 | 0 | 100 | 0 | 32 | 73.46 | 2350.56 | 0 | 0 | 0 | 32 | 32 | 3200 | 3200
469 | UPVC-A WING PLUMBING WORK-INTERNAL CONSEALED | 0 | Tentative | Material | (M)UPVC Elbow 1 1/4 (90 degree) | NOS | 27 | 23.61 | 637.47 | 27 | 23.61 | 637.47 | 0 | 23.61 | 0 | 27 | 20.72 | 559.4967 | 0 | 0 | 0 | 27 | 27 | 637.47 | 637.47
470 | UPVC-A WING PLUMBING WORK-INTERNAL CONSEALED | 0 | Tentative | Material | (M)UPVC FTA Brass Thread 1 1/4 | NOS | 72 | 236 | 16992 | 72 | 236 | 16992 | 0 | 236 | 0 | 72 | 139.62 | 10052.568 | 0 | 0 | 0 | 72 | 72 | 16992 | 16992
471 | UPVC-A WING PLUMBING WORK-INTERNAL CONSEALED | 0 | Tentative | Material | (M)UPVC Pipe 1 1/4 X 3m long (SCH-40) | NOS | 15 | 465.33 | 6979.95 | 15 | 465.33 | 6979.95 | 0 | 465.33 | 0 | 15 | 263.63 | 3954.4695 | 0 | 0 | 0 | 15 | 15 | 6979.95 | 6979.95
472 | PVC-A WING PLUMBING WORK-INTERNAL CONSEALED | 0 | Tentative | Material | (M)Chair Bracket with nut bolt & wishor | NOS | 61 | 590 | 35990 | 61 | 590 | 35990 | 0 | 590 | 0 | 61 | 649 | 39589 | 0 | 0 | 0 | 61 | 61 | 35990 | 35990
473 | PVC-A WING PLUMBING WORK-INTERNAL CONSEALED | 0 | Tentative | Material | (M)GI C-Bracket 6" x 2" | NOS | 285 | 43.81 | 12485.85 | 285 | 43.81 | 12485.85 | 0 | 43.81 | 0 | 285 | 43.81 | 12485.1375 | 0 | 0 | 0 | 285 | 285 | 12485.85 | 12485.85
474 | PVC-A WING PLUMBING WORK-INTERNAL CONSEALED | 0 | Tentative | Material | (M)GI U Clamp with Nut Bolt & Washer 3" | NOS | 30 | 17.7 | 531 | 30 | 17.7 | 531 | 0 | 17.7 | 0 | 30 | 17.7 | 531 | 0 | 0 | 0 | 30 | 30 | 531 | 531
475 | PVC-A WING PLUMBING WORK-INTERNAL CONSEALED | 0 | Tentative | Material | (M)P-Trap 110 mm (Ceramic) | NOS | 70 | 177 | 12390 | 70 | 177 | 12390 | 0 | 177 | 0 | 70 | 106.2 | 7434 | 0 | 0 | 0 | 70 | 70 | 12390 | 12390
476 | PVC-A WING PLUMBING WORK-INTERNAL CONSEALED | 0 | Tentative | Material | (M)PVC BUSHING 50mm x 40 mm | NOS | 150 | 11.83 | 1774.5 | 150 | 11.83 | 1774.5 | 0 | 11.83 | 0 | 150 | 10.3 | 1544.49 | 0 | 0 | 0 | 150 | 150 | 1774.5 | 1774.5
477 | PVC-A WING PLUMBING WORK-INTERNAL CONSEALED | 0 | Tentative | Material | (M)PVC Elbow 40 mm | NOS | 225 | 70.8 | 15930 | 225 | 70.8 | 15930 | 0 | 70.8 | 0 | 225 | 13.18 | 2965.095 | 0 | 0 | 0 | 225 | 225 | 15930 | 15930
478 | PVC-A WING PLUMBING WORK-INTERNAL CONSEALED | 0 | Tentative | Material | (M)PVC Elbow 50 mm | NOS | 150 | 38.77 | 5815.5 | 150 | 38.77 | 5815.5 | 0 | 38.77 | 0 | 150 | 21.76 | 3263.805 | 0 | 0 | 0 | 150 | 150 | 5815.5 | 5815.5
479 | PVC-A WING PLUMBING WORK-INTERNAL CONSEALED | 0 | Tentative | Material | (M)PVC Gray Pipes S/F 10ft long 40 mm (4Kg/Sqcm) | NOS | 140 | 281.81 | 39453.4 | 140 | 281.81 | 39453.4 | 0 | 281.81 | 0 | 140 | 112.03 | 15684.48 | 0 | 0 | 0 | 140 | 140 | 39453.4 | 39453.4
480 | PVC-A WING PLUMBING WORK-INTERNAL CONSEALED | 0 | Tentative | Material | (M)PVC Gray Pipes S/F 10ft long 50 mm (4Kg/Sqcm) | NOS | 40 | 306.8 | 12272 | 40 | 306.8 | 12272 | 0 | 306.8 | 0 | 40 | 167.72 | 6708.972 | 0 | 0 | 0 | 40 | 40 | 12272 | 12272
481 | PVC-A WING PLUMBING WORK-INTERNAL CONSEALED | 0 | Tentative | Material | (M)PVC Nahani Trap 75 mm | NOS | 161 | 66.49 | 10704.89 | 161 | 66.49 | 10704.89 | 0 | 66.49 | 0 | 161 | 65.41 | 10530.3499 | 0 | 0 | 0 | 161 | 161 | 10704.89 | 10704.89
482 | PVC-A WING PLUMBING WORK-INTERNAL CONSEALED | 0 | Tentative | Material | (M)PVC Shoe 40 mm | NOS | 80 | 17.81 | 1424.8 | 80 | 17.81 | 1424.8 | 0 | 17.81 | 0 | 80 | 17.61 | 1409.144 | 0 | 0 | 0 | 80 | 80 | 1424.8 | 1424.8
483 | PVC-A WING PLUMBING WORK-INTERNAL CONSEALED | 0 | Tentative | Material | (M)PVC Shoe 50 mm | NOS | 50 | 48.62 | 2431 | 50 | 48.62 | 2431 | 0 | 48.62 | 0 | 50 | 27.3 | 1364.78 | 0 | 0 | 0 | 50 | 50 | 2431 | 2431
484 | PVC-A WING PLUMBING WORK-INTERNAL CONSEALED | 0 | Tentative | Material | (M)SWR Multi Floor Trap 4" Height 110 mm | NOS | 170 | 105.17 | 17878.9 | 170 | 105.17 | 17878.9 | 0 | 105.17 | 0 | 170 | 103.61 | 17614.278 | 0 | 0 | 0 | 170 | 170 | 17878.9 | 17878.9
485 | PVC-A WING PLUMBING WORK-INTERNAL CONSEALED | 0 | Tentative | Material | (M)SWR Pipes 'B' type R/F 10ft long S/S 110mm | NOS | 15 | 885 | 13275 | 15 | 885 | 13275 | 0 | 885 | 0 | 15 | 630.1 | 9451.4985 | 0 | 0 | 0 | 15 | 15 | 13275 | 13275
486 | PVC-A WING PLUMBING WORK-INTERNAL CONSEALED | 0 | Tentative | Material | (M)SWR Pipes 'B' type R/F 10ft long S/S 75mm | NOS | 150 | 417.93 | 62689.5 | 150 | 417.93 | 62689.5 | 0 | 417.93 | 0 | 150 | 417.69 | 62653.755 | 0 | 0 | 0 | 150 | 150 | 62689.5 | 62689.5
487 | PVC-A WING PLUMBING WORK-INTERNAL CONSEALED | 0 | Tentative | Material | (M)SWR Pipes 'B' type R/F 3ft long D/S 75mm | NOS | 40 | 147.24 | 5889.6 | 40 | 147.24 | 5889.6 | 0 | 147.24 | 0 | 40 | 147 | 5880.06 | 0 | 0 | 0 | 40 | 40 | 5889.6 | 5889.6
488 | PVC-A WING PLUMBING WORK-INTERNAL CONSEALED | 0 | Tentative | Material | (M)SWR Plain Tee 75 mm | NOS | 155 | 59.03 | 9149.65 | 155 | 59.03 | 9149.65 | 0 | 59.03 | 0 | 155 | 58.28 | 9033.803 | 0 | 0 | 0 | 155 | 155 | 9149.65 | 9149.65
489 | PVC-A WING PLUMBING WORK-INTERNAL CONSEALED | 0 | Tentative | Material | (M)SWR Shoe 75 mm | NOS | 260 | 70.8 | 18408 | 260 | 70.8 | 18408 | 0 | 70.8 | 0 | 260 | 38.21 | 9933.898 | 0 | 0 | 0 | 260 | 260 | 18408 | 18408
490 | PVC-A WING PLUMBING WORK-INTERNAL CONSEALED | 0 | Tentative | Material | (M)SWR Single Y 75 mm | NOS | 15 | 135.7 | 2035.5 | 15 | 135.7 | 2035.5 | 0 | 135.7 | 0 | 15 | 76.41 | 1146.219 | 0 | 0 | 0 | 15 | 15 | 2035.5 | 2035.5
491 | A BLDG INT. CONC. PLUB. - TOILET & BATHROOM (EACH 3-FLOOR) | 0 | Started | Labour | (L)Internal Concealed Work | NOS | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 63562.5 | 254250 | 2 | 63562.5 | 127125 | 4 | 2 | 0 | -127125
492 | A BLDG INT. CONC. PLUB. -PRES., TESTING & LEVL. (EACH 6-FLR) | 0 | Started | Labour | (L)Internal Concealed Work | NOS | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 15255 | 30510 | 1 | 15255 | 15255 | 2 | 1 | 0 | -15255
493 | A BLDG INT. CONC. PLUB. -KITCHEN PLUMBING (EACH 6-FLR) | 0 | Tentative | Labour | (L)Internal Concealed Work | NOS | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 40680 | 81360 | 0 | 0 | 0 | 2 | 2 | 0 | 0
494 | A BLDG INT. CONC. PLUB. - P-TRAP, N-TRAP & OUT. (EACH 6-FLR) | 0 | Tentative | Labour | (L)Internal Concealed Work | NOS | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 25425 | 50850 | 0 | 0 | 0 | 2 | 2 | 0 | 0
495 | A BLDG EXT. DUCT. PLUB. - TERR LINE (EACH 6 FLOOR) | 0 | Tentative | Labour | (L)External Plumbing Work | NOS | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 6102 | 24408 | 0 | 0 | 0 | 4 | 4 | 0 | 0
496 | A BLDG EXT. DUCT. PLUB. - KITCHEN PVC, UPVC (EACH 6 FLOOR) | 0 | Tentative | Labour | (L)External Plumbing Work | NOS | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 10170 | 40680 | 0 | 0 | 0 | 4 | 4 | 0 | 0
497 | A BLDG EXT. DUCT. PLUB. - TOILET PVC [CT & MT] (EACH 6 FLR) | 0 | Tentative | Labour | (L)External Plumbing Work | NOS | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 14238 | 56952 | 0 | 0 | 0 | 4 | 4 | 0 | 0
498 | A BLDG EXT. DUCT. PLUB. - TOILET UPVC [CT & MT] (EACH 6 FLR) | 0 | Tentative | Labour | (L)External Plumbing Work | NOS | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 10170 | 40680 | 0 | 0 | 0 | 4 | 4 | 0 | 0
499 | A BLDG EXT. DUCT. PLUB. -RAIN WATER LINE & ALL.PRV FIXING | 0 | Tentative | Labour | (L)External Plumbing Work | NOS | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 10170 | 20340 | 0 | 0 | 0 | 2 | 2 | 0 | 0
500 | A BLDG EXT. DUCT. PLUB. -ALL DUCT ANTISYPHON LINES COMPL. | 0 | Tentative | Labour | (L)External Plumbing Work | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 12204 | 12204 | 0 | 0 | 0 | 1 | 1 | 0 | 0
501 | A BLDG EXT. DUCT. PLUB. -MISC. DUCT WORK. | 0 | Tentative | Labour | (L)Miss. Work (Plumbing) | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 8136 | 8136 | 0 | 0 | 0 | 1 | 1 | 0 | 0
502 | A BLDG EXT. DUCT. PLUB. - LOOPING 50% & COMPLETED 100% | 0 | Tentative | Labour | (L)External Plumbing Work | NOS | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 20340 | 40680 | 0 | 0 | 0 | 2 | 2 | 0 | 0
503 | A BLDG SANITRY. - ORISSA PAN COMPL. (EACH 4 FLOOR) | 0 | Tentative | Labour | (L)Sanitry Work | NOS | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 13221 | 39663 | 0 | 0 | 0 | 3 | 3 | 0 | 0
504 | A BLDG SANITRY. -LEDGE WALL & CH. BRACKET (EACH 6 FLR) | 0 | Tentative | Labour | (L)Sanitry Work | NOS | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 14543.1 | 29086.2 | 0 | 0 | 0 | 2 | 2 | 0 | 0
505 | A BLDG SANITRY. - COMMODE & BASIN FIXING (EACH 4 FLOOR) | 0 | Tentative | Labour | (L)Sanitry Work | NOS | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 21153.6 | 63460.8 | 0 | 0 | 0 | 3 | 3 | 0 | 0
506 | A BLDG CP - ALL TYPES OF CP FITTING (EACH 4 FLOOR) | 0 | Tentative | Labour | (L)CP WORK | NOS | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 32950.8 | 98852.4 | 0 | 0 | 0 | 3 | 3 | 0 | 0
507 | A BLDG CP - CP Testing upto 12th Floor | 0 | Tentative | Labour | (L)CP WORK | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 23187.6 | 23187.6 | 0 | 0 | 0 | 1 | 1 | 0 | 0
508 | A BLDG PARKING DRAINAGE LINE-50% & COMPLETED-100% | 0 | Tentative | Labour | (L)External Plumbing Work | NOS | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 20340 | 40680 | 0 | 0 | 0 | 2 | 2 | 0 | 0
509 | A BLDG MISC. WORK - COMPL. OF ALL MISC. WORKS | 0 | Tentative | Labour | (L)Miss. Work (Plumbing) | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 10170 | 10170 | 0 | 0 | 0 | 1 | 1 | 0 | 0
510 | A BLDG RETENTION - AFTER COMPLETION OF RET. PERIOD | 0 | Tentative | Labour | (L)Retention (Plumbing) | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 50850 | 50850 | 0 | 0 | 0 | 1 | 1 | 0 | 0
511 | A BLDG OHWT SLEEVES-OUTLET,DRAIN & OVERFLOW | 0 | Tentative | Material | (M)GI SLEEVE ONE SIDE THREAD (OD -100MM, L-450MM) | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
512 | A BLDG OHWT SLEEVES-OUTLET,DRAIN & OVERFLOW | 0 | Tentative | Material | (M)GI SLEEVE ONE SIDE THREAD (OD -50MM, L-450MM) | NOS | 2 | 708 | 1416 | 2 | 708 | 1416 | 0 | 708 | 0 | 2 | 389.67 | 779.34 | 0 | 0 | 0 | 2 | 2 | 1416 | 1416
513 | A BLDG OHWT SLEEVES-OUTLET,DRAIN & OVERFLOW | 0 | Tentative | Material | (M)GI SLEEVE ONE SIDE THREAD (OD -65MM, L-450MM) | NOS | 6 | 708 | 4248 | 6 | 708 | 4248 | 0 | 708 | 0 | 6 | 537.19 | 3223.14 | 0 | 0 | 0 | 6 | 6 | 4248 | 4248
514 | A BLDG OHWT SLEEVES-OUTLET,DRAIN & OVERFLOW | 0 | Tentative | Material | (M)GI SLEEVE ONE SIDE THREAD (OD -80MM, L-450MM) | NOS | 2 | 826 | 1652 | 2 | 826 | 1652 | 0 | 826 | 0 | 2 | 640.62 | 1281.24 | 0 | 0 | 0 | 2 | 2 | 1652 | 1652
515 | A BLDG OHWT SLEEVES-OUTLET,DRAIN & OVERFLOW | 0 | Tentative | Material | (M)SWR Pipes 'B' type S/F 10ft long S/S 160mm | NOS | 2 | 944 | 1888 | 2 | 944 | 1888 | 0 | 944 | 0 | 2 | 1393.39 | 2786.78 | 0 | 0 | 0 | 2 | 2 | 1888 | 1888
516 | A BLDG OHWT SLEEVES-OUTLET,DRAIN & OVERFLOW | 0 | Tentative | Material | (M)SWR Plain Bend 160 mm | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
517 | A BLDG CT, MT, DRY TERR, ATT.BAL, BED.BAL & STAND OUT WP WOR | 0 | Tentative | Material | (M)Artificial Sand | BRASS | 64 | 5880 | 376320 | 64 | 5880 | 376320 | 0 | 5880 | 0 | 64 | 6300 | 403200 | 0 | 0 | 0 | 64 | 64 | 376320 | 376320
518 | A BLDG CT, MT, DRY TERR, ATT.BAL, BED.BAL & STAND OUT WP WOR | 0 | Tentative | Material | (M)CEMENT PPC 50KG | BAG | 1031 | 320 | 329920 | 1031 | 320 | 329920 | 0 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1031 | 1031 | 329920 | 329920
519 | A BLDG CT, MT, DRY TERR, ATT.BAL, BED.BAL & STAND OUT WP WOR | 0 | Tentative | Material | (M)Pidifin - 2k - 15kg | PACKET | 209 | 1465 | 306185 | 209 | 1465 | 306185 | 0 | 1465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 209 | 209 | 306185 | 306185
520 | A BLDG CT, MT, DRY TERR, ATT.BAL, BED.BAL & STAND OUT WP WOR | 0 | Tentative | Material | (M)Red Bricks 4" | NOS | 47000 | 8.5 | 399500 | 47000 | 8.5 | 399500 | 0 | 8.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47000 | 47000 | 399500 | 399500
521 | FIRE BOOSTER PUMP_7.5 HP | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Installation Charge | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 3540 | 3540 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
522 | FIRE BOOSTER PUMP_7.5 HP | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Supply Charge | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 44250 | 44250 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
523 | FIRE BOOSTER ELECTRICAL STARTER_7.5 HP | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Installation Charge | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 1180 | 1180 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
524 | FIRE BOOSTER ELECTRICAL STARTER_7.5 HP | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Supply Charge | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 6318.9 | 6318.9 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
525 | 150 MM - Butterfly Valve | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Installation Charge | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 566.4 | 566.4 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
526 | 150 MM - Butterfly Valve | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Supply Charge | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 3826.74 | 3826.74 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
527 | 100 MM - Butterfly Valve | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Installation Charge | NOS | 2 | 1.18 | 2.36 | 0 | 0 | 0 | 0 | 1.18 | 0 | 2 | 377.6 | 755.2 | 0 | 0 | 0 | 2 | 2 | 2.36 | 2.36
528 | 100 MM - Butterfly Valve | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Supply Charge | NOS | 2 | 1.18 | 2.36 | 0 | 0 | 0 | 0 | 1.18 | 0 | 2 | 2476.82 | 4953.64 | 0 | 0 | 0 | 2 | 2 | 2.36 | 2.36
529 | 100MM Non ReturnValve | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Installation Charge | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 377.6 | 377.6 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
530 | 100MM Non ReturnValve | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Supply Charge | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 2069.72 | 2069.72 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
531 | Air release valves with Ball Valve | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Installation Charge | NOS | 2 | 1.18 | 2.36 | 0 | 0 | 0 | 0 | 1.18 | 0 | 2 | 153.4 | 306.8 | 0 | 0 | 0 | 2 | 2 | 2.36 | 2.36
532 | Air release valves with Ball Valve | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Supply Charge | NOS | 2 | 1.18 | 2.36 | 0 | 0 | 0 | 0 | 1.18 | 0 | 2 | 1321.6 | 2643.2 | 0 | 0 | 0 | 2 | 2 | 2.36 | 2.36
533 | Ball Valve of of 20 mm | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Installation Charge | NOS | 14 | 1.18 | 16.52 | 0 | 0 | 0 | 0 | 1.18 | 0 | 14 | 118 | 1652 | 0 | 0 | 0 | 14 | 14 | 16.52 | 16.52
534 | Ball Valve of of 20 mm | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Supply Charge | NOS | 14 | 1.18 | 16.52 | 0 | 0 | 0 | 0 | 1.18 | 0 | 14 | 469.64 | 6574.96 | 0 | 0 | 0 | 14 | 14 | 16.52 | 16.52
535 | SS Single Hydrant Valve of 80 mm inlet & 63 mm outlet dia | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Installation Charge | NOS | 14 | 1.18 | 16.52 | 0 | 0 | 0 | 0 | 1.18 | 0 | 14 | 236 | 3304 | 0 | 0 | 0 | 14 | 14 | 16.52 | 16.52
536 | SS Single Hydrant Valve of 80 mm inlet & 63 mm outlet dia | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Supply Charge | NOS | 14 | 1.18 | 16.52 | 0 | 0 | 0 | 0 | 1.18 | 0 | 14 | 4248 | 59472 | 0 | 0 | 0 | 14 | 14 | 16.52 | 16.52
537 | SINGLE DOOR HOSE BOX | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Installation Charge | NOS | 14 | 1.18 | 16.52 | 0 | 0 | 0 | 0 | 1.18 | 0 | 14 | 236 | 3304 | 0 | 0 | 0 | 14 | 14 | 16.52 | 16.52
538 | SINGLE DOOR HOSE BOX | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Supply Charge | NOS | 14 | 1.18 | 16.52 | 0 | 0 | 0 | 0 | 1.18 | 0 | 14 | 1109.2 | 15528.8 | 0 | 0 | 0 | 14 | 14 | 16.52 | 16.52
539 | HOSE PIPE | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Installation Charge | NOS | 14 | 1.18 | 16.52 | 0 | 0 | 0 | 0 | 1.18 | 0 | 14 | 118 | 1652 | 0 | 0 | 0 | 14 | 14 | 16.52 | 16.52
540 | HOSE PIPE | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Supply Charge | NOS | 14 | 1.18 | 16.52 | 0 | 0 | 0 | 0 | 1.18 | 0 | 14 | 3584 | 50176 | 0 | 0 | 0 | 14 | 14 | 16.52 | 16.52
541 | BRANCH PIPE | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Installation Charge | NOS | 14 | 1.18 | 16.52 | 0 | 0 | 0 | 0 | 1.18 | 0 | 14 | 118 | 1652 | 0 | 0 | 0 | 14 | 14 | 16.52 | 16.52
542 | BRANCH PIPE | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Supply Charge | NOS | 14 | 1.18 | 16.52 | 0 | 0 | 0 | 0 | 1.18 | 0 | 14 | 1545.8 | 21641.2 | 0 | 0 | 0 | 14 | 14 | 16.52 | 16.52
543 | HOSE REEL | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Installation Charge | NOS | 14 | 1.18 | 16.52 | 0 | 0 | 0 | 0 | 1.18 | 0 | 14 | 413 | 5782 | 0 | 0 | 0 | 14 | 14 | 16.52 | 16.52
544 | HOSE REEL | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Supply Charge | NOS | 14 | 1.18 | 16.52 | 0 | 0 | 0 | 0 | 1.18 | 0 | 14 | 5428 | 75992 | 0 | 0 | 0 | 14 | 14 | 16.52 | 16.52
545 | GI Pipe 150 mm dia (Hydrant) | 0 | Tentative | Labour | (L)Fire Hydrent Systems_Installation Charge (GI Pipes) | RMT | 42 | 1.18 | 49.56 | 0 | 0 | 0 | 0 | 1.18 | 0 | 42 | 743.4 | 31222.8 | 0 | 0 | 0 | 42 | 42 | 49.56 | 49.56
546 | GI Pipe 150 mm dia (Hydrant) | 0 | Tentative | Labour | (L)Fire Hydrent Systems_Supply Charge (GI Pipes) | RMT | 42 | 1.18 | 49.56 | 0 | 0 | 0 | 0 | 1.18 | 0 | 42 | 2358.82 | 99070.44 | 0 | 0 | 0 | 42 | 42 | 49.56 | 49.56
547 | GI Pipe 100 mm dia (Booster) | 0 | Tentative | Labour | (L)Fire Hydrent Systems_Installation Charge (GI Pipes) | RMT | 18 | 1.18 | 21.24 | 0 | 0 | 0 | 0 | 1.18 | 0 | 18 | 495.6 | 8920.8 | 0 | 0 | 0 | 18 | 18 | 21.24 | 21.24
548 | GI Pipe 100 mm dia (Booster) | 0 | Tentative | Labour | (L)Fire Hydrent Systems_Supply Charge (GI Pipes) | RMT | 18 | 1.18 | 21.24 | 0 | 0 | 0 | 0 | 1.18 | 0 | 18 | 1611.88 | 29013.84 | 0 | 0 | 0 | 18 | 18 | 21.24 | 21.24
549 | GI Pipe 80 mm dia (Tapping) | 0 | Tentative | Labour | (L)Fire Hydrent Systems_Installation Charge (GI Pipes) | RMT | 9 | 1.18 | 10.62 | 0 | 0 | 0 | 0 | 1.18 | 0 | 9 | 371.7 | 3345.3 | 0 | 0 | 0 | 9 | 9 | 10.62 | 10.62
550 | GI Pipe 80 mm dia (Tapping) | 0 | Tentative | Labour | (L)Fire Hydrent Systems_Supply Charge (GI Pipes) | RMT | 9 | 1.18 | 10.62 | 0 | 0 | 0 | 0 | 1.18 | 0 | 9 | 1131.62 | 10184.58 | 0 | 0 | 0 | 9 | 9 | 10.62 | 10.62
551 | TALK BACK PANEL -14 ZONE | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Installation Charge | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 5380.8 | 5380.8 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
552 | TALK BACK PANEL -14 ZONE | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Supply Charge | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 14160 | 14160 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
553 | TALK BACK UNIT | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Installation Charge | NOS | 13 | 1.18 | 15.34 | 0 | 0 | 0 | 0 | 1.18 | 0 | 13 | 283.2 | 3681.6 | 0 | 0 | 0 | 13 | 13 | 15.34 | 15.34
554 | TALK BACK UNIT | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Supply Charge | NOS | 13 | 1.18 | 15.34 | 0 | 0 | 0 | 0 | 1.18 | 0 | 13 | 637.2 | 8283.6 | 0 | 0 | 0 | 13 | 13 | 15.34 | 15.34
555 | 0.5Sq.mm X 5Core Copper Flexible Cable | 0 | Tentative | Labour | (L)Fire Hydrent Systems_Installation Charge (Cable) | RMT | 60 | 1.18 | 70.8 | 0 | 0 | 0 | 0 | 1.18 | 0 | 60 | 42.48 | 2548.8 | 0 | 0 | 0 | 60 | 60 | 70.8 | 70.8
556 | 0.5Sq.mm X 5Core Copper Flexible Cable | 0 | Tentative | Labour | (L)Fire Hydrent Systems_Supply Charge (Cable) | RMT | 60 | 1.18 | 70.8 | 0 | 0 | 0 | 0 | 1.18 | 0 | 60 | 56.64 | 3398.4 | 0 | 0 | 0 | 60 | 60 | 70.8 | 70.8
557 | Battery | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Installation Charge | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 283.2 | 283.2 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
558 | Battery | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Supply Charge | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 1228.8 | 1228.8 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
559 | FIRE EXTINGUISHER -10 Kg MODULER TYPE | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Installation Charge | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 413 | 413 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
560 | FIRE EXTINGUISHER -10 Kg MODULER TYPE | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Supply Charge | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 4248 | 4248 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
561 | FIRE EXTINGUISHER - 6 Kg ABC TYPE | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Installation Charge | NOS | 36 | 1.18 | 42.48 | 0 | 0 | 0 | 0 | 1.18 | 0 | 36 | 153.4 | 5522.4 | 0 | 0 | 0 | 36 | 36 | 42.48 | 42.48
562 | FIRE EXTINGUISHER - 6 Kg ABC TYPE | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Supply Charge | NOS | 36 | 1.18 | 42.48 | 0 | 0 | 0 | 0 | 1.18 | 0 | 36 | 1203.6 | 43329.6 | 0 | 0 | 0 | 36 | 36 | 42.48 | 42.48
563 | STRUCTURAL STEEL [100 X 50] | 0 | Started | Labour | (L)Fire Hydrent Systems_Installation Charge (Stru.Steel | RMT | 15 | 1.18 | 17.7 | 0 | 0 | 0 | 0 | 1.18 | 0 | 15 | 318.6 | 4779 | 0 | 0 | 0 | 15 | 15 | 17.7 | 17.7
564 | STRUCTURAL STEEL [100 X 50] | 0 | Started | Labour | (L)Fire Hydrent Systems_Supply Charge (Stru.Steel) | RMT | 15 | 1.18 | 17.7 | 0 | 0 | 0 | 0 | 1.18 | 0 | 15 | 1014.8 | 15222 | 12 | 1014.8 | 12177.6 | 15 | 3 | 17.7 | -12159.9
565 | A BLDG FOLDING DOORS & FRAME FIXING (M+L) 1ST TO 12TH FLOOR | 0 | Tentative | Labour | (L)FOLDING DOORS FRAME (M+L) | SQFT | 1566.688 | 123.45 | 193407.63 | 0 | 0 | 0 | 0 | 123.45 | 0 | 1566.688 | 123.45 | 193406.6219 | 0 | 0 | 0 | 1566.688 | 1566.688 | 193407.634 | 193407.6336
566 | A BLDG FOLDING DOORS & FRAME FIXING (M+L) 1ST TO 12TH FLOOR | 0 | Tentative | Labour | (L)FOLDING DOORS MISC.WORK | SQFT | 1566.688 | 7.67 | 12016.5 | 0 | 0 | 0 | 0 | 7.67 | 0 | 1566.688 | 7.41 | 11605.5373 | 0 | 0 | 0 | 1566.688 | 1566.688 | 12016.497 | 12016.497
567 | A BLDG FOLDING DOORS & FRAME FIXING (M+L) 1ST TO 12TH FLOOR | 0 | Tentative | Labour | (L)FOLDING DOORS SHUTTER (M+L) | SQFT | 1566.688 | 247.8 | 388225.29 | 0 | 0 | 0 | 0 | 247.8 | 0 | 1566.688 | 239.53 | 375265.5838 | 0 | 0 | 0 | 1566.688 | 1566.688 | 388225.286 | 388225.2864
568 | B WING FOOTING PCC M15 (CEMENT PPC) | 10 | Started | Material | (M)CEMENT PPC 50KG | BAG | 551 | 320 | 176320 | 0 | 0 | 0 | 55 | 320 | 17600 | 0 | 0 | 0 | 0 | 0 | 0 | 496 | 551 | 158720 | 176320 | Building
569 | B WING FOOTING PCC M15 (CEMENT PPC) | 10 | Started | Material | (M)Crush Sand | BRASS | 28.12 | 3675 | 103341 | 0 | 0 | 0 | 3 | 3675 | 11025 | 0 | 0 | 0 | 0 | 0 | 0 | 25.12 | 28.12 | 92316 | 103341 | Building
570 | B WING FOOTING PCC M15 (CEMENT PPC) | 10 | Started | Material | (M)Metal No.III 20MM | BRASS | 41.895 | 3045 | 127570.28 | 0 | 0 | 0 | 4 | 3045 | 12180 | 0 | 0 | 0 | 0 | 0 | 0 | 37.895 | 41.895 | 115390.275 | 127570.275 | Building
571 | B WING FOOTING PCC M15 (CEMENT OPC-43) | 10 | Started | Material | (M)CEMENT OPC 43 | BAG | 487.2 | 378.88 | 184590.34 | 0 | 0 | 0 | 49 | 378.88 | 18565.12 | 0 | 0 | 0 | 0 | 0 | 0 | 438.2 | 487.2 | 166025.216 | 184590.336 | Building
572 | B WING FOOTING PCC M15 (CEMENT OPC-43) | 10 | Started | Material | (M)Crush Sand | BRASS | 24.864 | 3675 | 91375.2 | 0 | 0 | 0 | 2 | 3675 | 7350 | 0 | 0 | 0 | 0 | 0 | 0 | 22.864 | 24.864 | 84025.2 | 91375.2 | Building
573 | B WING FOOTING PCC M15 (CEMENT OPC-43) | 10 | Started | Material | (M)Metal No.III 20MM | BRASS | 37.044 | 3045 | 112798.98 | 0 | 0 | 0 | 4 | 3045 | 12180 | 0 | 0 | 0 | 0 | 0 | 0 | 33.044 | 37.044 | 100618.98 | 112798.98 | Building
574 | B WING COL.CONCRETE (FOOTING TO 6TH SLAB)-M30 | 10 | Started | Material | (M)CEMENT OPC 43 | BAG | 3167.2 | 378.88 | 1199988.74 | 0 | 0 | 0 | 317 | 378.88 | 120104.96 | 0 | 0 | 0 | 0 | 0 | 0 | 2850.2 | 3167.2 | 1079883.776 | 1199988.736 | Building
575 | B WING COL.CONCRETE (FOOTING TO 6TH SLAB)-M30 | 10 | Started | Material | (M)Crush Sand | BRASS | 73.616 | 3675 | 270538.8 | 0 | 0 | 0 | 7 | 3675 | 25725 | 0 | 0 | 0 | 0 | 0 | 0 | 66.616 | 73.616 | 244813.8 | 270538.8 | Building
576 | B WING COL.CONCRETE (FOOTING TO 6TH SLAB)-M30 | 10 | Started | Material | (M)Metal No.III 20MM | BRASS | 110.424 | 3045 | 336241.08 | 0 | 0 | 0 | 11 | 3045 | 33495 | 0 | 0 | 0 | 0 | 0 | 0 | 99.424 | 110.424 | 302746.08 | 336241.08 | Building
577 | B WING COL.CONCRETE (6TH TO OHWT)-M25 | 10 | Started | Material | (M)CEMENT OPC 43 | BAG | 3484.8 | 378.88 | 1320321.02 | 0 | 0 | 0 | 348 | 378.88 | 131850.24 | 0 | 0 | 0 | 0 | 0 | 0 | 3136.8 | 3484.8 | 1188470.784 | 1320321.024 | Building
578 | B WING COL.CONCRETE (6TH TO OHWT)-M25 | 10 | Started | Material | (M)Crush Sand | BRASS | 135.52 | 3675 | 498036 | 0 | 0 | 0 | 14 | 3675 | 51450 | 0 | 0 | 0 | 0 | 0 | 0 | 121.52 | 135.52 | 446586 | 498036 | Building
579 | B WING COL.CONCRETE (6TH TO OHWT)-M25 | 10 | Started | Material | (M)Metal No.III 20MM | BRASS | 209.572 | 3045 | 638146.74 | 0 | 0 | 0 | 21 | 3045 | 63945 | 0 | 0 | 0 | 0 | 0 | 0 | 188.572 | 209.572 | 574201.74 | 638146.74 | Building
580 | B WING SLAB CONCRETE (1ST TO 13TH SLAB)-M25 | 10 | Started | Material | (M)CEMENT OPC 43 | BAG | 18532.8 | 378.88 | 7021707.26 | 0 | 0 | 0 | 1853 | 378.88 | 702064.64 | 0 | 0 | 0 | 0 | 0 | 0 | 16679.8 | 18532.8 | 6319642.624 | 7021707.264 | Building
581 | B WING SLAB CONCRETE (1ST TO 13TH SLAB)-M25 | 10 | Started | Material | (M)Crush Sand | BRASS | 720.72 | 3675 | 2648646 | 0 | 0 | 0 | 72 | 3675 | 264600 | 0 | 0 | 0 | 0 | 0 | 0 | 648.72 | 720.72 | 2384046 | 2648646 | Building
582 | B WING SLAB CONCRETE (1ST TO 13TH SLAB)-M25 | 10 | Started | Material | (M)Metal No.III 20MM | BRASS | 1114.542 | 3045 | 3393780.39 | 0 | 0 | 0 | 111 | 3045 | 337995 | 0 | 0 | 0 | 0 | 0 | 0 | 1003.542 | 1114.542 | 3055785.39 | 3393780.39 | Building
583 | B WING FOOTING CONCRETE RMC-M25 | 10 | Started | Material | (M)RMC M-25 | CUM | 596 | 4600 | 2741600 | 0 | 0 | 0 | 60 | 4600 | 276000 | 0 | 0 | 0 | 0 | 0 | 0 | 536 | 596 | 2465600 | 2741600 | Building
584 | B WING ALL REINFORCEMENT-8MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 8mm (Fe 500, 0.395 KGS/Rm) | KG | 179441 | 59 | 10587019 | 0 | 0 | 0 | 17944 | 59 | 1058696 | 0 | 0 | 0 | 0 | 0 | 0 | 161497 | 179441 | 9528323 | 10587019 | Building
585 | B WING ALL REINFORCEMENT-10MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 10mm (Fe 500, 0.617 KGS/Rm) | KG | 47541 | 59 | 2804919 | 0 | 0 | 0 | 4754 | 59 | 280486 | 0 | 0 | 0 | 0 | 0 | 0 | 42787 | 47541 | 2524433 | 2804919 | Building
586 | B WING ALL REINFORCEMENT-12MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 12mm (Fe 500, 0.888 KGS/Rm) | KG | 94557 | 59 | 5578863 | 0 | 0 | 0 | 9456 | 59 | 557904 | 0 | 0 | 0 | 0 | 0 | 0 | 85101 | 94557 | 5020959 | 5578863 | Building
587 | B WING ALL REINFORCEMENT-16MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 16mm (Fe 500, 1.58 KGS/Rm) | KG | 67369 | 59 | 3974771 | 0 | 0 | 0 | 6737 | 59 | 397483 | 0 | 0 | 0 | 0 | 0 | 0 | 60632 | 67369 | 3577288 | 3974771 | Building
588 | B WING ALL REINFORCEMENT-20MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 20mm (Fe 500, 2.47 KGS/Rm) | KG | 44770 | 59 | 2641430 | 0 | 0 | 0 | 4477 | 59 | 264143 | 0 | 0 | 0 | 0 | 0 | 0 | 40293 | 44770 | 2377287 | 2641430 | Building
589 | B WING ALL REINFORCEMENT-25MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 25mm (Fe 500, 3.85 KGS/Rm) | KG | 13360 | 59 | 788240 | 0 | 0 | 0 | 1336 | 59 | 78824 | 0 | 0 | 0 | 0 | 0 | 0 | 12024 | 13360 | 709416 | 788240 | Building
590 | B WING ALL REINFORCEMENT-32MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 32mm (Fe 500, 6.31 KGS/Rm) | KG | 3050 | 59 | 179950 | 0 | 0 | 0 | 305 | 59 | 17995 | 0 | 0 | 0 | 0 | 0 | 0 | 2745 | 3050 | 161955 | 179950 | Building
591 | B WING ALL REINFORCEMENT BINDING WIRE | 10 | Started | Material | (M)MS Binding Wire 18G | KG | 3542 | 50 | 177100 | 0 | 0 | 0 | 354 | 50 | 17700 | 0 | 0 | 0 | 0 | 0 | 0 | 3188 | 3542 | 159400 | 177100 | Building
592 | B WING STEEL TESTING-(LAB) INDENT-708 | 0 | Started | Labour | (L)10MM STEEL TESTING-LAB. | NOS | 45 | 531 | 23895 | 0 | 0 | 0 | 0 | 531 | 0 | 45 | 531 | 23895 | 3 | 531 | 1593 | 45 | 42 | 23895 | 22302 | Building
593 | B WING STEEL TESTING-(LAB) INDENT-708 | 0 | Started | Labour | (L)12MM STEEL TESTING-LAB. | NOS | 45 | 531 | 23895 | 0 | 0 | 0 | 0 | 531 | 0 | 45 | 531 | 23895 | 6 | 531 | 3186 | 45 | 39 | 23895 | 20709 | Building
594 | B WING STEEL TESTING-(LAB) INDENT-708 | 0 | Started | Labour | (L)16MM STEEL TESTING-LAB. | NOS | 45 | 649 | 29205 | 0 | 0 | 0 | 0 | 649 | 0 | 45 | 649 | 29205 | 6 | 649 | 3894 | 45 | 39 | 29205 | 25311 | Building
595 | B WING STEEL TESTING-(LAB) INDENT-708 | 0 | Started | Labour | (L)20MM STEEL TESTING-LAB. | NOS | 45 | 649 | 29205 | 0 | 0 | 0 | 0 | 649 | 0 | 45 | 649 | 29205 | 6 | 649 | 3894 | 45 | 39 | 29205 | 25311 | Building
596 | B WING STEEL TESTING-(LAB) INDENT-708 | 0 | Started | Labour | (L)25MM STEEL TESTING-LAB. | NOS | 45 | 649 | 29205 | 0 | 0 | 0 | 0 | 649 | 0 | 45 | 649 | 29205 | 3 | 649 | 1947 | 45 | 42 | 29205 | 27258 | Building
597 | B WING STEEL TESTING-(LAB) INDENT-708 | 0 | Started | Labour | (L)8MM STEEL TESTING-LAB. | NOS | 45 | 531 | 23895 | 0 | 0 | 0 | 0 | 531 | 0 | 45 | 531 | 23895 | 6 | 531 | 3186 | 45 | 39 | 23895 | 20709 | Building
598 | B WING-BLOCK WORK-ALL FLOOR BLOCK WORK 125MM | 10 | Started | Material | (M)AAC Block 625 x 200 x 125mm | NOS | 93568 | 0 | 0 | 0 | 0 | 0 | 9357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 84211 | 93568 | 0 | 0 | Building
599 | B WING-BLOCK WORK-ALL FLOOR BLOCK WORK 125MM | 10 | Started | Material | (M)BLOCK ADHESIEVE | 40 KG/BAG | 1286.56 | 400 | 514624 | 0 | 0 | 0 | 129 | 400 | 51600 | 0 | 0 | 0 | 0 | 0 | 0 | 1157.56 | 1286.56 | 463024 | 514624 | Building
600 | B WING-BLOCK WORK-ALL FLOOR BLOCK WORK 230MM | 10 | Started | Material | (M)AAC Block 625 x 200 x 230mm | NOS | 3756.5208 | 0 | 0 | 0 | 0 | 0 | 376 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3380.5208 | 3756.5208 | 0 | 0 | Building
601 | B WING-BLOCK WORK-ALL FLOOR BLOCK WORK 230MM | 10 | Started | Material | (M)BLOCK ADHESIEVE | 40 KG/BAG | 102.6 | 400 | 41040 | 0 | 0 | 0 | 10 | 400 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 92.6 | 102.6 | 37040 | 41040 | Building
602 | DPC & PATALI M15-ALL FLOOR | 10 | Started | Material | (M)CEMENT PPC 50KG | BAG | 1123.2 | 320 | 359424 | 0 | 0 | 0 | 112 | 320 | 35840 | 0 | 0 | 0 | 2 | 304.61 | 609.22 | 1011.2 | 1121.2 | 323584 | 358814.78 | Building
603 | DPC & PATALI M15-ALL FLOOR | 10 | Started | Material | (M)Crush Sand | BRASS | 41.1632 | 3675 | 151274.76 | 0 | 0 | 0 | 4 | 3675 | 14700 | 0 | 0 | 0 | 0 | 0 | 0 | 37.1632 | 41.1632 | 136574.76 | 151274.76 | Building
604 | DPC & PATALI M15-ALL FLOOR | 10 | Started | Material | (M)Metal No.III 20MM | BRASS | 52.1664 | 3045 | 158846.69 | 0 | 0 | 0 | 5 | 3045 | 15225 | 0 | 0 | 0 | 0 | 0 | 0 | 47.1664 | 52.1664 | 143621.688 | 158846.688 | Building
605 | B WING ALL FLOOR BACK COAT INTERNAL PLASTER | 10 | Started | Material | (M)Artificial Sand | BRASS | 55.8012 | 5880 | 328111.06 | 0 | 0 | 0 | 6 | 5880 | 35280 | 0 | 0 | 0 | 0 | 0 | 0 | 49.8012 | 55.8012 | 292831.056 | 328111.056 | Building
606 | B WING ALL FLOOR BACK COAT INTERNAL PLASTER | 10 | Started | Material | (M)CEMENT PPC 50KG | BAG | 1195.74 | 320 | 382636.8 | 0 | 0 | 0 | 120 | 320 | 38400 | 0 | 0 | 0 | 0 | 0 | 0 | 1075.74 | 1195.74 | 344236.8 | 382636.8 | Building
607 | B WING ALL FLOOR BACK COAT INTERNAL PLASTER | 10 | Started | Material | (M)Perma Plasto-O-Proof | BUCKET | 47.8296 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42.8296 | 47.8296 | 0 | 0 | Building
608 | B WING ALL FLOOR SANLA INTERNAL PLASTER | 10 | Started | Material | (M)Artificial Sand | BRASS | 51.0573 | 5880 | 300216.92 | 0 | 0 | 0 | 5 | 5880 | 29400 | 0 | 0 | 0 | 0 | 0 | 0 | 46.0573 | 51.0573 | 270816.924 | 300216.924 | Building
609 | B WING ALL FLOOR SANLA INTERNAL PLASTER | 10 | Started | Material | (M)CEMENT PPC 50KG | BAG | 1094.085 | 320 | 350107.2 | 0 | 0 | 0 | 109 | 320 | 34880 | 0 | 0 | 0 | 0 | 0 | 0 | 985.085 | 1094.085 | 315227.2 | 350107.2 | Building
610 | B WING ALL FLOOR SANLA INTERNAL PLASTER | 10 | Started | Material | (M)Perma Plasto-O-Proof | BUCKET | 43.7634 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39.7634 | 43.7634 | 0 | 0 | Building
611 | B WING ALL FLOOR SANLA INTERNAL PLASTER | 10 | Started | Material | (M)SANLA-BADAM CHHAP | 12-15 KG/BAG | 1218.0813 | 120 | 146169.76 | 0 | 0 | 0 | 122 | 120 | 14640 | 0 | 0 | 0 | 0 | 0 | 0 | 1096.0813 | 1218.0813 | 131529.756 | 146169.756 | Building
612 | B WING ALL FLOOR SINGLE COAT INTERNAL- EXTERNAL PLASTER | 10 | Started | Material | (M)Artificial Sand | BRASS | 109.9791 | 5880 | 646677.11 | 0 | 0 | 0 | 11 | 5880 | 64680 | 0 | 0 | 0 | 0 | 0 | 0 | 98.9791 | 109.9791 | 581997.108 | 646677.108 | Building
613 | B WING ALL FLOOR SINGLE COAT INTERNAL- EXTERNAL PLASTER | 10 | Started | Material | (M)CEMENT PPC 50KG | BAG | 2249.5725 | 320 | 719863.2 | 0 | 0 | 0 | 225 | 320 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 2024.5725 | 2249.5725 | 647863.2 | 719863.2 | Building
614 | B WING ALL FLOOR SINGLE COAT INTERNAL- EXTERNAL PLASTER | 10 | Started | Material | (M)Perma Plasto-O-Proof | BUCKET | 89.9829 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80.9829 | 89.9829 | 0 | 0 | Building
615 | B WING ALL FLOOR DOUBLE COAT EXTERNAP PLASTER | 10 | Started | Material | (M)Artificial Sand | BRASS | 148.447 | 5880 | 872868.36 | 0 | 0 | 0 | 15 | 5880 | 88200 | 0 | 0 | 0 | 0 | 0 | 0 | 133.447 | 148.447 | 784668.36 | 872868.36 | Building
616 | B WING ALL FLOOR DOUBLE COAT EXTERNAP PLASTER | 10 | Started | Material | (M)CEMENT PPC 50KG | BAG | 3140.225 | 320 | 1004872 | 0 | 0 | 0 | 314 | 320 | 100480 | 0 | 0 | 0 | 0 | 0 | 0 | 2826.225 | 3140.225 | 904392 | 1004872 | Building
617 | B WING ALL FLOOR DOUBLE COAT EXTERNAP PLASTER | 10 | Started | Material | (M)Perma Plasto-O-Proof | BUCKET | 125.609 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112.609 | 125.609 | 0 | 0 | Building
618 | MISCELLANEOUS WORK GODOWN FABRICATION WORK | 0 | Started | Labour | (L)G.I. Sheet Fixing | SQFT | 914 | 0 | 0 | 914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 914 | 914 | 0 | 0
619 | MISCELLANEOUS WORK INDENT-893/B WING/SKIRTING CHE.COATING | 10 | Started | Material | (M)PERMA BOND SBR 25 LTR BUCKET | BUCKET | 5 | 4491.75 | 22458.75 | 5 | 4491.75 | 22458.75 | 1 | 4491.75 | 4491.75 | 5 | 5365.53 | 26827.63 | 0 | 0 | 0 | 4 | 5 | 17967 | 22458.75
620 | MISCELLANEOUS WORK INDENT-893/B WING/SKIRTING CHE.COATING | 10 | Started | Material | (M)PERMA DPS 25 LTR BUCKET | BUCKET | 3 | 7139 | 21417 | 3 | 7139 | 21417 | 0 | 7139 | 0 | 3 | 7226.9 | 21680.7 | 0 | 0 | 0 | 3 | 3 | 21417 | 21417
621 | FABRICATION WORK B WING WINDOW GRILL (WITH MATERIAL) | 0 | Started | Labour | (L)Fixing of Railing & Grills | SQFT | 675.94 | 0 | 0 | 675.94 | 0 | 0 | 0 | 0 | 0 | 675.94 | 100 | 67594 | 675.94 | 100 | 67594 | 675.94 | 0 | 0 | -67594
622 | B BLDG: MAIN ST-CASE RAILING | 0 | Started | Labour | (L)Main Staircase Railing(M+L) | RFT | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 112 | 240 | 26880 | 0 | 0 | 0 | 112 | 112 | 0 | 0
623 | B BLDG: FIRE ST-CASE RAILING | 0 | Started | Labour | (L)Fire Staircase Railing(M+L) | RFT | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 240 | 26400 | 0 | 0 | 0 | 110 | 110 | 0 | 0
624 | B BLDG: OHWT RAILING-ABV.FIRE ST CASE | 0 | Started | Labour | (L)OHWT MS Railing (Mat. + Lab.) | SQFT | 284.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 284.06 | 115 | 32666.9 | 0 | 0 | 0 | 284.06 | 284.06 | 0 | 0
625 | B BLDG: OHWT RAILING-ABV.MAIN ST CASE | 0 | Started | Labour | (L)OHWT MS Railing (Mat. + Lab.) | SQFT | 317.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 317.63 | 115 | 36527.45 | 0 | 0 | 0 | 317.63 | 317.63 | 0 | 0
626 | B BLDG: OHWT LADDER-ABV. FIRE ST CASE | 0 | Started | Labour | (L)MS Ladder For OHWT Labour + Material | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 11500 | 11500 | 0 | 0 | 0 | 1 | 1 | 0 | 0
627 | B BLDG: OHWT LADDER-ABV. MAIN ST CASE | 0 | Started | Labour | (L)MS Ladder For OHWT Labour + Material | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 9000 | 9000 | 1 | 9000 | 9000 | 1 | 0 | 0 | -9000
628 | B WING STAND OUT-DOWNTAKE & OUTLET (INDENT-946) | 10 | Started | Material | (M)Plumbing Nails 2" | KG | 1 | 87 | 87 | 0 | 0 | 0 | 0 | 87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 87 | 87
629 | B WING STAND OUT-DOWNTAKE & OUTLET-(INDENT-946) REVISED | 10 | Started | Material | (M)Plumbing Nails 2" | KG | 10 | 87 | 870 | 10 | 87 | 870 | 1 | 87 | 87 | 10 | 102.66 | 1026.6 | 0 | 0 | 0 | 9 | 10 | 783 | 870
630 | B WING STAND OUT-DOWNTAKE & OUTLET-(INDENT-946) REVISED | 10 | Started | Material | (M)PVC Elbow 50 mm | NOS | 55 | 38.77 | 2132.35 | 55 | 38.77 | 2132.35 | 6 | 38.77 | 232.62 | 55 | 21.77 | 1197.5425 | 0 | 0 | 0 | 49 | 55 | 1899.73 | 2132.35
631 | B WING STAND OUT-DOWNTAKE & OUTLET-(INDENT-946) REVISED | 10 | Started | Material | (M)PVC Reducer Bush 50 x 75 mm | NOS | 15 | 32.05 | 480.75 | 15 | 32.05 | 480.75 | 2 | 32.05 | 64.1 | 15 | 21.18 | 317.6805 | 0 | 0 | 0 | 13 | 15 | 416.65 | 480.75
632 | B WING STAND OUT-DOWNTAKE & OUTLET-(INDENT-946) REVISED | 10 | Started | Material | (M)PVC Shoe 50 mm | NOS | 20 | 48.62 | 972.4 | 20 | 48.62 | 972.4 | 2 | 48.62 | 97.24 | 20 | 27.23 | 544.5 | 0 | 0 | 0 | 18 | 20 | 875.16 | 972.4
633 | B WING STAND OUT-DOWNTAKE & OUTLET-(INDENT-946) REVISED | 10 | Started | Material | (M)Pvc Solution 473ml | NOS | 2 | 206.5 | 413 | 2 | 206.5 | 413 | 0 | 206.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 413 | 413
634 | B WING STAND OUT-DOWNTAKE & OUTLET-(INDENT-946) REVISED | 10 | Started | Material | (M)SWR Multi Floor Trap 4" Height 110 mm | NOS | 40 | 105.17 | 4206.8 | 40 | 105.17 | 4206.8 | 4 | 105.17 | 420.68 | 40 | 103.75 | 4149.82 | 0 | 0 | 0 | 36 | 40 | 3786.12 | 4206.8
635 | B WING STAND OUT-DOWNTAKE & OUTLET-(INDENT-946) REVISED | 10 | Started | Material | (M)SWR Pipe Clip 75 mm | NOS | 170 | 6.1 | 1037 | 170 | 6.1 | 1037 | 17 | 6.1 | 103.7 | 170 | 5.9 | 1003 | 0 | 0 | 0 | 153 | 170 | 933.3 | 1037
636 | B WING STAND OUT-DOWNTAKE & OUTLET-(INDENT-946) REVISED | 10 | Started | Material | (M)SWR Pipes 'B' type R/F 10ft long S/S 75mm | NOS | 70 | 417.93 | 29255.1 | 70 | 417.93 | 29255.1 | 7 | 417.93 | 2925.51 | 70 | 413 | 28910 | 0 | 0 | 0 | 63 | 70 | 26329.59 | 29255.1
637 | B WING STAND OUT-DOWNTAKE & OUTLET-(INDENT-946) REVISED | 10 | Started | Material | (M)SWR Plain Bend 75 mm | NOS | 50 | 75.52 | 3776 | 50 | 75.52 | 3776 | 5 | 75.52 | 377.6 | 50 | 42.29 | 2114.56 | 0 | 0 | 0 | 45 | 50 | 3398.4 | 3776
638 | B WING STAND OUT-DOWNTAKE & OUTLET-(INDENT-946) REVISED | 10 | Started | Material | (M)SWR Plain Tee 75 mm | NOS | 40 | 59.03 | 2361.2 | 40 | 59.03 | 2361.2 | 4 | 59.03 | 236.12 | 40 | 58.15 | 2326.02 | 0 | 0 | 0 | 36 | 40 | 2125.08 | 2361.2
639 | B WING STAND OUT-DOWNTAKE & OUTLET-(INDENT-946) REVISED | 10 | Started | Material | (M)SWR Single Y 75 mm | NOS | 15 | 135.7 | 2035.5 | 15 | 135.7 | 2035.5 | 2 | 135.7 | 271.4 | 15 | 75.99 | 1139.88 | 0 | 0 | 0 | 13 | 15 | 1764.1 | 2035.5
640 | INDENT-71/B WING/PLUM.SERVICES | 0 | Started | Material | (M)RCC Chamber Cover with Frame 300mm X 300mm MD | SET | 35 | 354 | 12390 | 35 | 354 | 12390 | 0 | 354 | 0 | 35 | 1151.37 | 40298.0585 | 0 | 0 | 0 | 35 | 35 | 12390 | 12390 | Building
641 | INDENT-71/B WING/PLUM.SERVICES | 0 | Started | Material | (M)RCC Chamber Cover with Frame 300mm X 450mm MD | SET | 12 | 649 | 7788 | 12 | 649 | 7788 | 0 | 649 | 0 | 12 | 629.66 | 7555.92 | 0 | 0 | 0 | 12 | 12 | 7788 | 7788 | Building
642 | INDENT-71/B WING/PLUM.SERVICES | 0 | Started | Material | (M)RCC Chamber Cover with Frame 600mm X 600mm HD (Drain Hole) | SET | 28 | 1475 | 41300 | 28 | 1475 | 41300 | 0 | 1475 | 0 | 28 | 2879.26 | 80619.2604 | 0 | 0 | 0 | 28 | 28 | 41300 | 41300 | Building
643 | INDENT-71/B WING/PLUM.SERVICES | 0 | Started | Material | (M)RCC Chamber Cover with Frame 900mm X 450mm MD | SET | 13 | 1770 | 23010 | 13 | 1770 | 23010 | 0 | 1770 | 0 | 13 | 1673.1 | 21750.2805 | 0 | 0 | 0 | 13 | 13 | 23010 | 23010 | Building
644 | INDENT-71/B WING/PLUM.SERVICES | 0 | Started | Material | (M)RCC Chamber Cover with Frame 900mm X 600mm HD (Drain Hole) | SET | 14 | 1829 | 25606 | 14 | 1829 | 25606 | 0 | 1829 | 0 | 14 | 3359.27 | 47029.7996 | 0 | 0 | 0 | 14 | 14 | 25606 | 25606 | Building
645 | INDENT-71/B WING/PLUM.SERVICES | 0 | Started | Material | (M)RCC PIPE 150mm NP-2 with pre-socketed collar | NOS | 40 | 649 | 25960 | 40 | 649 | 25960 | 0 | 649 | 0 | 40 | 531 | 21240 | 0 | 0 | 0 | 40 | 40 | 25960 | 25960 | Building
646 | INDENT-71/B WING/PLUM.SERVICES | 0 | Started | Material | (M)RCC PIPE 200mm NP-2 with pre-socketed collar | NOS | 32 | 885 | 28320 | 32 | 885 | 28320 | 0 | 885 | 0 | 32 | 649 | 20768 | 0 | 0 | 0 | 32 | 32 | 28320 | 28320 | Building
647 | INDENT-71/B WING/PLUM.SERVICES | 0 | Started | Material | (M)RCC PIPE 250mm NP-2 with pre-socketed collar | NOS | 28 | 1121 | 31388 | 28 | 1121 | 31388 | 0 | 1121 | 0 | 28 | 767 | 21476 | 0 | 0 | 0 | 28 | 28 | 31388 | 31388 | Building
648 | INDENT-71/B WING/PLUM.SERVICES | 0 | Started | Material | (M)RCC PIPE 300mm NP-2 with pre-socketed collar | NOS | 22 | 1357 | 29854 | 22 | 1357 | 29854 | 0 | 1357 | 0 | 22 | 908.6 | 19989.2 | 0 | 0 | 0 | 22 | 22 | 29854 | 29854 | Building
649 | INDENT-71/B WING/PLUM.SERVICES | 0 | Started | Material | (M)RCC Round Cover with Frame 24" HD | SET | 6 | 1416 | 8496 | 6 | 1416 | 8496 | 0 | 1416 | 0 | 6 | 2143.29 | 12859.7598 | 0 | 0 | 0 | 6 | 6 | 8496 | 8496 | Building
650 | INDENT-70/B BLDG/PARKING LOOPING PLUMBING WORK | 0 | Started | Material | (M)GI U Clamp with Nut Bolt & Washer 3" | NOS | 100 | 17.7 | 1770 | 100 | 17.7 | 1770 | 0 | 17.7 | 0 | 100 | 17.7 | 1770 | 0 | 0 | 0 | 100 | 100 | 1770 | 1770
651 | INDENT-70/B BLDG/PARKING LOOPING PLUMBING WORK | 0 | Started | Material | (M)GI U Clamp with Nut Bolt & Washer 4" | NOS | 50 | 19.12 | 956 | 50 | 19.12 | 956 | 0 | 19.12 | 0 | 50 | 21.24 | 1062 | 0 | 0 | 0 | 50 | 50 | 956 | 956
652 | INDENT-70/B BLDG/PARKING LOOPING PLUMBING WORK | 0 | Started | Material | (M)SWR Pipes 'B' type R/F 10ft long S/S 75mm | NOS | 50 | 417.93 | 20896.5 | 50 | 417.93 | 20896.5 | 0 | 417.93 | 0 | 50 | 485.02 | 24250.78 | 0 | 0 | 0 | 50 | 50 | 20896.5 | 20896.5
653 | INDENT-70/B BLDG/PARKING LOOPING PLUMBING WORK | 0 | Started | Material | (M)SWR Plain Bend 110 mm | NOS | 20 | 159.3 | 3186 | 20 | 159.3 | 3186 | 0 | 159.3 | 0 | 20 | 83.95 | 1678.9 | 0 | 0 | 0 | 20 | 20 | 3186 | 3186
654 | INDENT-70/B BLDG/PARKING LOOPING PLUMBING WORK | 0 | Started | Material | (M)SWR Plain Bend 75 mm | NOS | 60 | 75.52 | 4531.2 | 60 | 75.52 | 4531.2 | 0 | 75.52 | 0 | 60 | 47.97 | 2878.02 | 0 | 0 | 0 | 60 | 60 | 4531.2 | 4531.2
655 | INDENT-70/B BLDG/PARKING LOOPING PLUMBING WORK | 0 | Started | Material | (M)SWR Plug Bend 110 mm | NOS | 15 | 177 | 2655 | 15 | 177 | 2655 | 0 | 177 | 0 | 15 | 103.26 | 1548.93 | 0 | 0 | 0 | 15 | 15 | 2655 | 2655
656 | INDENT-70/B BLDG/PARKING LOOPING PLUMBING WORK | 0 | Started | Material | (M)SWR Plug Bend 75 mm | NOS | 50 | 80.24 | 4012 | 50 | 80.24 | 4012 | 0 | 80.24 | 0 | 50 | 59.3 | 2964.76 | 0 | 0 | 0 | 50 | 50 | 4012 | 4012
657 | INDENT-70/B BLDG/PARKING LOOPING PLUMBING WORK | 0 | Started | Material | (M)SWR Shoe 75 mm | NOS | 50 | 70.8 | 3540 | 50 | 70.8 | 3540 | 0 | 70.8 | 0 | 50 | 43.97 | 2198.34 | 0 | 0 | 0 | 50 | 50 | 3540 | 3540
658 | INDENT-70/B BLDG/PARKING LOOPING PLUMBING WORK | 0 | Started | Material | (M)SWR Single Y 110 mm | NOS | 10 | 177 | 1770 | 10 | 177 | 1770 | 0 | 177 | 0 | 10 | 163.89 | 1638.9 | 0 | 0 | 0 | 10 | 10 | 1770 | 1770
659 | INDENT-70/B BLDG/PARKING LOOPING PLUMBING WORK | 0 | Started | Material | (M)SWR Single Y 75 mm | NOS | 35 | 135.7 | 4749.5 | 35 | 135.7 | 4749.5 | 0 | 135.7 | 0 | 35 | 87.95 | 3078.089 | 0 | 0 | 0 | 35 | 35 | 4749.5 | 4749.5
660 | B WING ELEC.&STORM WATER SERVICES LINE CHAMBER WORK | 0 | Tentative | Material | (M)Artificial Sand | BRASS | 1 | 5880 | 5880 | 1 | 5880 | 5880 | 0 | 5880 | 0 | 1 | 6300 | 6300 | 0 | 0 | 0 | 1 | 1 | 5880 | 5880
661 | B WING ELEC.&STORM WATER SERVICES LINE CHAMBER WORK | 0 | Tentative | Material | (M)CEMENT PPC 50KG | BAG | 157 | 320 | 50240 | 157 | 320 | 50240 | 0 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157 | 157 | 50240 | 50240
662 | B WING ELEC.&STORM WATER SERVICES LINE CHAMBER WORK | 0 | Tentative | Material | (M)Crush Sand | BRASS | 9 | 3675 | 33075 | 9 | 3675 | 33075 | 0 | 3675 | 0 | 9 | 3675 | 33075 | 0 | 0 | 0 | 9 | 9 | 33075 | 33075
663 | B WING ELEC.&STORM WATER SERVICES LINE CHAMBER WORK | 0 | Tentative | Material | (M)Flyash Bricks 6" | NOS | 15970 | 8.96 | 143091.2 | 15970 | 8.96 | 143091.2 | 0 | 8.96 | 0 | 15970 | 9.24 | 147562.8 | 0 | 0 | 0 | 15970 | 15970 | 143091.2 | 143091.2
664 | B WING ELEC.&STORM WATER SERVICES LINE CHAMBER WORK | 0 | Tentative | Material | (M)Metal No.III 20MM | BRASS | 4 | 3045 | 12180 | 4 | 3045 | 12180 | 0 | 3045 | 0 | 4 | 3360 | 13440 | 0 | 0 | 0 | 4 | 4 | 12180 | 12180
665 | B BLDG LOBBY DOWNTAKE PVC-MATERIAL | 0 | Tentative | Material | (M)GI C-Bracket 6" x 2" | NOS | 40 | 43.81 | 1752.4 | 40 | 43.81 | 1752.4 | 0 | 43.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 1752.4 | 1752.4
666 | B BLDG LOBBY DOWNTAKE PVC-MATERIAL | 0 | Tentative | Material | (M)GI C-Bracket 6" x 3" | NOS | 100 | 44.2 | 4420 | 100 | 44.2 | 4420 | 0 | 44.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 4420 | 4420
667 | B BLDG LOBBY DOWNTAKE PVC-MATERIAL | 0 | Tentative | Material | (M)GI U Clamp with Nut Bolt & Washer 2" | NOS | 100 | 13.93 | 1393 | 100 | 13.93 | 1393 | 0 | 13.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 1393 | 1393
668 | B BLDG LOBBY DOWNTAKE PVC-MATERIAL | 0 | Tentative | Material | (M)GI U Clamp with Nut Bolt & Washer 3" | NOS | 80 | 17.7 | 1416 | 80 | 17.7 | 1416 | 0 | 17.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 80 | 1416 | 1416
669 | B BLDG LOBBY DOWNTAKE PVC-MATERIAL | 0 | Tentative | Material | (M)Plumbing Nails 1 1/2" | KG | 10 | 50 | 500 | 10 | 50 | 500 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 500 | 500
670 | B BLDG LOBBY DOWNTAKE PVC-MATERIAL | 0 | Tentative | Material | (M)PVC Elbow 50 mm | NOS | 100 | 38.77 | 3877 | 100 | 38.77 | 3877 | 0 | 38.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 3877 | 3877
671 | B BLDG LOBBY DOWNTAKE PVC-MATERIAL | 0 | Tentative | Material | (M)PVC Gray Pipes S/F 10ft long 50 mm (4Kg/Sqcm) | NOS | 45 | 306.8 | 13806 | 45 | 306.8 | 13806 | 0 | 306.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 13806 | 13806
672 | B BLDG LOBBY DOWNTAKE PVC-MATERIAL | 0 | Tentative | Material | (M)PVC Reducer Bush 50 x 75 mm | NOS | 40 | 32.05 | 1282 | 40 | 32.05 | 1282 | 0 | 32.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 1282 | 1282
673 | B BLDG LOBBY DOWNTAKE PVC-MATERIAL | 0 | Tentative | Material | (M)PVC SHOE BEND 50MM | NOS | 40 | 50 | 2000 | 40 | 50 | 2000 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 2000 | 2000
674 | B BLDG LOBBY DOWNTAKE PVC-MATERIAL | 0 | Tentative | Material | (M)RCC Round Cover with Frame 24" HD | SET | 3 | 1416 | 4248 | 3 | 1416 | 4248 | 0 | 1416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 4248 | 4248
675 | B BLDG LOBBY DOWNTAKE PVC-MATERIAL | 0 | Tentative | Material | (M)SWR Pipes 'B' type R/F 10ft long S/S 75mm | NOS | 40 | 417.93 | 16717.2 | 40 | 417.93 | 16717.2 | 0 | 417.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 16717.2 | 16717.2
676 | B BLDG LOBBY DOWNTAKE PVC-MATERIAL | 0 | Tentative | Material | (M)SWR Single Y 75 mm | NOS | 40 | 135.7 | 5428 | 40 | 135.7 | 5428 | 0 | 135.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 5428 | 5428
677 | B BLDG RAIN WATER LINE-PLUMBING WORK | 0 | Tentative | Material | (M)10MM NUT BOLT & WASHER | NOS | 100 | 5.9 | 590 | 100 | 5.9 | 590 | 0 | 5.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 590 | 590
678 | B BLDG RAIN WATER LINE-PLUMBING WORK | 0 | Tentative | Material | (M)10MM THREAD ROD FOR FASTNER-2MTR | NOS | 30 | 153.4 | 4602 | 30 | 153.4 | 4602 | 0 | 153.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 4602 | 4602
679 | B BLDG RAIN WATER LINE-PLUMBING WORK | 0 | Tentative | Material | (M)Bullet Fastner - 10mm | NOS | 50 | 19.53 | 976.5 | 50 | 19.53 | 976.5 | 0 | 19.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 976.5 | 976.5
680 | B BLDG RAIN WATER LINE-PLUMBING WORK | 0 | Tentative | Material | (M)GI Clip 4" | NOS | 25 | 5.9 | 147.5 | 25 | 5.9 | 147.5 | 0 | 5.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 25 | 147.5 | 147.5
681 | B BLDG RAIN WATER LINE-PLUMBING WORK | 0 | Tentative | Material | (M)Hanging Clamp-4'' | NOS | 60 | 35.4 | 2124 | 60 | 35.4 | 2124 | 0 | 35.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 60 | 2124 | 2124
682 | B BLDG RAIN WATER LINE-PLUMBING WORK | 0 | Tentative | Material | (M)SWR Pipe Coupler 160 mm | NOS | 4 | 237.18 | 948.72 | 4 | 237.18 | 948.72 | 0 | 237.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 948.72 | 948.72
683 | B BLDG RAIN WATER LINE-PLUMBING WORK | 0 | Tentative | Material | (M)SWR Pipes 'B' type R/F 10ft long S/S 110mm | NOS | 66 | 885 | 58410 | 66 | 885 | 58410 | 0 | 885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66 | 66 | 58410 | 58410
684 | B BLDG RAIN WATER LINE-PLUMBING WORK | 0 | Tentative | Material | (M)SWR Pipes 'B' type R/F 10ft long S/S 160mm | NOS | 30 | 1180 | 35400 | 30 | 1180 | 35400 | 0 | 1180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 35400 | 35400
685 | B BLDG RAIN WATER LINE-PLUMBING WORK | 0 | Tentative | Material | (M)SWR Pipes 'B' type R/F 10ft long S/S 75mm | NOS | 25 | 417.93 | 10448.25 | 25 | 417.93 | 10448.25 | 0 | 417.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 25 | 10448.25 | 10448.25
686 | B BLDG RAIN WATER LINE-PLUMBING WORK | 0 | Tentative | Material | (M)SWR Plain Bend 160 mm | NOS | 8 | 177 | 1416 | 8 | 177 | 1416 | 0 | 177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 1416 | 1416
687 | B BLDG RAIN WATER LINE-PLUMBING WORK | 0 | Tentative | Material | (M)SWR Plain Tee 160 mm | NOS | 2 | 236 | 472 | 2 | 236 | 472 | 0 | 236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 472 | 472
688 | B BLDG RAIN WATER LINE-PLUMBING WORK | 0 | Tentative | Material | (M)SWR Plain Tee 160 x 110 mm | NOS | 4 | 224.2 | 896.8 | 4 | 224.2 | 896.8 | 0 | 224.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 896.8 | 896.8
689 | B BLDG RAIN WATER LINE-PLUMBING WORK | 0 | Tentative | Material | (M)SWR Reducer 110 x 75 mm | NOS | 22 | 59 | 1298 | 22 | 59 | 1298 | 0 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 22 | 1298 | 1298
690 | B BLDG RAIN WATER LINE-PLUMBING WORK | 0 | Tentative | Material | (M)SWR Reducer 160 x 110 mm | NOS | 2 | 118 | 236 | 2 | 118 | 236 | 0 | 118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 236 | 236
691 | B BLDG RAIN WATER LINE-PLUMBING WORK | 0 | Tentative | Material | (M)SWR Shoe 75 mm | NOS | 40 | 70.8 | 2832 | 40 | 70.8 | 2832 | 0 | 70.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 2832 | 2832
692 | B WING EAST SIDE ROAD GUTTER CROSSING TO STORM WATER | 0 | Tentative | Material | (M)PVC Agri Pipes S/F 10ft long (6KGS/Class 3) 110 mm - 4" | NOS | 5 | 885 | 4425 | 5 | 885 | 4425 | 0 | 885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 4425 | 4425
693 | B WING EAST SIDE ROAD GUTTER CROSSING TO STORM WATER | 0 | Tentative | Material | (M)PVC Agri Pipes S/F 10ft long (6KGS/Class 3) 160 mm - 6" | NOS | 20 | 1298 | 25960 | 20 | 1298 | 25960 | 0 | 1298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 25960 | 25960
694 | INDENT-941/B WING/RISING MAIN LINE | 10 | Started | Material | (M)Brass Ball Valve 1 1/2" | NOS | 1 | 2207 | 2207 | 1 | 2207 | 2207 | 0 | 2207 | 0 | 1 | 1268.5 | 1268.5 | 0 | 0 | 0 | 1 | 1 | 2207 | 2207
695 | INDENT-941/B WING/RISING MAIN LINE | 10 | Started | Material | (M)Brass Ball Valve 2 1/2" | NOS | 1 | 5743.66 | 5743.66 | 1 | 5743.66 | 5743.66 | 0 | 5743.66 | 0 | 1 | 6488.82 | 6488.82 | 0 | 0 | 0 | 1 | 1 | 5743.66 | 5743.66
696 | INDENT-941/B WING/RISING MAIN LINE | 10 | Started | Material | (M)Brass Foot Valve 2 1/2" | NOS | 1 | 8850 | 8850 | 1 | 8850 | 8850 | 0 | 8850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 8850 | 8850
697 | INDENT-941/B WING/RISING MAIN LINE | 10 | Started | Material | (M)Brass Foot Valve 2" | NOS | 1 | 3470.86 | 3470.86 | 1 | 3470.86 | 3470.86 | 0 | 3470.86 | 0 | 1 | 3470.86 | 3470.86 | 0 | 0 | 0 | 1 | 1 | 3470.86 | 3470.86
698 | INDENT-941/B WING/RISING MAIN LINE | 10 | Started | Material | (M)Brass NRV 1 1/2" | NOS | 1 | 1841 | 1841 | 1 | 1841 | 1841 | 0 | 1841 | 0 | 1 | 1194.81 | 1194.81 | 0 | 0 | 0 | 1 | 1 | 1841 | 1841
699 | INDENT-941/B WING/RISING MAIN LINE | 10 | Started | Material | (M)Brass NRV 1 1/4'' | NOS | 1 | 1482 | 1482 | 1 | 1482 | 1482 | 0 | 1482 | 0 | 1 | 961.82 | 961.82 | 0 | 0 | 0 | 1 | 1 | 1482 | 1482
700 | INDENT-941/B WING/RISING MAIN LINE | 10 | Started | Material | (M)Brass NRV 2 1/2" | NOS | 1 | 5354 | 5354 | 1 | 5354 | 5354 | 0 | 5354 | 0 | 1 | 4422.4 | 4422.4 | 0 | 0 | 0 | 1 | 1 | 5354 | 5354
701 | INDENT-941/B WING/RISING MAIN LINE | 10 | Started | Material | (M)GI U Clamp with Nut Bolt & Washer 1 1/2" | NOS | 50 | 13.5 | 675 | 50 | 13.5 | 675 | 5 | 13.5 | 67.5 | 50 | 11.95 | 597.37 | 0 | 0 | 0 | 45 | 50 | 607.5 | 675
702 | INDENT-941/B WING/RISING MAIN LINE | 10 | Started | Material | (M)GI U Clamp with Nut Bolt & Washer 2 1/2" | NOS | 50 | 19.58 | 979 | 50 | 19.58 | 979 | 5 | 19.58 | 97.9 | 50 | 15.93 | 796.5 | 0 | 0 | 0 | 45 | 50 | 881.1 | 979
703 | INDENT-941/B WING/RISING MAIN LINE | 10 | Started | Material | (M)PVC Ball Cock 2" | NOS | 1 | 441.32 | 441.32 | 1 | 441.32 | 441.32 | 0 | 441.32 | 0 | 1 | 441.32 | 441.32 | 0 | 0 | 0 | 1 | 1 | 441.32 | 441.32
704 | INDENT-941/B WING/RISING MAIN LINE | 10 | Started | Material | (M)UPVC Adhesives / Solvent (717) - 473ml | NOS | 4 | 535.72 | 2142.88 | 4 | 535.72 | 2142.88 | 0 | 535.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 2142.88 | 2142.88
705 | INDENT-941/B WING/RISING MAIN LINE | 10 | Started | Material | (M)UPVC Coupler 1 1/2" | NOS | 20 | 19.56 | 391.2 | 20 | 19.56 | 391.2 | 2 | 19.56 | 39.12 | 20 | 17.15 | 342.96 | 0 | 0 | 0 | 18 | 20 | 352.08 | 391.2
706 | INDENT-941/B WING/RISING MAIN LINE | 10 | Started | Material | (M)UPVC Coupler 2 1/2" | NOS | 20 | 60.18 | 1203.6 | 20 | 60.18 | 1203.6 | 2 | 60.18 | 120.36 | 20 | 52.63 | 1052.66 | 0 | 0 | 0 | 18 | 20 | 1083.24 | 1203.6
707 | INDENT-941/B WING/RISING MAIN LINE | 10 | Started | Material | (M)UPVC Elbow 1 1/2" (90 degree) | NOS | 12 | 35.36 | 424.32 | 12 | 35.36 | 424.32 | 1 | 35.36 | 35.36 | 12 | 27.85 | 334.23 | 0 | 0 | 0 | 11 | 12 | 388.96 | 424.32
708 | INDENT-941/B WING/RISING MAIN LINE | 10 | Started | Material | (M)UPVC Elbow 2 1/2" (90 degree) | NOS | 12 | 97.38 | 1168.56 | 12 | 97.38 | 1168.56 | 1 | 97.38 | 97.38 | 12 | 85.22 | 1022.6796 | 0 | 0 | 0 | 11 | 12 | 1071.18 | 1168.56
709 | INDENT-941/B WING/RISING MAIN LINE | 10 | Started | Material | (M)UPVC FTA Brass Thread 2 1/2" | NOS | 1 | 717.6 | 717.6 | 1 | 717.6 | 717.6 | 0 | 717.6 | 0 | 1 | 474.2 | 474.2 | 0 | 0 | 0 | 1 | 1 | 717.6 | 717.6
710 | INDENT-941/B WING/RISING MAIN LINE | 10 | Started | Material | (M)UPVC MTA Brass Thread 1 1/2" | NOS | 2 | 325.9 | 651.8 | 2 | 325.9 | 651.8 | 0 | 325.9 | 0 | 2 | 215.36 | 430.71 | 0 | 0 | 0 | 2 | 2 | 651.8 | 651.8
711 | INDENT-941/B WING/RISING MAIN LINE | 10 | Started | Material | (M)UPVC MTA Brass Thread 1 1/4 | NOS | 2 | 315.71 | 631.42 | 2 | 315.71 | 631.42 | 0 | 315.71 | 0 | 2 | 176.8 | 353.6 | 0 | 0 | 0 | 2 | 2 | 631.42 | 631.42
712 | INDENT-941/B WING/RISING MAIN LINE | 10 | Started | Material | (M)UPVC MTA Brass Thread 2 1/2" | NOS | 4 | 910.26 | 3641.04 | 4 | 910.26 | 3641.04 | 0 | 910.26 | 0 | 4 | 797.03 | 3188.1 | 0 | 0 | 0 | 4 | 4 | 3641.04 | 3641.04
713 | INDENT-941/B WING/RISING MAIN LINE | 10 | Started | Material | (M)UPVC Pipe 1 1/2" X 3m long (SCH-80) | NOS | 20 | 469.95 | 9399 | 20 | 469.95 | 9399 | 2 | 469.95 | 939.9 | 20 | 410.75 | 8215.06 | 0 | 0 | 0 | 18 | 20 | 8459.1 | 9399
714 | INDENT-941/B WING/RISING MAIN LINE | 10 | Started | Material | (M)UPVC Pipe 2 1/2" X 3m long (SCH-80) | NOS | 20 | 996.6 | 19932 | 20 | 996.6 | 19932 | 2 | 996.6 | 1993.2 | 20 | 868.59 | 17371.78 | 0 | 0 | 0 | 18 | 20 | 17938.8 | 19932
715 | INDENT-941/B WING/RISING MAIN LINE | 10 | Started | Material | (M)UPVC Red/Coupling 2 1/2" x 2" | NOS | 1 | 51.92 | 51.92 | 1 | 51.92 | 51.92 | 0 | 51.92 | 0 | 1 | 49.77 | 49.77 | 0 | 0 | 0 | 1 | 1 | 51.92 | 51.92
716 | INDENT-941/B WING/RISING MAIN LINE | 10 | Started | Material | (M)UPVC Reducer Tee 2" x 1 1/4" | NOS | 12 | 46 | 552 | 12 | 46 | 552 | 1 | 46 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 12 | 506 | 552
717 | INDENT-942/B WING/UPVC RAISING MAIN LINE | 10 | Started | Material | (M)Brass Ball Valve 1 1/4" | NOS | 1 | 649 | 649 | 1 | 649 | 649 | 0 | 649 | 0 | 1 | 944 | 944 | 0 | 0 | 0 | 1 | 1 | 649 | 649
718 | INDENT-942/B WING/UPVC RAISING MAIN LINE | 10 | Started | Material | (M)Brass Foot Valve 1 1/2" | NOS | 1 | 1800 | 1800 | 1 | 1800 | 1800 | 0 | 1800 | 0 | 1 | 2453.22 | 2453.22 | 0 | 0 | 0 | 1 | 1 | 1800 | 1800
719 | INDENT-942/B WING/UPVC RAISING MAIN LINE | 10 | Started | Material | (M)Brass Foot Valve 1 1/4" | NOS | 1 | 1390 | 1390 | 1 | 1390 | 1390 | 0 | 1390 | 0 | 1 | 1544.62 | 1544.62 | 0 | 0 | 0 | 1 | 1 | 1390 | 1390
720 | INDENT-942/B WING/UPVC RAISING MAIN LINE | 10 | Started | Material | (M)GI C-Bracket 15" x 3" | NOS | 40 | 80.24 | 3209.6 | 40 | 80.24 | 3209.6 | 4 | 80.24 | 320.96 | 40 | 56.17 | 2246.72 | 0 | 0 | 0 | 36 | 40 | 2888.64 | 3209.6
721 | INDENT-942/B WING/UPVC RAISING MAIN LINE | 10 | Started | Material | (M)GI U Clamp with Nut Bolt & Washer 1 1/4" | NOS | 50 | 8.5 | 425 | 50 | 8.5 | 425 | 5 | 8.5 | 42.5 | 50 | 10.75 | 537.65 | 0 | 0 | 0 | 45 | 50 | 382.5 | 425
722 | INDENT-942/B WING/UPVC RAISING MAIN LINE | 10 | Started | Material | (M)Plumbing Nails 3" | KG | 6 | 103.84 | 623.04 | 6 | 103.84 | 623.04 | 1 | 103.84 | 103.84 | 6 | 102.66 | 615.96 | 0 | 0 | 0 | 5 | 6 | 519.2 | 623.04
723 | INDENT-942/B WING/UPVC RAISING MAIN LINE | 10 | Started | Material | (M)PVC Ball Cock 1 1/2" | NOS | 1 | 369.94 | 369.94 | 1 | 369.94 | 369.94 | 0 | 369.94 | 0 | 1 | 369.94 | 369.94 | 0 | 0 | 0 | 1 | 1 | 369.94 | 369.94
724 | INDENT-942/B WING/UPVC RAISING MAIN LINE | 10 | Started | Material | (M)PVC Ball Cock 1 1/4" | NOS | 1 | 324.5 | 324.5 | 1 | 324.5 | 324.5 | 0 | 324.5 | 0 | 1 | 324.5 | 324.5 | 0 | 0 | 0 | 1 | 1 | 324.5 | 324.5
725 | INDENT-942/B WING/UPVC RAISING MAIN LINE | 10 | Started | Material | (M)UPVC Adhesives / Solvent (717) - 473ml | NOS | 6 | 535.72 | 3214.32 | 6 | 535.72 | 3214.32 | 1 | 535.72 | 535.72 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 6 | 2678.6 | 3214.32
726 | INDENT-942/B WING/UPVC RAISING MAIN LINE | 10 | Started | Material | (M)UPVC Coupler 1 1/4" | NOS | 20 | 25.48 | 509.6 | 20 | 25.48 | 509.6 | 2 | 25.48 | 50.96 | 20 | 14.27 | 285.46 | 0 | 0 | 0 | 18 | 20 | 458.64 | 509.6
727 | INDENT-942/B WING/UPVC RAISING MAIN LINE | 10 | Started | Material | (M)UPVC Elbow 1 1/4 (90 degree) | NOS | 12 | 23.61 | 283.32 | 12 | 23.61 | 283.32 | 1 | 23.61 | 23.61 | 12 | 20.68 | 248.1996 | 0 | 0 | 0 | 11 | 12 | 259.71 | 283.32
728 | INDENT-942/B WING/UPVC RAISING MAIN LINE | 10 | Started | Material | (M)UPVC FTA Brass Thread 1 1/2" | NOS | 1 | 258.55 | 258.55 | 1 | 258.55 | 258.55 | 0 | 258.55 | 0 | 1 | 170.85 | 170.85 | 0 | 0 | 0 | 1 | 1 | 258.55 | 258.55
729 | INDENT-942/B WING/UPVC RAISING MAIN LINE | 10 | Started | Material | (M)UPVC FTA Brass Thread 1 1/4 | NOS | 1 | 236 | 236 | 1 | 236 | 236 | 0 | 236 | 0 | 1 | 132.76 | 132.76 | 0 | 0 | 0 | 1 | 1 | 236 | 236
730 | INDENT-942/B WING/UPVC RAISING MAIN LINE | 10 | Started | Material | (M)UPVC MTA Brass Thread 1 1/2" | NOS | 2 | 325.9 | 651.8 | 2 | 325.9 | 651.8 | 0 | 325.9 | 0 | 2 | 215.36 | 430.71 | 0 | 0 | 0 | 2 | 2 | 651.8 | 651.8
731 | INDENT-942/B WING/UPVC RAISING MAIN LINE | 10 | Started | Material | (M)UPVC MTA Brass Thread 1 1/4 | NOS | 2 | 315.71 | 631.42 | 2 | 315.71 | 631.42 | 0 | 315.71 | 0 | 2 | 176.8 | 353.6 | 0 | 0 | 0 | 2 | 2 | 631.42 | 631.42
732 | INDENT-942/B WING/UPVC RAISING MAIN LINE | 10 | Started | Material | (M)UPVC Pipe 1 1/4" X 3m long (SCH-80) | NOS | 20 | 513.75 | 10275 | 20 | 513.75 | 10275 | 2 | 513.75 | 1027.5 | 20 | 339.49 | 6789.72 | 0 | 0 | 0 | 18 | 20 | 9247.5 | 10275
733 | INDENT-18/B WING/DOWNTAKE LINE | 10 | Started | Material | (M)GI Barrel Nipple 3" x 12" | NOS | 2 | 300 | 600 | 2 | 300 | 600 | 0 | 300 | 0 | 2 | 350.13 | 700.26 | 0 | 0 | 0 | 2 | 2 | 600 | 600 | Building
734 | INDENT-18/B WING/DOWNTAKE LINE | 10 | Started | Material | (M)PVC Gully Trap 110 mm - Square | NOS | 35 | 799 | 27965 | 35 | 799 | 27965 | 4 | 799 | 3196 | 35 | 326.5 | 11427.36 | 0 | 0 | 0 | 31 | 35 | 24769 | 27965 | Building
735 | INDENT-18/B WING/DOWNTAKE LINE | 10 | Started | Material | (M)UPVC Elbow 1 1/2" (90 degree) | NOS | 20 | 35.36 | 707.2 | 20 | 35.36 | 707.2 | 2 | 35.36 | 70.72 | 20 | 32.88 | 657.52 | 0 | 0 | 0 | 18 | 20 | 636.48 | 707.2 | Building
736 | INDENT-18/B WING/DOWNTAKE LINE | 10 | Started | Material | (M)UPVC Elbow 1 1/4 (90 degree) | NOS | 80 | 23.61 | 1888.8 | 80 | 23.61 | 1888.8 | 8 | 23.61 | 188.88 | 80 | 24.41 | 1952.76 | 0 | 0 | 0 | 72 | 80 | 1699.92 | 1888.8 | Building
737 | INDENT-18/B WING/DOWNTAKE LINE | 10 | Started | Material | (M)UPVC Reducer Tee 1 1/2" x 1" | NOS | 6 | 43.84 | 263.04 | 6 | 43.84 | 263.04 | 1 | 43.84 | 43.84 | 6 | 45.32 | 271.9002 | 0 | 0 | 0 | 5 | 6 | 219.2 | 263.04 | Building
738 | INDENT-18/B WING/DOWNTAKE LINE | 10 | Started | Material | (M)UPVC Reducer Tee 1 1/2" x 1/2" | NOS | 20 | 38 | 760 | 20 | 38 | 760 | 2 | 38 | 76 | 20 | 44.06 | 881.24 | 0 | 0 | 0 | 18 | 20 | 684 | 760 | Building
739 | INDENT-18/B WING/DOWNTAKE LINE | 10 | Started | Material | (M)UPVC Reducer Tee 1" x 1/2" | NOS | 25 | 30 | 750 | 25 | 30 | 750 | 3 | 30 | 90 | 25 | 20.13 | 503.33 | 0 | 0 | 0 | 22 | 25 | 660 | 750 | Building
740 | INDENT-18/B WING/DOWNTAKE LINE | 10 | Started | Material | (M)UPVC Reducer Tee 2" x 1 1/4" | NOS | 10 | 46 | 460 | 10 | 46 | 460 | 1 | 46 | 46 | 10 | 65.37 | 653.68 | 0 | 0 | 0 | 9 | 10 | 414 | 460 | Building
741 | INDENT-18/B WING/DOWNTAKE LINE | 10 | Started | Material | (M)UPVC Tee 1 1/4" | NOS | 15 | 33.04 | 495.6 | 15 | 33.04 | 495.6 | 2 | 33.04 | 66.08 | 15 | 68.12 | 1021.83 | 0 | 0 | 0 | 13 | 15 | 429.52 | 495.6 | Building
742 | INDENT-866,867 & 868/B BLDG/PRV | 0 | Started | Material | (M)Pressure Reducing Valve 1 1/2" | NOS | 8 | 3555.22 | 28441.76 | 8 | 3555.22 | 28441.76 | 0 | 3555.22 | 0 | 8 | 3555.22 | 28441.78 | 0 | 0 | 0 | 8 | 8 | 28441.76 | 28441.76 | Building
743 | INDENT-866,867 & 868/B BLDG/PRV | 0 | Started | Material | (M)Pressure Reducing Valve 1 1/4" | NOS | 14 | 3236.57 | 45311.98 | 14 | 3236.57 | 45311.98 | 0 | 3236.57 | 0 | 14 | 3236.56 | 45311.8806 | 0 | 0 | 0 | 14 | 14 | 45311.98 | 45311.98 | Building
744 | INDENT-866,867 & 868/B BLDG/PRV | 0 | Started | Material | (M)Pressure Reducing Valve 1" | NOS | 18 | 2792.65 | 50267.7 | 18 | 2792.65 | 50267.7 | 0 | 2792.65 | 0 | 18 | 2792.65 | 50267.6406 | 0 | 0 | 0 | 18 | 18 | 50267.7 | 50267.7 | Building
745 | INDENT-866,867 & 868/B BLDG/PRV | 0 | Started | Material | (M)Pressure Reducing Valve 2" | NOS | 6 | 4051.71 | 24310.26 | 6 | 4051.71 | 24310.26 | 0 | 4051.71 | 0 | 6 | 4051.71 | 24310.2402 | 0 | 0 | 0 | 6 | 6 | 24310.26 | 24310.26 | Building
746 | BORE LINE FROM B BLDG TO UGWT-UPVC MATERIAL | 0 | Tentative | Material | (M)UPVC Coupler 1 1/2" | NOS | 120 | 19.56 | 2347.2 | 120 | 19.56 | 2347.2 | 0 | 19.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 120 | 2347.2 | 2347.2
747 | BORE LINE FROM B BLDG TO UGWT-UPVC MATERIAL | 0 | Tentative | Material | (M)UPVC Elbow 1 1/2" (45 degree) Shoe | NOS | 4 | 26.08 | 104.32 | 4 | 26.08 | 104.32 | 0 | 26.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 104.32 | 104.32
748 | BORE LINE FROM B BLDG TO UGWT-UPVC MATERIAL | 0 | Tentative | Material | (M)UPVC Elbow 1 1/2" (90 degree) | NOS | 20 | 35.36 | 707.2 | 20 | 35.36 | 707.2 | 0 | 35.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 707.2 | 707.2
749 | BORE LINE FROM B BLDG TO UGWT-UPVC MATERIAL | 0 | Tentative | Material | (M)UPVC Pipe 1 1/2" X 3m long (SCH-40) | NOS | 110 | 236 | 25960 | 110 | 236 | 25960 | 0 | 236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 110 | 25960 | 25960
750 | BORE LINE FROM B BLDG TO UGWT-UPVC MATERIAL | 0 | Tentative | Material | (M)Upvc Solvent 237ml | NOS | 8 | 143.72 | 1149.76 | 8 | 143.72 | 1149.76 | 0 | 143.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 1149.76 | 1149.76
751 | B BUILDING DRAINAGE LINE (B WING TO UGWT) UPVC MATERIAL | 0 | Tentative | Material | (M)UPVC Adhesives / Solvent (717) - 473ml | NOS | 1 | 535.72 | 535.72 | 1 | 535.72 | 535.72 | 0 | 535.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 535.72 | 535.72
752 | B BUILDING DRAINAGE LINE (B WING TO UGWT) UPVC MATERIAL | 0 | Tentative | Material | (M)UPVC Coupler 1 1/2" | NOS | 15 | 19.56 | 293.4 | 15 | 19.56 | 293.4 | 0 | 19.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 293.4 | 293.4
753 | B BUILDING DRAINAGE LINE (B WING TO UGWT) UPVC MATERIAL | 0 | Tentative | Material | (M)UPVC Coupler 2 1/2" | NOS | 13 | 60.18 | 782.34 | 13 | 60.18 | 782.34 | 0 | 60.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13 | 782.34 | 782.34
754 | B BUILDING DRAINAGE LINE (B WING TO UGWT) UPVC MATERIAL | 0 | Tentative | Material | (M)UPVC Elbow 1 1/2" (45 degree) Shoe | NOS | 3 | 26.08 | 78.24 | 3 | 26.08 | 78.24 | 0 | 26.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 78.24 | 78.24
755 | B BUILDING DRAINAGE LINE (B WING TO UGWT) UPVC MATERIAL | 0 | Tentative | Material | (M)UPVC Elbow 1 1/2" (90 degree) | NOS | 4 | 35.36 | 141.44 | 4 | 35.36 | 141.44 | 0 | 35.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 141.44 | 141.44
756 | B BUILDING DRAINAGE LINE (B WING TO UGWT) UPVC MATERIAL | 0 | Tentative | Material | (M)UPVC Elbow 2 1/2" (45 degree) Shoe | NOS | 3 | 89.83 | 269.49 | 3 | 89.83 | 269.49 | 0 | 89.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 269.49 | 269.49
757 | B BUILDING DRAINAGE LINE (B WING TO UGWT) UPVC MATERIAL | 0 | Tentative | Material | (M)UPVC Elbow 2 1/2" (90 degree) | NOS | 4 | 97.38 | 389.52 | 4 | 97.38 | 389.52 | 0 | 97.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 389.52 | 389.52
758 | B BUILDING DRAINAGE LINE (B WING TO UGWT) UPVC MATERIAL | 0 | Tentative | Material | (M)UPVC Pipe 1 1/2" X 3m long (SCH-80) | NOS | 15 | 469.95 | 7049.25 | 15 | 469.95 | 7049.25 | 0 | 469.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 7049.25 | 7049.25
759 | B BUILDING DRAINAGE LINE (B WING TO UGWT) UPVC MATERIAL | 0 | Tentative | Material | (M)UPVC Pipe 2 1/2" X 3m long (SCH-80) | NOS | 13 | 1175.98 | 15287.74 | 13 | 1175.98 | 15287.74 | 0 | 1175.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13 | 15287.74 | 15287.74
760 | B BUILDING DRAINAGE LINE (B WING TO UGWT) UPVC MATERIAL | 0 | Tentative | Material | (M)UPVC Reducer Bushing 1 1/2" x 1 1/4" | NOS | 1 | 29.5 | 29.5 | 1 | 29.5 | 29.5 | 0 | 29.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 29.5 | 29.5
761 | B BUILDING DRAINAGE LINE (B WING TO UGWT) UPVC MATERIAL | 0 | Tentative | Material | (M)UPVC Reducer Coupling 2 1/2" x 1 1/2" | NOS | 2 | 48.38 | 96.76 | 2 | 48.38 | 96.76 | 0 | 48.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 96.76 | 96.76
762 | RECYCLE LINE FROM STP TO B WING-UPVC MATERIAL | 0 | Tentative | Material | (M)UPVC Adhesives / Solvent (717) - 473ml | NOS | 4 | 535.72 | 2142.88 | 4 | 535.72 | 2142.88 | 0 | 535.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 2142.88 | 2142.88
763 | RECYCLE LINE FROM STP TO B WING-UPVC MATERIAL | 0 | Tentative | Material | (M)UPVC Coupler 2 1/2" | NOS | 23 | 35.4 | 814.2 | 23 | 35.4 | 814.2 | 0 | 35.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 23 | 814.2 | 814.2
764 | RECYCLE LINE FROM STP TO B WING-UPVC MATERIAL | 0 | Tentative | Material | (M)UPVC Coupler 2" | NOS | 5 | 27.66 | 138.3 | 5 | 27.66 | 138.3 | 0 | 27.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 138.3 | 138.3
765 | RECYCLE LINE FROM STP TO B WING-UPVC MATERIAL | 0 | Tentative | Material | (M)UPVC Elbow 2 1/2" (90 degree) | NOS | 6 | 97.38 | 584.28 | 6 | 97.38 | 584.28 | 0 | 97.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 584.28 | 584.28
766 | RECYCLE LINE FROM STP TO B WING-UPVC MATERIAL | 0 | Tentative | Material | (M)UPVC Pipe 2 1/2" X 3m long (SCH-80) | NOS | 23 | 1175.98 | 27047.54 | 23 | 1175.98 | 27047.54 | 0 | 1175.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 23 | 27047.54 | 27047.54
767 | RECYCLE LINE FROM STP TO B WING-UPVC MATERIAL | 0 | Tentative | Material | (M)UPVC Pipe 2" X 3m long (SCH-80) | NOS | 5 | 826 | 4130 | 5 | 826 | 4130 | 0 | 826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 4130 | 4130
768 | RECYCLE LINE FROM STP TO B WING-UPVC MATERIAL | 0 | Tentative | Material | (M)UPVC Reducer Coupling 2 1/2" x 2" | NOS | 1 | 53.49 | 53.49 | 1 | 53.49 | 53.49 | 0 | 53.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 53.49 | 53.49
769 | RECYCLE LINE FROM STP TO B WING-UPVC MATERIAL | 0 | Tentative | Material | (M)UPVC Reducer Coupling 2" x 1 1/2" | NOS | 2 | 41.3 | 82.6 | 2 | 41.3 | 82.6 | 0 | 41.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 82.6 | 82.6
770 | INDENT-50/B WING/CP-FTTING (4BHK) | 10 | Started | Material | (M)Basin Waste Coupling F/T | NOS | 44 | 307.49 | 13529.56 | 44 | 307.49 | 13529.56 | 4 | 307.49 | 1229.96 | 44 | 307.5 | 13529.8328 | 0 | 0 | 0 | 40 | 44 | 12299.6 | 13529.56 | Building
771 | INDENT-50/B WING/CP-FTTING (4BHK) | 10 | Started | Material | (M)CP Bib Cock | NOS | 22 | 1008.61 | 22189.42 | 22 | 1008.61 | 22189.42 | 2 | 1008.61 | 2017.22 | 22 | 779 | 17138.0132 | 0 | 0 | 0 | 20 | 22 | 20172.2 | 22189.42 | Building
772 | INDENT-50/B WING/CP-FTTING (4BHK) | 10 | Started | Material | (M)CP Bottle Trap | NOS | 44 | 177 | 7788 | 44 | 177 | 7788 | 4 | 177 | 708 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 44 | 7080 | 7788 | Building
773 | INDENT-50/B WING/CP-FTTING (4BHK) | 10 | Started | Material | (M)CP Ext. Piece - 1/2" x 1" | NOS | 330 | 29.5 | 9735 | 330 | 29.5 | 9735 | 33 | 29.5 | 973.5 | 0 | 0 | 0 | 0 | 0 | 0 | 297 | 330 | 8761.5 | 9735 | Building
774 | INDENT-50/B WING/CP-FTTING (4BHK) | 10 | Started | Material | (M)CP Health Faucet | NOS | 33 | 631.4 | 20836.2 | 33 | 631.4 | 20836.2 | 3 | 631.4 | 1894.2 | 33 | 631.39 | 20836.0152 | 0 | 0 | 0 | 30 | 33 | 18942 | 20836.2 | Building
775 | INDENT-50/B WING/CP-FTTING (4BHK) | 10 | Started | Material | (M)CP JALI SS - 50mm | NOS | 11 | 29.5 | 324.5 | 11 | 29.5 | 324.5 | 1 | 29.5 | 29.5 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 11 | 295 | 324.5 | Building
776 | INDENT-50/B WING/CP-FTTING (4BHK) | 10 | Started | Material | (M)CP Nozzle Bib Cock | NOS | 11 | 697 | 7667 | 11 | 697 | 7667 | 1 | 697 | 697 | 11 | 697 | 7667.0253 | 0 | 0 | 0 | 10 | 11 | 6970 | 7667 | Building
777 | INDENT-50/B WING/CP-FTTING (4BHK) | 10 | Started | Material | (M)CP Over Head Shower | NOS | 44 | 557.6 | 24534.4 | 44 | 557.6 | 24534.4 | 4 | 557.6 | 2230.4 | 44 | 557.6 | 24534.2768 | 0 | 0 | 0 | 40 | 44 | 22304 | 24534.4 | Building
778 | INDENT-50/B WING/CP-FTTING (4BHK) | 10 | Started | Material | (M)CP Pillar Cock (DLX-CHR-508KN) | NOS | 44 | 1025 | 45100 | 44 | 1025 | 45100 | 4 | 1025 | 4100 | 44 | 1025 | 45099.7888 | 0 | 0 | 0 | 40 | 44 | 41000 | 45100 | Building
779 | INDENT-50/B WING/CP-FTTING (4BHK) | 10 | Started | Material | (M)CP Shower Arm | NOS | 44 | 344.4 | 15153.6 | 44 | 344.4 | 15153.6 | 4 | 344.4 | 1377.6 | 44 | 357 | 15707.8768 | 0 | 0 | 0 | 40 | 44 | 13776 | 15153.6 | Building
780 | INDENT-50/B WING/CP-FTTING (4BHK) | 10 | Started | Material | (M)CP Sink Cock | NOS | 22 | 1459.61 | 32111.42 | 22 | 1459.61 | 32111.42 | 2 | 1459.61 | 2919.22 | 22 | 1115.19 | 24534.2768 | 0 | 0 | 0 | 20 | 22 | 29192.2 | 32111.42 | Building
781 | INDENT-50/B WING/CP-FTTING (4BHK) | 10 | Started | Material | (M)CP Wall Mixer | NOS | 44 | 3361.99 | 147927.56 | 44 | 3361.99 | 147927.56 | 4 | 3361.99 | 13447.96 | 44 | 3362 | 147927.868 | 0 | 0 | 0 | 40 | 44 | 134479.6 | 147927.56 | Building
782 | INDENT-50/B WING/CP-FTTING (4BHK) | 10 | Started | Material | (M)GI Plug 1/2" | NOS | 110 | 29.5 | 3245 | 110 | 29.5 | 3245 | 11 | 29.5 | 324.5 | 0 | 0 | 0 | 0 | 0 | 0 | 99 | 110 | 2920.5 | 3245 | Building
783 | INDENT-50/B WING/CP-FTTING (4BHK) | 10 | Started | Material | (M)PVC FLOOR TRAP JALI-6'' (BROWN) | NOS | 60 | 59 | 3540 | 60 | 59 | 3540 | 6 | 59 | 354 | 60 | 52.65 | 3159 | 0 | 0 | 0 | 54 | 60 | 3186 | 3540 | Building
784 | INDENT-50/B WING/CP-FTTING (4BHK) | 10 | Started | Material | (M)PVC FLOOR TRAP JALI-6'' (GRAY) | NOS | 25 | 59 | 1475 | 25 | 59 | 1475 | 3 | 59 | 177 | 25 | 36.2 | 904.875 | 0 | 0 | 0 | 22 | 25 | 1298 | 1475 | Building
785 | INDENT-50/B WING/CP-FTTING (4BHK) | 10 | Started | Material | (M)PVC Waste / Fiexible Pipe | NOS | 11 | 141.6 | 1557.6 | 11 | 141.6 | 1557.6 | 1 | 141.6 | 141.6 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 11 | 1416 | 1557.6 | Building
786 | INDENT-50/B WING/CP-FTTING (4BHK) | 10 | Started | Material | (M)Teflon Tape | NOS | 300 | 19.48 | 5844 | 300 | 19.48 | 5844 | 30 | 19.48 | 584.4 | 0 | 0 | 0 | 0 | 0 | 0 | 270 | 300 | 5259.6 | 5844 | Building
787 | INDENT-50/B WING/CP-FTTING (4BHK) | 10 | Started | Material | (M)Two Way Bib Cock | NOS | 33 | 1008.61 | 33284.13 | 33 | 1008.61 | 33284.13 | 3 | 1008.61 | 3025.83 | 33 | 885.6 | 29224.8594 | 0 | 0 | 0 | 30 | 33 | 30258.3 | 33284.13 | Building
788 | INDENT-51/B WING/CHANGES FLAT | 10 | Started | Material | (M)CP Health Faucet | NOS | 5 | 631.4 | 3157 | 5 | 631.4 | 3157 | 1 | 631.4 | 631.4 | 5 | 631.39 | 3156.972 | 0 | 0 | 0 | 4 | 5 | 2525.6 | 3157
789 | INDENT-51/B WING/CHANGES FLAT | 10 | Started | Material | (M)Ruby Wall Hung Closet 500 x 350 x 335 | NOS | 5 | 5900 | 29500 | 5 | 5900 | 29500 | 1 | 5900 | 5900 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 23600 | 29500
790 | INDENT-51/B WING/CHANGES FLAT | 10 | Started | Material | (M)Two Way Bib Cock | NOS | 5 | 1008.61 | 5043.05 | 5 | 1008.61 | 5043.05 | 1 | 1008.61 | 1008.61 | 5 | 885.6 | 4428.009 | 0 | 0 | 0 | 4 | 5 | 4034.44 | 5043.05
791 | INDENT-49/B WING/CP-FTTING (2 & 2.5BHK) | 10 | Started | Material | (M)Basin Waste Coupling F/T | NOS | 218 | 307.49 | 67032.82 | 218 | 307.49 | 67032.82 | 22 | 307.49 | 6764.78 | 218 | 307.5 | 67034.1716 | 0 | 0 | 0 | 196 | 218 | 60268.04 | 67032.82
792 | INDENT-49/B WING/CP-FTTING (2 & 2.5BHK) | 10 | Started | Material | (M)CP Bib Cock | NOS | 218 | 1008.61 | 219876.98 | 218 | 1008.61 | 219876.98 | 22 | 1008.61 | 22189.42 | 218 | 779 | 169822.1308 | 0 | 0 | 0 | 196 | 218 | 197687.56 | 219876.98
793 | INDENT-49/B WING/CP-FTTING (2 & 2.5BHK) | 10 | Started | Material | (M)CP Bottle Trap | NOS | 218 | 177 | 38586 | 218 | 177 | 38586 | 22 | 177 | 3894 | 0 | 0 | 0 | 0 | 0 | 0 | 196 | 218 | 34692 | 38586
794 | INDENT-49/B WING/CP-FTTING (2 & 2.5BHK) | 10 | Started | Material | (M)CP Ext. Piece - 1/2" x 1" | NOS | 1308 | 29.5 | 38586 | 1308 | 29.5 | 38586 | 131 | 29.5 | 3864.5 | 0 | 0 | 0 | 0 | 0 | 0 | 1177 | 1308 | 34721.5 | 38586
795 | INDENT-49/B WING/CP-FTTING (2 & 2.5BHK) | 10 | Started | Material | (M)CP Health Faucet | NOS | 109 | 631.4 | 68822.6 | 109 | 631.4 | 68822.6 | 11 | 631.4 | 6945.4 | 109 | 631.39 | 68821.9896 | 0 | 0 | 0 | 98 | 109 | 61877.2 | 68822.6
796 | INDENT-49/B WING/CP-FTTING (2 & 2.5BHK) | 10 | Started | Material | (M)CP JALI SS - 50mm | NOS | 109 | 29.5 | 3215.5 | 109 | 29.5 | 3215.5 | 11 | 29.5 | 324.5 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 109 | 2891 | 3215.5
797 | INDENT-49/B WING/CP-FTTING (2 & 2.5BHK) | 10 | Started | Material | (M)CP Nozzle Bib Cock | NOS | 109 | 697 | 75973 | 109 | 697 | 75973 | 11 | 697 | 7667 | 109 | 697 | 75973.2507 | 0 | 0 | 0 | 98 | 109 | 68306 | 75973
798 | INDENT-49/B WING/CP-FTTING (2 & 2.5BHK) | 10 | Started | Material | (M)CP Over Head Shower | NOS | 218 | 557.6 | 121556.8 | 218 | 557.6 | 121556.8 | 22 | 557.6 | 12267.2 | 218 | 557.6 | 121556.1896 | 0 | 0 | 0 | 196 | 218 | 109289.6 | 121556.8
799 | INDENT-49/B WING/CP-FTTING (2 & 2.5BHK) | 10 | Started | Material | (M)CP Pillar Cock (DLX-CHR-508KN) | NOS | 218 | 1025 | 223450 | 218 | 1025 | 223450 | 22 | 1025 | 22550 | 218 | 1025 | 223448.9536 | 0 | 0 | 0 | 196 | 218 | 200900 | 223450
800 | INDENT-49/B WING/CP-FTTING (2 & 2.5BHK) | 10 | Started | Material | (M)CP Shower Arm | NOS | 218 | 344.4 | 75079.2 | 218 | 344.4 | 75079.2 | 22 | 344.4 | 7576.8 | 218 | 357 | 77825.3896 | 0 | 0 | 0 | 196 | 218 | 67502.4 | 75079.2
801 | INDENT-49/B WING/CP-FTTING (2 & 2.5BHK) | 10 | Started | Material | (M)CP Sink Cock | NOS | 218 | 1459.61 | 318194.98 | 218 | 1459.61 | 318194.98 | 22 | 1459.61 | 32111.42 | 218 | 1115.19 | 243112.3792 | 0 | 0 | 0 | 196 | 218 | 286083.56 | 318194.98
802 | INDENT-49/B WING/CP-FTTING (2 & 2.5BHK) | 10 | Started | Material | (M)CP Wall Mixer | NOS | 218 | 3361.99 | 732913.82 | 218 | 3361.99 | 732913.82 | 22 | 3361.99 | 73963.78 | 218 | 3362 | 732915.346 | 0 | 0 | 0 | 196 | 218 | 658950.04 | 732913.82
803 | INDENT-49/B WING/CP-FTTING (2 & 2.5BHK) | 10 | Started | Material | (M)GI Plug 1/2" | NOS | 654 | 29.5 | 19293 | 654 | 29.5 | 19293 | 65 | 29.5 | 1917.5 | 0 | 0 | 0 | 0 | 0 | 0 | 589 | 654 | 17375.5 | 19293
804 | INDENT-49/B WING/CP-FTTING (2 & 2.5BHK) | 10 | Started | Material | (M)PVC FLOOR TRAP JALI-6'' (BROWN) | NOS | 330 | 59 | 19470 | 330 | 59 | 19470 | 33 | 59 | 1947 | 330 | 52.65 | 17374.5 | 0 | 0 | 0 | 297 | 330 | 17523 | 19470
805 | INDENT-49/B WING/CP-FTTING (2 & 2.5BHK) | 10 | Started | Material | (M)PVC FLOOR TRAP JALI-6'' (GRAY) | NOS | 230 | 59 | 13570 | 230 | 59 | 13570 | 23 | 59 | 1357 | 230 | 36.2 | 8324.85 | 0 | 0 | 0 | 207 | 230 | 12213 | 13570
806 | INDENT-49/B WING/CP-FTTING (2 & 2.5BHK) | 10 | Started | Material | (M)PVC Waste / Fiexible Pipe | NOS | 109 | 141.6 | 15434.4 | 109 | 141.6 | 15434.4 | 11 | 141.6 | 1557.6 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 109 | 13876.8 | 15434.4
807 | INDENT-49/B WING/CP-FTTING (2 & 2.5BHK) | 10 | Started | Material | (M)Teflon Tape | NOS | 1550 | 19.48 | 30194 | 1550 | 19.48 | 30194 | 155 | 19.48 | 3019.4 | 0 | 0 | 0 | 0 | 0 | 0 | 1395 | 1550 | 27174.6 | 30194
808 | INDENT-49/B WING/CP-FTTING (2 & 2.5BHK) | 10 | Started | Material | (M)Two Way Bib Cock | NOS | 109 | 1008.61 | 109938.49 | 109 | 1008.61 | 109938.49 | 11 | 1008.61 | 11094.71 | 109 | 885.6 | 96530.5962 | 0 | 0 | 0 | 98 | 109 | 98843.78 | 109938.49
809 | INDENT-42/B WING/SANITARY FITTING MATERIAL | 0 | Started | Material | (M)Basin Rack Bolt - 12x100mm | NOS | 524 | 118 | 61832 | 524 | 118 | 61832 | 0 | 118 | 0 | 524 | 52.85 | 27693.4 | 0 | 0 | 0 | 524 | 524 | 61832 | 61832
810 | INDENT-42/B WING/SANITARY FITTING MATERIAL | 0 | Started | Material | (M)DAFFODIL WASH BASIN 575 X 420 X 200 | NOS | 142 | 5310 | 754020 | 142 | 5310 | 754020 | 0 | 5310 | 0 | 142 | 947.84 | 134592.5842 | 0 | 0 | 0 | 142 | 142 | 754020 | 754020
811 | INDENT-42/B WING/SANITARY FITTING MATERIAL | 0 | Started | Material | (M)GLASS LAMBI | KG | 80 | 118 | 9440 | 80 | 118 | 9440 | 0 | 118 | 0 | 80 | 71.66 | 5732.704 | 0 | 0 | 0 | 80 | 80 | 9440 | 9440
812 | INDENT-42/B WING/SANITARY FITTING MATERIAL | 0 | Started | Material | (M)IRIS WASH BASIN 450 X 300 X 180 | NOS | 120 | 2336.4 | 280368 | 120 | 2336.4 | 280368 | 0 | 2336.4 | 0 | 120 | 841.64 | 100996.2 | 0 | 0 | 0 | 120 | 120 | 280368 | 280368
813 | INDENT-42/B WING/SANITARY FITTING MATERIAL | 0 | Started | Material | (M)Ruby Topaz Seat Cover | NOS | 142 | 1770 | 251340 | 142 | 1770 | 251340 | 0 | 1770 | 0 | 142 | 446.04 | 63337.68 | 0 | 0 | 0 | 142 | 142 | 251340 | 251340
814 | INDENT-42/B WING/SANITARY FITTING MATERIAL | 0 | Started | Material | (M)Ruby Wall Hung Closet 500 x 350 x 335 | NOS | 142 | 5900 | 837800 | 142 | 5900 | 837800 | 0 | 5900 | 0 | 142 | 2843.51 | 403777.7242 | 0 | 0 | 0 | 142 | 142 | 837800 | 837800
815 | INDENT-645/B BLDG/ORISSA PAN INSTALLATION WORK | 0 | Started | Material | (M)CEMENT PPC 50KG | BAG | 70 | 320 | 22400 | 70 | 320 | 22400 | 0 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 70 | 22400 | 22400
816 | INDENT-645/B BLDG/ORISSA PAN INSTALLATION WORK | 0 | Started | Material | (M)Crush Sand | BRASS | 2 | 3675 | 7350 | 2 | 3675 | 7350 | 0 | 3675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 7350 | 7350
817 | INDENT-645/B BLDG/ORISSA PAN INSTALLATION WORK | 0 | Started | Material | (M)Metal No.I 6mm (Grit) | BRASS | 3 | 3000 | 9000 | 3 | 3000 | 9000 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 9000 | 9000
818 | INDENT-645/B BLDG/ORISSA PAN INSTALLATION WORK | 0 | Started | Material | (M)Orissa Pan 23" | NOS | 120 | 5310 | 637200 | 0 | 0 | 0 | 0 | 5310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 120 | 637200 | 637200
819 | B WING CP FITTING (BALANCE MATERIAL) | 0 | Tentative | Material | (M)Angle Cock | NOS | 262 | 1239 | 324618 | 262 | 1239 | 324618 | 0 | 1239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 262 | 262 | 324618 | 324618
820 | B WING CP FITTING (BALANCE MATERIAL) | 0 | Tentative | Material | (M)Inlet Pipe - 1/2'' (Long-24") | NOS | 262 | 283.2 | 74198.4 | 262 | 283.2 | 74198.4 | 0 | 283.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 262 | 262 | 74198.4 | 74198.4
821 | INDENT-64/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)Brass Ball Valve 4" | NOS | 1 | 14155.28 | 14155.28 | 1 | 14155.28 | 14155.28 | 0 | 14155.28 | 0 | 1 | 14155.98 | 14155.98 | 0 | 0 | 0 | 1 | 1 | 14155.28 | 14155.28 | Building
822 | INDENT-64/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)Brass Strainers 100mm | NOS | 1 | 12272 | 12272 | 1 | 12272 | 12272 | 0 | 12272 | 0 | 1 | 7198.7 | 7198.7 | 0 | 0 | 0 | 1 | 1 | 12272 | 12272 | Building
823 | INDENT-64/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)GI Elbow 3" | NOS | 3 | 476.02 | 1428.06 | 3 | 476.02 | 1428.06 | 0 | 476.02 | 0 | 3 | 476.01 | 1428.0399 | 0 | 0 | 0 | 3 | 3 | 1428.06 | 1428.06 | Building
824 | INDENT-64/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)GI Elbow 4" | NOS | 2 | 780.75 | 1561.5 | 2 | 780.75 | 1561.5 | 0 | 780.75 | 0 | 2 | 780.75 | 1561.5 | 0 | 0 | 0 | 2 | 2 | 1561.5 | 1561.5 | Building
825 | INDENT-64/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Adhesives / Solvent (717) - 473ml | NOS | 30 | 535.72 | 16071.6 | 30 | 535.72 | 16071.6 | 0 | 535.72 | 0 | 30 | 535.72 | 16071.6 | 0 | 0 | 0 | 30 | 30 | 16071.6 | 16071.6 | Building
826 | INDENT-64/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Coupler 4" | NOS | 12 | 149.86 | 1798.32 | 12 | 149.86 | 1798.32 | 0 | 149.86 | 0 | 12 | 149.8 | 1797.6204 | 0 | 0 | 0 | 12 | 12 | 1798.32 | 1798.32 | Building
827 | INDENT-64/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Elbow 4" (90 degree) | NOS | 12 | 258.64 | 3103.68 | 12 | 258.64 | 3103.68 | 0 | 258.64 | 0 | 12 | 258.63 | 3103.5804 | 0 | 0 | 0 | 12 | 12 | 3103.68 | 3103.68 | Building
828 | INDENT-64/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC MTA Brass Thread 4" | NOS | 6 | 3212.56 | 19275.36 | 6 | 3212.56 | 19275.36 | 0 | 3212.56 | 0 | 6 | 3212.57 | 19275.4398 | 0 | 0 | 0 | 6 | 6 | 19275.36 | 19275.36 | Building
829 | INDENT-64/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Pipe 4" X 3m long (SCH-40) | NOS | 22 | 1446.56 | 31824.32 | 22 | 1446.56 | 31824.32 | 0 | 1446.56 | 0 | 22 | 1446.56 | 31824.3596 | 0 | 0 | 0 | 22 | 22 | 31824.32 | 31824.32 | Building
830 | INDENT-64/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Reducer Coupling 4" x 2 1/2" | NOS | 3 | 150.22 | 450.66 | 3 | 150.22 | 450.66 | 0 | 150.22 | 0 | 3 | 150.2 | 450.6099 | 0 | 0 | 0 | 3 | 3 | 450.66 | 450.66 | Building
831 | INDENT-64/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Reducer Coupling 4" x 3" | NOS | 3 | 148.51 | 445.53 | 3 | 148.51 | 445.53 | 0 | 148.51 | 0 | 3 | 148.48 | 445.4301 | 0 | 0 | 0 | 3 | 3 | 445.53 | 445.53 | Building
832 | INDENT-64/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Reducer Tee 4" x 2 1/2" | NOS | 6 | 322.88 | 1937.28 | 6 | 322.88 | 1937.28 | 0 | 322.88 | 0 | 6 | 322.87 | 1937.22 | 0 | 0 | 0 | 6 | 6 | 1937.28 | 1937.28 | Building
833 | INDENT-64/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Solvent 473ml | NOS | 10 | 330.4 | 3304 | 10 | 330.4 | 3304 | 0 | 330.4 | 0 | 10 | 330.4 | 3304 | 0 | 0 | 0 | 10 | 10 | 3304 | 3304 | Building
834 | INDENT-64/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Tee 4" | NOS | 3 | 339.53 | 1018.59 | 3 | 339.53 | 1018.59 | 0 | 339.53 | 0 | 3 | 339.52 | 1018.5699 | 0 | 0 | 0 | 3 | 3 | 1018.59 | 1018.59 | Building
835 | INDENT-65/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)AMBADI (TAG) | KG | 2 | 413 | 826 | 2 | 413 | 826 | 0 | 413 | 0 | 2 | 413 | 826 | 1 | 413 | 413 | 2 | 1 | 826 | 413 | Building
836 | INDENT-65/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)Brass Ball Valve 3" | NOS | 2 | 8363.02 | 16726.04 | 2 | 8363.02 | 16726.04 | 0 | 8363.02 | 0 | 2 | 9220.34 | 18440.68 | 0 | 0 | 0 | 2 | 2 | 16726.04 | 16726.04 | Building
837 | INDENT-65/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)Brass Strainers 80mm | NOS | 2 | 11159.55 | 22319.1 | 2 | 11159.55 | 22319.1 | 0 | 11159.55 | 0 | 2 | 12052.58 | 24105.16 | 0 | 0 | 0 | 2 | 2 | 22319.1 | 22319.1 | Building
838 | INDENT-65/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)GI Elbow 2 1/2" | NOS | 5 | 322.79 | 1613.95 | 5 | 322.79 | 1613.95 | 0 | 322.79 | 0 | 5 | 322.79 | 1613.95 | 0 | 0 | 0 | 5 | 5 | 1613.95 | 1613.95 | Building
839 | INDENT-65/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)GI Plug 3" | NOS | 4 | 89.32 | 357.28 | 4 | 89.32 | 357.28 | 0 | 89.32 | 0 | 4 | 89.33 | 357.3 | 0 | 0 | 0 | 4 | 4 | 357.28 | 357.28 | Building
840 | INDENT-65/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)GI Socket 3" | NOS | 2 | 309.98 | 619.96 | 2 | 309.98 | 619.96 | 0 | 309.98 | 0 | 2 | 309.99 | 619.98 | 0 | 0 | 0 | 2 | 2 | 619.96 | 619.96 | Building
841 | INDENT-65/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)Holdtite (500 gm) | NOS | 8 | 123.32 | 986.56 | 8 | 123.32 | 986.56 | 0 | 123.32 | 0 | 8 | 123.31 | 986.48 | 0 | 0 | 0 | 8 | 8 | 986.56 | 986.56 | Building
842 | INDENT-65/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)Teflon Tape | NOS | 20 | 19.48 | 389.6 | 20 | 19.48 | 389.6 | 0 | 19.48 | 0 | 20 | 19.47 | 389.4 | 0 | 0 | 0 | 20 | 20 | 389.6 | 389.6 | Building
843 | INDENT-65/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Coupler 3" | NOS | 20 | 84.29 | 1685.8 | 20 | 84.29 | 1685.8 | 0 | 84.29 | 0 | 20 | 84.29 | 1685.74 | 0 | 0 | 0 | 20 | 20 | 1685.8 | 1685.8 | Building
844 | INDENT-65/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Elbow 3" (90 degree) | NOS | 10 | 153.93 | 1539.3 | 10 | 153.93 | 1539.3 | 0 | 153.93 | 0 | 10 | 153.93 | 1539.32 | 0 | 0 | 0 | 10 | 10 | 1539.3 | 1539.3 | Building
845 | INDENT-65/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC MTA Brass Thread 3" | NOS | 12 | 1133.62 | 13603.44 | 12 | 1133.62 | 13603.44 | 0 | 1133.62 | 0 | 12 | 1133.64 | 13603.6596 | 0 | 0 | 0 | 12 | 12 | 13603.44 | 13603.44 | Building
846 | INDENT-65/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Pipe 3" X 3m long (SCH-40) | NOS | 30 | 1004.78 | 30143.4 | 30 | 1004.78 | 30143.4 | 0 | 1004.78 | 0 | 30 | 1004.78 | 30143.46 | 0 | 0 | 0 | 30 | 30 | 30143.4 | 30143.4 | Building
847 | INDENT-65/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Reducer Coupling 3" x 2 1/2" | NOS | 6 | 82.34 | 494.04 | 6 | 82.34 | 494.04 | 0 | 82.34 | 0 | 6 | 82.34 | 494.04 | 0 | 0 | 0 | 6 | 6 | 494.04 | 494.04 | Building
848 | INDENT-65/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Reducer Tee 3" x 1 1/2" | NOS | 6 | 184.73 | 1108.38 | 6 | 184.73 | 1108.38 | 0 | 184.73 | 0 | 6 | 184.73 | 1108.38 | 0 | 0 | 0 | 6 | 6 | 1108.38 | 1108.38 | Building
849 | INDENT-65/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Reducer Tee 3" x 2 1/2" | NOS | 3 | 174.94 | 524.82 | 3 | 174.94 | 524.82 | 0 | 174.94 | 0 | 3 | 184.29 | 552.8799 | 0 | 0 | 0 | 3 | 3 | 524.82 | 524.82 | Building
850 | INDENT-65/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Reducer Tee 3" x 2" | NOS | 10 | 184.57 | 1845.7 | 10 | 184.57 | 1845.7 | 0 | 184.57 | 0 | 10 | 184.56 | 1845.64 | 0 | 0 | 0 | 10 | 10 | 1845.7 | 1845.7 | Building
851 | INDENT-65/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Tee 3" | NOS | 3 | 191.16 | 573.48 | 3 | 191.16 | 573.48 | 0 | 191.16 | 0 | 3 | 191.1 | 573.3099 | 0 | 0 | 0 | 3 | 3 | 573.48 | 573.48 | Building
852 | INDENT-66/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)Brass Ball Valve 2 1/2" | NOS | 1 | 5743.66 | 5743.66 | 1 | 5743.66 | 5743.66 | 0 | 5743.66 | 0 | 1 | 5743.66 | 5743.66 | 0 | 0 | 0 | 1 | 1 | 5743.66 | 5743.66 | Building
853 | INDENT-66/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)Brass Strainers 65mm | NOS | 1 | 8883.52 | 8883.52 | 1 | 8883.52 | 8883.52 | 0 | 8883.52 | 0 | 1 | 10212.01 | 10212.01 | 0 | 0 | 0 | 1 | 1 | 8883.52 | 8883.52 | Building
854 | INDENT-66/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Ball Valves 2 1/2" | NOS | 12 | 843.84 | 10126.08 | 12 | 843.84 | 10126.08 | 0 | 843.84 | 0 | 12 | 843.84 | 10126.1004 | 0 | 0 | 0 | 12 | 12 | 10126.08 | 10126.08 | Building
855 | INDENT-66/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Ball Valves 2" | NOS | 20 | 303.96 | 6079.2 | 20 | 303.96 | 6079.2 | 0 | 303.96 | 0 | 20 | 303.97 | 6079.36 | 0 | 0 | 0 | 20 | 20 | 6079.2 | 6079.2 | Building
856 | INDENT-66/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Coupler 2 1/2" | NOS | 46 | 60.18 | 2768.28 | 46 | 60.18 | 2768.28 | 0 | 60.18 | 0 | 46 | 60.1 | 2764.4804 | 0 | 0 | 0 | 46 | 46 | 2768.28 | 2768.28 | Building
857 | INDENT-66/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Elbow 2 1/2" (45 degree) Shoe | NOS | 10 | 89.83 | 898.3 | 10 | 89.83 | 898.3 | 0 | 89.83 | 0 | 10 | 89.83 | 898.34 | 0 | 0 | 0 | 10 | 10 | 898.3 | 898.3 | Building
858 | INDENT-66/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Elbow 2 1/2" (90 degree) | NOS | 80 | 97.38 | 7790.4 | 80 | 97.38 | 7790.4 | 0 | 97.38 | 0 | 80 | 97.37 | 7789.88 | 0 | 0 | 0 | 80 | 80 | 7790.4 | 7790.4 | Building
859 | INDENT-66/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC MTA Brass Thread 2 1/2" | NOS | 10 | 910.26 | 9102.6 | 10 | 910.26 | 9102.6 | 0 | 910.26 | 0 | 10 | 910.25 | 9102.52 | 0 | 0 | 0 | 10 | 10 | 9102.6 | 9102.6 | Building
860 | INDENT-66/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Pipe 2 1/2" X 3m long (SCH-40) | NOS | 74 | 767 | 56758 | 74 | 767 | 56758 | 0 | 767 | 0 | 74 | 766.89 | 56750.1412 | 0 | 0 | 0 | 74 | 74 | 56758 | 56758 | Building
861 | INDENT-66/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Red/Coupling 2 1/2" x 2" | NOS | 12 | 51.92 | 623.04 | 12 | 51.92 | 623.04 | 0 | 51.92 | 0 | 12 | 56.79 | 681.5196 | 0 | 0 | 0 | 12 | 12 | 623.04 | 623.04 | Building
862 | INDENT-66/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Reducer Bushing 2" x 1 1/2" | NOS | 16 | 24.2 | 387.2 | 16 | 24.2 | 387.2 | 0 | 24.2 | 0 | 16 | 44.94 | 718.96 | 0 | 0 | 0 | 16 | 16 | 387.2 | 387.2 | Building
863 | INDENT-66/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Reducer Bushing 2" x 1 1/4" | NOS | 12 | 23.6 | 283.2 | 12 | 23.6 | 283.2 | 0 | 23.6 | 0 | 12 | 17.51 | 210.1404 | 0 | 0 | 0 | 12 | 12 | 283.2 | 283.2 | Building
864 | INDENT-66/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Reducer Bushing 2" x 1" | NOS | 10 | 22.42 | 224.2 | 10 | 22.42 | 224.2 | 0 | 22.42 | 0 | 10 | 20.41 | 204.14 | 0 | 0 | 0 | 10 | 10 | 224.2 | 224.2 | Building
865 | INDENT-66/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Reducer Coupling 2 1/2" x 1 1/4" | NOS | 4 | 49.56 | 198.24 | 4 | 49.56 | 198.24 | 0 | 49.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 198.24 | 198.24 | Building
866 | INDENT-66/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Reducer Tee 2 1/2" x 2" | NOS | 46 | 124.82 | 5741.72 | 46 | 124.82 | 5741.72 | 0 | 124.82 | 0 | 46 | 124.82 | 5741.7384 | 0 | 0 | 0 | 46 | 46 | 5741.72 | 5741.72 | Building
867 | INDENT-66/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Reducer Tee 2 1/2" x 1 1/2" | NOS | 16 | 124.84 | 1997.44 | 16 | 124.84 | 1997.44 | 0 | 124.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 16 | 1997.44 | 1997.44 | Building
868 | INDENT-66/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Reducer Tee 2 1/2" x 1 1/4" | NOS | 8 | 64.46 | 515.68 | 8 | 64.46 | 515.68 | 0 | 64.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 515.68 | 515.68 | Building
869 | INDENT-66/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Reducer Tee 2 1/2" x 1" | NOS | 10 | 62.06 | 620.6 | 10 | 62.06 | 620.6 | 0 | 62.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 620.6 | 620.6 | Building
870 | INDENT-66/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Tee 2 1/2" | NOS | 9 | 134.76 | 1212.84 | 9 | 134.76 | 1212.84 | 0 | 134.76 | 0 | 9 | 134.73 | 1212.5997 | 0 | 0 | 0 | 9 | 9 | 1212.84 | 1212.84 | Building
871 | INDENT-67/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Ball Valves 1 1/2" | NOS | 25 | 198.24 | 4956 | 25 | 198.24 | 4956 | 0 | 198.24 | 0 | 25 | 198.24 | 4956 | 0 | 0 | 0 | 25 | 25 | 4956 | 4956 | Building
872 | INDENT-67/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Coupler 1 1/2" | NOS | 10 | 19.56 | 195.6 | 10 | 19.56 | 195.6 | 0 | 19.56 | 0 | 10 | 19.56 | 195.64 | 0 | 0 | 0 | 10 | 10 | 195.6 | 195.6 | Building
873 | INDENT-67/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Coupler 2" | NOS | 45 | 27.66 | 1244.7 | 45 | 27.66 | 1244.7 | 0 | 27.66 | 0 | 45 | 31.55 | 1419.8985 | 0 | 0 | 0 | 45 | 45 | 1244.7 | 1244.7 | Building
874 | INDENT-67/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Elbow 1 1/2" (45 degree) Shoe | NOS | 10 | 26.08 | 260.8 | 10 | 26.08 | 260.8 | 0 | 26.08 | 0 | 10 | 26.03 | 260.3 | 0 | 0 | 0 | 10 | 10 | 260.8 | 260.8 | Building
875 | INDENT-67/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Elbow 1 1/2" (90 degree) | NOS | 50 | 35.36 | 1768 | 50 | 35.36 | 1768 | 0 | 35.36 | 0 | 50 | 31.81 | 1590.64 | 0 | 0 | 0 | 50 | 50 | 1768 | 1768 | Building
876 | INDENT-67/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Elbow 1 1/4 (90 degree) | NOS | 50 | 23.61 | 1180.5 | 50 | 23.61 | 1180.5 | 0 | 23.61 | 0 | 50 | 23.62 | 1181.18 | 0 | 0 | 0 | 50 | 50 | 1180.5 | 1180.5 | Building
877 | INDENT-67/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Elbow 2" (45 degree) Shoe | NOS | 10 | 41.46 | 414.6 | 10 | 41.46 | 414.6 | 0 | 41.46 | 0 | 10 | 41.47 | 414.66 | 0 | 0 | 0 | 10 | 10 | 414.6 | 414.6 | Building
878 | INDENT-67/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Elbow 2" (90 degree) | NOS | 80 | 59 | 4720 | 80 | 59 | 4720 | 0 | 59 | 0 | 80 | 51.38 | 4110.184 | 0 | 0 | 0 | 80 | 80 | 4720 | 4720 | Building
879 | INDENT-67/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Pipe 1 1/2" X 3m long (SCH-40) | NOS | 30 | 236 | 7080 | 30 | 236 | 7080 | 0 | 236 | 0 | 30 | 361.59 | 10847.619 | 0 | 0 | 0 | 30 | 30 | 7080 | 7080 | Building
880 | INDENT-67/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Pipe 2" X 3m long (SCH-40) | NOS | 60 | 485.88 | 29152.8 | 60 | 485.88 | 29152.8 | 0 | 485.88 | 0 | 60 | 485.89 | 29153.322 | 0 | 0 | 0 | 60 | 60 | 29152.8 | 29152.8 | Building
881 | INDENT-67/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Reducer Coupling 1 1/2" x 1 1/4" | NOS | 10 | 20.48 | 204.8 | 10 | 20.48 | 204.8 | 0 | 20.48 | 0 | 10 | 20.48 | 204.84 | 0 | 0 | 0 | 10 | 10 | 204.8 | 204.8 | Building
882 | INDENT-67/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Reducer Coupling 2" x 1 1/4" | NOS | 5 | 29.26 | 146.3 | 5 | 29.26 | 146.3 | 0 | 29.26 | 0 | 5 | 29.27 | 146.37 | 0 | 0 | 0 | 5 | 5 | 146.3 | 146.3 | Building
883 | INDENT-67/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Reducer Tee 1 1/2" x 1" | NOS | 10 | 43.84 | 438.4 | 10 | 43.84 | 438.4 | 0 | 43.84 | 0 | 10 | 43.85 | 438.48 | 0 | 0 | 0 | 10 | 10 | 438.4 | 438.4 | Building
884 | INDENT-67/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Reducer Tee 2" x 1 1/2" | NOS | 12 | 110.83 | 1329.96 | 12 | 110.83 | 1329.96 | 0 | 110.83 | 0 | 12 | 63.64 | 763.6404 | 0 | 0 | 0 | 12 | 12 | 1329.96 | 1329.96 | Building
885 | INDENT-67/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Reducer Tee 2" x 1 1/4" | NOS | 12 | 46 | 552 | 12 | 46 | 552 | 0 | 46 | 0 | 12 | 63.27 | 759.2604 | 0 | 0 | 0 | 12 | 12 | 552 | 552 | Building
886 | INDENT-67/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Reducer Tee 2" x 1" | NOS | 14 | 62.97 | 881.58 | 14 | 62.97 | 881.58 | 0 | 62.97 | 0 | 14 | 62.98 | 881.6794 | 0 | 0 | 0 | 14 | 14 | 881.58 | 881.58 | Building
887 | INDENT-67/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Tee 2" | NOS | 8 | 71.1 | 568.8 | 8 | 71.1 | 568.8 | 0 | 71.1 | 0 | 8 | 71.11 | 568.86 | 0 | 0 | 0 | 8 | 8 | 568.8 | 568.8 | Building
888 | INDENT-68/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)GI C-Bracket 12" x 3" | NOS | 70 | 62.13 | 4349.1 | 70 | 62.13 | 4349.1 | 0 | 62.13 | 0 | 70 | 62.13 | 4348.897 | 0 | 0 | 0 | 70 | 70 | 4349.1 | 4349.1 | Building
889 | INDENT-68/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)GI C-Bracket 4" x 3" | NOS | 40 | 39.43 | 1577.2 | 40 | 39.43 | 1577.2 | 0 | 39.43 | 0 | 40 | 39.42 | 1576.96 | 0 | 0 | 0 | 40 | 40 | 1577.2 | 1577.2 | Building
890 | INDENT-68/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)GI C-Bracket 6" x 3" | NOS | 125 | 44.2 | 5525 | 125 | 44.2 | 5525 | 0 | 44.2 | 0 | 125 | 44.2 | 5525.3625 | 0 | 0 | 0 | 125 | 125 | 5525 | 5525 | Building
891 | INDENT-68/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)GI U Clamp with Nut Bolt & Washer 2 1/2" | NOS | 80 | 19.58 | 1566.4 | 80 | 19.58 | 1566.4 | 0 | 19.58 | 0 | 80 | 15.93 | 1274.4 | 0 | 0 | 0 | 80 | 80 | 1566.4 | 1566.4 | Building
892 | INDENT-68/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)GI U Clamp with Nut Bolt & Washer 2" | NOS | 80 | 13.93 | 1114.4 | 80 | 13.93 | 1114.4 | 0 | 13.93 | 0 | 80 | 12.54 | 1003.48 | 0 | 0 | 0 | 80 | 80 | 1114.4 | 1114.4 | Building
893 | INDENT-68/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)GI U Clamp with Nut Bolt & Washer 3" | NOS | 50 | 17.7 | 885 | 50 | 17.7 | 885 | 0 | 17.7 | 0 | 50 | 17.52 | 876.16 | 0 | 0 | 0 | 50 | 50 | 885 | 885 | Building
894 | INDENT-68/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)GI U Clamp with Nut Bolt & Washer 4" | NOS | 50 | 19.12 | 956 | 50 | 19.12 | 956 | 0 | 19.12 | 0 | 50 | 19.12 | 955.8 | 0 | 0 | 0 | 50 | 50 | 956 | 956 | Building
895 | INDENT-68/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Ball Valves 1 1/4" | NOS | 50 | 140.76 | 7038 | 50 | 140.76 | 7038 | 0 | 140.76 | 0 | 50 | 140.75 | 7037.52 | 0 | 0 | 0 | 50 | 50 | 7038 | 7038 | Building
896 | INDENT-68/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Ball Valves 1" | NOS | 30 | 104.4 | 3132 | 30 | 104.4 | 3132 | 0 | 104.4 | 0 | 30 | 104.41 | 3132.201 | 0 | 0 | 0 | 30 | 30 | 3132 | 3132 | Building
897 | INDENT-68/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Elbow 1" (90 degree) | NOS | 30 | 15.2 | 456 | 30 | 15.2 | 456 | 0 | 15.2 | 0 | 30 | 15.2 | 455.961 | 0 | 0 | 0 | 30 | 30 | 456 | 456 | Building
898 | INDENT-68/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Pipe 1 1/4 X 3m long (SCH-40) | NOS | 10 | 465.33 | 4653.3 | 10 | 465.33 | 4653.3 | 0 | 465.33 | 0 | 10 | 303.51 | 3035.08 | 0 | 0 | 0 | 10 | 10 | 4653.3 | 4653.3 | Building
899 | INDENT-68/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Pipe 1" X 3m long (SCH-40) | NOS | 30 | 177 | 5310 | 30 | 177 | 5310 | 0 | 177 | 0 | 30 | 225.79 | 6773.799 | 0 | 0 | 0 | 30 | 30 | 5310 | 5310 | Building
900 | INDENT-68/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Pipe 3/4" X 3m long (SCH-40) | NOS | 10 | 147.5 | 1475 | 10 | 147.5 | 1475 | 0 | 147.5 | 0 | 10 | 154.13 | 1541.32 | 0 | 0 | 0 | 10 | 10 | 1475 | 1475 | Building
901 | INDENT-68/B BLDG/TOP TERR.LOOPING | 0 | Started | Material | (M)UPVC Reducer Tee 1 1/4" x 1" | NOS | 10 | 33.99 | 339.9 | 10 | 33.99 | 339.9 | 0 | 33.99 | 0 | 10 | 34 | 339.96 | 0 | 0 | 0 | 10 | 10 | 339.9 | 339.9 | Building
902 | B Bldg Toilet & Bathroom-1,2,3 Floor | 0 | Tentative | Labour | (L)Internal Concealed Work | NOS | 98906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98906 | 1 | 98906 | 0 | 0 | 0 | 98906 | 98906 | 0 | 0
903 | B Bldg Toilet & Bathroom-4,5,6 Floor | 0 | Tentative | Labour | (L)Internal Concealed Work | NOS | 98906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98906 | 1 | 98906 | 0 | 0 | 0 | 98906 | 98906 | 0 | 0
904 | B Bldg Toilet & Bathroom-7,8,9 Floor | 0 | Tentative | Labour | (L)Internal Concealed Work | NOS | 98906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98906 | 1 | 98906 | 0 | 0 | 0 | 98906 | 98906 | 0 | 0
905 | B Bldg Toilet & Bathroom-10,11,12 Floor | 0 | Tentative | Labour | (L)Internal Concealed Work | NOS | 98906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98906 | 1 | 98906 | 0 | 0 | 0 | 98906 | 98906 | 0 | 0
906 | B Bldg Pressure Testing & Levelling up to 12th | 0 | Tentative | Labour | (L)Internal Concealed Work | NOS | 39562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39562 | 1 | 39562 | 0 | 0 | 0 | 39562 | 39562 | 0 | 0
907 | B Bldg Kitchen Plumbing upto 12th Floor | 0 | Started | Labour | (L)Internal Concealed Work | NOS | 110776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110776 | 1 | 110776 | 0 | 0 | 0 | 110776 | 110776 | 0 | 0
908 | B Bldg P-Trap, N-Trap & Outlet upto 12th Floor | 0 | Tentative | Labour | (L)Internal Concealed Work | NOS | 79126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79126 | 1 | 79126 | 0 | 0 | 0 | 79126 | 79126 | 0 | 0
909 | B Bldg Duct F:01-05 Terr. line upto12th Floor | 0 | Tentative | Labour | (L)External Plumbing Work | NOS | 18990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18990 | 1 | 18990 | 0 | 0 | 0 | 18990 | 18990 | 0 | 0
910 | B Bldg Duct F:06-10 Terr. line upto12th Floor | 0 | Tentative | Labour | (L)External Plumbing Work | NOS | 18990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18990 | 1 | 18990 | 0 | 0 | 0 | 18990 | 18990 | 0 | 0
911 | B Bldg Duct F:01-05 Kitchen PVC,UPVC upto12th | 0 | Started | Labour | (L)External Plumbing Work | NOS | 31650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31650 | 1 | 31650 | 31650 | 1 | 31650 | 31650 | 0 | 0 | -31650
912 | B Bldg Duct F:06-10 Kitchen PVC,UPVC upto12th | 0 | Started | Labour | (L)External Plumbing Work | NOS | 31650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31650 | 1 | 31650 | 31650 | 1 | 31650 | 31650 | 0 | 0 | -31650
913 | B Bldg Duct F:01-05 Toilet PVC (CT,MT) upto12th | 0 | Started | Labour | (L)External Plumbing Work | NOS | 44310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44310 | 1 | 44310 | 44310 | 1 | 44310 | 44310 | 0 | 0 | -44310
914 | B Bldg Duct F:06-10 Toilet PVC (CT,MT) upto12th | 0 | Started | Labour | (L)External Plumbing Work | NOS | 44310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44310 | 1 | 44310 | 44310 | 1 | 44310 | 44310 | 0 | 0 | -44310
915 | B Bldg Duct F:01-05 Toilet UPVC-CT,MT upto12th | 0 | Started | Labour | (L)External Plumbing Work | NOS | 31650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31650 | 1 | 31650 | 31650 | 1 | 31650 | 31650 | 0 | 0 | -31650
916 | B Bldg Duct F:06-10 Toilet UPVC-CT,MT upto12th | 0 | Started | Labour | (L)External Plumbing Work | NOS | 31650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31650 | 1 | 31650 | 31650 | 1 | 31650 | 31650 | 0 | 0 | -31650
917 | B Bldg Duct Top Terrace Rainwater Lines Comp. | 0 | Started | Labour | (L)External Plumbing Work | NOS | 15825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15825 | 1 | 15825 | 15825 | 1 | 15825 | 15825 | 0 | 0 | -15825
918 | B Bldg All Duct Antisyphon Lines Comp. | 0 | Started | Labour | (L)External Plumbing Work | NOS | 18990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18990 | 1 | 18990 | 18990 | 1 | 18990 | 18990 | 0 | 0 | -18990
919 | B Bldg All Duct PRV Fixing Comp. | 0 | Started | Labour | (L)External Plumbing Work | NOS | 15825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15825 | 1 | 15825 | 15825 | 1 | 15825 | 15825 | 0 | 0 | -15825
920 | B Bldg All Duct Miscellaneous Work. | 0 | Started | Labour | (L)External Plumbing Work | NOS | 12660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12660 | 1 | 12660 | 12660 | 1 | 12660 | 12660 | 0 | 0 | -12660
921 | B Bldg "Looping" Top Terr-100% Comp. | 0 | Started | Labour | (L)External Plumbing Work | NOS | 63300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63300 | 1 | 63300 | 63300 | 1 | 63300 | 63300 | 0 | 0 | -63300
922 | B Bldg Sanitry-Orissa Pan upto 12th floor | 0 | Started | Labour | (L)Sanitry Work | NOS | 61719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61719 | 1 | 61719 | 61719 | 1 | 61719 | 61719 | 0 | 0 | -61719
923 | B Bldg Sanitry-Legde Wall, Ch.Bracket upto 12th | 0 | Started | Labour | (L)Sanitry Work | NOS | 45260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45260 | 1 | 45260 | 45260 | 1 | 45260 | 45260 | 0 | 0 | -45260
924 | B Bldg Sanitry-Commode & basin upto 12th floor | 0 | Started | Labour | (L)Sanitry Work | NOS | 98748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98748 | 1 | 98748 | 65832 | 1 | 65832 | 98748 | 32916 | 0 | -65832
925 | B Bldg CP-1,2,3,4th Floor | 0 | Tentative | Labour | (L)CP WORK | NOS | 51273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51273 | 1 | 51273 | 0 | 0 | 0 | 51273 | 51273 | 0 | 0
926 | B Bldg CP-5,6,7,8th Floor | 0 | Tentative | Labour | (L)CP WORK | NOS | 51273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51273 | 1 | 51273 | 0 | 0 | 0 | 51273 | 51273 | 0 | 0
927 | B Bldg CP-9,10,11,12th Floor | 0 | Tentative | Labour | (L)CP WORK | NOS | 51273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51273 | 1 | 51273 | 0 | 0 | 0 | 51273 | 51273 | 0 | 0
928 | B Bldg CP- Testing upto 12th Floor | 0 | Tentative | Labour | (L)CP WORK | NOS | 36081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36081 | 1 | 36081 | 0 | 0 | 0 | 36081 | 36081 | 0 | 0
929 | B Bldg "Parking" Drainage Line-100% Comp. | 0 | Started | Labour | (L)External Plumbing Work | NOS | 63300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63300 | 1 | 63300 | 31650 | 1 | 31650 | 63300 | 31650 | 0 | -31650
930 | B Bldg "Miscellaneous" after comp. of work | 0 | Tentative | Labour | (L)Miss. Work (Plumbing) | NOS | 15825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15825 | 1 | 15825 | 0 | 0 | 0 | 15825 | 15825 | 0 | 0
931 | B Bldg "Retention" after comp. of work | 0 | Tentative | Labour | (L)Retention (Plumbing) | NOS | 79125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79125 | 1 | 79125 | 0 | 0 | 0 | 79125 | 79125 | 0 | 0
932 | B Bldg "PF" to be Release after comp.of work | 0 | Tentative | Labour | (L)PF (Plumbing) | NOS | 23738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23738 | 1 | 23738 | 0 | 0 | 0 | 23738 | 23738 | 0 | 0
933 | B WING SOLAR SYSTEM PROVISION FOR 120 FLATS | 0 | Tentative | Material | (M)SOLAR SYSTEM-12000 LTR /DAY | SET | 1 | 118000 | 118000 | 1 | 118000 | 118000 | 0 | 118000 | 0 | 1 | 1034880 | 1034880 | 0 | 0 | 0 | 1 | 1 | 118000 | 118000
934 | B WING GARBAGE SYSTEM PROVISION FOR 120 FLATS | 0 | Tentative | Material | (M)Garbage Chute System with Installation | NOS | 1 | 672000 | 672000 | 1 | 672000 | 672000 | 0 | 672000 | 0 | 1 | 233200 | 233200 | 0 | 0 | 0 | 1 | 1 | 672000 | 672000
935 | INDENT-583/B BLDG/DOOR FRAME | 0 | Started | Material | (M)BEDROOM DOOR FRAME (Redmaranty Wood) - 0.9M X 2.25M | SET | 286 | 3550 | 1015300 | 286 | 3550 | 1015300 | 0 | 3550 | 0 | 286 | 4298.51 | 1229373.86 | 0 | 0 | 0 | 286 | 286 | 1015300 | 1015300 | Building
936 | INDENT-583/B BLDG/DOOR FRAME | 0 | Started | Material | (M)MAIN DOOR FRAME (Redmaranty Wood) - 1.05M X 2.25M | SET | 120 | 4700 | 564000 | 120 | 4700 | 564000 | 0 | 4700 | 0 | 120 | 5690.99 | 682918.8 | 0 | 0 | 0 | 120 | 120 | 564000 | 564000 | Building
937 | WOODEN DOOR SHUTTER INDENT-986/B WING/DOOR SHUTTER | 10 | Started | Material | (M)BEDROOM DOOR-32MM THK | NOS | 286 | 5175 | 1480050 | 286 | 5175 | 1480050 | 29 | 5175 | 150075 | 286 | 4680.88 | 1338732.538 | 0 | 0 | 0 | 257 | 286 | 1329975 | 1480050
938 | WOODEN DOOR SHUTTER INDENT-986/B WING/DOOR SHUTTER | 10 | Started | Material | (M)MAIN DOOR-35MM THK | NOS | 120 | 6130 | 735600 | 120 | 6130 | 735600 | 12 | 6130 | 73560 | 120 | 5500.62 | 660074.064 | 0 | 0 | 0 | 108 | 120 | 662040 | 735600
939 | WOODEN DOOR SHUTTER INDENT-986/B WING/DOOR SHUTTER | 10 | Started | Material | (M)TOILET DOOR-32MM THK | NOS | 262 | 7729 | 2024998 | 262 | 7729 | 2024998 | 26 | 7729 | 200954 | 262 | 4261 | 1116382.9432 | 0 | 0 | 0 | 236 | 262 | 1824044 | 2024998
940 | INDENT-46/B WING/MAIN DOOR FITTING-120 FLAT | 10 | Started | Material | (M)Magnetic Door Catcher-3'' | NOS | 120 | 59 | 7080 | 120 | 59 | 7080 | 12 | 59 | 708 | 120 | 47.2 | 5664 | 0 | 0 | 0 | 108 | 120 | 6372 | 7080
941 | INDENT-46/B WING/MAIN DOOR FITTING-120 FLAT | 10 | Started | Material | (M)Mortise Lock with Key | NOS | 120 | 2065 | 247800 | 120 | 2065 | 247800 | 12 | 2065 | 24780 | 120 | 1829 | 219480 | 0 | 0 | 0 | 108 | 120 | 223020 | 247800
942 | INDENT-46/B WING/MAIN DOOR FITTING-120 FLAT | 10 | Started | Material | (M)Screw 8 x 25mm | NOS | 2900 | 1.18 | 3422 | 2900 | 1.18 | 3422 | 290 | 1.18 | 342.2 | 2900 | 0.87 | 2513.14 | 0 | 0 | 0 | 2610 | 2900 | 3079.8 | 3422
943 | INDENT-46/B WING/MAIN DOOR FITTING-120 FLAT | 10 | Started | Material | (M)SS Aldrop-10'' | NOS | 120 | 236 | 28320 | 120 | 236 | 28320 | 12 | 236 | 2832 | 120 | 336.3 | 40356 | 0 | 0 | 0 | 108 | 120 | 25488 | 28320
944 | INDENT-46/B WING/MAIN DOOR FITTING-120 FLAT | 10 | Started | Material | (M)SS Hinges - 5" | NOS | 480 | 100.3 | 48144 | 480 | 100.3 | 48144 | 48 | 100.3 | 4814.4 | 480 | 80.24 | 38515.2 | 0 | 0 | 0 | 432 | 480 | 43329.6 | 48144
945 | INDENT-46/B WING/MAIN DOOR FITTING-120 FLAT | 10 | Started | Material | (M)SS Screw 8 x 32mm Full thread | NOS | 4400 | 2.07 | 9108 | 4400 | 2.07 | 9108 | 440 | 2.07 | 910.8 | 4400 | 1.33 | 5841 | 0 | 0 | 0 | 3960 | 4400 | 8197.2 | 9108
946 | INDENT-46/B WING/MAIN DOOR FITTING-120 FLAT | 10 | Started | Material | (M)SS Tadi Patti-8'' | NOS | 120 | 88.5 | 10620 | 120 | 88.5 | 10620 | 12 | 88.5 | 1062 | 120 | 106.2 | 12744 | 0 | 0 | 0 | 108 | 120 | 9558 | 10620
947 | INDENT-46/B WING/MAIN DOOR FITTING-120 FLAT | 10 | Started | Material | (M)SS Tower Bolt-10" | NOS | 120 | 236 | 28320 | 120 | 236 | 28320 | 12 | 236 | 2832 | 120 | 148.68 | 17841.6 | 0 | 0 | 0 | 108 | 120 | 25488 | 28320
948 | INDENT-46 & 47/B WING/BED ROOM DOOR FITTING | 10 | Started | Material | (M)Cylinderical Lock with Key-Bedroom | NOS | 286 | 1888 | 539968 | 286 | 1888 | 539968 | 29 | 1888 | 54752 | 286 | 586.22 | 167660.064 | 0 | 0 | 0 | 257 | 286 | 485216 | 539968
949 | INDENT-46 & 47/B WING/BED ROOM DOOR FITTING | 10 | Started | Material | (M)Magnetic Door Catcher-3'' | NOS | 286 | 59 | 16874 | 286 | 59 | 16874 | 29 | 59 | 1711 | 286 | 47.2 | 13499.2 | 0 | 0 | 0 | 257 | 286 | 15163 | 16874
950 | INDENT-46 & 47/B WING/BED ROOM DOOR FITTING | 10 | Started | Material | (M)Screw 8 x 25mm | NOS | 5750 | 1.18 | 6785 | 5750 | 1.18 | 6785 | 575 | 1.18 | 678.5 | 5750 | 0.87 | 5026.075 | 0 | 0 | 0 | 5175 | 5750 | 6106.5 | 6785
951 | INDENT-46 & 47/B WING/BED ROOM DOOR FITTING | 10 | Started | Material | (M)SS Hinges - 4" | NOS | 1144 | 100.3 | 114743.2 | 1144 | 100.3 | 114743.2 | 114 | 100.3 | 11434.2 | 1144 | 70.8 | 80995.2 | 0 | 0 | 0 | 1030 | 1144 | 103309 | 114743.2
952 | INDENT-46 & 47/B WING/BED ROOM DOOR FITTING | 10 | Started | Material | (M)SS Screw 8 x 32mm Full thread | NOS | 10300 | 2.07 | 21321 | 10300 | 2.07 | 21321 | 1030 | 2.07 | 2132.1 | 10300 | 1.32 | 13627.93 | 0 | 0 | 0 | 9270 | 10300 | 19188.9 | 21321
953 | INDENT-46 & 47/B WING/BED ROOM DOOR FITTING | 10 | Started | Material | (M)SS Tower Bolt-10" | NOS | 286 | 236 | 67496 | 286 | 236 | 67496 | 29 | 236 | 6844 | 286 | 148.68 | 42522.48 | 0 | 0 | 0 | 257 | 286 | 60652 | 67496
954 | INDENT-47/B WING/TOILET DOOR FITTING WORK | 10 | Started | Material | (M)Cylindrical Lock without Key-Toilet | NOS | 262 | 1947 | 510114 | 262 | 1947 | 510114 | 26 | 1947 | 50622 | 262 | 529.58 | 138751.008 | 0 | 0 | 0 | 236 | 262 | 459492 | 510114
955 | INDENT-47/B WING/TOILET DOOR FITTING WORK | 10 | Started | Material | (M)Nylon Buffer-3'' | NOS | 262 | 17.7 | 4637.4 | 262 | 17.7 | 4637.4 | 26 | 17.7 | 460.2 | 262 | 17.7 | 4637.4 | 0 | 0 | 0 | 236 | 262 | 4177.2 | 4637.4
956 | INDENT-47/B WING/TOILET DOOR FITTING WORK | 10 | Started | Material | (M)Raval Plug | NOS | 4250 | 1.18 | 5015 | 4250 | 1.18 | 5015 | 425 | 1.18 | 501.5 | 4250 | 0.59 | 2507.5 | 0 | 0 | 0 | 3825 | 4250 | 4513.5 | 5015
957 | INDENT-47/B WING/TOILET DOOR FITTING WORK | 10 | Started | Material | (M)Screw 8 x 25mm | NOS | 3200 | 1.18 | 3776 | 3200 | 1.18 | 3776 | 320 | 1.18 | 377.6 | 3200 | 0.87 | 2773.12 | 0 | 0 | 0 | 2880 | 3200 | 3398.4 | 3776
958 | INDENT-47/B WING/TOILET DOOR FITTING WORK | 10 | Started | Material | (M)SS Hinges - 4" | NOS | 786 | 100.3 | 78835.8 | 786 | 100.3 | 78835.8 | 79 | 100.3 | 7923.7 | 786 | 68.44 | 53793.84 | 0 | 0 | 0 | 707 | 786 | 70912.1 | 78835.8
959 | INDENT-47/B WING/TOILET DOOR FITTING WORK | 10 | Started | Material | (M)SS Screw 8 x 32mm Full thread | NOS | 9450 | 2.07 | 19561.5 | 9450 | 2.07 | 19561.5 | 945 | 2.07 | 1956.15 | 9450 | 1.33 | 12544.875 | 0 | 0 | 0 | 8505 | 9450 | 17605.35 | 19561.5
960 | INDENT-47/B WING/TOILET DOOR FITTING WORK | 10 | Started | Material | (M)Tower Bolt - SS 4" | NOS | 262 | 59 | 15458 | 262 | 59 | 15458 | 26 | 59 | 1534 | 262 | 56.64 | 14839.68 | 0 | 0 | 0 | 236 | 262 | 13924 | 15458
961 | B BLDG WOODEN DOOR MATERIAL -MISC. MATERIAL | 10 | Started | Material | (M)BLACK JAPAN-LIQUID | LTR | 40 | 200 | 8000 | 40 | 200 | 8000 | 4 | 200 | 800 | 40 | 141.6 | 5664 | 0 | 0 | 0 | 36 | 40 | 7200 | 8000
962 | B BLDG WOODEN DOOR MATERIAL -MISC. MATERIAL | 10 | Started | Material | (M)PU FOAM-750 ML | NOS | 36 | 708 | 25488 | 36 | 708 | 25488 | 4 | 708 | 2832 | 36 | 678.5 | 24426 | 0 | 0 | 0 | 32 | 36 | 22656 | 25488
963 | B BLDG WOODEN DOOR MATERIAL -MISC. MATERIAL | 10 | Started | Material | (M)THINNER-LIQUID | LTR | 20 | 190 | 3800 | 20 | 190 | 3800 | 2 | 190 | 380 | 20 | 118 | 2360 | 0 | 0 | 0 | 18 | 20 | 3420 | 3800
964 | B BLDG (F6-10) MAIN DOOR FIXING-SHUTTER 1ST TO 12TH FLOOR | 0 | Started | Labour | (L)Main Door Shutter Fixing Work | NOS | 12 | 1 | 12 | 0 | 0 | 0 | 0 | 1 | 0 | 12 | 2900.36 | 34804.32 | 12 | 2900.36 | 34804.32 | 12 | 0 | 12 | -34792.32
965 | B BLDG (F6-10) MAIN DOOR FIXING-ACCESSORIES FIXING 1ST TO 1 | 0 | Tentative | Labour | (L)Main Door Shutter Fixing Work | NOS | 12 | 1 | 12 | 0 | 0 | 0 | 0 | 1 | 0 | 12 | 2175.27 | 26103.24 | 0 | 0 | 0 | 12 | 12 | 12 | 12
966 | B BLDG (F6-10) MAIN DOOR FIXING-MOULDING PATTI FIXING 1ST T | 0 | Tentative | Labour | (L)Main Door Shutter Fixing Work | NOS | 12 | 1 | 12 | 0 | 0 | 0 | 0 | 1 | 0 | 12 | 2175.27 | 26103.24 | 0 | 0 | 0 | 12 | 12 | 12 | 12
967 | B BLDG (F6-10) BEDROOM DOOR FIXING-SHUTTER 1ST TO 12TH FLOOR | 0 | Started | Labour | (L)Bed Door Shutter Fixing Work | NOS | 12 | 700 | 8400 | 0 | 0 | 0 | 0 | 700 | 0 | 12 | 3262.91 | 39154.86 | 12 | 3262.91 | 39154.86 | 12 | 0 | 8400 | -30754.86
968 | B BLDG (F6-10) BEDROOM DOOR FIXING-ACCESSORIES FIXING 1ST T | 0 | Tentative | Labour | (L)Bed Door Shutter Fixing Work | NOS | 12 | 700 | 8400 | 0 | 0 | 0 | 0 | 700 | 0 | 12 | 1087.64 | 13051.62 | 0 | 0 | 0 | 12 | 12 | 8400 | 8400
969 | B BLDG (F6-10) BEDROOM DOOR FIXING-MOULDING PATTI FIXING 1S | 0 | Tentative | Labour | (L)Bed Door Shutter Fixing Work | NOS | 12 | 700 | 8400 | 0 | 0 | 0 | 0 | 700 | 0 | 12 | 1087.64 | 13051.62 | 0 | 0 | 0 | 12 | 12 | 8400 | 8400
970 | B BLDG (F6-10) TOILET DOOR FIXING-SHUTTER 1ST TO 12TH FLOOR | 0 | Started | Labour | (L)Toilet Door Shutter Fixing Work | NOS | 12 | 550 | 6600 | 0 | 0 | 0 | 0 | 550 | 0 | 12 | 3262.91 | 39154.86 | 12 | 3262.91 | 39154.86 | 12 | 0 | 6600 | -32554.86
971 | B BLDG (F6-10) TOILET DOOR FIXING-ACCESSORIES FIXING 1ST TO | 0 | Tentative | Labour | (L)Toilet Door Shutter Fixing Work | NOS | 12 | 550 | 6600 | 0 | 0 | 0 | 0 | 550 | 0 | 12 | 1087.64 | 13051.62 | 0 | 0 | 0 | 12 | 12 | 6600 | 6600
972 | B BLDG (F6-10) TOILET DOOR FIXING-MOULDING PATTI FIXING 1ST | 0 | Tentative | Labour | (L)Toilet Door Shutter Fixing Work | NOS | 12 | 550 | 6600 | 0 | 0 | 0 | 0 | 550 | 0 | 12 | 1087.64 | 13051.62 | 0 | 0 | 0 | 12 | 12 | 6600 | 6600
973 | B BLDG (F6-10) WOODE DOOR SHUTTER-CLEANING,MISC. WORK | 0 | Tentative | Labour | (L)CLEANING,MISC. WORK-(DOOR & SHUTTERS) | NOS | 1 | 4678 | 4678 | 0 | 0 | 0 | 0 | 4678 | 0 | 1 | 4678 | 4678 | 0 | 0 | 0 | 1 | 1 | 4678 | 4678
974 | B BLDG (F6-10) WOODE DOOR SHUTTER-RETENTION | 0 | Tentative | Labour | (L)RETENTION-LABOUR (DOOR SHUTTER) | NOS | 1 | 11695 | 11695 | 0 | 0 | 0 | 0 | 11695 | 0 | 1 | 11695 | 11695 | 0 | 0 | 0 | 1 | 1 | 11695 | 11695
975 | B BLDG MOULDING TEAK WOOD PATTI- UPTO 12TH FLOOR | 0 | Tentative | Material | (M)Fevicol | KG | 15 | 247.8 | 3717 | 15 | 247.8 | 3717 | 0 | 247.8 | 0 | 15 | 241.9 | 3628.5 | 0 | 0 | 0 | 15 | 15 | 3717 | 3717
976 | B BLDG MOULDING TEAK WOOD PATTI- UPTO 12TH FLOOR | 0 | Tentative | Material | (M)Moulding Patti-3'6'' x 1'' x 1/4'' (Teak wood patti) | NOS | 24 | 17.7 | 424.8 | 24 | 17.7 | 424.8 | 0 | 17.7 | 0 | 24 | 77 | 1847.88 | 0 | 0 | 0 | 24 | 24 | 424.8 | 424.8
977 | B BLDG MOULDING TEAK WOOD PATTI- UPTO 12TH FLOOR | 0 | Tentative | Material | (M)Moulding Patti-3'6'' x 2'' x 1/4'' (Teak wood patti) | NOS | 270 | 23.6 | 6372 | 270 | 23.6 | 6372 | 0 | 23.6 | 0 | 270 | 106.2 | 28674 | 0 | 0 | 0 | 270 | 270 | 6372 | 6372
978 | B BLDG MOULDING TEAK WOOD PATTI- UPTO 12TH FLOOR | 0 | Tentative | Material | (M)Moulding Patti-4'0'' x 1'' x 1/4'' (Teak wood patti) | NOS | 120 | 21.24 | 2548.8 | 120 | 21.24 | 2548.8 | 0 | 21.24 | 0 | 120 | 84.96 | 10195.2 | 0 | 0 | 0 | 120 | 120 | 2548.8 | 2548.8
979 | B BLDG MOULDING TEAK WOOD PATTI- UPTO 12TH FLOOR | 0 | Tentative | Material | (M)Moulding Patti-4'0'' x 2'' x 1/4'' (Teak wood patti) | NOS | 120 | 25.96 | 3115.2 | 120 | 25.96 | 3115.2 | 0 | 25.96 | 0 | 120 | 118 | 14160 | 0 | 0 | 0 | 120 | 120 | 3115.2 | 3115.2
980 | B BLDG MOULDING TEAK WOOD PATTI- UPTO 12TH FLOOR | 0 | Tentative | Material | (M)Moulding Patti-7'9'' x 1'' x 1/4'' (Teak wood patti) | NOS | 460 | 29.5 | 13570 | 460 | 29.5 | 13570 | 0 | 29.5 | 0 | 460 | 167.8 | 77186.16 | 0 | 0 | 0 | 460 | 460 | 13570 | 13570
981 | B BLDG MOULDING TEAK WOOD PATTI- UPTO 12TH FLOOR | 0 | Tentative | Material | (M)Moulding Patti-7'9'' x 2'' x 1/4'' (Teak wood patti) | NOS | 600 | 47.2 | 28320 | 600 | 47.2 | 28320 | 0 | 47.2 | 0 | 600 | 233.05 | 139830 | 0 | 0 | 0 | 600 | 600 | 28320 | 28320
982 | B BLDG MOULDING TEAK WOOD PATTI- UPTO 12TH FLOOR | 0 | Tentative | Material | (M)Nails 17 no x 1 1/4" | KG | 10 | 330.4 | 3304 | 10 | 330.4 | 3304 | 0 | 330.4 | 0 | 10 | 160.48 | 1604.8 | 0 | 0 | 0 | 10 | 10 | 3304 | 3304
983 | B BLDG (F01-05) MAIN DOOR FIXING-SHUTTER 1ST TO 12TH FLOOR | 0 | Started | Labour | (L)Main Door Shutter Fixing Work | NOS | 12 | 1 | 12 | 0 | 0 | 0 | 0 | 1 | 0 | 12 | 2559.36 | 30712.32 | 8 | 2559.36 | 20474.88 | 12 | 4 | 12 | -20462.88
984 | B BLDG (F01-05) MAIN DOOR FIXING-ACCESSORIES FIXING 1ST-12T | 0 | Tentative | Labour | (L)Main Door Shutter Fixing Work | NOS | 12 | 1 | 12 | 0 | 0 | 0 | 0 | 1 | 0 | 12 | 1919.52 | 23034.24 | 0 | 0 | 0 | 12 | 12 | 12 | 12
985 | B BLDG (F01-05) MAIN DOOR FIXING-MOULD. PATTI FIXING 1ST-12 | 0 | Tentative | Labour | (L)Main Door Shutter Fixing Work | NOS | 12 | 1 | 12 | 0 | 0 | 0 | 0 | 1 | 0 | 12 | 1919.52 | 23034.24 | 0 | 0 | 0 | 12 | 12 | 12 | 12
986 | B BLDG (F01-05) BED DOOR FIXING-SHUTTER 1ST - 12TH FLOOR | 0 | Started | Labour | (L)Bed Door Shutter Fixing Work | NOS | 12 | 700 | 8400 | 0 | 0 | 0 | 0 | 700 | 0 | 12 | 2879.28 | 34551.36 | 8 | 2879.28 | 23034.24 | 12 | 4 | 8400 | -14634.24
987 | B BLDG (F01-05) BED DOOR FIXING-ACCESS. FIXING 1ST-12TH | 0 | Tentative | Labour | (L)Bed Door Shutter Fixing Work | NOS | 12 | 700 | 8400 | 0 | 0 | 0 | 0 | 700 | 0 | 12 | 959.76 | 11517.12 | 0 | 0 | 0 | 12 | 12 | 8400 | 8400
988 | B BLDG (F01-05) BED DOOR FIXING-MOUL. PATTI FIXING 1ST-12TH | 0 | Tentative | Labour | (L)Bed Door Shutter Fixing Work | NOS | 12 | 700 | 8400 | 0 | 0 | 0 | 0 | 700 | 0 | 12 | 959.76 | 11517.12 | 0 | 0 | 0 | 12 | 12 | 8400 | 8400
989 | B BLDG (F01-05) TOILET DOOR FIXING-SHUTTER 1ST-12TH FLOOR | 0 | Started | Labour | (L)Toilet Door Shutter Fixing Work | NOS | 12 | 550 | 6600 | 0 | 0 | 0 | 0 | 550 | 0 | 12 | 2879.28 | 34551.36 | 8 | 2879.28 | 23034.24 | 12 | 4 | 6600 | -16434.24
990 | B BLDG (F01-05) TOILET DOOR FIXING-ACCESS. FIXING 1ST-12TH | 0 | Tentative | Labour | (L)Toilet Door Shutter Fixing Work | NOS | 12 | 550 | 6600 | 0 | 0 | 0 | 0 | 550 | 0 | 12 | 959.76 | 11517.12 | 0 | 0 | 0 | 12 | 12 | 6600 | 6600
991 | B BLDG (F01-05) TOILET DOOR FIXING-MOULD. PATTI FIXING 1ST- | 0 | Tentative | Labour | (L)Toilet Door Shutter Fixing Work | NOS | 12 | 550 | 6600 | 0 | 0 | 0 | 0 | 550 | 0 | 12 | 959.76 | 11517.12 | 0 | 0 | 0 | 12 | 12 | 6600 | 6600
992 | B BLDG (F01-05) WOODE DOOR SHUTTER-CLEANING,MISC. WORK | 0 | Tentative | Labour | (L)CLEANING,MISC. WORK-(DOOR & SHUTTERS) | NOS | 1 | 4678 | 4678 | 0 | 0 | 0 | 0 | 4678 | 0 | 1 | 4128 | 4128 | 0 | 0 | 0 | 1 | 1 | 4678 | 4678
993 | B BLDG (F01-05) WOODE DOOR SHUTTER-RETENTION | 0 | Tentative | Labour | (L)RETENTION-LABOUR (DOOR SHUTTER) | NOS | 1 | 11695 | 11695 | 0 | 0 | 0 | 0 | 11695 | 0 | 1 | 10320 | 10320 | 0 | 0 | 0 | 1 | 1 | 11695 | 11695
994 | GYPSUM 2ND CLASS GYPSUM 2ND CLASS-TILE PROTECTION LAYER | 10 | Started | Material | (M)GYPSUM 2ND CLASS-20KG/BAG | BAG | 1080 | 250 | 270000 | 1080 | 250 | 270000 | 108 | 250 | 27000 | 1080 | 135.03 | 145832.4 | 0 | 0 | 0 | 972 | 1080 | 243000 | 270000
995 | B BLDG ACID WASH MATERIAL (INCL.FLAT,PASSAGE & ST-CASE) | 0 | Started | Material | (M)MULTI CLEAN (PERMA) 25LTR/BUCKET | BUCKET | 60 | 4720 | 283200 | 24 | 4720 | 113280 | 0 | 4720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 60 | 283200 | 283200
996 | TILE & STONE WORK INDENT-981/B WING PASSAGE LOBBY TILING | 10 | Started | Material | (M)CEMENT PPC 50KG | BAG | 485 | 320 | 155200 | 485 | 320 | 155200 | 49 | 320 | 15680 | 0 | 0 | 0 | 0 | 0 | 0 | 436 | 485 | 139520 | 155200
997 | TILE & STONE WORK INDENT-981/B WING PASSAGE LOBBY TILING | 10 | Started | Material | (M)Crush Sand | BRASS | 20.5 | 3675 | 75337.5 | 20.5 | 3675 | 75337.5 | 2 | 3675 | 7350 | 20.5 | 3570 | 73185 | 0 | 0 | 0 | 18.5 | 20.5 | 67987.5 | 75337.5
998 | TILE & STONE WORK INDENT-981/B WING PASSAGE LOBBY TILING | 10 | Started | Material | (M)DUNKAN WHITE-600X600 (4 TILE/BOX or 15.5 SQFT) | BOX | 1045 | 604 | 631180 | 1045 | 604 | 631180 | 105 | 604 | 63420 | 1045 | 603.99 | 631174.566 | 0 | 0 | 0 | 940 | 1045 | 567760 | 631180
999 | TILE & STONE WORK INDENT-981/B WING PASSAGE LOBBY TILING | 10 | Started | Material | (M)Metal No.I 6mm (Grit) | BRASS | 20.5 | 3000 | 61500 | 20.5 | 3000 | 61500 | 2 | 3000 | 6000 | 20.5 | 3675 | 75337.5 | 0 | 0 | 0 | 18.5 | 20.5 | 55500 | 61500
1000 | TILE & STONE WORK INDENT-21/B WING/KITCHEN OTTA TOP | 10 | Started | Material | (M)NEW TEL.BLACK GRANITE-SP 79'' X 29'' | SQFT | 17 | 140 | 2380 | 17 | 140 | 2380 | 2 | 140 | 280 | 17 | 187.89 | 3194.13 | 0 | 0 | 0 | 15 | 17 | 2100 | 2380
1001 | TILE & STONE WORK INDENT-21/B WING/KITCHEN OTTA TOP | 10 | Started | Material | (M)NEW TEL.BLACK GRANITE-SP 84'' X 29'' | SQFT | 35 | 140 | 4900 | 35 | 140 | 4900 | 4 | 140 | 560 | 35 | 187.89 | 6576.15 | 0 | 0 | 0 | 31 | 35 | 4340 | 4900
1002 | TILE & STONE WORK INDENT-565/B WING KITCHEN OTTA-GRANITE | 10 | Started | Material | (M)CEMENT PPC 50KG | BAG | 103 | 320 | 32960 | 103 | 320 | 32960 | 10 | 320 | 3200 | 103 | 300.01 | 30900.6592 | 0 | 0 | 0 | 93 | 103 | 29760 | 32960
1003 | TILE & STONE WORK INDENT-565/B WING KITCHEN OTTA-GRANITE | 10 | Started | Material | (M)Crush Sand | BRASS | 3 | 3675 | 11025 | 3 | 3675 | 11025 | 0 | 3675 | 0 | 3 | 3675 | 11025 | 0 | 0 | 0 | 3 | 3 | 11025 | 11025
1004 | TILE & STONE WORK INDENT-565/B WING KITCHEN OTTA-GRANITE | 10 | Started | Material | (M)Epoxy Resin Adhesive Araldite 1.8 kg | (1+0.8) KG/SET | 20 | 800 | 16000 | 20 | 800 | 16000 | 2 | 800 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 20 | 14400 | 16000
1005 | TILE & STONE WORK INDENT-565/B WING KITCHEN OTTA-GRANITE | 10 | Started | Material | (M)Metal No.I 6mm (Grit) | BRASS | 4 | 3000 | 12000 | 4 | 3000 | 12000 | 0 | 3000 | 0 | 4 | 3360 | 13440 | 0 | 0 | 0 | 4 | 4 | 12000 | 12000
1006 | TILE & STONE WORK INDENT-565/B WING KITCHEN OTTA-GRANITE | 10 | Started | Material | (M)MYK Laticrete Grout 500 series | KG | 25 | 150 | 3750 | 25 | 150 | 3750 | 3 | 150 | 450 | 25 | 65 | 1624.9975 | 0 | 0 | 0 | 22 | 25 | 3300 | 3750
1007 | TILE & STONE WORK INDENT-565/B WING KITCHEN OTTA-GRANITE | 10 | Started | Material | (M)NEW TEL.BLACK GRANITE-SP 104'' X 29'' | SQFT | 262.5 | 140 | 36750 | 262.5 | 140 | 36750 | 26 | 140 | 3640 | 0 | 0 | 0 | 0 | 0 | 0 | 236.5 | 262.5 | 33110 | 36750
1008 | TILE & STONE WORK INDENT-565/B WING KITCHEN OTTA-GRANITE | 10 | Started | Material | (M)NEW TEL.BLACK GRANITE-SP 30'' X 29'' | SQFT | 75 | 140 | 10500 | 75 | 140 | 10500 | 8 | 140 | 1120 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 75 | 9380 | 10500
1009 | TILE & STONE WORK INDENT-565/B WING KITCHEN OTTA-GRANITE | 10 | Started | Material | (M)NEW TEL.BLACK GRANITE-SP 46'' X 29'' | SQFT | 120 | 140 | 16800 | 120 | 140 | 16800 | 12 | 140 | 1680 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 120 | 15120 | 16800
1010 | TILE & STONE WORK INDENT-565/B WING KITCHEN OTTA-GRANITE | 10 | Started | Material | (M)NEW TEL.BLACK GRANITE-SP 48'' X 29'' | SQFT | 1200 | 140 | 168000 | 1200 | 140 | 168000 | 120 | 140 | 16800 | 0 | 0 | 0 | 0 | 0 | 0 | 1080 | 1200 | 151200 | 168000
1011 | TILE & STONE WORK INDENT-565/B WING KITCHEN OTTA-GRANITE | 10 | Started | Material | (M)NEW TEL.BLACK GRANITE-SP 60'' X 29'' | SQFT | 1350 | 140 | 189000 | 1350 | 140 | 189000 | 135 | 140 | 18900 | 0 | 0 | 0 | 0 | 0 | 0 | 1215 | 1350 | 170100 | 189000
1012 | TILE & STONE WORK INDENT-565/B WING KITCHEN OTTA-GRANITE | 10 | Started | Material | (M)NEW TEL.BLACK GRANITE-SP 79'' X 29'' | SQFT | 1418 | 140 | 198520 | 1418 | 140 | 198520 | 142 | 140 | 19880 | 0 | 0 | 0 | 0 | 0 | 0 | 1276 | 1418 | 178640 | 198520
1013 | TILE & STONE WORK INDENT-565/B WING KITCHEN OTTA-GRANITE | 10 | Started | Material | (M)NEW TEL.BLACK GRANITE-SP 84'' X 29'' | SQFT | 420 | 140 | 58800 | 420 | 140 | 58800 | 42 | 140 | 5880 | 52.5 | 187.68 | 9853.2 | 0 | 0 | 0 | 378 | 420 | 52920 | 58800
1014 | TILE & STONE WORK INDENT-565/B WING KITCHEN OTTA-GRANITE | 10 | Started | Material | (M)SS Kitchen Sink with Coupling 22" X 18" | NOS | 120 | 4130 | 495600 | 120 | 4130 | 495600 | 12 | 4130 | 49560 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 120 | 446040 | 495600
1015 | TILE & STONE WORK INDENT-480/413/B BLDG TILING & STONE WORK | 0 | Started | Material | (M)CEMENT PPC 50KG | BAG | 5283 | 320 | 1690560 | 5283 | 320 | 1690560 | 0 | 320 | 0 | 3200 | 304.75 | 975202.35 | 65 | 304.61 | 19799.49 | 5283 | 5218 | 1690560 | 1670760.51
1016 | TILE & STONE WORK INDENT-480/413/B BLDG TILING & STONE WORK | 0 | Started | Material | (M)Crush Sand | BRASS | 94 | 3675 | 345450 | 94 | 3675 | 345450 | 0 | 3675 | 0 | 94 | 3675 | 345450 | 0 | 0 | 0 | 94 | 94 | 345450 | 345450
1017 | TILE & STONE WORK INDENT-480/413/B BLDG TILING & STONE WORK | 0 | Started | Material | (M)GRANITE Steel Gray 16-18mm Thk | SQFT | 1694 | 88.5 | 149919 | 1694 | 88.5 | 149919 | 0 | 88.5 | 0 | 1694 | 88.23 | 149461.62 | 0 | 0 | 0 | 1694 | 1694 | 149919 | 149919
1018 | TILE & STONE WORK INDENT-480/413/B BLDG TILING & STONE WORK | 0 | Started | Material | (M)Metal No.I 6mm (Grit) | BRASS | 141 | 3000 | 423000 | 141 | 3000 | 423000 | 0 | 3000 | 0 | 141 | 3675 | 518175 | 0 | 0 | 0 | 141 | 141 | 423000 | 423000
1019 | TILE & STONE WORK INDENT-568/B BLDG/TILE GROUT | 0 | Started | Material | (M)Epoxy Resin Adhesive Araldite 1.8 kg | (1+0.8) KG/SET | 8 | 800 | 6400 | 8 | 800 | 6400 | 0 | 800 | 0 | 8 | 1380 | 11039.992 | 0 | 0 | 0 | 8 | 8 | 6400 | 6400 | Building
1020 | TILE & STONE WORK INDENT-568/B BLDG/TILE GROUT | 0 | Started | Material | (M)SPACER 3MM | PACKET | 120 | 17.7 | 2124 | 120 | 17.7 | 2124 | 0 | 17.7 | 0 | 120 | 68.44 | 8212.8 | 0 | 0 | 0 | 120 | 120 | 2124 | 2124 | Building
1021 | TILE & STONE WORK INDENT-568/B BLDG/TILE GROUT | 0 | Started | Material | (M)TILE GROUT BRIGHT WHITE-644 | KG | 540 | 63.02 | 34030.8 | 540 | 63.02 | 34030.8 | 0 | 63.02 | 0 | 540 | 63.01 | 34026.48 | 0 | 0 | 0 | 540 | 540 | 34030.8 | 34030.8 | Building
1022 | TILE & STONE WORK INDENT-568/B BLDG/TILE GROUT | 0 | Started | Material | (M)TILE GROUT BURGENDY-6109 | KG | 330 | 63.02 | 20796.6 | 330 | 63.02 | 20796.6 | 0 | 63.02 | 0 | 330 | 63.01 | 20793.96 | 0 | 0 | 0 | 330 | 330 | 20796.6 | 20796.6 | Building
1023 | TILE & STONE WORK INDENT-568/B BLDG/TILE GROUT | 0 | Started | Material | (M)TILE GROUT IVORY | KG | 420 | 63.02 | 26468.4 | 420 | 63.02 | 26468.4 | 0 | 63.02 | 0 | 420 | 63.01 | 26465.04 | 0 | 0 | 0 | 420 | 420 | 26468.4 | 26468.4 | Building
1024 | TILE & STONE WORK INDENT-568/B BLDG/TILE GROUT | 0 | Started | Material | (M)TILE GROUT SILK-603 | KG | 360 | 63.02 | 22687.2 | 360 | 63.02 | 22687.2 | 0 | 63.02 | 0 | 360 | 62.89 | 22641.84 | 0 | 0 | 0 | 360 | 360 | 22687.2 | 22687.2 | Building
1025 | TILE & STONE WORK INDENT-568/B BLDG/TILE GROUT | 0 | Started | Material | (M)TILE GROUT-MILKY GREY | KG | 540 | 63.02 | 34030.8 | 540 | 63.02 | 34030.8 | 0 | 63.02 | 0 | 540 | 63.01 | 34026.48 | 0 | 0 | 0 | 540 | 540 | 34030.8 | 34030.8 | Building
1026 | Flat No-01 to 05, B Bldg-1,2,3 Floor | 0 | Tentative | Labour | (L)Toilet Door frames (Lab) | NOS | 50788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50788 | 1 | 50788 | 0 | 0 | 0 | 50788 | 50788 | 0 | 0
1027 | Flat No-01 to 05, B Bldg-4,5,6 Floor | 0 | Tentative | Labour | (L)Toilet Door frames (Lab) | NOS | 52904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52904 | 1 | 52904 | 0 | 0 | 0 | 52904 | 52904 | 0 | 0
1028 | Flat No-01 to 05, B Bldg-7,8,9 Floor | 0 | Tentative | Labour | (L)Toilet Door frames (Lab) | NOS | 52904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52904 | 1 | 52904 | 0 | 0 | 0 | 52904 | 52904 | 0 | 0
1029 | Flat No-01 to 05, B Bldg-10,11,12 Floor | 0 | Tentative | Labour | (L)Toilet Door frames (Lab) | NOS | 55020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55020 | 1 | 55020 | 0 | 0 | 0 | 55020 | 55020 | 0 | 0
1030 | Flat No-01 to 05, B Bldg Kadappa-1,2,3 Floor | 0 | Tentative | Labour | (L)Kitchen Platform (Lab) | NOS | 32146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32146 | 1 | 32146 | 0 | 0 | 0 | 32146 | 32146 | 0 | 0
1031 | Flat No-01 to 05, B Bldg Kadappa-4,5,6 Floor | 0 | Tentative | Labour | (L)Kitchen Platform (Lab) | NOS | 32146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32146 | 1 | 32146 | 0 | 0 | 0 | 32146 | 32146 | 0 | 0
1032 | Flat No-01 to 05, B Bldg Kadappa-7,8,9 Floor | 0 | Tentative | Labour | (L)Kitchen Platform (Lab) | NOS | 32146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32146 | 1 | 32146 | 0 | 0 | 0 | 32146 | 32146 | 0 | 0
1033 | Flat No-01 to 05, B Bldg Kadappa-10,11,12 Floor | 0 | Tentative | Labour | (L)Kitchen Platform (Lab) | NOS | 32146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32146 | 1 | 32146 | 0 | 0 | 0 | 32146 | 32146 | 0 | 0
1034 | Flat No-01 to 05, B Bldg Granite-1,2,3 Floor | 0 | Tentative | Labour | (L)Kitchen Platform (Lab) | NOS | 40913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40913 | 1 | 40913 | 0 | 0 | 0 | 40913 | 40913 | 0 | 0
1035 | Flat No-01 to 05, B Bldg Granite-4,5,6 Floor | 0 | Tentative | Labour | (L)Kitchen Platform (Lab) | NOS | 40913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40913 | 1 | 40913 | 0 | 0 | 0 | 40913 | 40913 | 0 | 0
1036 | Flat No-01 to 05, B Bldg Granite-7,8,9 Floor | 0 | Tentative | Labour | (L)Kitchen Platform (Lab) | NOS | 40913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40913 | 1 | 40913 | 0 | 0 | 0 | 40913 | 40913 | 0 | 0
1037 | Flat No-01 to 05, B Bldg Granite-10,11,12 Floor | 0 | Tentative | Labour | (L)Kitchen Platform (Lab) | NOS | 40913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40913 | 1 | 40913 | 0 | 0 | 0 | 40913 | 40913 | 0 | 0
1038 | Flat No-01 to 05, B Bldg -After Comp. of Miss. Work | 0 | Tentative | Labour | (L)Miss. Work (Tiling & Stone work) | NOS | 4334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4334 | 1 | 4334 | 0 | 0 | 0 | 4334 | 4334 | 0 | 0
1039 | Flat No-01 to 05, B Bldg -Cleaning Comp. upto 12th Floor | 0 | Tentative | Labour | (L)Cleaning Work (Tiling & Stone work) | NOS | 2601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2601 | 1 | 2601 | 0 | 0 | 0 | 2601 | 2601 | 0 | 0
1040 | Flat No-01 to 05, B Bldg -Comp. of Acid Wash | 0 | Tentative | Labour | (L)Cleaning Work (Tiling & Stone work) | NOS | 3901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3901 | 1 | 3901 | 0 | 0 | 0 | 3901 | 3901 | 0 | 0
1041 | Flat No-01 to 05, B Bldg -Retention after Comp.of all work | 0 | Tentative | Labour | (L)Retention (Tiling & Stone work) | NOS | 27089 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27089 | 1 | 27089 | 0 | 0 | 0 | 27089 | 27089 | 0 | 0
1042 | Flat No-06 to 10, B Bldg-1,2,3 Floor | 0 | Tentative | Labour | (L)Toilet Door frames (Lab) | NOS | 56407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56407 | 1 | 56407 | 0 | 0 | 0 | 56407 | 56407 | 0 | 0
1043 | Flat No-06 to 10, B Bldg-4,5,6 Floor | 0 | Tentative | Labour | (L)Toilet Door frames (Lab) | NOS | 58758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58758 | 1 | 58758 | 0 | 0 | 0 | 58758 | 58758 | 0 | 0
1044 | Flat No-06 to 10, B Bldg-7,8,9 Floor | 0 | Tentative | Labour | (L)Toilet Door frames (Lab) | NOS | 58758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58758 | 1 | 58758 | 0 | 0 | 0 | 58758 | 58758 | 0 | 0
1045 | Flat No-06 to 10, B Bldg-10,11,12 Floor | 0 | Tentative | Labour | (L)Toilet Door frames (Lab) | NOS | 61108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61108 | 1 | 61108 | 0 | 0 | 0 | 61108 | 61108 | 0 | 0
1046 | Flat No-06 to 10, B Bldg Kadappa-1,2,3 Floor | 0 | Tentative | Labour | (L)Kitchen Platform (Lab) | NOS | 35702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35702 | 1 | 35702 | 0 | 0 | 0 | 35702 | 35702 | 0 | 0
1047 | Flat No-06 to 10, B Bldg Kadappa-4,5,6 Floor | 0 | Tentative | Labour | (L)Kitchen Platform (Lab) | NOS | 35702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35702 | 1 | 35702 | 0 | 0 | 0 | 35702 | 35702 | 0 | 0
1048 | Flat No-06 to 10, B Bldg Kadappa-7,8,9 Floor | 0 | Tentative | Labour | (L)Kitchen Platform (Lab) | NOS | 35702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35702 | 1 | 35702 | 0 | 0 | 0 | 35702 | 35702 | 0 | 0
1049 | Flat No-06 to 10, B Bldg Kadappa-10,11,12 Floor | 0 | Tentative | Labour | (L)Kitchen Platform (Lab) | NOS | 35702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35702 | 1 | 35702 | 0 | 0 | 0 | 35702 | 35702 | 0 | 0
1050 | Flat No-06 to 10, B Bldg Granite-1,2,3 Floor | 0 | Started | Labour | (L)Kitchen Platform (Lab) | NOS | 45439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45439 | 1 | 45439 | 45439 | 1 | 45439 | 45439 | 0 | 0 | -45439
1051 | Flat No-06 to 10, B Bldg Granite-4,5,6 Floor | 0 | Started | Labour | (L)Kitchen Platform (Lab) | NOS | 45439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45439 | 1 | 45439 | 45439 | 1 | 45439 | 45439 | 0 | 0 | -45439
1052 | Flat No-06 to 10, B Bldg Granite-7,8,9 Floor | 0 | Started | Labour | (L)Kitchen Platform (Lab) | NOS | 45439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45439 | 1 | 45439 | 45439 | 1 | 45439 | 45439 | 0 | 0 | -45439
1053 | Flat No-06 to 10, B Bldg Granite-10,11,12 Floor | 0 | Tentative | Labour | (L)Kitchen Platform (Lab) | NOS | 45439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45439 | 1 | 45439 | 0 | 0 | 0 | 45439 | 45439 | 0 | 0
1054 | Flat No-06 to 10, B Bldg -After Comp. of Miss. Work | 0 | Tentative | Labour | (L)Miss. Work (Tiling & Stone work) | NOS | 4814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4814 | 1 | 4814 | 0 | 0 | 0 | 4814 | 4814 | 0 | 0
1055 | Flat No-06 to 10, B Bldg -Cleaning Comp. upto 12th Floor | 0 | Tentative | Labour | (L)Cleaning Work (Tiling & Stone work) | NOS | 2888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2888 | 1 | 2888 | 0 | 0 | 0 | 2888 | 2888 | 0 | 0
1056 | Flat No-06 to 10, B Bldg -Comp. of Acid Wash | 0 | Tentative | Labour | (L)Cleaning Work (Tiling & Stone work) | NOS | 4332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4332 | 1 | 4332 | 0 | 0 | 0 | 4332 | 4332 | 0 | 0
1057 | Flat No-06 to 10, B Bldg -Retention after Comp.of all work | 0 | Tentative | Labour | (L)Retention (Tiling & Stone work) | NOS | 30086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30086 | 1 | 30086 | 0 | 0 | 0 | 30086 | 30086 | 0 | 0
1058 | B Bldg.Flat-06 to 10 Dado Master Toilet-1,2,3 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 26975.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26975.99 | 1 | 26975.99 | 26975.99 | 1 | 26975.99 | 26975.99 | 0 | 0 | -26975.99
1059 | B Bldg.Flat-06 to 10 Dado Master Toilet-4,5,6 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 26975.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26975.99 | 1 | 26975.99 | 26975.99 | 1 | 26975.99 | 26975.99 | 0 | 0 | -26975.99
1060 | B Bldg.Flat-06 to 10 Dado Master Toilet-7,8,9 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 26975.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26975.99 | 1 | 26975.99 | 26975.99 | 1 | 26975.99 | 26975.99 | 0 | 0 | -26975.99
1061 | B Bldg.Flat-06 to 10 Dado Master Toilet-10,11,12 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 26975.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26975.99 | 1 | 26975.99 | 26975.99 | 1 | 26975.99 | 26975.99 | 0 | 0 | -26975.99
1062 | B Bldg.Flat-06 to 10 Dado Common Toilet-1,2,3 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 26975.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26975.99 | 1 | 26975.99 | 26975.99 | 1 | 26975.99 | 26975.99 | 0 | 0 | -26975.99
1063 | B Bldg.Flat-06 to 10 Dado Common Toilet-4,5,6 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 26975.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26975.99 | 1 | 26975.99 | 26975.99 | 1 | 26975.99 | 26975.99 | 0 | 0 | -26975.99
1064 | B Bldg.Flat-06 to 10 Dado Common Toilet-7,8,9 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 26975.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26975.99 | 1 | 26975.99 | 26975.99 | 1 | 26975.99 | 26975.99 | 0 | 0 | -26975.99
1065 | B Bldg.Flat-06 to 10 Dado Common Toilet-10,11,12 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 26975.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26975.99 | 1 | 26975.99 | 26975.99 | 1 | 26975.99 | 26975.99 | 0 | 0 | -26975.99
1066 | B Bldg.Flat-06 to 10 Dado Kitchen-1,2,3 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 32371.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32371.19 | 1 | 32371.19 | 32371.19 | 1 | 32371.19 | 32371.19 | 0 | 0 | -32371.19
1067 | B Bldg.Flat-06 to 10 Dado Kitchen-4,5,6 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 32371.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32371.19 | 1 | 32371.19 | 32371.19 | 1 | 32371.19 | 32371.19 | 0 | 0 | -32371.19
1068 | B Bldg.Flat-06 to 10 Dado Kitchen-7,8,9 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 32371.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32371.19 | 1 | 32371.19 | 32371.19 | 1 | 32371.19 | 32371.19 | 0 | 0 | -32371.19
1069 | B Bldg.Flat-06 to 10 Dado Kitchen-10,11,12 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 32371.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32371.19 | 1 | 32371.19 | 32371.19 | 1 | 32371.19 | 32371.19 | 0 | 0 | -32371.19
1070 | B Bldg.Flat-06 to 10 Dado Dry Terrace-1,2,3 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 21580.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21580.79 | 1 | 21580.79 | 21580.79 | 1 | 21580.79 | 21580.79 | 0 | 0 | -21580.79
1071 | B Bldg.Flat-06 to 10 Dado Dry Terrace-4,5,6 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 21580.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21580.79 | 1 | 21580.79 | 21580.79 | 1 | 21580.79 | 21580.79 | 0 | 0 | -21580.79
1072 | B Bldg.Flat-06 to 10 Dado Dry Terrace-7,8,9 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 21580.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21580.79 | 1 | 21580.79 | 21580.79 | 1 | 21580.79 | 21580.79 | 0 | 0 | -21580.79
1073 | B Bldg.Flat-06 to 10 Dado Dry Terrace-10,11,12 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 21580.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21580.79 | 1 | 21580.79 | 21580.79 | 1 | 21580.79 | 21580.79 | 0 | 0 | -21580.79
1074 | B Bldg.Flat-06 to 10 Flooring Flat -1,2,3 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 150266.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150266.27 | 1 | 150266.27 | 150266.27 | 1 | 150266.27 | 150266.27 | 0 | 0 | -150266.27
1075 | B Bldg.Flat-06 to 10 Flooring Flat-4,5,6 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 150266.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150266.27 | 1 | 150266.27 | 150266.27 | 1 | 150266.27 | 150266.27 | 0 | 0 | -150266.27
1076 | B Bldg.Flat-06 to 10 Flooring Flat-7,8,9 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 150266.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150266.27 | 1 | 150266.27 | 150266.27 | 1 | 150266.27 | 150266.27 | 0 | 0 | -150266.27
1077 | B Bldg.Flat-06 to 10 Flooring Flat-10,11,12 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 150266.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150266.27 | 1 | 150266.27 | 150266.27 | 1 | 150266.27 | 150266.27 | 0 | 0 | -150266.27
1078 | B Bldg.Flat-06 to 10 Flooring Terrace-1,2,3 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 37566.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37566.57 | 1 | 37566.57 | 37566.57 | 1 | 37566.57 | 37566.57 | 0 | 0 | -37566.57
1079 | B Bldg.Flat-06 to 10 Flooring Terrace-4,5,6 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 37566.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37566.57 | 1 | 37566.57 | 37566.57 | 1 | 37566.57 | 37566.57 | 0 | 0 | -37566.57
1080 | B Bldg.Flat-06 to 10 Flooring Terrace-7,8,9 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 37566.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37566.57 | 1 | 37566.57 | 37566.57 | 1 | 37566.57 | 37566.57 | 0 | 0 | -37566.57
1081 | B Bldg.Flat-06 to 10 Flooring Terrace-10,11,12 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 37566.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37566.57 | 1 | 37566.57 | 37566.57 | 1 | 37566.57 | 37566.57 | 0 | 0 | -37566.57
1082 | B Bldg.Flat-06 to 10 Skirting-1,2,3 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 43960.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43960.88 | 1 | 43960.88 | 43960.88 | 1 | 43960.88 | 43960.88 | 0 | 0 | -43960.88
1083 | B Bldg.Flat-06 to 10 Skirting-4,5,6 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 43960.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43960.88 | 1 | 43960.88 | 43960.88 | 1 | 43960.88 | 43960.88 | 0 | 0 | -43960.88
1084 | B Bldg.Flat-06 to 10 Skirting-7,8,9 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 43960.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43960.88 | 1 | 43960.88 | 43960.88 | 1 | 43960.88 | 43960.88 | 0 | 0 | -43960.88
1085 | B Bldg.Flat-06 to 10 Skirting-10,11,12 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 43960.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43960.88 | 1 | 43960.88 | 43960.88 | 1 | 43960.88 | 43960.88 | 0 | 0 | -43960.88
1086 | B Bldg.Flat-06 to 10 Umbra Patti-1,2,3 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 15985.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15985.77 | 1 | 15985.77 | 15985.77 | 1 | 15985.77 | 15985.77 | 0 | 0 | -15985.77
1087 | B Bldg.Flat-06 to 10 Umbra Patti-4,5,6 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 15985.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15985.77 | 1 | 15985.77 | 15985.77 | 1 | 15985.77 | 15985.77 | 0 | 0 | -15985.77
1088 | B Bldg.Flat-06 to 10 Umbra Patti-7,8,9 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 15985.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15985.77 | 1 | 15985.77 | 15985.77 | 1 | 15985.77 | 15985.77 | 0 | 0 | -15985.77
1089 | B Bldg.Flat-06 to 10 Umbra Patti-10,11,12 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 15985.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15985.77 | 1 | 15985.77 | 15985.77 | 1 | 15985.77 | 15985.77 | 0 | 0 | -15985.77
1090 | B Bldg.Flat-06 to 10 Flooring Toilet/WC-1,2,3 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 19982.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19982.22 | 1 | 19982.22 | 19982.22 | 1 | 19982.22 | 19982.22 | 0 | 0 | -19982.22
1091 | B Bldg.Flat-06 to 10 Flooring Toilet/WC-4,5,6 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 19982.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19982.22 | 1 | 19982.22 | 19982.22 | 1 | 19982.22 | 19982.22 | 0 | 0 | -19982.22
1092 | B Bldg.Flat-06 to 10 Flooring Toilet/WC-7,8,9 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 19982.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19982.22 | 1 | 19982.22 | 19982.22 | 1 | 19982.22 | 19982.22 | 0 | 0 | -19982.22
1093 | B Bldg.Flat-06 to 10 Flooring Toilet/WC-10,11,12 Floor | 0 | Tentative | Labour | (L)Tiling Work | NOS | 19982.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19982.22 | 1 | 19982.22 | 0 | 0 | 0 | 19982.22 | 19982.22 | 0 | 0
1094 | B Bldg.Flat-06 to 10 Acid Wash-1,2,3,4 Floor | 0 | Tentative | Labour | (L)Tiling Work | NOS | 31971.516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31971.516 | 1 | 31971.516 | 0 | 0 | 0 | 31971.516 | 31971.516 | 0 | 0
1095 | B Bldg.Flat-06 to 10 Acid Wash-5,6,7,8 Floor | 0 | Tentative | Labour | (L)Tiling Work | NOS | 31971.516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31971.516 | 1 | 31971.516 | 0 | 0 | 0 | 31971.516 | 31971.516 | 0 | 0
1096 | B Bldg.Flat-06 to 10 Acid Wash-9,10,11,12 Floor | 0 | Tentative | Labour | (L)Tiling Work | NOS | 31971.516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31971.516 | 1 | 31971.516 | 0 | 0 | 0 | 31971.516 | 31971.516 | 0 | 0
1097 | B Bldg.Flat-06 to 10 "Cleaning & Misc.Work" after Comp of Wo | 0 | Tentative | Labour | (L)Tiling Work | NOS | 34378.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34378.01 | 1 | 34378.01 | 0 | 0 | 0 | 34378.01 | 34378.01 | 0 | 0
1098 | B Bldg.Flat-06 to 10 "Rentention" after 12 Month Comp. | 0 | Tentative | Labour | (L)Tiling Work | NOS | 85945.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85945.02 | 1 | 85945.02 | 0 | 0 | 0 | 85945.02 | 85945.02 | 0 | 0
1099 | B Bldg.Flat-01 to 05, Dado Master Toilet-1,2,3 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 23684.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23684.54 | 1 | 23684.54 | 23684.54 | 1 | 23684.54 | 23684.54 | 0 | 0 | -23684.54
1100 | B Bldg.Flat-01 to 05, Dado Master Toilet-4,5,6 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 23684.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23684.54 | 1 | 23684.54 | 23684.54 | 1 | 23684.54 | 23684.54 | 0 | 0 | -23684.54
1101 | B Bldg.Flat-01 to 05, Dado Master Toilet-7,8,9 Floor | 0 | Tentative | Labour | (L)Tiling Work | NOS | 23684.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23684.54 | 1 | 23684.54 | 0 | 0 | 0 | 23684.54 | 23684.54 | 0 | 0
1102 | B Bldg.Flat-01 to 05, Dado Common Toilet-1,2,3 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 23684.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23684.54 | 1 | 23684.54 | 23684.54 | 1 | 23684.54 | 23684.54 | 0 | 0 | -23684.54
1103 | B Bldg.Flat-01 to 05, Dado Common Toilet-4,5,6 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 23684.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23684.54 | 1 | 23684.54 | 23684.54 | 1 | 23684.54 | 23684.54 | 0 | 0 | -23684.54
1104 | B Bldg.Flat-01 to 05, Dado Common Toilet-7,8,9 Floor | 0 | Tentative | Labour | (L)Tiling Work | NOS | 23684.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23684.54 | 1 | 23684.54 | 0 | 0 | 0 | 23684.54 | 23684.54 | 0 | 0
1105 | B Bldg.Flat-01 to 05, Dado Kitchen-1,2,3 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 28421.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28421.45 | 1 | 28421.45 | 28421.45 | 1 | 28421.45 | 28421.45 | 0 | 0 | -28421.45
1106 | B Bldg.Flat-01 to 05, Dado Kitchen-4,5,6 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 28421.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28421.45 | 1 | 28421.45 | 28421.45 | 1 | 28421.45 | 28421.45 | 0 | 0 | -28421.45
1107 | B Bldg.Flat-01 to 05, Dado Kitchen-7,8,9 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 28421.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28421.45 | 1 | 28421.45 | 28421.45 | 1 | 28421.45 | 28421.45 | 0 | 0 | -28421.45
1108 | B Bldg.Flat-01 to 05, Dado Dry Terrace-1,2,3 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 18947.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18947.63 | 1 | 18947.63 | 18947.63 | 1 | 18947.63 | 18947.63 | 0 | 0 | -18947.63
1109 | B Bldg.Flat-01 to 05, Dado Dry Terrace-4,5,6 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 18947.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18947.63 | 1 | 18947.63 | 18947.63 | 1 | 18947.63 | 18947.63 | 0 | 0 | -18947.63
1110 | B Bldg.Flat-01 to 05, Flooring Flat -1,2,3 Floor | 0 | Tentative | Labour | (L)Tiling Work | NOS | 126317.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126317.54 | 1 | 126317.54 | 0 | 0 | 0 | 126317.54 | 126317.54 | 0 | 0
1111 | B Bldg.Flat-01 to 05, Flooring Terrace-1,2,3 Floor | 0 | Tentative | Labour | (L)Tiling Work | NOS | 31579.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31579.39 | 1 | 31579.39 | 0 | 0 | 0 | 31579.39 | 31579.39 | 0 | 0
1112 | B Bldg.Flat-01 to 05, Skirting-1,2,3 Floor | 0 | Tentative | Labour | (L)Tiling Work | NOS | 42105.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42105.85 | 1 | 42105.85 | 0 | 0 | 0 | 42105.85 | 42105.85 | 0 | 0
1113 | B Bldg.Flat-01 to 05, Umbra Patti-1,2,3 Floor | 0 | Tentative | Labour | (L)Tiling Work | NOS | 17544.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17544.1 | 1 | 17544.1 | 0 | 0 | 0 | 17544.1 | 17544.1 | 0 | 0
1114 | B Bldg.Flat-01 to 05, Flooring Toilet/WC-1,2,3 Floor | 0 | Tentative | Labour | (L)Tiling Work | NOS | 17544.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17544.1 | 1 | 17544.1 | 0 | 0 | 0 | 17544.1 | 17544.1 | 0 | 0
1115 | B Bldg.Flat-01 to 05, Flooring Toilet/WC-4,5,6 Floor | 0 | Tentative | Labour | (L)Tiling Work | NOS | 17544.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17544.1 | 1 | 17544.1 | 0 | 0 | 0 | 17544.1 | 17544.1 | 0 | 0
1116 | B Bldg.Flat-01 to 05, Flooring Toilet/WC-7,8,9 Floor | 0 | Tentative | Labour | (L)Tiling Work | NOS | 17544.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17544.1 | 1 | 17544.1 | 0 | 0 | 0 | 17544.1 | 17544.1 | 0 | 0
1117 | B Bldg.Flat-01 to 05, Acid Wash-1st to 5th Floor | 0 | Tentative | Labour | (L)Tiling Work | NOS | 34177.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34177.37 | 1 | 34177.37 | 0 | 0 | 0 | 34177.37 | 34177.37 | 0 | 0
1118 | B Bldg.Flat-01 to 05, Cleaning & Misc. Work 1st to 5th floor | 0 | Tentative | Labour | (L)Tiling Work | NOS | 12249.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12249.97 | 1 | 12249.97 | 0 | 0 | 0 | 12249.97 | 12249.97 | 0 | 0
1119 | B Bldg.Flat-01 to 05, Retention after 12 Month Comp.1st-5th | 0 | Tentative | Labour | (L)Tiling Work | NOS | 30624.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30624.92 | 1 | 30624.92 | 0 | 0 | 0 | 30624.92 | 30624.92 | 0 | 0
1120 | B Bldg.Flat-01 to 05: Dado Master Toilet-10,11,12 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 23684.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23684.54 | 1 | 23684.54 | 23684.54 | 1 | 23684.54 | 23684.54 | 0 | 0 | -23684.54
1121 | B Bldg.Flat-01 to 05: Dado Common Toilet-10,11,12 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 23684.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23684.54 | 1 | 23684.54 | 23684.54 | 1 | 23684.54 | 23684.54 | 0 | 0 | -23684.54
1122 | B Bldg.Flat-01 to 05: Dado Kitchen-10,11,12 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 28421.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28421.45 | 1 | 28421.45 | 28421.45 | 1 | 28421.45 | 28421.45 | 0 | 0 | -28421.45
1123 | B Bldg.Flat-01 to 05: Dado Dry Terrace-7,8,9 Floor | 0 | Tentative | Labour | (L)Tiling Work | NOS | 18947.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18947.63 | 1 | 18947.63 | 0 | 0 | 0 | 18947.63 | 18947.63 | 0 | 0
1124 | B Bldg.Flat-01 to 05: Dado Dry Terrace-10,11,12 Floor | 0 | Tentative | Labour | (L)Tiling Work | NOS | 18947.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18947.63 | 1 | 18947.63 | 0 | 0 | 0 | 18947.63 | 18947.63 | 0 | 0
1125 | B Bldg.Flat-01 to 05: Flooring Flat-4,5,6 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 126317.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126317.54 | 1 | 126317.54 | 126317.54 | 1 | 126317.54 | 126317.54 | 0 | 0 | -126317.54
1126 | B Bldg.Flat-01 to 05: Flooring Flat-7,8,9 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 126317.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126317.54 | 1 | 126317.54 | 126317.54 | 1 | 126317.54 | 126317.54 | 0 | 0 | -126317.54
1127 | B Bldg.Flat-01 to 05: Flooring Flat-10,11,12 Floor | 0 | Tentative | Labour | (L)Tiling Work | NOS | 126317.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126317.54 | 1 | 126317.54 | 0 | 0 | 0 | 126317.54 | 126317.54 | 0 | 0
1128 | B Bldg.Flat-01 to 05: Flooring Terrace-4,5,6 Floor | 0 | Tentative | Labour | (L)Tiling Work | NOS | 31579.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31579.39 | 1 | 31579.39 | 0 | 0 | 0 | 31579.39 | 31579.39 | 0 | 0
1129 | B Bldg.Flat-01 to 05: Flooring Terrace-7,8,9 Floor | 0 | Tentative | Labour | (L)Tiling Work | NOS | 31579.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31579.39 | 1 | 31579.39 | 0 | 0 | 0 | 31579.39 | 31579.39 | 0 | 0
1130 | B Bldg.Flat-01 to 05: Flooring Terrace-10,11,12 Floor | 0 | Tentative | Labour | (L)Tiling Work | NOS | 31579.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31579.39 | 1 | 31579.39 | 0 | 0 | 0 | 31579.39 | 31579.39 | 0 | 0
1131 | B Bldg.Flat-01 to 05: Skirting-4,5,6 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 42105.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42105.85 | 1 | 42105.85 | 42105.85 | 1 | 42105.85 | 42105.85 | 0 | 0 | -42105.85
1132 | B Bldg.Flat-01 to 05: Skirting-7,8,9 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 42105.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42105.85 | 1 | 42105.85 | 42105.85 | 1 | 42105.85 | 42105.85 | 0 | 0 | -42105.85
1133 | B Bldg.Flat-01 to 05: Skirting-10,11,12 Floor | 0 | Tentative | Labour | (L)Tiling Work | NOS | 42105.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42105.85 | 1 | 42105.85 | 0 | 0 | 0 | 42105.85 | 42105.85 | 0 | 0
1134 | B Bldg.Flat-01 to 05: Umbra Patti-4,5,6 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 17544.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17544.1 | 1 | 17544.1 | 17544.1 | 1 | 17544.1 | 17544.1 | 0 | 0 | -17544.1
1135 | B Bldg.Flat-01 to 05: Umbra Patti-7,8,9 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 17544.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17544.1 | 1 | 17544.1 | 17544.1 | 1 | 17544.1 | 17544.1 | 0 | 0 | -17544.1
1136 | B Bldg.Flat-01 to 05: Umbra Patti-10,11,12 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 17544.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17544.1 | 1 | 17544.1 | 17544.1 | 1 | 17544.1 | 17544.1 | 0 | 0 | -17544.1
1137 | B Bldg.Flat-01 to 05: Flooring Toilet/WC-10,11,12 Floor | 0 | Started | Labour | (L)Tiling Work | NOS | 17544.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17544.1 | 1 | 17544.1 | 17544.1 | 1 | 17544.1 | 17544.1 | 0 | 0 | -17544.1
1138 | B Bldg.Flat-01 to 05: Acid Wash-6th to 12th Floor | 0 | Tentative | Labour | (L)Tiling Work | NOS | 50034.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50034.24 | 1 | 50034.24 | 0 | 0 | 0 | 50034.24 | 50034.24 | 0 | 0
1139 | B Bldg.Flat-01 to 05: Cleaning & Misc. 6th to 12th floor | 0 | Tentative | Labour | (L)Tiling Work | NOS | 17933.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17933.44 | 1 | 17933.44 | 0 | 0 | 0 | 17933.44 | 17933.44 | 0 | 0
1140 | B Bldg.Flat-01 to 05: Retention after 12 Month Comp.6th to 1 | 0 | Tentative | Labour | (L)Tiling Work | NOS | 44833.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44833.59 | 1 | 44833.59 | 0 | 0 | 0 | 44833.59 | 44833.59 | 0 | 0
1141 | B BLDG -COMPLETION OF LOBBY,MID. LAND. TILE-1ST TO 12TH FLOO | 0 | Tentative | Labour | (L)Tiling Work | NOS | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 8963.01 | 107556.0912 | 0 | 0 | 0 | 12 | 12 | 0 | 0
1142 | B BLDG -LANDING ,LOBBY SKIRTING UP TO 12TH FLOOR | 0 | Tentative | Labour | (L)Tiling Work | NOS | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 13444.51 | 26889.0226 | 0 | 0 | 0 | 2 | 2 | 0 | 0
1143 | B BLDG -GRANITE MID-LANDING,SKIRTING,TAPPA UP TO 12TH FLOOR | 0 | Tentative | Labour | (L)Tiling Work | NOS | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 6722.26 | 13444.5114 | 0 | 0 | 0 | 2 | 2 | 0 | 0
1144 | B BLDG -TAPPA WITH RISER UP TO 12TH FLOOR | 0 | Tentative | Labour | (L)Stone Work | NOS | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 7469.17 | 89630.076 | 0 | 0 | 0 | 12 | 12 | 0 | 0
1145 | B BLDG TAPPA W/O RISER UPTP 12TH FLOOR | 0 | Tentative | Labour | (L)Stone Work | NOS | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 6722.26 | 80667.0684 | 0 | 0 | 0 | 12 | 12 | 0 | 0
1146 | B BLDG -KOTA TAPPA SKIRTING UPTO 12TH FLOOR | 0 | Tentative | Labour | (L)Tiling Work | NOS | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 8963.01 | 17926.0152 | 0 | 0 | 0 | 2 | 2 | 0 | 0
1147 | B BLDG TAPPA GROOVE CUTTING UPTO 12TH FLOOR | 0 | Tentative | Labour | (L)Stone Work | NOS | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 13444.51 | 26889.0226 | 0 | 0 | 0 | 2 | 2 | 0 | 0
1148 | B BLDG LIFT DOOR FRAME,UMBRA PATTI-13 PASSENGER UPTO 12TH FL | 0 | Tentative | Labour | (L)Stone Work | NOS | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1867.29 | 22407.5184 | 0 | 0 | 0 | 12 | 12 | 0 | 0
1149 | B BLDG LIFT DOOR FRAME,UMBRA PATTI-8 PASSENGER UPTO 12TH FL | 0 | Tentative | Labour | (L)Stone Work | NOS | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 1867.29 | 22407.5184 | 0 | 0 | 0 | 12 | 12 | 0 | 0
1150 | B BLDG ACID WASH UPTO 12TH FLOOR | 0 | Tentative | Labour | (L)Tiling Work | NOS | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 20166.77 | 40333.534 | 0 | 0 | 0 | 2 | 2 | 0 | 0
1151 | B BLDG MISC. WORK UPTO 12TH FLOOR | 0 | Tentative | Labour | (L)Tiling Work | NOS | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4818.82 | 9637.6426 | 0 | 0 | 0 | 2 | 2 | 0 | 0
1152 | B BLDG RETENTION UP TO 12TH FLOOR | 0 | Tentative | Labour | (L)Tiling Work | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 24094.11 | 24094.11 | 0 | 0 | 0 | 1 | 1 | 0 | 0
1153 | B WING FLAT FLOORING & DADO TILE | 0 | Started | Material | (M)CHICAGO BLANCO 300 x 450mm | BOX | 40 | 339.53 | 13581.2 | 40 | 339.53 | 13581.2 | 0 | 339.53 | 0 | 40 | 287.76 | 11510.2 | 0 | 0 | 0 | 40 | 40 | 13581.2 | 13581.2
1154 | B WING FLAT FLOORING & DADO TILE | 0 | Started | Material | (M)CHICAGO BROWN 300 x 300mm | BOX | 25 | 339.56 | 8489 | 25 | 339.56 | 8489 | 0 | 339.56 | 0 | 25 | 287.76 | 7193.88 | 0 | 0 | 0 | 25 | 25 | 8489 | 8489
1155 | B WING FLAT FLOORING & DADO TILE | 0 | Started | Material | (M)CHICAGO BROWN 300 x 450mm | BOX | 95 | 339.56 | 32258.2 | 95 | 339.56 | 32258.2 | 0 | 339.56 | 0 | 95 | 287.75 | 27336.6965 | 0 | 0 | 0 | 95 | 95 | 32258.2 | 32258.2
1156 | B WING FLAT FLOORING & DADO TILE | 0 | Started | Material | (M)CHICAGO CREMA 300 x 450mm | BOX | 70 | 339.56 | 23769.2 | 70 | 339.56 | 23769.2 | 0 | 339.56 | 0 | 70 | 287.75 | 20142.843 | 0 | 0 | 0 | 70 | 70 | 23769.2 | 23769.2
1157 | B WING FLAT FLOORING & DADO TILE | 0 | Started | Material | (M)CHICAGO GREY 300 x 300mm | BOX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1158 | B WING FLAT FLOORING & DADO TILE | 0 | Started | Material | (M)CHICAGO GREY 300 x 450mm | BOX | 70 | 339.53 | 23767.1 | 70 | 339.53 | 23767.1 | 0 | 339.53 | 0 | 70 | 287.75 | 20142.843 | 0 | 0 | 0 | 70 | 70 | 23767.1 | 23767.1
1159 | B WING FLAT FLOORING & DADO TILE | 0 | Started | Material | (M)COTTO RED 400 x 400mm | BOX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1160 | B WING FLAT FLOORING & DADO TILE | 0 | Started | Material | (M)PORTICO GREY-300 x 300 (FL WO DOT-A) | BOX | 129 | 339.53 | 43799.37 | 129 | 339.53 | 43799.37 | 0 | 339.53 | 0 | 129 | 287.75 | 37120.3563 | 0 | 0 | 0 | 129 | 129 | 43799.37 | 43799.37
1161 | B WING FLAT FLOORING & DADO TILE | 0 | Started | Material | (M)PORTICO GREY-300 x 300 (FLA) | BOX | 10 | 339.53 | 3395.3 | 10 | 339.53 | 3395.3 | 0 | 339.53 | 0 | 10 | 287.75 | 2877.54 | 0 | 0 | 0 | 10 | 10 | 3395.3 | 3395.3
1162 | B WING FLAT FLOORING & DADO TILE | 0 | Started | Material | (M)Vitrified Tile 800mm x 800mm (ZEST WHITE) | BOX | 374 | 1180 | 441320 | 374 | 1180 | 441320 | 0 | 1180 | 0 | 374 | 930.15 | 347876.1 | 0 | 0 | 0 | 374 | 374 | 441320 | 441320
1163 | TILING & STONE WORK B WING FIRE ST CASE TAPPA WORK | 0 | Started | Material | (M)CEMENT PPC 50KG | BAG | 36 | 320 | 11520 | 36 | 320 | 11520 | 0 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 36 | 11520 | 11520
1164 | TILING & STONE WORK B WING FIRE ST CASE TAPPA WORK | 0 | Started | Material | (M)Crush Sand | BRASS | 2 | 3675 | 7350 | 2 | 3675 | 7350 | 0 | 3675 | 0 | 2 | 3570 | 7140 | 0 | 0 | 0 | 2 | 2 | 7350 | 7350
1165 | TILING & STONE WORK B WING FIRE ST CASE TAPPA WORK | 0 | Started | Material | (M)Kota Stone Tread 59" X 11" (25mm thk) | NOS | 237 | 944 | 223728 | 237 | 944 | 223728 | 0 | 944 | 0 | 237 | 336 | 79632 | 0 | 0 | 0 | 237 | 237 | 223728 | 223728
1166 | TILING & STONE WORK B WING FIRE ST CASE TAPPA WORK | 0 | Started | Material | (M)Kota Stone Tread 60" X 11" (25MM THK) | SQFT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1167 | TILING & STONE WORK B WING FIRE ST CASE TAPPA WORK | 0 | Started | Material | (M)Metal No.I 6mm (Grit) | BRASS | 2 | 3000 | 6000 | 2 | 3000 | 6000 | 0 | 3000 | 0 | 2 | 3570 | 7140 | 0 | 0 | 0 | 2 | 2 | 6000 | 6000
1168 | TILING & STONE WORK B WING MAIN ST CASE TAPPA WORK | 0 | Started | Material | (M)CEMENT PPC 50KG | BAG | 58 | 320 | 18560 | 58 | 320 | 18560 | 0 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 58 | 18560 | 18560
1169 | TILING & STONE WORK B WING MAIN ST CASE TAPPA WORK | 0 | Started | Material | (M)Crush Sand | BRASS | 2.5 | 3675 | 9187.5 | 2.5 | 3675 | 9187.5 | 0 | 3675 | 0 | 2.5 | 3570 | 8925 | 0 | 0 | 0 | 2.5 | 2.5 | 9187.5 | 9187.5
1170 | TILING & STONE WORK B WING MAIN ST CASE TAPPA WORK | 0 | Started | Material | (M)DUNKAN WHITE-600X600 (4 TILE/BOX or 15.5 SQFT) | BOX | 54 | 604 | 32616 | 54 | 604 | 32616 | 0 | 604 | 0 | 54 | 603.99 | 32615.7192 | 0 | 0 | 0 | 54 | 54 | 32616 | 32616
1171 | TILING & STONE WORK B WING MAIN ST CASE TAPPA WORK | 0 | Started | Material | (M)Kota Stone Tread 59" X 11" (25mm thk & front edeg thk-20mm) | NOS | 219 | 944 | 206736 | 219 | 944 | 206736 | 0 | 944 | 0 | 219 | 336 | 73584 | 0 | 0 | 0 | 219 | 219 | 206736 | 206736
1172 | TILING & STONE WORK B WING MAIN ST CASE TAPPA WORK | 0 | Started | Material | (M)Kota Stone Tread 60" X 11" (25MM THK) | SQFT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1173 | TILING & STONE WORK B WING MAIN ST CASE TAPPA WORK | 0 | Started | Material | (M)Metal No.I 6mm (Grit) | BRASS | 2.5 | 3000 | 7500 | 2.5 | 3000 | 7500 | 0 | 3000 | 0 | 2.5 | 3570 | 8925 | 0 | 0 | 0 | 2.5 | 2.5 | 7500 | 7500
1174 | INDENT-132/B BLDG/BOTH LIFT DOOR FRAME GRANITE WORK | 0 | Started | Material | (M)Epoxy Resin Adhesive Araldite 1.8 kg | (1+0.8) KG/SET | 4.9998 | 800 | 3999.84 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.9998 | 4.9998 | 3999.84 | 3999.84
1175 | INDENT-132/B BLDG/BOTH LIFT DOOR FRAME GRANITE WORK | 0 | Started | Material | (M)GRANITE Steel Gray 16-18mm Thk | SQFT | 750 | 88.5 | 66375 | 750 | 88.5 | 66375 | 0 | 88.5 | 0 | 750 | 90.86 | 68145 | 0 | 0 | 0 | 750 | 750 | 66375 | 66375
1176 | INDENT-132/B BLDG/BOTH LIFT DOOR FRAME GRANITE WORK | 0 | Started | Material | (M)TILE ADHESIVE MYK 335/BAG-20KG | 20 KG/BAG | 32.5 | 300 | 9750 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32.5 | 32.5 | 9750 | 9750
1177 | B BLDG PARKING CHEQURED TILE FLOORING WORK | 0 | Tentative | Material | (M)CEMENT PPC 50KG | BAG | 80 | 320 | 25600 | 80 | 320 | 25600 | 0 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 80 | 25600 | 25600
1178 | B BLDG PARKING CHEQURED TILE FLOORING WORK | 0 | Tentative | Material | (M)Chequered Tiles 300 X 300 (Thk-25mm) | SQFT | 10500 | 35.4 | 371700 | 10500 | 35.4 | 371700 | 0 | 35.4 | 0 | 10500 | 34.22 | 359310 | 0 | 0 | 0 | 10500 | 10500 | 371700 | 371700
1179 | B BLDG PARKING CHEQURED TILE FLOORING WORK | 0 | Tentative | Material | (M)Metal No.I 6mm (Grit) | BRASS | 23 | 3000 | 69000 | 23 | 3000 | 69000 | 0 | 3000 | 0 | 23 | 3675 | 84525 | 0 | 0 | 0 | 23 | 23 | 69000 | 69000
1180 | B BLDG PARKING CHEQURED TILE FLOORING WORK | 0 | Tentative | Labour | (L)Chequred Tile Flooring | SQFT | 10500 | 11 | 115500 | 0 | 0 | 0 | 0 | 11 | 0 | 10500 | 11 | 115500 | 0 | 0 | 0 | 10500 | 10500 | 115500 | 115500
1181 | FIRE EXIT DOOR B WING FIRE EXIT DOOR (INDENT-976) | 10 | Started | Material | (M)FIRE EXIT DOOR (1.2M X 2.25 M) | SET | 14 | 5000 | 70000 | 14 | 5000 | 70000 | 1 | 5000 | 5000 | 14 | 12980 | 181720 | 0 | 0 | 0 | 13 | 14 | 65000 | 70000
1182 | FIRE EXIT DOOR B WING FIRE EXIT DOOR (INDENT-976) | 10 | Started | Material | (M)FIRE EXIT DOOR (1.5 M X 2.2 5M) | SET | 1 | 4500 | 4500 | 1 | 4500 | 4500 | 0 | 4500 | 0 | 1 | 18644 | 18644 | 0 | 0 | 0 | 1 | 1 | 4500 | 4500
1183 | FIRE BOOSTER PUMP_7.5 HP | 0 | Started | Labour | (L)Fire Hydrent Systems-Installation Charge | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 3540 | 3540 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
1184 | FIRE BOOSTER PUMP_7.5 HP | 0 | Started | Labour | (L)Fire Hydrent Systems-Supply Charge | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 44250 | 44250 | 1 | 44250 | 44250 | 1 | 0 | 1.18 | -44248.82
1185 | FIRE BOOSTER ELECTRICAL STARTER_7.5 HP | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Installation Charge | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 1180 | 1180 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
1186 | FIRE BOOSTER ELECTRICAL STARTER_7.5 HP | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Supply Charge | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 6318.9 | 6318.9 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
1187 | 150 MM - Butterfly Valve | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Installation Charge | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 566.4 | 566.4 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
1188 | 150 MM - Butterfly Valve | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Supply Charge | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 3826.74 | 3826.74 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
1189 | 100 MM - Butterfly valve | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Installation Charge | NOS | 2 | 1.18 | 2.36 | 0 | 0 | 0 | 0 | 1.18 | 0 | 2 | 377.6 | 755.2 | 0 | 0 | 0 | 2 | 2 | 2.36 | 2.36
1190 | 100 MM - Butterfly valve | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Supply Charge | NOS | 2 | 1.18 | 2.36 | 0 | 0 | 0 | 0 | 1.18 | 0 | 2 | 2476.82 | 4953.64 | 0 | 0 | 0 | 2 | 2 | 2.36 | 2.36
1191 | 100MM Non ReturnValve | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Installation Charge | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 377.6 | 377.6 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
1192 | 100MM Non ReturnValve | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Supply Charge | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 2069.72 | 2069.72 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
1193 | Air release valves with Ball Valve | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Installation Charge | NOS | 2 | 1.18 | 2.36 | 0 | 0 | 0 | 0 | 1.18 | 0 | 2 | 153.4 | 306.8 | 0 | 0 | 0 | 2 | 2 | 2.36 | 2.36
1194 | Air release valves with Ball Valve | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Supply Charge | NOS | 2 | 1.18 | 2.36 | 0 | 0 | 0 | 0 | 1.18 | 0 | 2 | 1321.6 | 2643.2 | 0 | 0 | 0 | 2 | 2 | 2.36 | 2.36
1195 | Ball Valve of of 20 mm | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Installation Charge | NOS | 14 | 1.18 | 16.52 | 0 | 0 | 0 | 0 | 1.18 | 0 | 14 | 118 | 1652 | 0 | 0 | 0 | 14 | 14 | 16.52 | 16.52
1196 | Ball Valve of of 20 mm | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Supply Charge | NOS | 14 | 1.18 | 16.52 | 0 | 0 | 0 | 0 | 1.18 | 0 | 14 | 469.64 | 6574.96 | 0 | 0 | 0 | 14 | 14 | 16.52 | 16.52
1197 | SS Single Hydrant Valve of 80 mm inlet & 63 mm outlet dia | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Installation Charge | NOS | 14 | 1.18 | 16.52 | 0 | 0 | 0 | 0 | 1.18 | 0 | 14 | 236 | 3304 | 0 | 0 | 0 | 14 | 14 | 16.52 | 16.52
1198 | SS Single Hydrant Valve of 80 mm inlet & 63 mm outlet dia | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Supply Charge | NOS | 14 | 1.18 | 16.52 | 0 | 0 | 0 | 0 | 1.18 | 0 | 14 | 4248 | 59472 | 0 | 0 | 0 | 14 | 14 | 16.52 | 16.52
1199 | SINGLE DOOR HOSE BOX | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Installation Charge | NOS | 14 | 1.18 | 16.52 | 0 | 0 | 0 | 0 | 1.18 | 0 | 14 | 236 | 3304 | 0 | 0 | 0 | 14 | 14 | 16.52 | 16.52
1200 | SINGLE DOOR HOSE BOX | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Supply Charge | NOS | 14 | 1.18 | 16.52 | 0 | 0 | 0 | 0 | 1.18 | 0 | 14 | 1109.2 | 15528.8 | 0 | 0 | 0 | 14 | 14 | 16.52 | 16.52
1201 | HOSE PIPE | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Installation Charge | NOS | 14 | 1.18 | 16.52 | 0 | 0 | 0 | 0 | 1.18 | 0 | 14 | 118 | 1652 | 0 | 0 | 0 | 14 | 14 | 16.52 | 16.52
1202 | HOSE PIPE | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Supply Charge | NOS | 14 | 1.18 | 16.52 | 0 | 0 | 0 | 0 | 1.18 | 0 | 14 | 3584 | 50176 | 0 | 0 | 0 | 14 | 14 | 16.52 | 16.52
1203 | BRANCH PIPE | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Installation Charge | NOS | 14 | 1.18 | 16.52 | 0 | 0 | 0 | 0 | 1.18 | 0 | 14 | 118 | 1652 | 0 | 0 | 0 | 14 | 14 | 16.52 | 16.52
1204 | BRANCH PIPE | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Supply Charge | NOS | 14 | 1.18 | 16.52 | 0 | 0 | 0 | 0 | 1.18 | 0 | 14 | 1545.8 | 21641.2 | 0 | 0 | 0 | 14 | 14 | 16.52 | 16.52
1205 | HOSE REEL | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Installation Charge | NOS | 14 | 1.18 | 16.52 | 0 | 0 | 0 | 0 | 1.18 | 0 | 14 | 413 | 5782 | 0 | 0 | 0 | 14 | 14 | 16.52 | 16.52
1206 | HOSE REEL | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Supply Charge | NOS | 14 | 1.18 | 16.52 | 0 | 0 | 0 | 0 | 1.18 | 0 | 14 | 5428 | 75992 | 0 | 0 | 0 | 14 | 14 | 16.52 | 16.52
1207 | GI Pipe 150 mm dia (Hydrant) | 0 | Started | Labour | (L)Fire Hydrent Systems_Installation Charge (GI Pipes) | RMT | 42 | 1.18 | 49.56 | 0 | 0 | 0 | 0 | 1.18 | 0 | 42 | 743.4 | 31222.8 | 0 | 0 | 0 | 42 | 42 | 49.56 | 49.56
1208 | GI Pipe 150 mm dia (Hydrant) | 0 | Started | Labour | (L)Fire Hydrent Systems_Supply Charge (GI Pipes) | RMT | 42 | 1.18 | 49.56 | 0 | 0 | 0 | 0 | 1.18 | 0 | 42 | 2358.82 | 99070.44 | 42 | 2358.82 | 99070.44 | 42 | 0 | 49.56 | -99020.88
1209 | GI Pipe 100 mm dia (Booster) | 0 | Started | Labour | (L)Fire Hydrent Systems_Installation Charge (GI Pipes) | RMT | 18 | 1.18 | 21.24 | 0 | 0 | 0 | 0 | 1.18 | 0 | 18 | 495.6 | 8920.8 | 0 | 0 | 0 | 18 | 18 | 21.24 | 21.24
1210 | GI Pipe 100 mm dia (Booster) | 0 | Started | Labour | (L)Fire Hydrent Systems_Supply Charge (GI Pipes) | RMT | 18 | 1.18 | 21.24 | 0 | 0 | 0 | 0 | 1.18 | 0 | 18 | 1611.88 | 29013.84 | 18 | 1611.88 | 29013.84 | 18 | 0 | 21.24 | -28992.6
1211 | GI Pipe 80 mm dia (Tapping) | 0 | Started | Labour | (L)Fire Hydrent Systems_Installation Charge (GI Pipes) | RMT | 9 | 1.18 | 10.62 | 0 | 0 | 0 | 0 | 1.18 | 0 | 9 | 371.7 | 3345.3 | 0 | 0 | 0 | 9 | 9 | 10.62 | 10.62
1212 | GI Pipe 80 mm dia (Tapping) | 0 | Started | Labour | (L)Fire Hydrent Systems_Supply Charge (GI Pipes) | RMT | 9 | 1.18 | 10.62 | 0 | 0 | 0 | 0 | 1.18 | 0 | 9 | 1131.62 | 10184.58 | 9 | 1131.62 | 10184.58 | 9 | 0 | 10.62 | -10173.96
1213 | TALK BACK PANEL -14 ZONE | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Installation Charge | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 5380.8 | 5380.8 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
1214 | TALK BACK PANEL -14 ZONE | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Supply Charge | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 14160 | 14160 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
1215 | TALK BACK UNIT | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Installation Charge | NOS | 13 | 1.18 | 15.34 | 0 | 0 | 0 | 0 | 1.18 | 0 | 13 | 283.2 | 3681.6 | 0 | 0 | 0 | 13 | 13 | 15.34 | 15.34
1216 | TALK BACK UNIT | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Supply Charge | NOS | 13 | 1.18 | 15.34 | 0 | 0 | 0 | 0 | 1.18 | 0 | 13 | 637.2 | 8283.6 | 0 | 0 | 0 | 13 | 13 | 15.34 | 15.34
1217 | 0.5Sq.mm X 5Core Copper Flexible Cable | 0 | Tentative | Labour | (L)Fire Hydrent Systems_Installation Charge (Cable) | RMT | 60 | 1.18 | 70.8 | 0 | 0 | 0 | 0 | 1.18 | 0 | 60 | 42.48 | 2548.8 | 0 | 0 | 0 | 60 | 60 | 70.8 | 70.8
1218 | 0.5Sq.mm X 5Core Copper Flexible Cable | 0 | Tentative | Labour | (L)Fire Hydrent Systems_Supply Charge (Cable) | RMT | 60 | 1.18 | 70.8 | 0 | 0 | 0 | 0 | 1.18 | 0 | 60 | 56.64 | 3398.4 | 0 | 0 | 0 | 60 | 60 | 70.8 | 70.8
1219 | Battery | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Installation Charge | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 283.2 | 283.2 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
1220 | Battery | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Supply Charge | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 1228.8 | 1228.8 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
1221 | FIRE EXTINGUISHER -10 Kg MODULER TYPE | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Installation Charge | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 413 | 413 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
1222 | FIRE EXTINGUISHER -10 Kg MODULER TYPE | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Supply Charge | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 4248 | 4248 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
1223 | FIRE EXTINGUISHER - 6 Kg ABC TYPE | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Installation Charge | NOS | 48 | 1.18 | 56.64 | 0 | 0 | 0 | 0 | 1.18 | 0 | 48 | 153.4 | 7363.2 | 0 | 0 | 0 | 48 | 48 | 56.64 | 56.64
1224 | FIRE EXTINGUISHER - 6 Kg ABC TYPE | 0 | Tentative | Labour | (L)Fire Hydrent Systems-Supply Charge | NOS | 48 | 1.18 | 56.64 | 0 | 0 | 0 | 0 | 1.18 | 0 | 48 | 1203.6 | 57772.8 | 0 | 0 | 0 | 48 | 48 | 56.64 | 56.64
1225 | STRUCTURAL STEEL [100 X 50] | 0 | Tentative | Labour | (L)Fire Hydrent Systems_Installation Charge (Stru.Steel | RMT | 15 | 1.18 | 17.7 | 0 | 0 | 0 | 0 | 1.18 | 0 | 15 | 318.6 | 4779 | 0 | 0 | 0 | 15 | 15 | 17.7 | 17.7
1226 | STRUCTURAL STEEL [100 X 50] | 0 | Tentative | Labour | (L)Fire Hydrent Systems_Supply Charge (Stru.Steel) | RMT | 15 | 1.18 | 17.7 | 0 | 0 | 0 | 0 | 1.18 | 0 | 15 | 1014.8 | 15222 | 0 | 0 | 0 | 15 | 15 | 17.7 | 17.7
1227 | INDENT-509/B WING/WATERPROOFING WORK | 10 | Started | Material | (M)Artificial Sand | BRASS | 92 | 5880 | 540960 | 92 | 5880 | 540960 | 9 | 5880 | 52920 | 92 | 5880 | 540960 | 0 | 0 | 0 | 83 | 92 | 488040 | 540960
1228 | INDENT-509/B WING/WATERPROOFING WORK | 10 | Started | Material | (M)CEMENT PPC 50KG | BAG | 1486 | 320 | 475520 | 1486 | 320 | 475520 | 149 | 320 | 47680 | 311 | 300.23 | 93371.8812 | 0 | 0 | 0 | 1337 | 1486 | 427840 | 475520
1229 | INDENT-509/B WING/WATERPROOFING WORK | 10 | Started | Material | (M)Dr.Fixit LW+ 50Ltr Drum | DRUM | 8 | 3800 | 30400 | 8 | 3800 | 30400 | 1 | 3800 | 3800 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 8 | 26600 | 30400
1230 | INDENT-509/B WING/WATERPROOFING WORK | 10 | Started | Material | (M)Pidifin - 2k - 15kg | PACKET | 228 | 1465 | 334020 | 228 | 1465 | 334020 | 23 | 1465 | 33695 | 0 | 0 | 0 | 0 | 0 | 0 | 205 | 228 | 300325 | 334020
1231 | INDENT-509/B WING/WATERPROOFING WORK | 10 | Started | Material | (M)Red Bricks 4" | NOS | 73012 | 8.5 | 620602 | 73012 | 8.5 | 620602 | 7301 | 8.5 | 62058.5 | 73012 | 8.4 | 613300.8 | 0 | 0 | 0 | 65711 | 73012 | 558543.5 | 620602
1232 | INDENT-840/B BLDG/TOP TERRACE & OHWT WP | 10 | Started | Material | (M)Artificial Sand | BRASS | 30 | 5880 | 176400 | 30 | 5880 | 176400 | 3 | 5880 | 17640 | 30 | 6195 | 185850 | 0 | 0 | 0 | 27 | 30 | 158760 | 176400
1233 | INDENT-840/B BLDG/TOP TERRACE & OHWT WP | 10 | Started | Material | (M)CEMENT PPC 50KG | BAG | 486 | 320 | 155520 | 486 | 320 | 155520 | 49 | 320 | 15680 | 486 | 305 | 148229.2224 | 55 | 304.61 | 16753.41 | 437 | 431 | 139840 | 138766.59
1234 | INDENT-840/B BLDG/TOP TERRACE & OHWT WP | 10 | Started | Material | (M)Dr.Fixit LW+ 50Ltr Drum | DRUM | 2 | 3800 | 7600 | 2 | 3800 | 7600 | 0 | 3800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 7600 | 7600
1235 | INDENT-840/B BLDG/TOP TERRACE & OHWT WP | 10 | Started | Material | (M)Pidifin - 2k - 15kg | PACKET | 130 | 1465 | 190450 | 130 | 1465 | 190450 | 13 | 1465 | 19045 | 0 | 0 | 0 | 0 | 0 | 0 | 117 | 130 | 171405 | 190450
1236 | INDENT-840/B BLDG/TOP TERRACE & OHWT WP | 10 | Started | Material | (M)Red Bricks 4" | NOS | 37400 | 8.5 | 317900 | 37400 | 8.5 | 317900 | 3740 | 8.5 | 31790 | 0 | 0 | 0 | 0 | 0 | 0 | 33660 | 37400 | 286110 | 317900
1237 | B BLDG: CHEM. COATING-1,2,3,4 FLOOR | 0 | Tentative | Labour | (L)CHEMICAL COAT (WP WORK) | NOS | 29180 | 1 | 29180 | 0 | 0 | 0 | 0 | 1 | 0 | 29180 | 1 | 29180 | 0 | 0 | 0 | 29180 | 29180 | 29180 | 29180
1238 | B BLDG: CHEM. COATING-5,6,7,8 FLOOR | 0 | Tentative | Labour | (L)CHEMICAL COAT (WP WORK) | NOS | 32098 | 1 | 32098 | 0 | 0 | 0 | 0 | 1 | 0 | 32098 | 1 | 32098 | 0 | 0 | 0 | 32098 | 32098 | 32098 | 32098
1239 | B BLDG: CHEM. COATING-9,10,11,12 FLOOR | 0 | Tentative | Labour | (L)CHEMICAL COAT (WP WORK) | NOS | 35988 | 1 | 35988 | 0 | 0 | 0 | 0 | 1 | 0 | 35988 | 1 | 35988 | 0 | 0 | 0 | 35988 | 35988 | 35988 | 35988
1240 | B BLDG: BASE COAT-1,2,3,4 FLOOR | 0 | Tentative | Labour | (L)BASE COAT (WP WORK) | NOS | 53496 | 1 | 53496 | 0 | 0 | 0 | 0 | 1 | 0 | 53496 | 1 | 53496 | 0 | 0 | 0 | 53496 | 53496 | 53496 | 53496
1241 | B BLDG: BASE COAT-5,6,7,8 FLOOR | 0 | Tentative | Labour | (L)BASE COAT (WP WORK) | NOS | 58845 | 1 | 58845 | 0 | 0 | 0 | 0 | 1 | 0 | 58845 | 1 | 58845 | 0 | 0 | 0 | 58845 | 58845 | 58845 | 58845
1242 | B BLDG: BASE COAT-9,10,11,12 FLOOR | 0 | Tentative | Labour | (L)BASE COAT (WP WORK) | NOS | 65978 | 1 | 65978 | 0 | 0 | 0 | 0 | 1 | 0 | 65978 | 1 | 65978 | 0 | 0 | 0 | 65978 | 65978 | 65978 | 65978
1243 | B BLDG: BRICK BAT TERRACE-1,2,3,4 FLOOR | 0 | Tentative | Labour | (L)BRICK BAT (WP WORK) | NOS | 20770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20770 | 1 | 20770 | 0 | 0 | 0 | 20770 | 20770 | 0 | 0
1244 | B BLDG: BRICK BAT TERRACE-5,6,7,8 FLOOR | 0 | Tentative | Labour | (L)BRICK BAT (WP WORK) | NOS | 22290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22290 | 1 | 22290 | 0 | 0 | 0 | 22290 | 22290 | 0 | 0
1245 | B BLDG: BRICK BAT TERRACE-9,10,11,12 FLOOR | 0 | Started | Labour | (L)BRICK BAT (WP WORK) | NOS | 23810 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23810 | 1 | 23810 | 23810 | 1 | 23810 | 23810 | 0 | 0 | -23810
1246 | B BLDG: BRICK BAT TOILET & D.BAL-1,2,3,4 FLOOR | 0 | Tentative | Labour | (L)BRICK BAT (WP WORK) | NOS | 41034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41034 | 1 | 41034 | 0 | 0 | 0 | 41034 | 41034 | 0 | 0
1247 | B BLDG: BRICK BAT TOILET & D.BAL-5,6,7,8 FLOOR | 0 | Tentative | Labour | (L)BRICK BAT (WP WORK) | NOS | 45086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45086 | 1 | 45086 | 0 | 0 | 0 | 45086 | 45086 | 0 | 0
1248 | B BLDG: BRICK BAT TOILET & D.BAL-9,10,11,12 FLOOR | 0 | Tentative | Labour | (L)BRICK BAT (WP WORK) | NOS | 49645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49645 | 1 | 49645 | 0 | 0 | 0 | 49645 | 49645 | 0 | 0
1249 | B BLDG: FINISHING TERRACE-1,2,3,4 FLOOR | 0 | Tentative | Labour | (L)FINISHING (WP WORK) | NOS | 25076 | 1 | 25076 | 0 | 0 | 0 | 0 | 1 | 0 | 25076 | 1 | 25076 | 0 | 0 | 0 | 25076 | 25076 | 25076 | 25076
1250 | B BLDG: FINISHING TERRACE-5,6,7,8 FLOOR | 0 | Started | Labour | (L)FINISHING (WP WORK) | NOS | 27356 | 1 | 27356 | 0 | 0 | 0 | 0 | 1 | 0 | 27356 | 1 | 27356 | 13678 | 1 | 13678 | 27356 | 13678 | 27356 | 13678
1251 | B BLDG: FINISHING TERRACE-9,10,11,12 FLOOR | 0 | Started | Labour | (L)FINISHING (WP WORK) | NOS | 29636 | 1 | 29636 | 0 | 0 | 0 | 0 | 1 | 0 | 29636 | 1 | 29636 | 29636 | 1 | 29636 | 29636 | 0 | 29636 | 0
1252 | B BLDG: FINISHING TOILET & D.BALC-1,2,3,4 FLOOR | 0 | Tentative | Labour | (L)FINISHING (WP WORK) | NOS | 55472 | 1 | 55472 | 0 | 0 | 0 | 0 | 1 | 0 | 55472 | 1 | 55472 | 0 | 0 | 0 | 55472 | 55472 | 55472 | 55472
1253 | B BLDG: FINISHING TOILET & D.BALC-5,6,7,8 FLOOR | 0 | Tentative | Labour | (L)FINISHING (WP WORK) | NOS | 61550 | 1 | 61550 | 0 | 0 | 0 | 0 | 1 | 0 | 61550 | 1 | 61550 | 0 | 0 | 0 | 61550 | 61550 | 61550 | 61550
1254 | B BLDG: FINISHING TOILET & D.BALC-9,10,11,12 FLOOR | 0 | Tentative | Labour | (L)FINISHING (WP WORK) | NOS | 68390 | 1 | 68390 | 0 | 0 | 0 | 0 | 1 | 0 | 68390 | 1 | 68390 | 0 | 0 | 0 | 68390 | 68390 | 68390 | 68390
1255 | B BLDG: FINISHING STANDING BALC.COMP-UPTO 6TH | 0 | Tentative | Labour | (L)FINISHING (WP WORK) | NOS | 18237 | 1 | 18237 | 0 | 0 | 0 | 0 | 1 | 0 | 18237 | 1 | 18237 | 0 | 0 | 0 | 18237 | 18237 | 18237 | 18237
1256 | B BLDG: FINISHING STANDING BALC.COMP-UPTO 12TH | 0 | Tentative | Labour | (L)FINISHING (WP WORK) | NOS | 18237 | 1 | 18237 | 0 | 0 | 0 | 0 | 1 | 0 | 18237 | 1 | 18237 | 0 | 0 | 0 | 18237 | 18237 | 18237 | 18237
1257 | B BLDG: COMPL.OF ALL FLAT | 0 | Tentative | Labour | (L)KIT.KATTA (WP WORK) | NOS | 16211 | 1.18 | 19128.98 | 0 | 0 | 0 | 0 | 1.18 | 0 | 16211 | 1 | 16211 | 0 | 0 | 0 | 16211 | 16211 | 19128.98 | 19128.98
1258 | B BLDG: COMPL. FO ALL FLAT WORK | 0 | Tentative | Labour | (L)CLEANING (WP WORK) | NOS | 12158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12158 | 1 | 12158 | 0 | 0 | 0 | 12158 | 12158 | 0 | 0
1259 | B BLDG: RETENTION | 0 | Tentative | Labour | (L)RETENTION (WP WORK) | NOS | 90060 | 1 | 90060 | 0 | 0 | 0 | 0 | 1 | 0 | 90060 | 1 | 90060 | 0 | 0 | 0 | 90060 | 90060 | 90060 | 90060
1260 | B WING INTERNAL DUCT WATERPROOFING WORK | 0 | Started | Labour | (L)Waterproofing (Lab) | SQFT | 504.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 504.37 | 21 | 10591.77 | 504.37 | 21 | 10591.77 | 504.37 | 0 | 0 | -10591.77
1261 | INDENT-984/B WING/TOP TERRACE/WATERPROOFING WORK | 0 | Started | Labour | (L)Waterproofing (Lab) | SQFT | 7322.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7322.39 | 21 | 153770.19 | 7322.39 | 21 | 153770.19 | 7322.39 | 0 | 0 | -153770.19
1262 | INDENT-37/B BLDG/TOP TERR.EXTERNAL BOX WP WORK | 0 | Started | Labour | (L)Waterproofing (Lab) | SQFT | 1773.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1773.89 | 21 | 37251.69 | 1773.89 | 21 | 37251.69 | 1773.89 | 0 | 0 | -37251.69
1263 | INDENT-37/B BLDG/TOP TERR.KANI WP WORK | 0 | Started | Labour | (L)TOP TERRACE KANI WP | RFT | 930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 930 | 12 | 11160 | 930 | 12 | 11160 | 930 | 0 | 0 | -11160
1264 | INDENT-37/B BLDG/8TH FLOOR REFUGE AREA WP WORK | 0 | Started | Labour | (L)Waterproofing (Lab) | SQFT | 580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 580 | 21 | 12180 | 557.4 | 21 | 11705.4 | 580 | 22.6 | 0 | -11705.4
1265 | INDENT-37/B BLDG/OHWT (ABV.FIRE ST CASE) WP WORK | 0 | Started | Labour | (L)Waterproofing (Lab) | SQFT | 1222.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1222.87 | 21 | 25680.27 | 1222.87 | 21 | 25680.27 | 1222.87 | 0 | 0 | -25680.27
1266 | INDENT-37/B BLDG/OHWT (ABV.MAIN ST CASE) WP WORK | 0 | Started | Labour | (L)Waterproofing (Lab) | SQFT | 1579.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1579.89 | 21 | 33177.69 | 1417.95 | 21 | 29776.95 | 1579.89 | 161.94 | 0 | -29776.95
1267 | INDENT-20/B WING/BOTH LIFT SHAFT ELECTRICAL WORK | 10 | Started | Material | (M)16 amp 2-way SP switch-1module | NOS | 8 | 130 | 1040 | 8 | 130 | 1040 | 1 | 130 | 130 | 8 | 100.3 | 802.4 | 0 | 0 | 0 | 7 | 8 | 910 | 1040
1268 | INDENT-20/B WING/BOTH LIFT SHAFT ELECTRICAL WORK | 10 | Started | Material | (M)16amp 4 Pole MCB-Type C | NOS | 2 | 1020 | 2040 | 2 | 1020 | 2040 | 0 | 1020 | 0 | 2 | 1319.24 | 2638.48 | 0 | 0 | 0 | 2 | 2 | 2040 | 2040
1269 | INDENT-20/B WING/BOTH LIFT SHAFT ELECTRICAL WORK | 10 | Started | Material | (M)2.5 sq.mm x 3 core Copper Armoured Cable | RMT | 310 | 136 | 42160 | 310 | 136 | 42160 | 31 | 136 | 4216 | 310 | 140.84 | 43661.888 | 0 | 0 | 0 | 279 | 310 | 37944 | 42160
1270 | INDENT-20/B WING/BOTH LIFT SHAFT ELECTRICAL WORK | 10 | Started | Material | (M)20W LED Tubelight-4 Ft | NOS | 34 | 190.1 | 6463.4 | 34 | 190.1 | 6463.4 | 3 | 190.1 | 570.3 | 34 | 188.8 | 6419.2 | 0 | 0 | 0 | 31 | 34 | 5893.1 | 6463.4
1271 | INDENT-20/B WING/BOTH LIFT SHAFT ELECTRICAL WORK | 10 | Started | Material | (M)25amp 2 Pole MCB-Type C | NOS | 2 | 750 | 1500 | 2 | 750 | 1500 | 0 | 750 | 0 | 2 | 613.6 | 1227.2 | 0 | 0 | 0 | 2 | 2 | 1500 | 1500
1272 | INDENT-20/B WING/BOTH LIFT SHAFT ELECTRICAL WORK | 10 | Started | Material | (M)4 sq.mm x 4 core Copper Armoured Cable | RMT | 150 | 198 | 29700 | 150 | 198 | 29700 | 15 | 198 | 2970 | 150 | 254.17 | 38125.8 | 0 | 0 | 0 | 135 | 150 | 26730 | 29700
1273 | INDENT-20/B WING/BOTH LIFT SHAFT ELECTRICAL WORK | 10 | Started | Material | (M)6A Sockets | NOS | 30 | 177 | 5310 | 30 | 177 | 5310 | 3 | 177 | 531 | 30 | 35.4 | 1062 | 0 | 0 | 0 | 27 | 30 | 4779 | 5310
1274 | INDENT-20/B WING/BOTH LIFT SHAFT ELECTRICAL WORK | 10 | Started | Material | (M)6A Switches | NOS | 64 | 41.3 | 2643.2 | 64 | 41.3 | 2643.2 | 6 | 41.3 | 247.8 | 64 | 16.52 | 1057.28 | 0 | 0 | 0 | 58 | 64 | 2395.4 | 2643.2
1275 | INDENT-20/B WING/BOTH LIFT SHAFT ELECTRICAL WORK | 10 | Started | Material | (M)8 Gauge Copper wire | RMT | 310 | 469 | 145390 | 310 | 469 | 145390 | 31 | 469 | 14539 | 310 | 151.5 | 46963.977 | 0 | 0 | 0 | 279 | 310 | 130851 | 145390
1276 | INDENT-20/B WING/BOTH LIFT SHAFT ELECTRICAL WORK | 10 | Started | Material | (M)Flexible Cable 2.5 sq.mm x 2 core | RMT | 110 | 100 | 11000 | 110 | 100 | 11000 | 11 | 100 | 1100 | 100 | 86.46 | 8646.4 | 0 | 0 | 0 | 99 | 110 | 9900 | 11000
1277 | INDENT-20/B WING/BOTH LIFT SHAFT ELECTRICAL WORK | 10 | Started | Material | (M)MS Saddle 3/4" | NOS | 800 | 8 | 6400 | 800 | 8 | 6400 | 80 | 8 | 640 | 720 | 1.72 | 1235.52 | 0 | 0 | 0 | 720 | 800 | 5760 | 6400
1278 | INDENT-20/B WING/BOTH LIFT SHAFT ELECTRICAL WORK | 10 | Started | Material | (M)PVC Conduits Pipe 20mm-3mtr | NOS | 35 | 35 | 1225 | 35 | 35 | 1225 | 4 | 35 | 140 | 35 | 47.2 | 1652 | 0 | 0 | 0 | 31 | 35 | 1085 | 1225
1279 | INDENT-20/B WING/BOTH LIFT SHAFT ELECTRICAL WORK | 10 | Started | Material | (M)Raval Plug | NOS | 1200 | 1.18 | 1416 | 1200 | 1.18 | 1416 | 120 | 1.18 | 141.6 | 1200 | 0.47 | 566.4 | 0 | 0 | 0 | 1080 | 1200 | 1274.4 | 1416
1280 | INDENT-20/B WING/BOTH LIFT SHAFT ELECTRICAL WORK | 10 | Started | Material | (M)RCBO 16amp - FP - 300mA (B-Type) | NOS | 1 | 3127 | 3127 | 1 | 3127 | 3127 | 0 | 3127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3127 | 3127
1281 | INDENT-20/B WING/BOTH LIFT SHAFT ELECTRICAL WORK | 10 | Started | Material | (M)RCBO 25amp - DP - 30mA (A-Type) | NOS | 1 | 3351.2 | 3351.2 | 1 | 3351.2 | 3351.2 | 0 | 3351.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3351.2 | 3351.2
1282 | INDENT-20/B WING/BOTH LIFT SHAFT ELECTRICAL WORK | 10 | Started | Material | (M)Screw 8 x 35mm | NOS | 1600 | 0.77 | 1232 | 1600 | 0.77 | 1232 | 160 | 0.77 | 123.2 | 1600 | 0.77 | 1227.2 | 0 | 0 | 0 | 1440 | 1600 | 1108.8 | 1232
1283 | INDENT-20/B WING/BOTH LIFT SHAFT ELECTRICAL WORK | 10 | Started | Material | (M)Screw 8 x 75mm | KG | 180 | 1.42 | 255.6 | 180 | 1.42 | 255.6 | 18 | 1.42 | 25.56 | 180 | 1.78 | 320.994 | 0 | 0 | 0 | 162 | 180 | 230.04 | 255.6
1284 | INDENT-20/B WING/BOTH LIFT SHAFT ELECTRICAL WORK | 10 | Started | Material | (M)Sunmike Board 8'' x 10'' | NOS | 30 | 150 | 4500 | 30 | 150 | 4500 | 3 | 150 | 450 | 30 | 94.4 | 2832 | 0 | 0 | 0 | 27 | 30 | 4050 | 4500
1285 | B BLDG ELEC.WORK (MAT.)- SLAB PIPING 1ST TO 13TH SLAB | 0 | Tentative | Labour | (L)SLAB PIPING | Slab | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 82472.74 | 1072145.6394 | 0 | 0 | 0 | 13 | 13 | 0 | 0
1286 | B BLDG ELEC.WORK (MAT.)- WALL PIPING 1ST TO 12TH FLOOR | 0 | Tentative | Labour | (L)WALL PIPING | FLOORS | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 63419.1 | 761029.2 | 0 | 0 | 0 | 12 | 12 | 0 | 0
1287 | B BLDG ELEC.WORK (MAT.)- DB FIXING 1ST TO 12TH FLOOR | 0 | Tentative | Labour | (L)DB FIXING | FLOORS | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 16992 | 203904 | 0 | 0 | 0 | 12 | 12 | 0 | 0
1288 | B BLDG ELEC.WORK (MAT.)- WIRING 1ST TO 12TH FLOOR | 0 | Started | Labour | (L)WIRING | FLOORS | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 147419.76 | 1769037.12 | 7 | 147419.76 | 1031938.32 | 12 | 5 | 0 | -1031938.32
1289 | B BLDG ELEC.WORK (MAT.)- PLATES & SWITCHES 1ST TO 12TH FLOOR | 0 | Started | Labour | (L)PLATES & SWITCHES | FLOORS | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 129551.02 | 1554612.24 | 5 | 129551.02 | 647755.1 | 12 | 7 | 0 | -647755.1
1290 | B BLDG ELEC.WORK (MAT.)- TESTING ALL FLOOR FLATS | 0 | Tentative | Labour | (L)ELECTRICAL WORK. | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 57333.84 | 57333.84 | 0 | 0 | 0 | 1 | 1 | 0 | 0
1291 | B BLDG ELEC.WORK (MAT.)-RETENTION AFTER COMP. OF RET. PERIOD | 0 | Tentative | Labour | (L)ELECTRICAL WORK. | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 199076.62 | 199076.62 | 0 | 0 | 0 | 1 | 1 | 0 | 0
1292 | B BLDG ELEC.WORK (LAB.)- SLAB PIPING 1ST TO 13TH SLAB | 0 | Tentative | Labour | (L)SLAB PIPING | Slab | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 27180.31 | 353344.0001 | 0 | 0 | 0 | 13 | 13 | 0 | 0
1293 | B BLDG ELEC.WORK (LAB.)- WALL PIPING 1ST TO 12TH FLOOR | 0 | Tentative | Labour | (L)WALL PIPING | FLOORS | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 20900.67 | 250808.0004 | 0 | 0 | 0 | 12 | 12 | 0 | 0
1294 | B BLDG ELEC.WORK (LAB.)- DB FIXING 1ST TO 12TH FLOOR | 0 | Tentative | Labour | (L)DB FIXING | FLOORS | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 5600 | 67200 | 0 | 0 | 0 | 12 | 12 | 0 | 0
1295 | B BLDG ELEC.WORK (LAB.)- WIRING 1ST TO 12TH FLOOR | 0 | Started | Labour | (L)WIRING | FLOORS | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 48585 | 583020 | 8 | 48585 | 388680 | 12 | 4 | 0 | -388680
1296 | B BLDG ELEC.WORK (LAB.)- PLATES & SWITCHES 1ST TO 12TH FLOOR | 0 | Tentative | Labour | (L)PLATES & SWITCHES | FLOORS | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 42696 | 512352 | 0 | 0 | 0 | 12 | 12 | 0 | 0
1297 | B BLDG ELEC.WORK (LAB.)- TESTING ALL FLOOR FLATS | 0 | Tentative | Labour | (L)ELECTRICAL WORK. | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 18895 | 18895 | 0 | 0 | 0 | 1 | 1 | 0 | 0
1298 | B BLDG ELEC.WORK (LAB.)- PF AMOUNT | 0 | Tentative | Labour | (L)ELECTRICAL WORK. | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 33742 | 33742 | 0 | 0 | 0 | 1 | 1 | 0 | 0
1299 | B BLDG ELEC.WORK (LAB.)-RETENTION AFTER COMP. OF RET. PERIOD | 0 | Tentative | Labour | (L)ELECTRICAL WORK. | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 168709 | 168709 | 0 | 0 | 0 | 1 | 1 | 0 | 0
1300 | B WING METER ROOM PLY WORK | 0 | Started | Material | (M)Backlight Sheet 8' x 4' x 3mm | NOS | 12 | 2000 | 24000 | 12 | 2000 | 24000 | 0 | 2000 | 0 | 12 | 1166.67 | 14000.04 | 0 | 0 | 0 | 12 | 12 | 24000 | 24000
1301 | B WING METER ROOM PLY WORK | 0 | Started | Material | (M)Plywood 8' x 4' x 20mm (Waterproofing) | NOS | 13 | 2500 | 32500 | 13 | 2500 | 32500 | 0 | 2500 | 0 | 13 | 2710.61 | 35237.93 | 0 | 0 | 0 | 13 | 13 | 32500 | 32500
1302 | B WING METER ROOM PLY WORK | 0 | Started | Material | (M)PVC Raval Plug 75 X 8 | NOS | 800 | 0.59 | 472 | 800 | 0.59 | 472 | 0 | 0.59 | 0 | 800 | 4.98 | 3984 | 0 | 0 | 0 | 800 | 800 | 472 | 472
1303 | B WING METER ROOM PLY WORK | 0 | Started | Material | (M)Self Tapping Screw 6 x 19mm | NOS | 400 | 1.18 | 472 | 400 | 1.18 | 472 | 0 | 1.18 | 0 | 400 | 1.18 | 472.4 | 0 | 0 | 0 | 400 | 400 | 472 | 472
1304 | B WING METER ROOM PLY WORK | 0 | Started | Material | (M)SS Wood Screw 100 x 12mm | NOS | 700 | 2.36 | 1652 | 700 | 2.36 | 1652 | 0 | 2.36 | 0 | 700 | 7.22 | 5056.8 | 0 | 0 | 0 | 700 | 700 | 1652 | 1652
1305 | B BLDG (AUTO CHANGEOVER PANEL & SUB DIST. PANEL) | 0 | Tentative | Material | (M)14_Common Area Changeover Panel (B Wing Meter) | SET | 1 | 70800 | 70800 | 1 | 70800 | 70800 | 0 | 70800 | 0 | 1 | 77996.82 | 77996.82 | 0 | 0 | 0 | 1 | 1 | 70800 | 70800
1306 | B BLDG (AUTO CHANGEOVER PANEL & SUB DIST. PANEL) | 0 | Tentative | Material | (M)19_B Bldg Mech.Parking C/O Panel-4 (Locn-DTC) | SET | 1 | 88500 | 88500 | 1 | 88500 | 88500 | 0 | 88500 | 0 | 1 | 70440.1 | 70440.1 | 0 | 0 | 0 | 1 | 1 | 88500 | 88500
1307 | B BLDG (AUTO CHANGEOVER PANEL & SUB DIST. PANEL) | 0 | Tentative | Material | (M)2_Sub Dist.Panel-2 (B Wing Meter Room-1) | SET | 1 | 76700 | 76700 | 1 | 76700 | 76700 | 0 | 76700 | 0 | 1 | 61455.58 | 61455.58 | 0 | 0 | 0 | 1 | 1 | 76700 | 76700
1308 | B BLDG (AUTO CHANGEOVER PANEL & SUB DIST. PANEL) | 0 | Tentative | Material | (M)28_METER ROOM BUS BAR PANEL-1 (LOCN- B,C BLDG) | SET | 4 | 25877.4 | 103509.6 | 4 | 25877.4 | 103509.6 | 0 | 25877.4 | 0 | 4 | 18880 | 75520 | 0 | 0 | 0 | 4 | 4 | 103509.6 | 103509.6
1309 | B BLDG (AUTO CHANGEOVER PANEL & SUB DIST. PANEL) | 0 | Tentative | Material | (M)29_METER ROOM BUS BAR PANEL-2 (LOCM- B,C BLDG) | SET | 2 | 22915.6 | 45831.2 | 2 | 22915.6 | 45831.2 | 0 | 22915.6 | 0 | 2 | 15930 | 31860 | 0 | 0 | 0 | 2 | 2 | 45831.2 | 45831.2
1310 | B BLDG (AUTO CHANGEOVER PANEL & SUB DIST. PANEL) | 0 | Tentative | Material | (M)3_Sub Dist.Panel-3 (B Wing Meter Room-2) | SET | 1 | 76700 | 76700 | 1 | 76700 | 76700 | 0 | 76700 | 0 | 1 | 61455.58 | 61455.58 | 0 | 0 | 0 | 1 | 1 | 76700 | 76700
1311 | B BLDG (AUTO CHANGEOVER PANEL & SUB DIST. PANEL) | 0 | Tentative | Material | (M)5_B Bldg Mech.Parking Meter Panel-4 (Locn-DTC) | SET | 1 | 47200 | 47200 | 1 | 47200 | 47200 | 0 | 47200 | 0 | 1 | 47299.12 | 47299.12 | 0 | 0 | 0 | 1 | 1 | 47200 | 47200
1312 | B BLDG VIDEO DOOR PHONE SYSTEM -(MATERIAL + LABOUR) | 0 | Tentative | Material | (M)Caller ID Instrument | SET | 2 | 5900 | 11800 | 2 | 5900 | 11800 | 0 | 5900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 11800 | 11800
1313 | B BLDG VIDEO DOOR PHONE SYSTEM -(MATERIAL + LABOUR) | 0 | Tentative | Material | (M)Intercom Telephone | SET | 122 | 2832 | 345504 | 122 | 2832 | 345504 | 0 | 2832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122 | 122 | 345504 | 345504
1314 | B BLDG VIDEO DOOR PHONE SYSTEM -(MATERIAL + LABOUR) | 0 | Tentative | Material | (M)Video Door Phone (VDP) | SET | 120 | 8850 | 1062000 | 120 | 8850 | 1062000 | 0 | 8850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 120 | 1062000 | 1062000
1315 | B WING ELECTRICAL MAINS PIPING -BRACKET FIXING MATERIAL | 0 | Started | Material | (M)FASTNER 12 X 100 | NOS | 90 | 33.04 | 2973.6 | 90 | 33.04 | 2973.6 | 0 | 33.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 90 | 2973.6 | 2973.6
1316 | B BLDG 2ND FLOOR 5 NOS FLAT ELECTRICAL WORK | 0 | Started | Material | (M)1.0 Sqmm 2 Core Polycab Copper Flexible Cable | RMT | 360 | 23.6 | 8496 | 360 | 23.6 | 8496 | 0 | 23.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360 | 360 | 8496 | 8496
1317 | B BLDG 2ND FLOOR 5 NOS FLAT ELECTRICAL WORK | 0 | Started | Material | (M)1.5 Sqmm 2 Core Polycab Copper Flexible Cable | RMT | 270 | 33.64 | 9082.8 | 270 | 33.64 | 9082.8 | 0 | 33.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270 | 270 | 9082.8 | 9082.8
1318 | B BLDG 2ND FLOOR 5 NOS FLAT ELECTRICAL WORK | 0 | Started | Material | (M)Insulation Tape | NOS | 5 | 11.8 | 59 | 5 | 11.8 | 59 | 0 | 11.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 59 | 59
1319 | B BLDG 2ND FLOOR 5 NOS FLAT ELECTRICAL WORK | 0 | Started | Material | (M)LED Tube Light-10wt | NOS | 22 | 159.3 | 3504.6 | 22 | 159.3 | 3504.6 | 0 | 159.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 22 | 3504.6 | 3504.6
1320 | B BLDG 2ND FLOOR 5 NOS FLAT ELECTRICAL WORK | 0 | Started | Material | (M)SPIKE GUARD (3MTR/NOS) | NOS | 10 | 165.2 | 1652 | 10 | 165.2 | 1652 | 0 | 165.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 1652 | 1652
1321 | B.Bldg Wall Gyp.Mat- 1st & 2nd Floor | 0 | Tentative | Labour | (L)Wall Gypsum Work | SQFT | 14563.4783 | 27.14 | 395252.8 | 0 | 0 | 0 | 0 | 27.14 | 0 | 14563.4783 | 24.15 | 351708.0009 | 0 | 0 | 0 | 14563.4783 | 14563.4783 | 395252.801 | 395252.8011
1322 | B.Bldg Wall Gyp.Mat- 3rd & 4th Floor | 0 | Tentative | Labour | (L)Wall Gypsum Work | SQFT | 14563.4783 | 27.14 | 395252.8 | 0 | 0 | 0 | 0 | 27.14 | 0 | 14563.4783 | 24.15 | 351708.0009 | 0 | 0 | 0 | 14563.4783 | 14563.4783 | 395252.801 | 395252.8011
1323 | B.Bldg Wall Gyp.Mat- 5th & 6th Floor | 0 | Started | Labour | (L)Wall Gypsum Work | SQFT | 15603.6956 | 27.14 | 423484.3 | 0 | 0 | 0 | 0 | 27.14 | 0 | 15603.6956 | 24.15 | 376829.2588 | 7801.8478 | 24.15 | 188414.62 | 15603.6956 | 7801.8478 | 423484.299 | 235069.6786
1324 | B.Bldg Wall Gyp.Mat- 7th & 8th Floor | 0 | Started | Labour | (L)Wall Gypsum Work | SQFT | 15603.6956 | 27.14 | 423484.3 | 0 | 0 | 0 | 0 | 27.14 | 0 | 15603.6956 | 24.15 | 376829.2588 | 15603.6956 | 24.15 | 376829.26 | 15603.6956 | 0 | 423484.299 | 46655.0386
1325 | B.Bldg Wall Gyp.Mat- 9th & 10th Floor | 0 | Started | Labour | (L)Wall Gypsum Work | SQFT | 16643.9565 | 27.14 | 451716.98 | 0 | 0 | 0 | 0 | 27.14 | 0 | 16643.9565 | 24.15 | 401951.5595 | 16643.9565 | 24.15 | 401951.54 | 16643.9565 | 0 | 451716.979 | 49765.4394
1326 | B.Bldg Wall Gyp.Mat- 11th & 12th Floor | 0 | Started | Labour | (L)Wall Gypsum Work | SQFT | 16643.9565 | 27.14 | 451716.98 | 0 | 0 | 0 | 0 | 27.14 | 0 | 16643.9565 | 24.15 | 401951.5595 | 16643.9565 | 24.15 | 401951.54 | 16643.9565 | 0 | 451716.979 | 49765.4394
1327 | B.Bldg Wall Gyp.Mat- Skirting Work | 0 | Started | Labour | (L)Wall Gypsum Work | SQFT | 3120.7391 | 27.14 | 84696.86 | 0 | 0 | 0 | 0 | 27.14 | 0 | 3120.7391 | 24.15 | 75365.8593 | 3120.7391 | 24.15 | 75365.84 | 3120.7391 | 0 | 84696.859 | 9331.0192
1328 | B.Bldg Wall Gyp.Mat- Misc.Work | 0 | Tentative | Labour | (L)Wall Gypsum Work | SQFT | 2080.4783 | 27.14 | 56464.18 | 0 | 0 | 0 | 0 | 27.14 | 0 | 2080.4783 | 24.15 | 50243.5609 | 0 | 0 | 0 | 2080.4783 | 2080.4783 | 56464.181 | 56464.1811
1329 | B.Bldg Wall Gyp.Mat- Retention | 0 | Tentative | Labour | (L)Wall Gypsum Work | SQFT | 5201.2174 | 27.14 | 141161.04 | 0 | 0 | 0 | 0 | 27.14 | 0 | 5201.2174 | 24.15 | 125609.4002 | 0 | 0 | 0 | 5201.2174 | 5201.2174 | 141161.04 | 141161.0402
1330 | B.Bldg Ceiling Gyp.Mat- 1,2,3,4 Floor | 0 | Tentative | Labour | (L)Ceiling Gypsum Work | SQFT | 8734.75 | 14.16 | 123684.06 | 0 | 0 | 0 | 0 | 14.16 | 0 | 8734.75 | 12.6 | 110057.86 | 0 | 0 | 0 | 8734.75 | 8734.75 | 123684.06 | 123684.06
1331 | B.Bldg Ceiling Gyp.Mat- 5,6,7,8 Floor | 0 | Started | Labour | (L)Ceiling Gypsum Work | SQFT | 9114.5833 | 14.16 | 129062.5 | 0 | 0 | 0 | 0 | 14.16 | 0 | 9114.5833 | 12.6 | 114843.7596 | 6835.9375 | 12.6 | 86132.81 | 9114.5833 | 2278.6458 | 129062.5 | 42929.6895
1332 | B.Bldg Ceiling Gyp.Mat- 9,10,11,12 Floor | 0 | Started | Labour | (L)Ceiling Gypsum Work | SQFT | 10253.8333 | 14.16 | 145194.28 | 0 | 0 | 0 | 0 | 14.16 | 0 | 10253.8333 | 12.6 | 129198.2996 | 10253.8333 | 12.6 | 129198.3 | 10253.8333 | 0 | 145194.28 | 15995.9795
1333 | B.Bldg Ceiling Gyp.Mat- Main St-Case upto 12th | 0 | Started | Labour | (L)Ceiling Gypsum Work | SQFT | 1139.3333 | 14.16 | 16132.96 | 0 | 0 | 0 | 0 | 14.16 | 0 | 1139.3333 | 12.6 | 14355.5996 | 1139.3333 | 12.6 | 14355.6 | 1139.3333 | 0 | 16132.96 | 1777.3595
1334 | B.Bldg Ceiling Gyp.Mat- Fire St-Case upto 12th | 0 | Started | Labour | (L)Ceiling Gypsum Work | SQFT | 1139.3333 | 14.16 | 16132.96 | 0 | 0 | 0 | 0 | 14.16 | 0 | 1139.3333 | 12.6 | 14355.5996 | 1139.3333 | 12.6 | 14355.6 | 1139.3333 | 0 | 16132.96 | 1777.3595
1335 | B.Bldg Ceiling Gyp.Mat- Passage upto 6th floor | 0 | Tentative | Labour | (L)Ceiling Gypsum Work | SQFT | 2468.5 | 14.16 | 34953.96 | 0 | 0 | 0 | 0 | 14.16 | 0 | 2468.5 | 12.6 | 31103.1 | 0 | 0 | 0 | 2468.5 | 2468.5 | 34953.96 | 34953.96
1336 | B.Bldg Ceiling Gyp.Mat- Passage upto 12th floor | 0 | Tentative | Labour | (L)Ceiling Gypsum Work | SQFT | 2468.5 | 14.16 | 34953.96 | 0 | 0 | 0 | 0 | 14.16 | 0 | 2468.5 | 12.6 | 31103.1 | 0 | 0 | 0 | 2468.5 | 2468.5 | 34953.96 | 34953.96
1337 | B.Bldg Ceiling Gyp.Mat- Miss.Work | 0 | Tentative | Labour | (L)Ceiling Gypsum Work | SQFT | 759.5833 | 14.16 | 10755.7 | 0 | 0 | 0 | 0 | 14.16 | 0 | 759.5833 | 12.6 | 9570.7596 | 0 | 0 | 0 | 759.5833 | 759.5833 | 10755.7 | 10755.6995
1338 | B.Bldg Ceiling Gyp.Mat- Rentention | 0 | Tentative | Labour | (L)Ceiling Gypsum Work | SQFT | 1898.8333 | 14.16 | 26887.48 | 0 | 0 | 0 | 0 | 14.16 | 0 | 1898.8333 | 12.6 | 23925.2996 | 0 | 0 | 0 | 1898.8333 | 1898.8333 | 26887.48 | 26887.4795
1339 | B.Bldg Wall Gyp.Lab1- 1st & 2nd Floor | 0 | Tentative | Labour | (L)Wall Gypsum Work | SQFT | 9020.6522 | 27.14 | 244820.5 | 0 | 0 | 0 | 0 | 27.14 | 0 | 9020.6522 | 27.14 | 244820.5006 | 0 | 0 | 0 | 9020.6522 | 9020.6522 | 244820.501 | 244820.5007
1340 | B.Bldg Wall Gyp.Lab1- 3rd & 4th Floor | 0 | Tentative | Labour | (L)Wall Gypsum Work | SQFT | 5412.3913 | 27.14 | 146892.3 | 0 | 0 | 0 | 0 | 27.14 | 0 | 5412.3913 | 27.14 | 146892.2999 | 0 | 0 | 0 | 5412.3913 | 5412.3913 | 146892.3 | 146892.2999
1341 | B.Bldg Wall Gyp.Lab1- 5th & 6th Floor | 0 | Started | Labour | (L)Wall Gypsum Work | SQFT | 5343 | 27.14 | 145009.02 | 0 | 0 | 0 | 0 | 27.14 | 0 | 5343 | 27.14 | 145009.02 | 2671.5 | 27.14 | 72504.52 | 5343 | 2671.5 | 145009.02 | 72504.5
1342 | B.Bldg Wall Gyp.Lab1- 7th & 8th Floor | 0 | Started | Labour | (L)Wall Gypsum Work | SQFT | 5204.2174 | 27.14 | 141242.46 | 0 | 0 | 0 | 0 | 27.14 | 0 | 5204.2174 | 27.14 | 141242.4602 | 5204.2174 | 27.14 | 141242.46 | 5204.2174 | 0 | 141242.46 | 0.0002
1343 | B.Bldg Wall Gyp.Lab1- 9th & 10th Floor | 0 | Started | Labour | (L)Wall Gypsum Work | SQFT | 5204.2174 | 27.14 | 141242.46 | 0 | 0 | 0 | 0 | 27.14 | 0 | 5204.2174 | 27.14 | 141242.4602 | 5204.2174 | 27.14 | 141242.46 | 5204.2174 | 0 | 141242.46 | 0.0002
1344 | B.Bldg Wall Gyp.Lab1- Skirting & But Filling | 0 | Started | Labour | (L)Wall Gypsum Work | SQFT | 2775.5652 | 27.14 | 75328.84 | 0 | 0 | 0 | 0 | 27.14 | 0 | 2775.5652 | 27.14 | 75328.8396 | 2775.5652 | 27.14 | 75328.84 | 2775.5652 | 0 | 75328.84 | -0.0005
1345 | B.Bldg Wall Gyp.Lab1- Retention | 0 | Tentative | Labour | (L)Wall Gypsum Work | SQFT | 1734.7391 | 27.14 | 47080.82 | 0 | 0 | 0 | 0 | 27.14 | 0 | 1734.7391 | 27.14 | 47080.8193 | 0 | 0 | 0 | 1734.7391 | 1734.7391 | 47080.819 | 47080.8192
1346 | B.Bldg Ceiling Gyp.Lab1- 1,2,3,4 Floor | 0 | Tentative | Labour | (L)Ceiling Gypsum Work | SQFT | 4313.8333 | 14.16 | 61083.88 | 0 | 0 | 0 | 0 | 14.16 | 0 | 4313.8333 | 14.16 | 61083.8796 | 0 | 0 | 0 | 4313.8333 | 4313.8333 | 61083.88 | 61083.8795
1347 | B.Bldg Ceiling Gyp.Lab1- 5,6,7,8 Floor | 0 | Started | Labour | (L)Ceiling Gypsum Work | SQFT | 4501.4167 | 14.16 | 63740.06 | 0 | 0 | 0 | 0 | 14.16 | 0 | 4501.4167 | 14.16 | 63740.0604 | 3376.0625 | 14.16 | 47805.05 | 4501.4167 | 1125.3542 | 63740.061 | 15935.0105
1348 | B.Bldg Ceiling Gyp.Lab1- 9,10,11,12 Floor | 0 | Started | Labour | (L)Ceiling Gypsum Work | SQFT | 5064.0833 | 14.16 | 71707.42 | 0 | 0 | 0 | 0 | 14.16 | 0 | 5064.0833 | 14.16 | 71707.4196 | 5064.0833 | 14.16 | 71707.42 | 5064.0833 | 0 | 71707.42 | -0.0005
1349 | B.Bldg Ceiling Gyp.Lab1- Main St-Case upto 12th | 0 | Started | Labour | (L)Ceiling Gypsum Work | SQFT | 1125.3333 | 14.16 | 15934.72 | 0 | 0 | 0 | 0 | 14.16 | 0 | 1125.3333 | 14.16 | 15934.7196 | 1125.3333 | 14.16 | 15934.72 | 1125.3333 | 0 | 15934.72 | -0.0005
1350 | B.Bldg Ceiling Gyp.Lab1- Passage upto 6th floor | 0 | Tentative | Labour | (L)Ceiling Gypsum Work | SQFT | 2438.25 | 14.16 | 34525.62 | 0 | 0 | 0 | 0 | 14.16 | 0 | 2438.25 | 14.16 | 34525.62 | 0 | 0 | 0 | 2438.25 | 2438.25 | 34525.62 | 34525.62
1351 | B.Bldg Ceiling Gyp.Lab1- Miss.Work | 0 | Tentative | Labour | (L)Ceiling Gypsum Work | SQFT | 375.0833 | 14.16 | 5311.18 | 0 | 0 | 0 | 0 | 14.16 | 0 | 375.0833 | 14.16 | 5311.1796 | 0 | 0 | 0 | 375.0833 | 375.0833 | 5311.18 | 5311.1795
1352 | B.Bldg Ceiling Gyp.Lab1- Rentention | 0 | Tentative | Labour | (L)Ceiling Gypsum Work | SQFT | 937.8333 | 14.16 | 13279.72 | 0 | 0 | 0 | 0 | 14.16 | 0 | 937.8333 | 14.16 | 13279.7196 | 0 | 0 | 0 | 937.8333 | 937.8333 | 13279.72 | 13279.7195
1353 | B.Bldg Wall Gyp.Lab_2 - 3rd & 4th Floor | 0 | Tentative | Labour | (L)Wall Gypsum Work | SQFT | 4302.1304 | 27.14 | 116759.82 | 0 | 0 | 0 | 0 | 27.14 | 0 | 4302.1304 | 23 | 98948.9992 | 0 | 0 | 0 | 4302.1304 | 4302.1304 | 116759.819 | 116759.8191
1354 | B.Bldg Wall Gyp.Lab_2 - 5th & 6th Floor | 0 | Started | Labour | (L)Wall Gypsum Work | SQFT | 4371.5217 | 27.14 | 118643.1 | 0 | 0 | 0 | 0 | 27.14 | 0 | 4371.5217 | 23 | 100544.9991 | 2185.7609 | 23 | 50272.5 | 4371.5217 | 2185.7608 | 118643.099 | 68370.5989
1355 | B.Bldg Wall Gyp.Lab_2 - 7th & 8th Floor | 0 | Started | Labour | (L)Wall Gypsum Work | SQFT | 5204.2174 | 27.14 | 141242.46 | 0 | 0 | 0 | 0 | 27.14 | 0 | 5204.2174 | 23 | 119697.0002 | 5204.2174 | 23 | 119697 | 5204.2174 | 0 | 141242.46 | 21545.4602
1356 | B.Bldg Wall Gyp.Lab_2 - 9th & 10th Floor | 0 | Started | Labour | (L)Wall Gypsum Work | SQFT | 5204.2174 | 27.14 | 141242.46 | 0 | 0 | 0 | 0 | 27.14 | 0 | 5204.2174 | 23 | 119697.0002 | 5204.2174 | 23 | 119697 | 5204.2174 | 0 | 141242.46 | 21545.4602
1357 | B.Bldg Wall Gyp.Lab_2 - 11th & 12th Floor | 0 | Started | Labour | (L)Wall Gypsum Work | SQFT | 11102.3044 | 27.14 | 301316.54 | 0 | 0 | 0 | 0 | 27.14 | 0 | 11102.3044 | 23 | 255353.0012 | 11102.3044 | 23 | 255353 | 11102.3044 | 0 | 301316.541 | 45963.5414
1358 | B.Bldg Wall Gyp.Lab_2 - Misc.Work | 0 | Tentative | Labour | (L)Wall Gypsum Work | SQFT | 1387.7826 | 27.14 | 37664.42 | 0 | 0 | 0 | 0 | 27.14 | 0 | 1387.7826 | 23 | 31918.9998 | 0 | 0 | 0 | 1387.7826 | 1387.7826 | 37664.42 | 37664.4198
1359 | B.Bldg Wall Gyp.Lab_2 - Cleaning | 0 | Tentative | Labour | (L)Wall Gypsum Work | SQFT | 1387.7826 | 27.14 | 37664.42 | 0 | 0 | 0 | 0 | 27.14 | 0 | 1387.7826 | 23 | 31918.9998 | 0 | 0 | 0 | 1387.7826 | 1387.7826 | 37664.42 | 37664.4198
1360 | B.Bldg Wall Gyp.Lab_2 - Retention | 0 | Tentative | Labour | (L)Wall Gypsum Work | SQFT | 1734.7391 | 27.14 | 47080.82 | 0 | 0 | 0 | 0 | 27.14 | 0 | 1734.7391 | 23 | 39898.9993 | 0 | 0 | 0 | 1734.7391 | 1734.7391 | 47080.819 | 47080.8192
1361 | B.Bldg Ceiling Gyp.Lab_2 - 1,2,3,4 Floor | 0 | Tentative | Labour | (L)Ceiling Gypsum Work | SQFT | 4313.8333 | 14.16 | 61083.88 | 0 | 0 | 0 | 0 | 14.16 | 0 | 4313.8333 | 12 | 51765.9996 | 0 | 0 | 0 | 4313.8333 | 4313.8333 | 61083.88 | 61083.8795
1362 | B.Bldg Ceiling Gyp.Lab_2 - 5,6,7,8 Floor | 0 | Started | Labour | (L)Ceiling Gypsum Work | SQFT | 4501.4167 | 14.16 | 63740.06 | 0 | 0 | 0 | 0 | 14.16 | 0 | 4501.4167 | 12 | 54017.0004 | 3376.0625 | 12 | 40512.75 | 4501.4167 | 1125.3542 | 63740.061 | 23227.3105
1363 | B.Bldg Ceiling Gyp.Lab_2 - 9,10,11,12 Floor | 0 | Started | Labour | (L)Ceiling Gypsum Work | SQFT | 5064.0833 | 14.16 | 71707.42 | 0 | 0 | 0 | 0 | 14.16 | 0 | 5064.0833 | 12 | 60768.9996 | 5064.0833 | 12 | 60769 | 5064.0833 | 0 | 71707.42 | 10938.4195
1364 | B.Bldg Ceiling Gyp.Lab_2 - Fire St-Case upto 12th | 0 | Started | Labour | (L)Ceiling Gypsum Work | SQFT | 1125.3333 | 14.16 | 15934.72 | 0 | 0 | 0 | 0 | 14.16 | 0 | 1125.3333 | 12 | 13503.9996 | 1125.3333 | 12 | 13504 | 1125.3333 | 0 | 15934.72 | 2430.7195
1365 | B.Bldg Ceiling Gyp.Lab_2 - Passage upto 12th floor | 0 | Tentative | Labour | (L)Ceiling Gypsum Work | SQFT | 2438.25 | 14.16 | 34525.62 | 0 | 0 | 0 | 0 | 14.16 | 0 | 2438.25 | 12 | 29259 | 0 | 0 | 0 | 2438.25 | 2438.25 | 34525.62 | 34525.62
1366 | B.Bldg Ceiling Gyp.Lab_2 - Miss.Work | 0 | Tentative | Labour | (L)Ceiling Gypsum Work | SQFT | 375.0833 | 14.16 | 5311.18 | 0 | 0 | 0 | 0 | 14.16 | 0 | 375.0833 | 12 | 4500.9996 | 0 | 0 | 0 | 375.0833 | 375.0833 | 5311.18 | 5311.1795
1367 | B.Bldg Ceiling Gyp.Lab_2 - Rentention | 0 | Tentative | Labour | (L)Ceiling Gypsum Work | SQFT | 937.8333 | 14.16 | 13279.72 | 0 | 0 | 0 | 0 | 14.16 | 0 | 937.8333 | 12 | 11253.9996 | 0 | 0 | 0 | 937.8333 | 937.8333 | 13279.72 | 13279.7195
1368 | LAB: Ext. Painting North Side Duct-100% | 0 | Started | Labour | (L)Apex Paint (Primer-1 Coat, Crackfill, Apex Paint-2 Coat) | SQFT | 4119.6257 | 11.51 | 47416.89 | 0 | 0 | 0 | 0 | 11.51 | 0 | 4119.6257 | 9.75 | 40166.3506 | 2380.8595 | 9.75 | 23213.38 | 4119.6257 | 1738.7662 | 47416.892 | 24203.5118
1369 | LAB: Ext. Painting East Side Duct-100% | 0 | Started | Labour | (L)Apex Paint (Primer-1 Coat, Crackfill, Apex Paint-2 Coat) | SQFT | 1909.2334 | 11.51 | 21975.28 | 0 | 0 | 0 | 0 | 11.51 | 0 | 1909.2334 | 9.75 | 18615.0257 | 1193.2707 | 9.75 | 11634.39 | 1909.2334 | 715.9627 | 21975.276 | 10340.8864
1370 | LAB: Ext. Painting Internal Duct (Big)-100% | 0 | Started | Labour | (L)Apex Paint (Primer-1 Coat, Crackfill, Apex Paint-2 Coat) | SQFT | 13637.3816 | 11.51 | 156966.26 | 0 | 0 | 0 | 0 | 11.51 | 0 | 13637.3816 | 9.75 | 132964.4706 | 8523.363 | 9.75 | 83102.79 | 13637.3816 | 5114.0186 | 156966.262 | 73863.4722
1371 | LAB: Ext. Painting Internal Duct (Small)-100% | 0 | Started | Labour | (L)Apex Paint (Primer-1 Coat, Crackfill, Apex Paint-2 Coat) | SQFT | 4165.0836 | 11.51 | 47940.11 | 0 | 0 | 0 | 0 | 11.51 | 0 | 4165.0836 | 9.75 | 40609.5651 | 2630.8779 | 9.75 | 25651.06 | 4165.0836 | 1534.2057 | 47940.112 | 22289.0522
1372 | LAB: Ext. Paint OHWT(abv. Fire St-Case)-100% | 0 | Started | Labour | (L)Apex Paint (Primer-1 Coat, Crackfill, Apex Paint-2 Coat) | SQFT | 1721.7194 | 11.51 | 19816.99 | 0 | 0 | 0 | 0 | 11.51 | 0 | 1721.7194 | 9.75 | 16786.7642 | 627.8882 | 9.75 | 6121.91 | 1721.7194 | 1093.8312 | 19816.99 | 13695.0803
1373 | LAB: Ext. Paint OHWT(abv. Main St-Case)-100% | 0 | Started | Labour | (L)Apex Paint (Primer-1 Coat, Crackfill, Apex Paint-2 Coat) | SQFT | 1721.7194 | 11.51 | 19816.99 | 0 | 0 | 0 | 0 | 11.51 | 0 | 1721.7194 | 9.75 | 16786.7642 | 627.8882 | 9.75 | 6121.91 | 1721.7194 | 1093.8312 | 19816.99 | 13695.0803
1374 | LAB: Ext. Painting Crackfill (Apex)-100% Comp | 0 | Started | Labour | (L)Apex Paint (Primer-1 Coat, Crackfill, Apex Paint-2 Coat) | SQFT | 1136.4485 | 11.51 | 13080.52 | 0 | 0 | 0 | 0 | 11.51 | 0 | 1136.4485 | 9.75 | 11080.3729 | 1136.4485 | 9.75 | 11080.37 | 1136.4485 | 0 | 13080.522 | 2000.1522
1375 | LAB: Ext. Painting North Side Elevation-100% | 0 | Started | Labour | (L)Elastomeric Paint (Primer, Crackfill,Basecoat,Paint-2 coat) | SQFT | 7862.7193 | 20.06 | 157726.15 | 0 | 0 | 0 | 0 | 20.06 | 0 | 7862.7193 | 17 | 133666.2281 | 5604.2787 | 17 | 95272.74 | 7862.7193 | 2258.4406 | 157726.149 | 62453.4092
1376 | LAB: Ext. Painting South Side Elevation-100% | 0 | Started | Labour | (L)Elastomeric Paint (Primer, Crackfill,Basecoat,Paint-2 coat) | SQFT | 8611.5497 | 20.06 | 172747.69 | 0 | 0 | 0 | 0 | 20.06 | 0 | 8611.5497 | 17 | 146396.3449 | 3664.4897 | 17 | 62296.32 | 8611.5497 | 4947.06 | 172747.687 | 110451.367
1377 | LAB: Ext. Painting East Side Elevation-100% | 0 | Started | Labour | (L)Elastomeric Paint (Primer, Crackfill,Basecoat,Paint-2 coat) | SQFT | 8611.5497 | 20.06 | 172747.69 | 0 | 0 | 0 | 0 | 20.06 | 0 | 8611.5497 | 17 | 146396.3449 | 4901.255 | 17 | 83321.34 | 8611.5497 | 3710.2947 | 172747.687 | 89426.347
1378 | LAB: Ext. Painting West Side Elevation-100% | 0 | Started | Labour | (L)Elastomeric Paint (Primer, Crackfill,Basecoat,Paint-2 coat) | SQFT | 8611.5497 | 20.06 | 172747.69 | 0 | 0 | 0 | 0 | 20.06 | 0 | 8611.5497 | 17 | 146396.3449 | 4901.2547 | 17 | 83321.33 | 8611.5497 | 3710.295 | 172747.687 | 89426.357
1379 | LAB: Ext. Painting Parapet-100% | 0 | Started | Labour | (L)Elastomeric Paint (Primer, Crackfill,Basecoat,Paint-2 coat) | SQFT | 3744.152 | 20.06 | 75107.69 | 0 | 0 | 0 | 0 | 20.06 | 0 | 3744.152 | 17 | 63650.584 | 796.6282 | 17 | 13542.68 | 3744.152 | 2947.5238 | 75107.689 | 61565.0091
1380 | LAB: Ext. Painting Crackfill (Elastomeric)-100% | 0 | Started | Labour | (L)Elastomeric Paint (Primer, Crackfill,Basecoat,Paint-2 coat) | SQFT | 1194.9421 | 20.06 | 23970.54 | 0 | 0 | 0 | 0 | 20.06 | 0 | 1194.9421 | 17 | 20314.0157 | 1194.9421 | 17 | 20314.02 | 1194.9421 | 0 | 23970.539 | 3656.5185
1381 | LAB: Ext. Painting Misc.Work-100% | 0 | Tentative | Labour | (L)Elastomeric Paint (Primer, Crackfill,Basecoat,Paint-2 coat) | SQFT | 1194.9421 | 20.06 | 23970.54 | 0 | 0 | 0 | 0 | 20.06 | 0 | 1194.9421 | 17 | 20314.0157 | 0 | 0 | 0 | 1194.9421 | 1194.9421 | 23970.539 | 23970.5385
1382 | LAB: Ext. Painting Lift 8 Passenger-100% | 0 | Started | Labour | (L)Primer 2 Coat (white wash) | SQFT | 2280 | 5.32 | 12129.6 | 0 | 0 | 0 | 0 | 5.32 | 0 | 2280 | 4.5 | 10260 | 2280 | 4.5 | 10260 | 2280 | 0 | 12129.6 | 1869.6
1383 | LAB: Ext. Painting Lift 13 Passenger-100% | 0 | Tentative | Labour | (L)Primer 2 Coat (white wash) | SQFT | 2280 | 5.32 | 12129.6 | 0 | 0 | 0 | 0 | 5.32 | 0 | 2280 | 4.5 | 10260 | 0 | 0 | 0 | 2280 | 2280 | 12129.6 | 12129.6
1384 | LAB: Ext. Painting Garbage Duct-100% | 0 | Started | Labour | (L)ACE Paint (Primer-1 Coat, Crackfill, ACE paint-2 Coat) | SQFT | 1073.4111 | 9.44 | 10133 | 0 | 0 | 0 | 0 | 9.44 | 0 | 1073.4111 | 8 | 8587.2888 | 288.55 | 8 | 2308.4 | 1073.4111 | 784.8611 | 10133.001 | 7824.6008
1385 | LAB: Ext. Painting Electrical Duct 1st-100% | 0 | Started | Labour | (L)ACE Paint (Primer-1 Coat, Crackfill, ACE paint-2 Coat) | SQFT | 536.7056 | 9.44 | 5066.5 | 0 | 0 | 0 | 0 | 9.44 | 0 | 536.7056 | 8 | 4293.6448 | 144.2763 | 8 | 1154.21 | 536.7056 | 392.4293 | 5066.501 | 3912.2909
1386 | LAB: Ext. Painting Electrical Duct 2nd-100% | 0 | Started | Labour | (L)ACE Paint (Primer-1 Coat, Crackfill, ACE paint-2 Coat) | SQFT | 536.7056 | 9.44 | 5066.5 | 0 | 0 | 0 | 0 | 9.44 | 0 | 536.7056 | 8 | 4293.6448 | 144.276 | 8 | 1154.21 | 536.7056 | 392.4296 | 5066.501 | 3912.2909
1387 | LAB: Ext. Painting Fire ST-Case-100% | 0 | Started | Labour | (L)ACE Paint (Primer-1 Coat, Crackfill, ACE paint-2 Coat) | SQFT | 1073.4111 | 9.44 | 10133 | 0 | 0 | 0 | 0 | 9.44 | 0 | 1073.4111 | 8 | 8587.2888 | 288.5512 | 8 | 2308.41 | 1073.4111 | 784.8599 | 10133.001 | 7824.5908
1388 | LAB: Ext. Painting Both ST-Case Pardi -100% | 0 | Started | Labour | (L)ACE Paint (Primer-1 Coat, Crackfill, ACE paint-2 Coat) | SQFT | 357.8037 | 9.44 | 3377.67 | 0 | 0 | 0 | 0 | 9.44 | 0 | 357.8037 | 8 | 2862.4296 | 96.1837 | 8 | 769.47 | 357.8037 | 261.62 | 3377.667 | 2608.1969
1389 | LAB: Ext. Painting Crackfill (ACE)-100% Comp | 0 | Started | Labour | (L)ACE Paint (Primer-1 Coat, Crackfill, ACE paint-2 Coat) | SQFT | 269.3146 | 9.44 | 2542.33 | 0 | 0 | 0 | 0 | 9.44 | 0 | 269.3146 | 8 | 2154.5168 | 0 | 0 | 0 | 269.3146 | 269.3146 | 2542.33 | 2542.3298
1390 | LAB: Ext. Painting Main Staircase-100% | 0 | Started | Labour | (L)OBD Paint (Putty 2 Coat, Paint-2 Coat) | SQFT | 2735.8667 | 8.86 | 24239.78 | 0 | 0 | 0 | 0 | 8.86 | 0 | 2735.8667 | 7.5 | 20519.0003 | 683.9733 | 7.5 | 5129.8 | 2735.8667 | 2051.8934 | 24239.779 | 19109.979
1391 | LAB: Ext. Painting "Clean. & Misc.Work"-100% | 0 | Tentative | Labour | (L)Cleaning (Painting) | SQFT | 2275.409 | 19.17 | 43619.59 | 0 | 0 | 0 | 0 | 19.17 | 0 | 2275.409 | 16.25 | 36971.5281 | 0 | 0 | 0 | 2275.409 | 2275.409 | 43619.591 | 43619.5905
1392 | LAB: Ext. Painting "PF"-100% | 0 | Tentative | Labour | (L)PF (Painting) | SQFT | 758.4789 | 19.17 | 14540.04 | 0 | 0 | 0 | 0 | 19.17 | 0 | 758.4789 | 16.25 | 12323.9927 | 0 | 0 | 0 | 758.4789 | 758.4789 | 14540.041 | 14540.0405
1393 | LAB: Ext. Painting "Retention"-100% | 0 | Tentative | Labour | (L)Retention (Painting) | SQFT | 3792.3479 | 19.17 | 72699.31 | 0 | 0 | 0 | 0 | 19.17 | 0 | 3792.3479 | 16.25 | 61619.2064 | 0 | 0 | 0 | 3792.3479 | 3792.3479 | 72699.309 | 72699.3092
1394 | MAT: Ext. Painting North Side Duct-100% | 0 | Started | Labour | (L)Apex Paint (Primer-1 Coat, Crackfill, Apex Paint-2 Coat) | SQFT | 5035.0769 | 11.51 | 57953.74 | 0 | 0 | 0 | 0 | 11.51 | 0 | 5035.0769 | 11.51 | 57928.5598 | 2909.9394 | 11.51 | 33478.87 | 5035.0769 | 2125.1375 | 57953.735 | 24474.8651
1395 | MAT: Ext. Painting East Side Duct-100% | 0 | Started | Labour | (L)Apex Paint (Primer-1 Coat, Crackfill, Apex Paint-2 Coat) | SQFT | 2333.5385 | 11.51 | 26859.03 | 0 | 0 | 0 | 0 | 11.51 | 0 | 2333.5385 | 11.5 | 26847.3604 | 1458.442 | 11.5 | 16779.37 | 2333.5385 | 875.0965 | 26859.028 | 10079.6581
1396 | MAT: Ext. Painting Internal Duct (Big)-100% | 0 | Started | Labour | (L)Apex Paint (Primer-1 Coat, Crackfill, Apex Paint-2 Coat) | SQFT | 16667.8974 | 11.51 | 191847.5 | 0 | 0 | 0 | 0 | 11.51 | 0 | 16667.8974 | 11.51 | 191764.1597 | 10417.4441 | 11.5 | 119852.68 | 16667.8974 | 6250.4533 | 191847.499 | 71994.8191
1397 | MAT: Ext. Painting Internal Duct (Small)-100% | 0 | Started | Labour | (L)Apex Paint (Primer-1 Coat, Crackfill, Apex Paint-2 Coat) | SQFT | 5090.6667 | 11.51 | 58593.57 | 0 | 0 | 0 | 0 | 11.51 | 0 | 5090.6667 | 11.5 | 58568.1203 | 3215.5168 | 11.5 | 36994.51 | 5090.6667 | 1875.1499 | 58593.574 | 21599.0637
1398 | MAT: Ext. Paint OHWT(abv. Fire St-Case)-100% | 0 | Started | Labour | (L)Apex Paint (Primer-1 Coat, Crackfill, Apex Paint-2 Coat) | SQFT | 2104.3077 | 11.51 | 24220.58 | 0 | 0 | 0 | 0 | 11.51 | 0 | 2104.3077 | 11.51 | 24210.0601 | 767.4184 | 11.51 | 8829.15 | 2104.3077 | 1336.8893 | 24220.582 | 15391.4316
1399 | MAT: Ext. Paint OHWT(abv. Main St-Case)-100% | 0 | Started | Labour | (L)Apex Paint (Primer-1 Coat, Crackfill, Apex Paint-2 Coat) | SQFT | 2104.3077 | 11.51 | 24220.58 | 0 | 0 | 0 | 0 | 11.51 | 0 | 2104.3077 | 11.51 | 24210.0601 | 767.4184 | 11.51 | 8829.15 | 2104.3077 | 1336.8893 | 24220.582 | 15391.4316
1400 | MAT: Ext. Painting Crackfill (Apex)-100% Comp | 0 | Started | Labour | (L)Apex Paint (Primer-1 Coat, Crackfill, Apex Paint-2 Coat) | SQFT | 1389.0256 | 11.51 | 15987.68 | 0 | 0 | 0 | 0 | 11.51 | 0 | 1389.0256 | 11.51 | 15980.7396 | 1389.0256 | 11.51 | 15980.74 | 1389.0256 | 0 | 15987.685 | 6.9447
1401 | MAT: Ext. Painting North Side Elevation-100% | 0 | Started | Labour | (L)Elastomeric Paint (Primer, Crackfill,Basecoat,Paint-2 coat) | SQFT | 9610 | 20.06 | 192776.6 | 0 | 0 | 0 | 0 | 20.06 | 0 | 9610 | 20.06 | 192776.6 | 6849.6741 | 20.06 | 137404.46 | 9610 | 2760.3259 | 192776.6 | 55372.14
1402 | MAT: Ext. Painting South Side Elevation-100% | 0 | Started | Labour | (L)Elastomeric Paint (Primer, Crackfill,Basecoat,Paint-2 coat) | SQFT | 10525.2353 | 20.06 | 211136.22 | 0 | 0 | 0 | 0 | 20.06 | 0 | 10525.2353 | 20.06 | 211136.2201 | 7502.0245 | 20.06 | 150490.62 | 10525.2353 | 3023.2108 | 211136.22 | 60645.6001
1403 | MAT: Ext. Painting East Side Elevation-100% | 0 | Started | Labour | (L)Elastomeric Paint (Primer, Crackfill,Basecoat,Paint-2 coat) | SQFT | 10525.2353 | 20.06 | 211136.22 | 0 | 0 | 0 | 0 | 20.06 | 0 | 10525.2353 | 20.06 | 211136.2201 | 7502.0245 | 20.06 | 150490.62 | 10525.2353 | 3023.2108 | 211136.22 | 60645.6001
1404 | MAT: Ext. Painting West Side Elevation-100% | 0 | Started | Labour | (L)Elastomeric Paint (Primer, Crackfill,Basecoat,Paint-2 coat) | SQFT | 10525.2353 | 20.06 | 211136.22 | 0 | 0 | 0 | 0 | 20.06 | 0 | 10525.2353 | 20.06 | 211136.2201 | 7502.0246 | 20.06 | 150490.62 | 10525.2353 | 3023.2107 | 211136.22 | 60645.6001
1405 | MAT: Ext. Painting Parapet-100% | 0 | Started | Labour | (L)Elastomeric Paint (Primer, Crackfill,Basecoat,Paint-2 coat) | SQFT | 4576.1765 | 20.06 | 91798.1 | 0 | 0 | 0 | 0 | 20.06 | 0 | 4576.1765 | 20.06 | 91798.1005 | 2288.0928 | 20.06 | 45899.14 | 4576.1765 | 2288.0837 | 91798.101 | 45898.9606
1406 | MAT: Ext. Painting Crackfill (Elasto)-100% | 0 | Started | Labour | (L)Elastomeric Paint (Primer, Crackfill,Basecoat,Paint-2 coat) | SQFT | 1460.4706 | 20.06 | 29297.04 | 0 | 0 | 0 | 0 | 20.06 | 0 | 1460.4706 | 20.06 | 29297.0402 | 1460.4706 | 20.06 | 29297.04 | 1460.4706 | 0 | 29297.04 | 0.0002
1407 | MAT: Ext. Painting Misc.Work-100% | 0 | Tentative | Labour | (L)Elastomeric Paint (Primer, Crackfill,Basecoat,Paint-2 coat) | SQFT | 1460.4706 | 20.06 | 29297.04 | 0 | 0 | 0 | 0 | 20.06 | 0 | 1460.4706 | 20.06 | 29297.0402 | 0 | 0 | 0 | 1460.4706 | 1460.4706 | 29297.04 | 29297.0402
1408 | MAT: Ext. Painting Lift 8 Passenger-100% | 0 | Started | Labour | (L)Primer 2 Coat (white wash) | SQFT | 2786.6667 | 5.32 | 14825.07 | 0 | 0 | 0 | 0 | 5.32 | 0 | 2786.6667 | 5.31 | 14797.2002 | 2786.56 | 5.31 | 14796.64 | 2786.6667 | 0.1067 | 14825.067 | 28.4268
1409 | MAT: Ext. Painting Lift 13 Passenger-100% | 0 | Tentative | Labour | (L)Primer 2 Coat (white wash) | SQFT | 2786.6667 | 5.32 | 14825.07 | 0 | 0 | 0 | 0 | 5.32 | 0 | 2786.6667 | 5.31 | 14797.2002 | 0 | 0 | 0 | 2786.6667 | 2786.6667 | 14825.067 | 14825.0668
1410 | MAT: Ext. Painting Garbage Duct-100% | 0 | Started | Labour | (L)ACE Paint (Primer-1 Coat, Crackfill, ACE paint-2 Coat) | SQFT | 1312 | 9.44 | 12385.28 | 0 | 0 | 0 | 0 | 9.44 | 0 | 1312 | 9.44 | 12385.28 | 352.6737 | 9.44 | 3329.25 | 1312 | 959.3263 | 12385.28 | 9056.03
1411 | MAT: Ext. Painting Electrical Duct 1st-100% | 0 | Started | Labour | (L)ACE Paint (Primer-1 Coat, Crackfill, ACE paint-2 Coat) | SQFT | 656 | 9.44 | 6192.64 | 0 | 0 | 0 | 0 | 9.44 | 0 | 656 | 9.44 | 6192.64 | 176.3375 | 9.44 | 1664.62 | 656 | 479.6625 | 6192.64 | 4528.02
1412 | MAT: Ext. Painting Electrical Duct 2nd-100% | 0 | Started | Labour | (L)ACE Paint (Primer-1 Coat, Crackfill, ACE paint-2 Coat) | SQFT | 656 | 9.44 | 6192.64 | 0 | 0 | 0 | 0 | 9.44 | 0 | 656 | 9.44 | 6192.64 | 176.3375 | 9.44 | 1664.62 | 656 | 479.6625 | 6192.64 | 4528.02
1413 | MAT: Ext. Painting Fire ST-Case-100% | 0 | Started | Labour | (L)ACE Paint (Primer-1 Coat, Crackfill, ACE paint-2 Coat) | SQFT | 1312 | 9.44 | 12385.28 | 0 | 0 | 0 | 0 | 9.44 | 0 | 1312 | 9.44 | 12385.28 | 352.6737 | 9.44 | 3329.25 | 1312 | 959.3263 | 12385.28 | 9056.03
1414 | MAT: Ext. Painting Both ST-Case Pardi -100% | 0 | Started | Labour | (L)ACE Paint (Primer-1 Coat, Crackfill, ACE paint-2 Coat) | SQFT | 437.375 | 9.44 | 4128.82 | 0 | 0 | 0 | 0 | 9.44 | 0 | 437.375 | 9.44 | 4128.82 | 117.5575 | 9.44 | 1109.74 | 437.375 | 319.8175 | 4128.82 | 3019.08
1415 | MAT: Ext. Painting Crackfill (ACE)-100% Comp | 0 | Tentative | Labour | (L)ACE Paint (Primer-1 Coat, Crackfill, ACE paint-2 Coat) | SQFT | 329.125 | 9.44 | 3106.94 | 0 | 0 | 0 | 0 | 9.44 | 0 | 329.125 | 9.44 | 3106.94 | 0 | 0 | 0 | 329.125 | 329.125 | 3106.94 | 3106.94
1416 | MAT: Ext. Painting Main Staircase-100% | 0 | Started | Labour | (L)OBD Paint (Putty 2 Coat, Paint-2 Coat) | SQFT | 3343.8667 | 8.86 | 29626.66 | 0 | 0 | 0 | 0 | 8.86 | 0 | 3343.8667 | 8.85 | 29593.2203 | 835.968 | 8.85 | 7398.32 | 3343.8667 | 2507.8987 | 29626.659 | 22228.339
1417 | MAT: Ext. Painting "PF"-100% | 0 | Tentative | Labour | (L)PF (Painting) | SQFT | 758.4789 | 19.17 | 14540.04 | 0 | 0 | 0 | 0 | 19.17 | 0 | 758.4789 | 19.17 | 14542.3127 | 0 | 0 | 0 | 758.4789 | 758.4789 | 14540.041 | 14540.0405
1418 | MAT: Ext. Painting "Retention"-100% | 0 | Tentative | Labour | (L)Retention (Painting) | SQFT | 3792.3479 | 19.17 | 72699.31 | 0 | 0 | 0 | 0 | 19.17 | 0 | 3792.3479 | 19.17 | 72710.6664 | 0 | 0 | 0 | 3792.3479 | 3792.3479 | 72699.309 | 72699.3092
1419 | B BLDG FLAT INT. PUTTY WORK (MAT.)- 1ST COAT 1ST TO 12 FLOOR | 0 | Started | Labour | (L)INTERNAL PUTTY (WALL & CEILING) | FLOORS | 12 | 1.18 | 14.16 | 0 | 0 | 0 | 0 | 1.18 | 0 | 12 | 19454.37 | 233452.38 | 12 | 19454.37 | 233452.38 | 12 | 0 | 14.16 | -233438.22
1420 | B BLDG FLAT INT. PUTTY WORK (MAT.)- 2ND COAT 1ST TO 12 FLOOR | 0 | Started | Labour | (L)INTERNAL PUTTY (WALL & CEILING) | FLOORS | 12 | 1.18 | 14.16 | 0 | 0 | 0 | 0 | 1.18 | 0 | 12 | 17897.95 | 214775.34 | 12 | 17897.95 | 214775.34 | 12 | 0 | 14.16 | -214761.18
1421 | B BLDG LOBBY INT. PUTTY WORK (MAT)- 1ST COAT 1ST TO 12 FLOOR | 0 | Started | Labour | (L)INTERNAL PUTTY (WALL & CEILING) | FLOORS | 2 | 1.18 | 2.36 | 0 | 0 | 0 | 0 | 1.18 | 0 | 2 | 12969.38 | 25938.76 | 2 | 12969.38 | 25938.76 | 2 | 0 | 2.36 | -25936.4
1422 | B BLDG LOBBY INT. PUTTY WORK (MAT)- 2ND COAT 1ST TO 12 FLOOR | 0 | Started | Labour | (L)INTERNAL PUTTY (WALL & CEILING) | FLOORS | 2 | 1.18 | 2.36 | 0 | 0 | 0 | 0 | 1.18 | 0 | 2 | 11932.16 | 23864.32 | 2 | 11932.16 | 23864.32 | 2 | 0 | 2.36 | -23861.96
1423 | B BLDG FLAT INT. PAINTING (MAT.)- 1ST COAT 1ST TO 12 FLOOR | 0 | Started | Labour | (L)INTERNAL OBD PAINT (WALL & CEILING) | FLOORS | 12 | 1.18 | 14.16 | 0 | 0 | 0 | 0 | 1.18 | 0 | 12 | 18676.16 | 224113.86 | 12 | 18676.16 | 224113.86 | 12 | 0 | 14.16 | -224099.7
1424 | B BLDG FLAT INT. PAINTING (MAT.)- 2ND COAT 1ST TO 12 FLOOR | 0 | Tentative | Labour | (L)INTERNAL OBD PAINT (WALL & CEILING) | FLOORS | 12 | 1.18 | 14.16 | 0 | 0 | 0 | 0 | 1.18 | 0 | 12 | 21788.7 | 261464.4 | 0 | 0 | 0 | 12 | 12 | 14.16 | 14.16
1425 | B BLDG LOBBY INT. PAINTING (MAT.)- 1ST COAT 1ST TO 12 FLOOR | 0 | Started | Labour | (L)INTERNAL OBD PAINT (WALL & CEILING) | FLOORS | 2 | 1.18 | 2.36 | 0 | 0 | 0 | 0 | 1.18 | 0 | 2 | 12450.18 | 24900.36 | 2 | 12450.18 | 24900.36 | 2 | 0 | 2.36 | -24898
1426 | B BLDG LOBBY INT. PAINTING (MAT.)- 2ND COAT 1ST TO 12 FLOOR | 0 | Tentative | Labour | (L)INTERNAL OBD PAINT (WALL & CEILING) | FLOORS | 2 | 1.18 | 2.36 | 0 | 0 | 0 | 0 | 1.18 | 0 | 2 | 14525.8 | 29051.6 | 0 | 0 | 0 | 2 | 2 | 2.36 | 2.36
1427 | B BLDG RAIL.(ST & FLAT) OIL PAINT (MAT.)- 1ST COAT UPTO 12TH | 0 | Started | Labour | (L)INTERNAL OIL PAINT | FLOORS | 2 | 1.18 | 2.36 | 0 | 0 | 0 | 0 | 1.18 | 0 | 2 | 10070.12 | 20140.24 | 2 | 10070.12 | 20140.24 | 2 | 0 | 2.36 | -20137.88
1428 | B BLDG RAIL.(ST & FLAT) OIL PAINT (MAT.)- 2ND COAT UPTO 12TH | 0 | Started | Labour | (L)INTERNAL OIL PAINT | FLOORS | 2 | 1.18 | 2.36 | 0 | 0 | 0 | 0 | 1.18 | 0 | 2 | 23497.34 | 46994.68 | 0 | 0 | 0 | 2 | 2 | 2.36 | 2.36
1429 | B BLDG PAINTING WORK RETENTION (MAT) -COMP.OF RET. PERIOD | 0 | Tentative | Labour | (L)INTERNAL OBD PAINT (WALL & CEILING) | FLOORS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 61033.14 | 61033.14 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
1430 | B BLDG FLAT INT. PUTTY WORK (LAB)- 1ST COAT 1ST TO 12 FLOOR | 0 | Started | Labour | (L)INTERNAL PUTTY (WALL & CEILING) | FLOORS | 12 | 1.18 | 14.16 | 0 | 0 | 0 | 0 | 1.18 | 0 | 12 | 20150.25 | 241803 | 12 | 20150.25 | 241803 | 12 | 0 | 14.16 | -241788.84
1431 | B BLDG FLAT INT. PUTTY WORK (LAB)- 2ND COAT 1ST TO 12 FLOOR | 0 | Started | Labour | (L)INTERNAL PUTTY (WALL & CEILING) | FLOORS | 12 | 1.18 | 14.16 | 0 | 0 | 0 | 0 | 1.18 | 0 | 12 | 18538.25 | 222459 | 12 | 18538.25 | 222459 | 12 | 0 | 14.16 | -222444.84
1432 | B BLDG LOBBY INT. PUTTY WORK (LAB)- 1ST COAT 1ST TO 12 FLOOR | 0 | Started | Labour | (L)INTERNAL PUTTY (WALL & CEILING) | FLOORS | 2 | 1.18 | 2.36 | 0 | 0 | 0 | 0 | 1.18 | 0 | 2 | 13434 | 26868 | 2 | 13434 | 26868 | 2 | 0 | 2.36 | -26865.64
1433 | B BLDG LOBBY INT. PUTTY WORK (LAB)- 2ND COAT 1ST TO 12 FLOOR | 0 | Started | Labour | (L)INTERNAL PUTTY (WALL & CEILING) | FLOORS | 2 | 1.18 | 2.36 | 0 | 0 | 0 | 0 | 1.18 | 0 | 2 | 12359 | 24718 | 2 | 12359 | 24718 | 2 | 0 | 2.36 | -24715.64
1434 | B BLDG FLAT INT. PAINTING (LAB)- 1ST COAT 1ST TO 12 FLOOR | 0 | Started | Labour | (L)INTERNAL OBD PAINT (WALL & CEILING) | FLOORS | 12 | 1.18 | 14.16 | 0 | 0 | 0 | 0 | 1.18 | 0 | 12 | 19344.25 | 232131 | 12 | 19344.25 | 232131 | 12 | 0 | 14.16 | -232116.84
1435 | B BLDG FLAT INT. PAINTING (LAB)- 2ND COAT 1ST TO 12 FLOOR | 0 | Started | Labour | (L)INTERNAL OBD PAINT (WALL & CEILING) | FLOORS | 12 | 1.18 | 14.16 | 0 | 0 | 0 | 0 | 1.18 | 0 | 12 | 22568.5 | 270822 | 0 | 0 | 0 | 12 | 12 | 14.16 | 14.16
1436 | B BLDG LOBBY INT. PAINTING (LAB)- 1ST COAT 1ST TO 12 FLOOR | 0 | Started | Labour | (L)INTERNAL OBD PAINT (WALL & CEILING) | FLOORS | 2 | 1.18 | 2.36 | 0 | 0 | 0 | 0 | 1.18 | 0 | 2 | 12896 | 25792 | 2 | 12896 | 25792 | 2 | 0 | 2.36 | -25789.64
1437 | B BLDG LOBBY INT. PAINTING (LAB)- 2ND COAT 1ST TO 12 FLOOR | 0 | Tentative | Labour | (L)INTERNAL OBD PAINT (WALL & CEILING) | FLOORS | 2 | 1.18 | 2.36 | 0 | 0 | 0 | 0 | 1.18 | 0 | 2 | 15046 | 30092 | 0 | 0 | 0 | 2 | 2 | 2.36 | 2.36
1438 | B BLDG RAIL.(ST & FLAT) OIL PAINT (LAB)- 1ST COAT UPTO 12TH | 0 | Started | Labour | (L)INTERNAL OIL PAINT | FLOORS | 2 | 1.18 | 2.36 | 0 | 0 | 0 | 0 | 1.18 | 0 | 2 | 10431 | 20862 | 2 | 10431 | 20862 | 2 | 0 | 2.36 | -20859.64
1439 | B BLDG RAIL.(ST & FLAT) OIL PAINT (LAB)- 2ND COAT UPTO 12TH | 0 | Started | Labour | (L)INTERNAL OIL PAINT | FLOORS | 2 | 1.18 | 2.36 | 0 | 0 | 0 | 0 | 1.18 | 0 | 2 | 24338 | 48676 | 0 | 0 | 0 | 2 | 2 | 2.36 | 2.36
1440 | B BLDG PAINT CLEANING WORK (LAB) 1ST TO 12TH FLOOR | 0 | Tentative | Labour | (L)INTERNAL OBD PAINT (WALL & CEILING) | FLOORS | 2 | 1.18 | 2.36 | 0 | 0 | 0 | 0 | 1.18 | 0 | 2 | 17241 | 34482 | 0 | 0 | 0 | 2 | 2 | 2.36 | 2.36
1441 | B BLDG MISC.PAINTING WORK (LAB) 1ST TO 12TH FLOOR | 0 | Tentative | Labour | (L)INTERNAL OBD PAINT (WALL & CEILING) | FLOORS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 34482 | 34482 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
1442 | B BLDG PF ON SUBMISSION OF CHALLAN (LAB) | 0 | Tentative | Labour | (L)INTERNAL OBD PAINT (WALL & CEILING) | FLOORS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 34482 | 34482 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
1443 | B BLDG PAINTING WORK RETENTION (LAB) -COMP.OF RET. PERIOD | 0 | Tentative | Labour | (L)INTERNAL OBD PAINT (WALL & CEILING) | FLOORS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 63217 | 63217 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
1444 | Flat:01-05, Alu.SD Wind. Mat.Rcvd-1,2,3 Floor | 0 | Started | Labour | (L)Aluminium SD & Window-1'' & 3/4'' | NOS | 223499 | 1.18 | 263728.82 | 0 | 0 | 0 | 0 | 1.18 | 0 | 223499 | 1.18 | 263728.82 | 223499 | 1.18 | 263728.82 | 223499 | 0 | 263728.82 | 0
1445 | Flat:01-05, Alu.SD Wind. Mat.Rcvd-4,5,6 Floor | 0 | Started | Labour | (L)Aluminium SD & Window-1'' & 3/4'' | NOS | 223499 | 1.18 | 263728.82 | 0 | 0 | 0 | 0 | 1.18 | 0 | 223499 | 1.18 | 263728.82 | 223499 | 1.18 | 263728.82 | 223499 | 0 | 263728.82 | 0
1446 | Flat:01-05, Alu.SD Wind. Mat.Rcvd-7,8,9 Floor | 0 | Started | Labour | (L)Aluminium SD & Window-1'' & 3/4'' | NOS | 223499 | 1.18 | 263728.82 | 0 | 0 | 0 | 0 | 1.18 | 0 | 223499 | 1.18 | 263728.82 | 223499 | 1.18 | 263728.82 | 223499 | 0 | 263728.82 | 0
1447 | Flat:01-05, Alu.SD Wind. Mat.Rcvd-10,11,12 Floor | 0 | Started | Labour | (L)Aluminium SD & Window-1'' & 3/4'' | NOS | 223499 | 1.18 | 263728.82 | 0 | 0 | 0 | 0 | 1.18 | 0 | 223499 | 1.18 | 263728.82 | 223499 | 1.18 | 263728.82 | 223499 | 0 | 263728.82 | 0
1448 | Flat:01-05, Alu.SD Wind. Fixing Comp-1,2,3 Floor | 0 | Tentative | Labour | (L)Aluminium SD & Window-1'' & 3/4'' | NOS | 124166 | 1.18 | 146515.88 | 0 | 0 | 0 | 0 | 1.18 | 0 | 124166 | 1.18 | 146515.88 | 0 | 0 | 0 | 124166 | 124166 | 146515.88 | 146515.88
1449 | Flat:01-05, Alu.SD Wind. Fixing Comp-4,5,6 Floor | 0 | Tentative | Labour | (L)Aluminium SD & Window-1'' & 3/4'' | NOS | 124166 | 1.18 | 146515.88 | 0 | 0 | 0 | 0 | 1.18 | 0 | 124166 | 1.18 | 146515.88 | 0 | 0 | 0 | 124166 | 124166 | 146515.88 | 146515.88
1450 | Flat:01-05, Alu.SD Wind. Fixing Comp-7,8,9 Floor | 0 | Started | Labour | (L)Aluminium SD & Window-1'' & 3/4'' | NOS | 124166 | 1.18 | 146515.88 | 0 | 0 | 0 | 0 | 1.18 | 0 | 124166 | 1.18 | 146515.88 | 124166 | 1.18 | 146515.88 | 124166 | 0 | 146515.88 | 0
1451 | Flat:01-05, Alu.SD Wind. Fixing Comp-10,11,12 Floor | 0 | Started | Labour | (L)Aluminium SD & Window-1'' & 3/4'' | NOS | 124166 | 1.18 | 146515.88 | 0 | 0 | 0 | 0 | 1.18 | 0 | 124166 | 1.18 | 146515.88 | 124166 | 1.18 | 146515.88 | 124166 | 0 | 146515.88 | 0
1452 | Flat:01-05, Louvers Mat.Rcvd-1st to 6th Floor | 0 | Started | Labour | (L)Louvers Window | NOS | 87219 | 1.18 | 102918.42 | 0 | 0 | 0 | 0 | 1.18 | 0 | 87219 | 1.18 | 102918.42 | 0 | 0 | 0 | 87219 | 87219 | 102918.42 | 102918.42
1453 | Flat:01-05, Louvers Mat.Rcvd-7th to 12th Floor | 0 | Started | Labour | (L)Louvers Window | NOS | 87219 | 1.18 | 102918.42 | 0 | 0 | 0 | 0 | 1.18 | 0 | 87219 | 1.18 | 102918.42 | 87219 | 1.18 | 102918.42 | 87219 | 0 | 102918.42 | 0
1454 | Flat:01-05, Louvers Fixing Comp-1st to 6th Floor | 0 | Started | Labour | (L)Louvers Window | NOS | 48455 | 1.18 | 57176.9 | 0 | 0 | 0 | 0 | 1.18 | 0 | 48455 | 1.18 | 57176.9 | 48455 | 1.18 | 57176.9 | 48455 | 0 | 57176.9 | 0
1455 | Flat:01-05, Louvers Fixing Comp-7th to 12th Floor | 0 | Started | Labour | (L)Louvers Window | NOS | 48455 | 1.18 | 57176.9 | 0 | 0 | 0 | 0 | 1.18 | 0 | 48455 | 1.18 | 57176.9 | 48455 | 1.18 | 57176.9 | 48455 | 0 | 57176.9 | 0
1456 | Flat:01-05, Checking-All types Window upto 6th | 0 | Tentative | Labour | (L)Checking (Window SD & Louvers) | NOS | 33918 | 1.18 | 40023.24 | 0 | 0 | 0 | 0 | 1.18 | 0 | 33918 | 1.18 | 40023.24 | 0 | 0 | 0 | 33918 | 33918 | 40023.24 | 40023.24
1457 | Flat:01-05, Alu.SD.Window-1,2,3,4,5,6 Floor Labour | 0 | Tentative | Labour | (L)Aluminium SD & Window-1'' & 3/4'' | NOS | 297998 | 1.18 | 351637.64 | 0 | 0 | 0 | 0 | 1.18 | 0 | 297998 | 1 | 297998 | 0 | 0 | 0 | 297998 | 297998 | 351637.64 | 351637.64
1458 | Flat:01-05, Alu.SD.Window-7,8,9,10,11,12 Floor Labour | 0 | Tentative | Labour | (L)Aluminium SD & Window-1'' & 3/4'' | NOS | 297998 | 1.18 | 351637.64 | 0 | 0 | 0 | 0 | 1.18 | 0 | 297998 | 1 | 297998 | 0 | 0 | 0 | 297998 | 297998 | 351637.64 | 351637.64
1459 | Flat:01-05, Louvers-1st to 6th Floor Labour | 0 | Tentative | Labour | (L)Louvers Window | NOS | 58146 | 1.18 | 68612.28 | 0 | 0 | 0 | 0 | 1.18 | 0 | 58146 | 1 | 58146 | 0 | 0 | 0 | 58146 | 58146 | 68612.28 | 68612.28
1460 | Flat:01-05, Louvers-7th to 12th Floor Labour | 0 | Tentative | Labour | (L)Louvers Window | NOS | 58146 | 1.18 | 68612.28 | 0 | 0 | 0 | 0 | 1.18 | 0 | 58146 | 1 | 58146 | 0 | 0 | 0 | 58146 | 58146 | 68612.28 | 68612.28
1461 | Flat:01-05, Checking-All types Window upto 12th | 0 | Tentative | Labour | (L)Checking (Window SD & Louvers) | NOS | 14536.5 | 1.18 | 17153.07 | 0 | 0 | 0 | 0 | 1.18 | 0 | 14536.5 | 1 | 14536.5 | 0 | 0 | 0 | 14536.5 | 14536.5 | 17153.07 | 17153.07
1462 | Flat:01-05, Retention Alu.W.SD & Louvers | 0 | Tentative | Labour | (L)Retention (All types of Alu.window) | NOS | 127513 | 1.18 | 150465.34 | 0 | 0 | 0 | 0 | 1.18 | 0 | 127513 | 1 | 127513 | 0 | 0 | 0 | 127513 | 127513 | 150465.34 | 150465.34
1463 | Flat:06-10, Alu.SD Wind. Mat.Rcvd-1,2,3 Floor | 0 | Started | Labour | (L)Aluminium SD & Window-1'' & 3/4'' | NOS | 246150 | 1.18 | 290457 | 0 | 0 | 0 | 0 | 1.18 | 0 | 246150 | 1.18 | 290457 | 246150 | 1.18 | 290457 | 246150 | 0 | 290457 | 0
1464 | Flat:06-10, Alu.SD Wind. Mat.Rcvd-4,5,6 Floor | 0 | Started | Labour | (L)Aluminium SD & Window-1'' & 3/4'' | NOS | 246150 | 1.18 | 290457 | 0 | 0 | 0 | 0 | 1.18 | 0 | 246150 | 1.18 | 290457 | 246150 | 1.18 | 290457 | 246150 | 0 | 290457 | 0
1465 | Flat:06-10, Alu.SD Wind. Mat.Rcvd-7,8,9 Floor | 0 | Started | Labour | (L)Aluminium SD & Window-1'' & 3/4'' | NOS | 246150 | 1.18 | 290457 | 0 | 0 | 0 | 0 | 1.18 | 0 | 246150 | 1.18 | 290457 | 246150 | 1.18 | 290457 | 246150 | 0 | 290457 | 0
1466 | Flat:06-10, Alu.SD Wind. Mat.Rcvd-10,11,12 Floor | 0 | Started | Labour | (L)Aluminium SD & Window-1'' & 3/4'' | NOS | 246150 | 1.18 | 290457 | 0 | 0 | 0 | 0 | 1.18 | 0 | 246150 | 1.18 | 290457 | 246150 | 1.18 | 290457 | 246150 | 0 | 290457 | 0
1467 | Flat:06-10, Alu.SD Wind. Fixing Comp-1,2,3 Floor | 0 | Started | Labour | (L)Aluminium SD & Window-1'' & 3/4'' | NOS | 136750 | 1.18 | 161365 | 0 | 0 | 0 | 0 | 1.18 | 0 | 136750 | 1.18 | 161365 | 136750 | 1.18 | 161365 | 136750 | 0 | 161365 | 0
1468 | Flat:06-10, Alu.SD Wind. Fixing Comp-4,5,6 Floor | 0 | Started | Labour | (L)Aluminium SD & Window-1'' & 3/4'' | NOS | 136750 | 1.18 | 161365 | 0 | 0 | 0 | 0 | 1.18 | 0 | 136750 | 1.18 | 161365 | 136750 | 1.18 | 161365 | 136750 | 0 | 161365 | 0
1469 | Flat:06-10, Alu.SD Wind. Fixing Comp-7,8,9 Floor | 0 | Started | Labour | (L)Aluminium SD & Window-1'' & 3/4'' | NOS | 136750 | 1.18 | 161365 | 0 | 0 | 0 | 0 | 1.18 | 0 | 136750 | 1.18 | 161365 | 136750 | 1.18 | 161365 | 136750 | 0 | 161365 | 0
1470 | Flat:06-10, Alu.SD Wind. Fixing Comp-10,11,12 Floor | 0 | Tentative | Labour | (L)Aluminium SD & Window-1'' & 3/4'' | NOS | 136750 | 1.18 | 161365 | 0 | 0 | 0 | 0 | 1.18 | 0 | 136750 | 1.18 | 161365 | 0 | 0 | 0 | 136750 | 136750 | 161365 | 161365
1471 | Flat:06-10, Louvers Mat.Rcvd-1st to 6th Floor | 0 | Started | Labour | (L)Louvers Window | NOS | 102296 | 1.18 | 120709.28 | 0 | 0 | 0 | 0 | 1.18 | 0 | 102296 | 1.18 | 120709.28 | 102296 | 1.18 | 120709.28 | 102296 | 0 | 120709.28 | 0
1472 | Flat:06-10, Louvers Mat.Rcvd-7th to 12th Floor | 0 | Started | Labour | (L)Louvers Window | NOS | 102296 | 1.18 | 120709.28 | 0 | 0 | 0 | 0 | 1.18 | 0 | 102296 | 1.18 | 120709.28 | 102296 | 1.18 | 120709.28 | 102296 | 0 | 120709.28 | 0
1473 | Flat:06-10, Louvers Fixing Comp-1st to 6th Floor | 0 | Started | Labour | (L)Louvers Window | NOS | 56831 | 1.18 | 67060.58 | 0 | 0 | 0 | 0 | 1.18 | 0 | 56831 | 1.18 | 67060.58 | 56831 | 1.18 | 67060.58 | 56831 | 0 | 67060.58 | 0
1474 | Flat:06-10, Louvers Fixing Comp-7th to 12th Floor | 0 | Tentative | Labour | (L)Louvers Window | NOS | 56831 | 1.18 | 67060.58 | 0 | 0 | 0 | 0 | 1.18 | 0 | 56831 | 1.18 | 67060.58 | 0 | 0 | 0 | 56831 | 56831 | 67060.58 | 67060.58
1475 | Flat:06-10, Checking-All types Window upto 6th | 0 | Tentative | Labour | (L)Checking (Window SD & Louvers) | NOS | 39782 | 1.18 | 46942.76 | 0 | 0 | 0 | 0 | 1.18 | 0 | 39782 | 1.18 | 46942.76 | 0 | 0 | 0 | 39782 | 39782 | 46942.76 | 46942.76
1476 | Flat:06-10, Alu.SD.Window-1,2,3,4,5,6 Floor Labour | 0 | Started | Labour | (L)Aluminium SD & Window-1'' & 3/4'' | NOS | 328200 | 1.18 | 387276 | 0 | 0 | 0 | 0 | 1.18 | 0 | 328200 | 1 | 328200 | 328200 | 1 | 328200 | 328200 | 0 | 387276 | 59076
1477 | Flat:06-10, Alu.SD.Window-7,8,9,10,11,12 Floor Labour | 0 | Started | Labour | (L)Aluminium SD & Window-1'' & 3/4'' | NOS | 328200 | 1.18 | 387276 | 0 | 0 | 0 | 0 | 1.18 | 0 | 328200 | 1 | 328200 | 0 | 0 | 0 | 328200 | 328200 | 387276 | 387276
1478 | Flat:06-10, Louvers-1st to 6th Floor Labour | 0 | Started | Labour | (L)Louvers Window | NOS | 68197 | 1.18 | 80472.46 | 0 | 0 | 0 | 0 | 1.18 | 0 | 68197 | 1 | 68197 | 68197 | 1 | 68197 | 68197 | 0 | 80472.46 | 12275.46
1479 | Flat:06-10, Louvers-7th to 12th Floor Labour | 0 | Started | Labour | (L)Louvers Window | NOS | 68197 | 1.18 | 80472.46 | 0 | 0 | 0 | 0 | 1.18 | 0 | 68197 | 1 | 68197 | 0 | 0 | 0 | 68197 | 68197 | 80472.46 | 80472.46
1480 | Flat:06-10, Checking-All types Window upto 12th | 0 | Started | Labour | (L)Checking (Window SD & Louvers) | NOS | 17049 | 1.18 | 20117.82 | 0 | 0 | 0 | 0 | 1.18 | 0 | 17049 | 1 | 17049 | 0 | 0 | 0 | 17049 | 17049 | 20117.82 | 20117.82
1481 | Flat:06-10, Retention Alu.W.SD & Louvers | 0 | Tentative | Labour | (L)Retention (All types of Alu.window) | NOS | 142078 | 1.18 | 167652.04 | 0 | 0 | 0 | 0 | 1.18 | 0 | 142078 | 1 | 142078 | 0 | 0 | 0 | 142078 | 142078 | 167652.04 | 167652.04
1482 | B WING SLIDDING DOOR SUPPORTING MATERIAL-PLY & CEMENT SHEET | 0 | Tentative | Material | (M)CEMENT SHEET 8'X4' (12MM) | SQFT | 192 | 62.69 | 12036.48 | 192 | 62.69 | 12036.48 | 0 | 62.69 | 0 | 192 | 53.76 | 10321.92 | 0 | 0 | 0 | 192 | 192 | 12036.48 | 12036.48
1483 | B WING SLIDDING DOOR SUPPORTING MATERIAL-PLY & CEMENT SHEET | 0 | Tentative | Material | (M)Fevicol | KG | 5 | 247.8 | 1239 | 5 | 247.8 | 1239 | 0 | 247.8 | 0 | 5 | 247.8 | 1239 | 0 | 0 | 0 | 5 | 5 | 1239 | 1239
1484 | B WING SLIDDING DOOR SUPPORTING MATERIAL-PLY & CEMENT SHEET | 0 | Tentative | Material | (M)Nails -14 no x 2" | KG | 6.5 | 118 | 767 | 6.5 | 118 | 767 | 0 | 118 | 0 | 6.5 | 177 | 1150.5 | 0 | 0 | 0 | 6.5 | 6.5 | 767 | 767
1485 | B WING SLIDDING DOOR SUPPORTING MATERIAL-PLY & CEMENT SHEET | 0 | Tentative | Material | (M)Plywood 8' x 4' x 18mm | NOS | 18 | 2176 | 39168 | 18 | 2176 | 39168 | 0 | 2176 | 0 | 18 | 2643.2 | 47577.6 | 0 | 0 | 0 | 18 | 18 | 39168 | 39168
1486 | B WING SLIDDING DOOR SUPPORTING MATERIAL-PLY & CEMENT SHEET | 0 | Tentative | Material | (M)RAVAL PLUG 35 x 8 mm | NOS | 900 | 0.6 | 540 | 900 | 0.6 | 540 | 0 | 0.6 | 0 | 900 | 0.53 | 477.9 | 0 | 0 | 0 | 900 | 900 | 540 | 540
1487 | B WING SLIDDING DOOR SUPPORTING MATERIAL-PLY & CEMENT SHEET | 0 | Tentative | Material | (M)SS Screw -75 x10 Full Thread | NOS | 450 | 2.36 | 1062 | 450 | 2.36 | 1062 | 0 | 2.36 | 0 | 450 | 7.67 | 3451.5 | 0 | 0 | 0 | 450 | 450 | 1062 | 1062
1488 | B BLDG ELE. DUCT 1ST FLOOR ALU.WINDOW SD (M.RATE-70%) | 0 | Tentative | Labour | (L)Alu. Window SD-3track, 20mm Series (Mat) | SQFT | 62.5 | 202.37 | 12648.13 | 0 | 0 | 0 | 0 | 202.37 | 0 | 62.5 | 202.37 | 12648.13 | 0 | 0 | 0 | 62.5 | 62.5 | 12648.125 | 12648.125
1489 | B BLDG ELE. DUCT 2ND FLOOR ALU.WINDOW SD (M.RATE-70%) | 0 | Tentative | Labour | (L)Alu. Window SD-3track, 20mm Series (Mat) | SQFT | 62.5 | 202.37 | 12648.13 | 0 | 0 | 0 | 0 | 202.37 | 0 | 62.5 | 202.37 | 12648.13 | 0 | 0 | 0 | 62.5 | 62.5 | 12648.125 | 12648.125
1490 | B BLDG ELE. DUCT 3RD FLOOR ALU.WINDOW SD (M.RATE-70%) | 0 | Tentative | Labour | (L)Alu. Window SD-3track, 20mm Series (Mat) | SQFT | 62.5 | 202.37 | 12648.13 | 0 | 0 | 0 | 0 | 202.37 | 0 | 62.5 | 202.37 | 12648.13 | 0 | 0 | 0 | 62.5 | 62.5 | 12648.125 | 12648.125
1491 | B BLDG ELE. DUCT 4TH FLOOR ALU.WINDOW SD (M.RATE-70%) | 0 | Tentative | Labour | (L)Alu. Window SD-3track, 20mm Series (Mat) | SQFT | 62.5 | 202.37 | 12648.13 | 0 | 0 | 0 | 0 | 202.37 | 0 | 62.5 | 202.37 | 12648.13 | 0 | 0 | 0 | 62.5 | 62.5 | 12648.125 | 12648.125
1492 | B BLDG ELE. DUCT 5TH FLOOR ALU.WINDOW SD (M.RATE-70%) | 0 | Tentative | Labour | (L)Alu. Window SD-3track, 20mm Series (Mat) | SQFT | 62.5 | 202.37 | 12648.13 | 0 | 0 | 0 | 0 | 202.37 | 0 | 62.5 | 202.37 | 12648.13 | 0 | 0 | 0 | 62.5 | 62.5 | 12648.125 | 12648.125
1493 | B BLDG ELE. DUCT 6TH FLOOR ALU.WINDOW SD (M.RATE-70%) | 0 | Tentative | Labour | (L)Alu. Window SD-3track, 20mm Series (Mat) | SQFT | 62.5 | 202.37 | 12648.13 | 0 | 0 | 0 | 0 | 202.37 | 0 | 62.5 | 202.37 | 12648.13 | 0 | 0 | 0 | 62.5 | 62.5 | 12648.125 | 12648.125
1494 | B BLDG ELE. DUCT 7TH FLOOR ALU.WINDOW SD (M.RATE-70%) | 0 | Tentative | Labour | (L)Alu. Window SD-3track, 20mm Series (Mat) | SQFT | 62.5 | 202.37 | 12648.13 | 0 | 0 | 0 | 0 | 202.37 | 0 | 62.5 | 202.37 | 12648.13 | 0 | 0 | 0 | 62.5 | 62.5 | 12648.125 | 12648.125
1495 | B BLDG ELE. DUCT 8TH FLOOR ALU.WINDOW SD (M.RATE-70%) | 0 | Tentative | Labour | (L)Alu. Window SD-3track, 20mm Series (Mat) | SQFT | 62.5 | 202.37 | 12648.13 | 0 | 0 | 0 | 0 | 202.37 | 0 | 62.5 | 202.37 | 12648.13 | 0 | 0 | 0 | 62.5 | 62.5 | 12648.125 | 12648.125
1496 | B BLDG ELE. DUCT 9TH FLOOR ALU.WINDOW SD (M.RATE-70%) | 0 | Tentative | Labour | (L)Alu. Window SD-3track, 20mm Series (Mat) | SQFT | 62.5 | 202.37 | 12648.13 | 0 | 0 | 0 | 0 | 202.37 | 0 | 62.5 | 202.37 | 12648.13 | 0 | 0 | 0 | 62.5 | 62.5 | 12648.125 | 12648.125
1497 | B BLDG ELE. DUCT 10TH FLOOR ALU.WINDOW SD (M.RATE-70%) | 0 | Tentative | Labour | (L)Alu. Window SD-3track, 20mm Series (Mat) | SQFT | 62.5 | 202.37 | 12648.13 | 0 | 0 | 0 | 0 | 202.37 | 0 | 62.5 | 202.37 | 12648.13 | 0 | 0 | 0 | 62.5 | 62.5 | 12648.125 | 12648.125
1498 | B BLDG ELE. DUCT 11TH FLOOR ALU.WINDOW SD (M.RATE-70%) | 0 | Tentative | Labour | (L)Alu. Window SD-3track, 20mm Series (Mat) | SQFT | 62.5 | 202.37 | 12648.13 | 0 | 0 | 0 | 0 | 202.37 | 0 | 62.5 | 202.37 | 12648.13 | 0 | 0 | 0 | 62.5 | 62.5 | 12648.125 | 12648.125
1499 | B BLDG ELE. DUCT 12TH FLOOR ALU.WINDOW SD (M.RATE-70%) | 0 | Tentative | Labour | (L)Alu. Window SD-3track, 20mm Series (Mat) | SQFT | 62.5 | 202.37 | 12648.13 | 0 | 0 | 0 | 0 | 202.37 | 0 | 62.5 | 202.37 | 12648.13 | 0 | 0 | 0 | 62.5 | 62.5 | 12648.125 | 12648.125
1500 | B BLDG ELE. DUCT 1ST FLOOR ALU.WINDOW SD (L.RATE-30%) | 0 | Tentative | Labour | (L)Alu. Window SD-3track, 20mm Series (Lab) | SQFT | 62.5 | 86.73 | 5420.63 | 0 | 0 | 0 | 0 | 86.73 | 0 | 62.5 | 73.5 | 4593.75 | 0 | 0 | 0 | 62.5 | 62.5 | 5420.625 | 5420.625
1501 | B BLDG ELE. DUCT 2ND FLOOR ALU.WINDOW SD (L.RATE-30%) | 0 | Tentative | Labour | (L)Alu. Window SD-3track, 20mm Series (Lab) | SQFT | 62.5 | 86.73 | 5420.63 | 0 | 0 | 0 | 0 | 86.73 | 0 | 62.5 | 73.5 | 4593.75 | 0 | 0 | 0 | 62.5 | 62.5 | 5420.625 | 5420.625
1502 | B BLDG ELE. DUCT 3RD FLOOR ALU.WINDOW SD (L.RATE-30%) | 0 | Tentative | Labour | (L)Alu. Window SD-3track, 20mm Series (Lab) | SQFT | 62.5 | 86.73 | 5420.63 | 0 | 0 | 0 | 0 | 86.73 | 0 | 62.5 | 73.5 | 4593.75 | 0 | 0 | 0 | 62.5 | 62.5 | 5420.625 | 5420.625
1503 | B BLDG ELE. DUCT 4TH FLOOR ALU.WINDOW SD (L.RATE-30%) | 0 | Tentative | Labour | (L)Alu. Window SD-3track, 20mm Series (Lab) | SQFT | 62.5 | 86.73 | 5420.63 | 0 | 0 | 0 | 0 | 86.73 | 0 | 62.5 | 73.5 | 4593.75 | 0 | 0 | 0 | 62.5 | 62.5 | 5420.625 | 5420.625
1504 | B BLDG ELE. DUCT 5TH FLOOR ALU.WINDOW SD (L.RATE-30%) | 0 | Tentative | Labour | (L)Alu. Window SD-3track, 20mm Series (Lab) | SQFT | 62.5 | 86.73 | 5420.63 | 0 | 0 | 0 | 0 | 86.73 | 0 | 62.5 | 73.5 | 4593.75 | 0 | 0 | 0 | 62.5 | 62.5 | 5420.625 | 5420.625
1505 | B BLDG ELE. DUCT 6TH FLOOR ALU.WINDOW SD (L.RATE-30%) | 0 | Tentative | Labour | (L)Alu. Window SD-3track, 20mm Series (Lab) | SQFT | 62.5 | 86.73 | 5420.63 | 0 | 0 | 0 | 0 | 86.73 | 0 | 62.5 | 73.5 | 4593.75 | 0 | 0 | 0 | 62.5 | 62.5 | 5420.625 | 5420.625
1506 | B BLDG ELE. DUCT 7TH FLOOR ALU.WINDOW SD (L.RATE-30%) | 0 | Tentative | Labour | (L)Alu. Window SD-3track, 20mm Series (Lab) | SQFT | 62.5 | 86.73 | 5420.63 | 0 | 0 | 0 | 0 | 86.73 | 0 | 62.5 | 73.5 | 4593.75 | 0 | 0 | 0 | 62.5 | 62.5 | 5420.625 | 5420.625
1507 | B BLDG ELE. DUCT 8TH FLOOR ALU.WINDOW SD (L.RATE-30%) | 0 | Tentative | Labour | (L)Alu. Window SD-3track, 20mm Series (Lab) | SQFT | 62.5 | 86.73 | 5420.63 | 0 | 0 | 0 | 0 | 86.73 | 0 | 62.5 | 73.5 | 4593.75 | 0 | 0 | 0 | 62.5 | 62.5 | 5420.625 | 5420.625
1508 | B BLDG ELE. DUCT 9TH FLOOR ALU.WINDOW SD (L.RATE-30%) | 0 | Tentative | Labour | (L)Alu. Window SD-3track, 20mm Series (Lab) | SQFT | 62.5 | 86.73 | 5420.63 | 0 | 0 | 0 | 0 | 86.73 | 0 | 62.5 | 73.5 | 4593.75 | 0 | 0 | 0 | 62.5 | 62.5 | 5420.625 | 5420.625
1509 | B BLDG ELE. DUCT 10TH FLOOR ALU.WINDOW SD (L.RATE-30%) | 0 | Tentative | Labour | (L)Alu. Window SD-3track, 20mm Series (Lab) | SQFT | 62.5 | 86.73 | 5420.63 | 0 | 0 | 0 | 0 | 86.73 | 0 | 62.5 | 73.5 | 4593.75 | 0 | 0 | 0 | 62.5 | 62.5 | 5420.625 | 5420.625
1510 | B BLDG ELE. DUCT 11TH FLOOR ALU.WINDOW SD (L.RATE-30%) | 0 | Tentative | Labour | (L)Alu. Window SD-3track, 20mm Series (Lab) | SQFT | 62.5 | 86.73 | 5420.63 | 0 | 0 | 0 | 0 | 86.73 | 0 | 62.5 | 73.5 | 4593.75 | 0 | 0 | 0 | 62.5 | 62.5 | 5420.625 | 5420.625
1511 | B BLDG ELE. DUCT 12TH FLOOR ALU.WINDOW SD (L.RATE-30%) | 0 | Tentative | Labour | (L)Alu. Window SD-3track, 20mm Series (Lab) | SQFT | 62.5 | 86.73 | 5420.63 | 0 | 0 | 0 | 0 | 86.73 | 0 | 62.5 | 73.5 | 4593.75 | 0 | 0 | 0 | 62.5 | 62.5 | 5420.625 | 5420.625
1512 | B BLDG FIRE & REG ST-CASE SD WINDOW UPTO 12TH FLR (MAT-70%) | 0 | Tentative | Labour | (L)2-TRACK SD WINDOW (MAT) | SQFT | 416 | 170.98 | 71127.68 | 0 | 0 | 0 | 0 | 170.98 | 0 | 416 | 170.98 | 71128.52 | 0 | 0 | 0 | 416 | 416 | 71127.68 | 71127.68
1513 | B BLDG FIRE & REG ST-CASE SD WINDOW UPTO 12TH FLR (LAB-70%) | 0 | Tentative | Labour | (L)2-TRACK SD WINDOW (LAB) | SQFT | 416 | 73.28 | 30484.48 | 0 | 0 | 0 | 0 | 73.28 | 0 | 416 | 62.1 | 25833.6 | 0 | 0 | 0 | 416 | 416 | 30484.48 | 30484.48
1514 | B BLDG FD:PROVIDING AND FIXING FD FRAME FOR 1,2,3 FLOOR | 0 | Tentative | Material | (M)FRENCH DOOR WITH FRAME-SINGLE FOLD SHUTTER | SQFT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1515 | B BLDG FD:PROVIDING AND FIXING FD FRAME FOR 1,2,3 FLOOR | 0 | Tentative | Labour | (L)FOLDING DOORS (M+L) - 3.25' x 7.5' | SQFT | 224.2267 | 354 | 79376.25 | 0 | 0 | 0 | 0 | 354 | 0 | 224.2267 | 354 | 79376.25 | 0 | 0 | 0 | 224.2267 | 224.2267 | 79376.252 | 79376.2518
1516 | B BLDG FD:PROVIDING AND FIXING FD FRAME FOR 4,5,6 FLOOR | 0 | Tentative | Material | (M)FRENCH DOOR WITH FRAME-SINGLE FOLD SHUTTER | SQFT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1517 | B BLDG FD:PROVIDING AND FIXING FD FRAME FOR 4,5,6 FLOOR | 0 | Tentative | Labour | (L)FOLDING DOORS (M+L) - 3.25' x 7.5' | SQFT | 233.9767 | 354 | 82827.75 | 0 | 0 | 0 | 0 | 354 | 0 | 233.9767 | 354 | 82827.75 | 0 | 0 | 0 | 233.9767 | 233.9767 | 82827.752 | 82827.7518
1518 | B BLDG FD:PROVIDING AND FIXING FD FRAME FOR 7,8,9 FLOOR | 0 | Tentative | Material | (M)FRENCH DOOR WITH FRAME-SINGLE FOLD SHUTTER | SQFT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1519 | B BLDG FD:PROVIDING AND FIXING FD FRAME FOR 7,8,9 FLOOR | 0 | Tentative | Labour | (L)FOLDING DOORS (M+L) - 3.25' x 7.5' | SQFT | 253.4734 | 354 | 89729.58 | 0 | 0 | 0 | 0 | 354 | 0 | 253.4734 | 354 | 89729.58 | 0 | 0 | 0 | 253.4734 | 253.4734 | 89729.584 | 89729.5836
1520 | B BLDG FD:PROVIDING AND FIXING FD FRAME FOR 10,11,12 FLOOR | 0 | Tentative | Material | (M)FRENCH DOOR WITH FRAME-SINGLE FOLD SHUTTER | SQFT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1521 | B BLDG FD:PROVIDING AND FIXING FD FRAME FOR 10,11,12 FLOOR | 0 | Tentative | Labour | (L)FOLDING DOORS (M+L) - 3.25' x 7.5' | SQFT | 263.2234 | 354 | 93181.08 | 0 | 0 | 0 | 0 | 354 | 0 | 263.2234 | 354 | 93181.08 | 0 | 0 | 0 | 263.2234 | 263.2234 | 93181.084 | 93181.0836
1522 | B BLDG FD: PROVIDING & FIXING SHUTTER GLASS-1ST LOT 30 SHUTT | 0 | Started | Material | (M)FRENCH DOOR WITH FRAME-SINGLE FOLD SHUTTER | SQFT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1523 | B BLDG FD: PROVIDING & FIXING SHUTTER GLASS-1ST LOT 30 SHUTT | 0 | Started | Labour | (L)FOLDING DOORS (M+L) - 3.25' x 7.5' | SQFT | 444.5267 | 354 | 157362.45 | 0 | 0 | 0 | 0 | 354 | 0 | 444.5267 | 354 | 157362.45 | 444.5267 | 354 | 157362.45 | 444.5267 | 0 | 157362.452 | 0.0018
1524 | B BLDG FD: PROVIDING & FIXING SHUTTER GLASS-2ND LOT 30 SHUTT | 0 | Started | Material | (M)FRENCH DOOR WITH FRAME-SINGLE FOLD SHUTTER | SQFT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1525 | B BLDG FD: PROVIDING & FIXING SHUTTER GLASS-2ND LOT 30 SHUTT | 0 | Started | Labour | (L)FOLDING DOORS (M+L) - 3.25' x 7.5' | SQFT | 482.3567 | 354 | 170754.27 | 0 | 0 | 0 | 0 | 354 | 0 | 482.3567 | 354 | 170754.27 | 482.3567 | 354 | 170754.27 | 482.3567 | 0 | 170754.272 | 0.0018
1526 | B BLDG FD: PROVIDING & FIXING SHUTTER GLASS-3RD LOT 30 SHUTT | 0 | Tentative | Material | (M)FRENCH DOOR WITH FRAME-SINGLE FOLD SHUTTER | SQFT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1527 | B BLDG FD: PROVIDING & FIXING SHUTTER GLASS-3RD LOT 30 SHUTT | 0 | Tentative | Labour | (L)FOLDING DOORS (M+L) - 3.25' x 7.5' | SQFT | 482.3567 | 354 | 170754.27 | 0 | 0 | 0 | 0 | 354 | 0 | 482.3567 | 354 | 170754.27 | 0 | 0 | 0 | 482.3567 | 482.3567 | 170754.272 | 170754.2718
1528 | B BLDG FD: PROVIDING & FIXING SHUTTER GLASS-4TH LOT 30 SHUTT | 0 | Tentative | Material | (M)FRENCH DOOR WITH FRAME-SINGLE FOLD SHUTTER | SQFT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1529 | B BLDG FD: PROVIDING & FIXING SHUTTER GLASS-4TH LOT 30 SHUTT | 0 | Tentative | Labour | (L)FOLDING DOORS (M+L) - 3.25' x 7.5' | SQFT | 482.3567 | 354 | 170754.27 | 0 | 0 | 0 | 0 | 354 | 0 | 482.3567 | 354 | 170754.27 | 0 | 0 | 0 | 482.3567 | 482.3567 | 170754.272 | 170754.2718
1530 | B BLDG FD: MISCELLANEOUS WORK | 0 | Tentative | Material | (M)FRENCH DOOR WITH FRAME-SINGLE FOLD SHUTTER | SQFT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1531 | B BLDG FD: MISCELLANEOUS WORK | 0 | Tentative | Labour | (L)FOLDING DOORS (M+L) - 3.25' x 7.5' | SQFT | 58.5 | 354 | 20709 | 0 | 0 | 0 | 0 | 354 | 0 | 58.5 | 354 | 20709 | 0 | 0 | 0 | 58.5 | 58.5 | 20709 | 20709
1532 | B BLDG CORE CUTTING WORK DEPTH-5'' | 0 | Started | Labour | (L)Core Cutting Dia-100mm | Inches | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 45 | 9000 | 140 | 45 | 6300 | 200 | 60 | 0 | -6300
1533 | B BLDG CORE CUTTING WORK DEPTH-5'' | 0 | Started | Labour | (L)Core Cutting Dia-125mm | Inches | 145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145 | 50 | 7250 | 130 | 50 | 6500 | 145 | 15 | 0 | -6500
1534 | B BLDG CORE CUTTING WORK DEPTH-5'' | 0 | Started | Labour | (L)Core Cutting Dia-50mm | Inches | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 30 | 150 | 5 | 30 | 150 | 5 | 0 | 0 | -150
1535 | B BLDG CORE CUTTING WORK DEPTH-5'' | 0 | Started | Labour | (L)Core Cutting Dia-75mm | Inches | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 35 | 875 | 5 | 35 | 175 | 25 | 20 | 0 | -175
1536 | B BLDG CORE CUTTING WORK DEPTH-9'' | 0 | Started | Labour | (L)Core Cutting Dia-100mm | Inches | 144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 45 | 6480 | 0 | 0 | 0 | 144 | 144 | 0 | 0
1537 | B BLDG CORE CUTTING WORK DEPTH-9'' | 0 | Started | Labour | (L)Core Cutting Dia-125mm | Inches | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 50 | 1800 | 18 | 50 | 900 | 36 | 18 | 0 | -900
1538 | B BLDG CORE CUTTING WORK DEPTH-9'' | 0 | Started | Labour | (L)Core Cutting Dia-75mm | Inches | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 35 | 315 | 9 | 35 | 315 | 9 | 0 | 0 | -315
1539 | INDENT-891/B BLDG/CORE CUTTING FOR PLUMBING WORK | 0 | Started | Labour | (L)Core Cutting Dia-100mm | Inches | 1188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1188 | 45 | 53460 | 0 | 0 | 0 | 1188 | 1188 | 0 | 0
1540 | INDENT-891/B BLDG/CORE CUTTING FOR PLUMBING WORK | 0 | Started | Labour | (L)Core Cutting Dia-125mm | Inches | 1080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1080 | 50 | 54000 | 0 | 0 | 0 | 1080 | 1080 | 0 | 0
1541 | LIGHTING ARRESTER LIGHTING ARRESTER WORK | 0 | Tentative | Material | (M)5 SPIKE COPPER 6'' DIA SPHERE ARRESTER WITH 50MM COPPER ROD | NOS | 7 | 1180 | 8260 | 7 | 1180 | 8260 | 0 | 1180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 8260 | 8260
1542 | LIGHTING ARRESTER LIGHTING ARRESTER WORK | 0 | Tentative | Material | (M)Anchor Fastners 200mm x 6mm | NOS | 30 | 70.8 | 2124 | 30 | 70.8 | 2124 | 0 | 70.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 2124 | 2124
1543 | LIGHTING ARRESTER LIGHTING ARRESTER WORK | 0 | Tentative | Material | (M)COPPER PLATE - 200 x 200 x 5MM | NOS | 7 | 1180 | 8260 | 7 | 1180 | 8260 | 0 | 1180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 8260 | 8260
1544 | LIGHTING ARRESTER LIGHTING ARRESTER WORK | 0 | Tentative | Material | (M)EARTHING STRIP INSULATOR | NOS | 480 | 59 | 28320 | 480 | 59 | 28320 | 0 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480 | 480 | 28320 | 28320
1545 | LIGHTING ARRESTER LIGHTING ARRESTER WORK | 0 | Tentative | Material | (M)GI NUT BOLT WITH DOUBLE WISHOR 25 x 6MM | SET | 480 | 29.5 | 14160 | 480 | 29.5 | 14160 | 0 | 29.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480 | 480 | 14160 | 14160
1546 | LIGHTING ARRESTER LIGHTING ARRESTER WORK | 0 | Tentative | Material | (M)GI PIPE 50MM x 1.2MTR (B-TYPE) | NOS | 6 | 590 | 3540 | 6 | 590 | 3540 | 0 | 590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 3540 | 3540
1547 | LIGHTING ARRESTER LIGHTING ARRESTER WORK | 0 | Tentative | Material | (M)GI PIPE 50MM x 2MTR (B-TYPE) | NOS | 1 | 1003 | 1003 | 1 | 1003 | 1003 | 0 | 1003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1003 | 1003
1548 | LIGHTING ARRESTER LIGHTING ARRESTER WORK | 0 | Tentative | Material | (M)GI PLATE - 200 x 200 x 6MM | NOS | 7 | 118 | 826 | 7 | 118 | 826 | 0 | 118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 826 | 826
1549 | LIGHTING ARRESTER LIGHTING ARRESTER WORK | 0 | Tentative | Material | (M)GI PLATE - 250 x 250 x 5MM | NOS | 7 | 147.5 | 1032.5 | 7 | 147.5 | 1032.5 | 0 | 147.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 1032.5 | 1032.5
1550 | LIGHTING ARRESTER LIGHTING ARRESTER WORK | 0 | Tentative | Material | (M)GI STRIP 25MM x 6MM | Mtr. | 460 | 59 | 27140 | 460 | 59 | 27140 | 0 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 460 | 460 | 27140 | 27140
1551 | LIGHTING ARRESTER LIGHTING ARRESTER WORK | 0 | Tentative | Material | (M)GI WEBS 75 x 75 x 5MM | NOS | 7 | 70.8 | 495.6 | 7 | 70.8 | 495.6 | 0 | 70.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 495.6 | 495.6
1552 | LIGHTING ARRESTER LIGHTING ARRESTER WORK | 0 | Tentative | Material | (M)SS Screw 35 x 8mm F/T | NOS | 1000 | 1.18 | 1180 | 1000 | 1.18 | 1180 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 1000 | 1180 | 1180
1553 | LIGHTING ARRESTER LIGHTING ARRESTER WORK | 0 | Tentative | Material | (M)TEST LINK BOX | NOS | 2 | 118 | 236 | 2 | 118 | 236 | 0 | 118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 236 | 236
1554 | C WING FOOTING PCC M15 (CEMENT PPC) | 10 | Started | Material | (M)CEMENT PPC 50KG | BAG | 465 | 320 | 148800 | 0 | 0 | 0 | 47 | 320 | 15040 | 0 | 0 | 0 | 0 | 0 | 0 | 418 | 465 | 133760 | 148800 | Building
1555 | C WING FOOTING PCC M15 (CEMENT PPC) | 10 | Started | Material | (M)Crush Sand | BRASS | 19.72 | 3675 | 72471 | 0 | 0 | 0 | 2 | 3675 | 7350 | 0 | 0 | 0 | 0 | 0 | 0 | 17.72 | 19.72 | 65121 | 72471 | Building
1556 | C WING FOOTING PCC M15 (CEMENT PPC) | 10 | Started | Material | (M)Metal No.III 20MM | BRASS | 23.97 | 3045 | 72988.65 | 0 | 0 | 0 | 2 | 3045 | 6090 | 0 | 0 | 0 | 0 | 0 | 0 | 21.97 | 23.97 | 66898.65 | 72988.65 | Building
1557 | C WING FOOTING PCC M15 (CEMENT OPC-43) | 10 | Started | Material | (M)CEMENT OPC 43 | BAG | 125 | 378.88 | 47360 | 0 | 0 | 0 | 13 | 378.88 | 4925.44 | 0 | 0 | 0 | 0 | 0 | 0 | 112 | 125 | 42434.56 | 47360 | Building
1558 | C WING FOOTING PCC M15 (CEMENT OPC-43) | 10 | Started | Material | (M)Crush Sand | BRASS | 5.4 | 3675 | 19845 | 0 | 0 | 0 | 1 | 3675 | 3675 | 0 | 0 | 0 | 0 | 0 | 0 | 4.4 | 5.4 | 16170 | 19845 | Building
1559 | C WING FOOTING PCC M15 (CEMENT OPC-43) | 10 | Started | Material | (M)Metal No.III 20MM | BRASS | 6.55 | 3045 | 19944.75 | 0 | 0 | 0 | 1 | 3045 | 3045 | 0 | 0 | 0 | 0 | 0 | 0 | 5.55 | 6.55 | 16899.75 | 19944.75 | Building
1560 | C WING FOOTING CONCRETE RMC-M25 | 10 | Started | Material | (M)RMC M-25 | CUM | 454 | 4600 | 2088400 | 0 | 0 | 0 | 45 | 4600 | 207000 | 0 | 0 | 0 | 0 | 0 | 0 | 409 | 454 | 1881400 | 2088400 | Building
1561 | C WING COL.CONCRETE (FOOTING TO 8TH SLAB) M30 | 10 | Started | Material | (M)CEMENT OPC 43 | BAG | 3270 | 378.88 | 1238937.6 | 0 | 0 | 0 | 327 | 378.88 | 123893.76 | 0 | 0 | 0 | 0 | 0 | 0 | 2943 | 3270 | 1115043.84 | 1238937.6 | Building
1562 | C WING COL.CONCRETE (FOOTING TO 8TH SLAB) M30 | 10 | Started | Material | (M)Crush Sand | BRASS | 83.1 | 3675 | 305392.5 | 0 | 0 | 0 | 8 | 3675 | 29400 | 0 | 0 | 0 | 0 | 0 | 0 | 75.1 | 83.1 | 275992.5 | 305392.5 | Building
1563 | C WING COL.CONCRETE (FOOTING TO 8TH SLAB) M30 | 10 | Started | Material | (M)Metal No.III 20MM | BRASS | 105.25 | 3045 | 320486.25 | 0 | 0 | 0 | 11 | 3045 | 33495 | 0 | 0 | 0 | 0 | 0 | 0 | 94.25 | 105.25 | 286991.25 | 320486.25 | Building
1564 | C WING COL.CONCRETE (8TH TO 13TH SLAB) M25 | 10 | Started | Material | (M)CEMENT OPC 43 | BAG | 1265 | 378.88 | 479283.2 | 0 | 0 | 0 | 127 | 378.88 | 48117.76 | 0 | 0 | 0 | 0 | 0 | 0 | 1138 | 1265 | 431165.44 | 479283.2 | Building
1565 | C WING COL.CONCRETE (8TH TO 13TH SLAB) M25 | 10 | Started | Material | (M)Crush Sand | BRASS | 34.27 | 3675 | 125942.25 | 0 | 0 | 0 | 3 | 3675 | 11025 | 0 | 0 | 0 | 0 | 0 | 0 | 31.27 | 34.27 | 114917.25 | 125942.25 | Building
1566 | C WING COL.CONCRETE (8TH TO 13TH SLAB) M25 | 10 | Started | Material | (M)Metal No.III 20MM | BRASS | 44 | 3045 | 133980 | 0 | 0 | 0 | 4 | 3045 | 12180 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 44 | 121800 | 133980 | Building
1567 | C WING SLAB CONC. (1ST TO 12TH SLAB) M25 | 10 | Started | Material | (M)CEMENT OPC 43 | BAG | 11430 | 378.88 | 4330598.4 | 0 | 0 | 0 | 1143 | 378.88 | 433059.84 | 0 | 0 | 0 | 0 | 0 | 0 | 10287 | 11430 | 3897538.56 | 4330598.4 | Building
1568 | C WING SLAB CONC. (1ST TO 12TH SLAB) M25 | 10 | Started | Material | (M)Crush Sand | BRASS | 333.725 | 3675 | 1226439.38 | 0 | 0 | 0 | 33 | 3675 | 121275 | 0 | 0 | 0 | 0 | 0 | 0 | 300.725 | 333.725 | 1105164.375 | 1226439.375 | Building
1569 | C WING SLAB CONC. (1ST TO 12TH SLAB) M25 | 10 | Started | Material | (M)Metal No.III 20MM | BRASS | 424.47 | 3045 | 1292511.15 | 0 | 0 | 0 | 42 | 3045 | 127890 | 0 | 0 | 0 | 0 | 0 | 0 | 382.47 | 424.47 | 1164621.15 | 1292511.15 | Building
1570 | C WING STELL (UP TO 12TH SLAB & ABOVE COL.)-8MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 8mm (Fe 500, 0.395 KGS/Rm) | KG | 108244.09 | 59 | 6386401.31 | 0 | 0 | 0 | 10824 | 59 | 638616 | 0 | 0 | 0 | 0 | 0 | 0 | 97420.09 | 108244.09 | 5747785.31 | 6386401.31 | Building
1571 | C WING STELL (UP TO 12TH SLAB & ABOVE COL.)-10MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 10mm (Fe 500, 0.617 KGS/Rm) | KG | 23464.9 | 59 | 1384429.1 | 0 | 0 | 0 | 2346 | 59 | 138414 | 0 | 0 | 0 | 81.444 | 59.36 | 4834.29 | 21118.9 | 23383.456 | 1246015.1 | 1379594.81 | Building
1572 | C WING STELL (UP TO 12TH SLAB & ABOVE COL.)-12MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 12mm (Fe 500, 0.888 KGS/Rm) | KG | 37291.21 | 59 | 2200181.39 | 0 | 0 | 0 | 3729 | 59 | 220011 | 0 | 0 | 0 | 1704.96 | 60.06 | 102395.12 | 33562.21 | 35586.25 | 1980170.39 | 2097786.27 | Building
1573 | C WING STELL (UP TO 12TH SLAB & ABOVE COL.)-16MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 16mm (Fe 500, 1.58 KGS/Rm) | KG | 36813.66 | 59 | 2172005.94 | 0 | 0 | 0 | 3681 | 59 | 217179 | 0 | 0 | 0 | 0 | 0 | 0 | 33132.66 | 36813.66 | 1954826.94 | 2172005.94 | Building
1574 | C WING STELL (UP TO 12TH SLAB & ABOVE COL.)-20MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 20mm (Fe 500, 2.47 KGS/Rm) | KG | 57828.52 | 59 | 3411882.68 | 0 | 0 | 0 | 5783 | 59 | 341197 | 0 | 0 | 0 | 0 | 0 | 0 | 52045.52 | 57828.52 | 3070685.68 | 3411882.68 | Building
1575 | C WING STELL (UP TO 12TH SLAB & ABOVE COL.)-25MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 25mm (Fe 500, 3.85 KGS/Rm) | KG | 101441.57 | 59 | 5985052.63 | 0 | 0 | 0 | 10144 | 59 | 598496 | 0 | 0 | 0 | 0 | 0 | 0 | 91297.57 | 101441.57 | 5386556.63 | 5985052.63 | Building
1576 | C WING STELL (UP TO 12TH SLAB & ABOVE COL.)-32MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 32mm (Fe 500, 6.31 KGS/Rm) | KG | 12937.93 | 59 | 763337.87 | 0 | 0 | 0 | 1294 | 59 | 76346 | 0 | 0 | 0 | 151.7 | 64.31 | 9755.83 | 11643.93 | 12786.23 | 686991.87 | 753582.04 | Building
1577 | C WING (UP TO 12TH SLAB & ABOVE COL.)-BINDING WIRE | 10 | Started | Material | (M)MS Binding Wire 18G | KG | 4807 | 50 | 240350 | 0 | 0 | 0 | 481 | 50 | 24050 | 0 | 0 | 0 | 0 | 0 | 0 | 4326 | 4807 | 216300 | 240350 | Building
1578 | C BLDG. PLINTH COMPLETION | 0 | Tentative | Labour | (L)FOOTING, COL. UP TO PLINTH | SQFT | 3281.8519 | 197.06 | 646721.74 | 0 | 0 | 0 | 0 | 197.06 | 0 | 3281.8519 | 191.16 | 627358.8078 | 0 | 0 | 0 | 3281.8519 | 3281.8519 | 646721.735 | 646721.7354
1579 | C BLDG.1ST SLAB | 0 | Tentative | Labour | (L)SHUTTERING, R/F & CASTING OF SLAB | SQFT | 4556.5802 | 197.06 | 897919.69 | 0 | 0 | 0 | 0 | 197.06 | 0 | 4556.5802 | 191.16 | 871035.8724 | 0 | 0 | 0 | 4556.5802 | 4556.5802 | 897919.694 | 897919.6942
1580 | C BLDG.2ND SLAB | 0 | Tentative | Labour | (L)SHUTTERING, R/F & CASTING OF SLAB | SQFT | 4556.5802 | 197.06 | 897919.69 | 0 | 0 | 0 | 0 | 197.06 | 0 | 4556.5802 | 191.16 | 871035.8724 | 0 | 0 | 0 | 4556.5802 | 4556.5802 | 897919.694 | 897919.6942
1581 | C BLDG.3RD SLAB | 0 | Tentative | Labour | (L)SHUTTERING, R/F & CASTING OF SLAB | SQFT | 3733.8642 | 197.06 | 735795.28 | 0 | 0 | 0 | 0 | 197.06 | 0 | 3733.8642 | 191.16 | 713765.4804 | 0 | 0 | 0 | 3733.8642 | 3733.8642 | 735795.279 | 735795.2793
1582 | C BLDG.4TH SLAB | 0 | Tentative | Labour | (L)SHUTTERING, R/F & CASTING OF SLAB | SQFT | 3953.5062 | 197.06 | 779077.93 | 0 | 0 | 0 | 0 | 197.06 | 0 | 3953.5062 | 191.16 | 755752.2444 | 0 | 0 | 0 | 3953.5062 | 3953.5062 | 779077.932 | 779077.9318
1583 | C BLDG.5TH SLAB | 0 | Tentative | Labour | (L)SHUTTERING, R/F & CASTING OF SLAB | SQFT | 3733.8642 | 197.06 | 735795.28 | 0 | 0 | 0 | 0 | 197.06 | 0 | 3733.8642 | 191.16 | 713765.4804 | 0 | 0 | 0 | 3733.8642 | 3733.8642 | 735795.279 | 735795.2793
1584 | C BLDG.6TH SLAB | 0 | Tentative | Labour | (L)SHUTTERING, R/F & CASTING OF SLAB | SQFT | 4578.9198 | 197.06 | 902321.94 | 0 | 0 | 0 | 0 | 197.06 | 0 | 4578.9198 | 191.16 | 875306.3076 | 0 | 0 | 0 | 4578.9198 | 4578.9198 | 902321.936 | 902321.9358
1585 | C BLDG.7TH SLAB | 0 | Tentative | Labour | (L)SHUTTERING, R/F & CASTING OF SLAB | SQFT | 4578.9198 | 197.06 | 902321.94 | 0 | 0 | 0 | 0 | 197.06 | 0 | 4578.9198 | 191.16 | 875306.3076 | 0 | 0 | 0 | 4578.9198 | 4578.9198 | 902321.936 | 902321.9358
1586 | C BLDG.8TH SLAB | 0 | Tentative | Labour | (L)SHUTTERING, R/F & CASTING OF SLAB | SQFT | 4653.3704 | 197.06 | 916993.17 | 0 | 0 | 0 | 0 | 197.06 | 0 | 4653.3704 | 191.16 | 889538.2848 | 0 | 0 | 0 | 4653.3704 | 4653.3704 | 916993.171 | 916993.171
1587 | C BLDG.9TH SLAB | 0 | Tentative | Labour | (L)SHUTTERING, R/F & CASTING OF SLAB | SQFT | 4653.3704 | 197.06 | 916993.17 | 0 | 0 | 0 | 0 | 197.06 | 0 | 4653.3704 | 191.16 | 889538.2848 | 0 | 0 | 0 | 4653.3704 | 4653.3704 | 916993.171 | 916993.171
1588 | C BLDG.10TH SLAB | 0 | Tentative | Labour | (L)SHUTTERING, R/F & CASTING OF SLAB | SQFT | 4653.3704 | 197.06 | 916993.17 | 0 | 0 | 0 | 0 | 197.06 | 0 | 4653.3704 | 191.16 | 889538.2848 | 0 | 0 | 0 | 4653.3704 | 4653.3704 | 916993.171 | 916993.171
1589 | C BLDG.11TH SLAB | 0 | Tentative | Labour | (L)SHUTTERING, R/F & CASTING OF SLAB | SQFT | 4653.3704 | 197.06 | 916993.17 | 0 | 0 | 0 | 0 | 197.06 | 0 | 4653.3704 | 191.16 | 889538.2848 | 0 | 0 | 0 | 4653.3704 | 4653.3704 | 916993.171 | 916993.171
1590 | C BLDG.12TH SLAB | 0 | Tentative | Labour | (L)SHUTTERING, R/F & CASTING OF SLAB | SQFT | 4765.0556 | 197.06 | 939001.86 | 0 | 0 | 0 | 0 | 197.06 | 0 | 4765.0556 | 191.16 | 910888.0272 | 0 | 0 | 0 | 4765.0556 | 4765.0556 | 939001.857 | 939001.8565
1591 | C BLDG.13TH SLAB | 0 | Started | Labour | (L)SHUTTERING, R/F & CASTING OF SLAB | SQFT | 4802.2778 | 197.06 | 946336.86 | 0 | 0 | 0 | 0 | 197.06 | 0 | 4802.2778 | 191.16 | 918003.4236 | 4802.2778 | 191.16 | 918003.42 | 4802.2778 | 0 | 946336.863 | 28333.4433
1592 | C BLDG.14TH SLAB | 0 | Started | Labour | (L)SHUTTERING, R/F & CASTING OF SLAB | SQFT | 4765.0556 | 197.06 | 939001.86 | 0 | 0 | 0 | 0 | 197.06 | 0 | 4765.0556 | 191.16 | 910888.0272 | 3435.8026 | 167.48 | 575428.02 | 4765.0556 | 1329.253 | 939001.857 | 363573.8365
1593 | C BLDG.PF | 0 | Tentative | Labour | (L)AFTER COMP. OF 6TH SLAB | SQFT | 352.679 | 197.06 | 69498.92 | 0 | 0 | 0 | 0 | 197.06 | 0 | 352.679 | 191.16 | 67418.118 | 0 | 0 | 0 | 352.679 | 352.679 | 69498.924 | 69498.9237
1594 | C BLDG.PF | 0 | Tentative | Labour | (L)AFTER COMP. OF RCC WORK | SQFT | 470.2346 | 197.06 | 92664.43 | 0 | 0 | 0 | 0 | 197.06 | 0 | 470.2346 | 191.16 | 89890.0452 | 0 | 0 | 0 | 470.2346 | 470.2346 | 92664.43 | 92664.4303
1595 | C BLDG.RETENTION | 0 | Started | Labour | (L)RETENTION-RCC WORK | SQFT | 2078.8457 | 197.06 | 409657.33 | 0 | 0 | 0 | 0 | 197.06 | 0 | 2078.8457 | 191.16 | 397392.1434 | 2078.8457 | 191.16 | 397392.14 | 2078.8457 | 0 | 409657.334 | 12265.1936
1596 | C BLDG. PLINTH COMP. | 0 | Tentative | Labour | (L)Plinth Beam, Soling, PCC | SQFT | 1616.4383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1616.4383 | 162 | 261863.0046 | 0 | 0 | 0 | 1616.4383 | 1616.4383 | 0 | 0
1597 | C BLDG .1ST SLAB | 0 | Tentative | Labour | (L)Hacking & Deshuttering | SQFT | 1438.9259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1438.9259 | 162 | 233105.9958 | 0 | 0 | 0 | 1438.9259 | 1438.9259 | 0 | 0
1598 | C BLDG. 2ND SLAB | 0 | Tentative | Labour | (L)Hacking & Deshuttering | SQFT | 1438.9259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1438.9259 | 162 | 233105.9958 | 0 | 0 | 0 | 1438.9259 | 1438.9259 | 0 | 0
1599 | C BLDG. 3RD SLAB | 0 | Tentative | Labour | (L)Hacking & Deshuttering | SQFT | 890.1173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 890.1173 | 162 | 144199.0026 | 0 | 0 | 0 | 890.1173 | 890.1173 | 0 | 0
1600 | C BLDG. 4TH SLAB | 0 | Tentative | Labour | (L)Hacking & Deshuttering | SQFT | 670.4753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 670.4753 | 162 | 108616.9986 | 0 | 0 | 0 | 670.4753 | 670.4753 | 0 | 0
1601 | C BLDG. 5TH SLAB | 0 | Tentative | Labour | (L)Hacking & Deshuttering | SQFT | 890.1173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 890.1173 | 162 | 144199.0026 | 0 | 0 | 0 | 890.1173 | 890.1173 | 0 | 0
1602 | C BLDG. 6TH SLAB | 0 | Tentative | Labour | (L)Hacking & Deshuttering | SQFT | 240.9938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240.9938 | 162 | 39040.9956 | 0 | 0 | 0 | 240.9938 | 240.9938 | 0 | 0
1603 | C BLDG. 7TH SLAB | 0 | Tentative | Labour | (L)Hacking & Deshuttering | SQFT | 240.9938 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240.9938 | 162 | 39040.9956 | 0 | 0 | 0 | 240.9938 | 240.9938 | 0 | 0
1604 | C BLDG. 8TH SLAB | 0 | Tentative | Labour | (L)Hacking & Deshuttering | SQFT | 244.9136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244.9136 | 162 | 39676.0032 | 0 | 0 | 0 | 244.9136 | 244.9136 | 0 | 0
1605 | C BLDG. 9TH SLAB | 0 | Tentative | Labour | (L)Hacking & Deshuttering | SQFT | 244.9136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244.9136 | 162 | 39676.0032 | 0 | 0 | 0 | 244.9136 | 244.9136 | 0 | 0
1606 | C BLDG. 10TH SLAB | 0 | Tentative | Labour | (L)Hacking & Deshuttering | SQFT | 244.9136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244.9136 | 162 | 39676.0032 | 0 | 0 | 0 | 244.9136 | 244.9136 | 0 | 0
1607 | C BLDG. 11TH SLAB | 0 | Tentative | Labour | (L)Hacking & Deshuttering | SQFT | 244.9136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 244.9136 | 162 | 39676.0032 | 0 | 0 | 0 | 244.9136 | 244.9136 | 0 | 0
1608 | C BLDG. 12TH SLAB | 0 | Tentative | Labour | (L)Hacking & Deshuttering | SQFT | 250.7901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250.7901 | 162 | 40627.9962 | 0 | 0 | 0 | 250.7901 | 250.7901 | 0 | 0
1609 | C BLDG. 13TH SLAB | 0 | Tentative | Labour | (L)Hacking & Deshuttering | SQFT | 252.7531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 252.7531 | 162 | 40946.0022 | 0 | 0 | 0 | 252.7531 | 252.7531 | 0 | 0
1610 | C BLDG. 14TH SLAB | 0 | Tentative | Labour | (L)Hacking & Deshuttering | SQFT | 250.7901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250.7901 | 162 | 40627.9962 | 0 | 0 | 0 | 250.7901 | 250.7901 | 0 | 0
1611 | C BLDG LMR & OHWT | 0 | Started | Labour | (L)Hacking & Deshuttering | SQFT | 66.6173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66.6173 | 162 | 10792.0026 | 0 | 0 | 0 | 66.6173 | 66.6173 | 0 | 0
1612 | C BLDG LMR & OHWT | 0 | Started | Labour | (L)LMR & OHWT COMPLETION | SQFT | 1265.7154 | 197.06 | 249421.88 | 0 | 0 | 0 | 0 | 197.06 | 0 | 1265.7154 | 162 | 205045.8948 | 97.4814 | 162 | 15791.99 | 1265.7154 | 1168.234 | 249421.877 | 233629.8867
1613 | C BLDG. MISC. WORK | 0 | Started | Labour | (L)ST-CASE PARDI,LINTEL & LOFT | SQFT | 783.7284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 783.7284 | 162 | 126964.0008 | 154.321 | 162 | 25000 | 783.7284 | 629.4074 | 0 | -25000
1614 | C BLDG PF | 0 | Tentative | Labour | (L)AFTER COMP.OF 6MONTH OF WORK | SQFT | 352.679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 352.679 | 162 | 57133.998 | 0 | 0 | 0 | 352.679 | 352.679 | 0 | 0
1615 | C BLDG CLEANING | 0 | Tentative | Labour | (L)UPTO 7TH & UPTO TOP TERR. | SQFT | 623.6543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 623.6543 | 162 | 101031.9966 | 0 | 0 | 0 | 623.6543 | 623.6543 | 0 | 0
1616 | C BLDG RETENTION | 0 | Started | Labour | (L)Retention Amount | SQFT | 2078.8457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2078.8457 | 162 | 336773.0034 | 2078.8457 | 162 | 336773 | 2078.8457 | 0 | 0 | -336773
1617 | C BLDG H FRAME FOR RCC: REMOVAL & ERECTION WORK | 0 | Started | Labour | (L)H FRAME ERECTION | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 13000 | 13000 | 0 | 0 | 0 | 1 | 1 | 0 | 0
1618 | C BLDG H FRAME FOR RCC: REMOVAL & ERECTION WORK | 0 | Started | Labour | (L)H FRAME REMOVAL | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 7000 | 7000 | 0 | 0 | 0 | 1 | 1 | 0 | 0
1619 | C BLDG MACHINERY WORK - RMC CONCRERE PUMP (OHWT) | 0 | Started | Labour | (L)RMC Concrete Pump Fixing & Operating | DAY | 4 | 15000 | 60000 | 0 | 0 | 0 | 0 | 15000 | 0 | 4 | 15000 | 60000 | 1 | 15000 | 15000 | 4 | 3 | 60000 | 45000
1620 | C BLDG RCC-OHWT CASTING, SET CONCRETE BREAKING & CLEANING WO | 0 | Started | Labour | (L)Hand Breaker With Oprator | DAY | 2 | 1200 | 2400 | 0 | 0 | 0 | 0 | 1200 | 0 | 2 | 1200 | 2400 | 2 | 1200 | 2400 | 2 | 0 | 2400 | 0
1621 | C BLDG RCC-OHWT CASTING, SET CONCRETE BREAKING & CLEANING WO | 0 | Started | Labour | (L)MC | NOS | 2 | 450 | 900 | 0 | 0 | 0 | 0 | 450 | 0 | 2 | 700 | 1400 | 2 | 700 | 1400 | 2 | 0 | 900 | -500
1622 | C BLDG RCC-OHWT CASTING, SET CONCRETE BREAKING & CLEANING WO | 0 | Started | Labour | (L)MC-LABOUR | NOS | 5 | 475 | 2375 | 0 | 0 | 0 | 0 | 475 | 0 | 5 | 850 | 4250 | 5 | 850 | 4250 | 5 | 0 | 2375 | -1875
1623 | C BLDG RCC-OHWT CASTING, SET CONCRETE BREAKING & CLEANING WO | 0 | Started | Labour | (L)SKILLED (MASON) | NOS | 1 | 1200 | 1200 | 0 | 0 | 0 | 0 | 1200 | 0 | 1 | 1300 | 1300 | 1 | 1300 | 1300 | 1 | 0 | 1200 | -100
1624 | C BLDG RCC WORK - MS.H FRAME PROVIDED ON RENT | 0 | Started | Labour | (L)MS. CROSS BRACING-2.7 MTR | NOS | 1500 | 2.95 | 4425 | 0 | 0 | 0 | 0 | 2.95 | 0 | 1500 | 2.95 | 4425 | 1500 | 2.95 | 4425 | 1500 | 0 | 4425 | 0
1625 | C BLDG RCC WORK - MS.H FRAME PROVIDED ON RENT | 0 | Started | Labour | (L)MS. H FRAME - 2 X 2 MTR | NOS | 1500 | 6.88 | 10320 | 0 | 0 | 0 | 0 | 6.88 | 0 | 1500 | 6.88 | 10325.12 | 1500 | 6.88 | 10325.12 | 1500 | 0 | 10320 | -5.12
1626 | C BLDG STEEL & CONCRETE TESTING (LAB) INDENT-708 | 0 | Started | Labour | (L)10MM STEEL TESTING-LAB. | NOS | 45 | 531 | 23895 | 0 | 0 | 0 | 0 | 531 | 0 | 45 | 531 | 23895 | 3 | 531 | 1593 | 45 | 42 | 23895 | 22302
1627 | C BLDG STEEL & CONCRETE TESTING (LAB) INDENT-708 | 0 | Started | Labour | (L)12MM STEEL TESTING-LAB. | NOS | 45 | 531 | 23895 | 0 | 0 | 0 | 0 | 531 | 0 | 45 | 531 | 23895 | 3 | 531 | 1593 | 45 | 42 | 23895 | 22302
1628 | C BLDG STEEL & CONCRETE TESTING (LAB) INDENT-708 | 0 | Started | Labour | (L)16MM STEEL TESTING-LAB. | NOS | 45 | 649 | 29205 | 0 | 0 | 0 | 0 | 649 | 0 | 45 | 649 | 29205 | 3 | 649 | 1947 | 45 | 42 | 29205 | 27258
1629 | C BLDG STEEL & CONCRETE TESTING (LAB) INDENT-708 | 0 | Started | Labour | (L)20MM STEEL TESTING-LAB. | NOS | 45 | 649 | 29205 | 0 | 0 | 0 | 0 | 649 | 0 | 45 | 649 | 29205 | 3 | 649 | 1947 | 45 | 42 | 29205 | 27258
1630 | C BLDG STEEL & CONCRETE TESTING (LAB) INDENT-708 | 0 | Started | Labour | (L)25MM STEEL TESTING-LAB. | NOS | 45 | 649 | 29205 | 0 | 0 | 0 | 0 | 649 | 0 | 45 | 649 | 29205 | 3 | 649 | 1947 | 45 | 42 | 29205 | 27258
1631 | C BLDG STEEL & CONCRETE TESTING (LAB) INDENT-708 | 0 | Started | Labour | (L)32MM STEEL TESTING-LAB. | NOS | 45 | 826 | 37170 | 0 | 0 | 0 | 0 | 826 | 0 | 45 | 826 | 37170 | 0 | 0 | 0 | 45 | 45 | 37170 | 37170
1632 | C BLDG STEEL & CONCRETE TESTING (LAB) INDENT-708 | 0 | Started | Labour | (L)8MM STEEL TESTING-LAB. | NOS | 45 | 531 | 23895 | 0 | 0 | 0 | 0 | 531 | 0 | 45 | 531 | 23895 | 3 | 531 | 1593 | 45 | 42 | 23895 | 22302
1633 | BLOCK WORK-ALL FLOOR BLOCK WORK 125MM | 10 | Started | Material | (M)AAC Block 625 x 200 x 125mm | NOS | 69696 | 0 | 0 | 0 | 0 | 0 | 6970 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62726 | 69696 | 0 | 0 | Building
1634 | BLOCK WORK-ALL FLOOR BLOCK WORK 125MM | 10 | Started | Material | (M)BLOCK ADHESIEVE | 40 KG/BAG | 950 | 400 | 380000 | 0 | 0 | 0 | 95 | 400 | 38000 | 0 | 0 | 0 | 0 | 0 | 0 | 855 | 950 | 342000 | 380000 | Building
1635 | BLOCK WORK-ALL FLOOR BLOCK WORK 230MM | 10 | Started | Material | (M)AAC Block 625 x 200 x 230mm | NOS | 5356.5204 | 0 | 0 | 0 | 0 | 0 | 536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4820.5204 | 5356.5204 | 0 | 0 | Building
1636 | BLOCK WORK-ALL FLOOR BLOCK WORK 230MM | 10 | Started | Material | (M)BLOCK ADHESIEVE | 40 KG/BAG | 142 | 400 | 56800 | 0 | 0 | 0 | 14 | 400 | 5600 | 0 | 0 | 0 | 0 | 0 | 0 | 128 | 142 | 51200 | 56800 | Building
1637 | DPC & PATALI M15-ALL FLOOR | 0 | Started | Material | (M)CEMENT PPC 50KG | BAG | 882.0036 | 320 | 282241.15 | 0 | 0 | 0 | 0 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 882.0036 | 882.0036 | 282241.152 | 282241.152 | Building
1638 | DPC & PATALI M15-ALL FLOOR | 0 | Started | Material | (M)Crush Sand | BRASS | 32.3238 | 3675 | 118789.97 | 0 | 0 | 0 | 0 | 3675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32.3238 | 32.3238 | 118789.965 | 118789.965 | Building
1639 | DPC & PATALI M15-ALL FLOOR | 0 | Started | Material | (M)Metal No.III 20MM | BRASS | 40.9642 | 3045 | 124735.99 | 0 | 0 | 0 | 0 | 3045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40.9642 | 40.9642 | 124735.989 | 124735.989 | Building
1640 | INDENT-560/C BLDG/INT.PLASTER 1ST TO 12T FLOOR | 10 | Started | Material | (M)Artificial Sand | BRASS | 70 | 5880 | 411600 | 70 | 5880 | 411600 | 7 | 5880 | 41160 | 70 | 6222.84 | 435598.8 | 0 | 0 | 0 | 63 | 70 | 370440 | 411600 | Building
1641 | INDENT-560/C BLDG/INT.PLASTER 1ST TO 12T FLOOR | 10 | Started | Material | (M)CEMENT PPC 50KG | BAG | 1194 | 320 | 382080 | 1194 | 320 | 382080 | 119 | 320 | 38080 | 0 | 0 | 0 | 0 | 0 | 0 | 1075 | 1194 | 344000 | 382080 | Building
1642 | INDENT-560/C BLDG/INT.PLASTER 1ST TO 12T FLOOR | 10 | Started | Material | (M)CHIKAN MESH-6'' (20Mtr/Bundle) | BUNDLE | 139 | 153.4 | 21322.6 | 139 | 153.4 | 21322.6 | 14 | 153.4 | 2147.6 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 139 | 19175 | 21322.6 | Building
1643 | INDENT-560/C BLDG/INT.PLASTER 1ST TO 12T FLOOR | 10 | Started | Material | (M)Nails 1 1/2" | KG | 100 | 100 | 10000 | 100 | 100 | 10000 | 10 | 100 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 100 | 9000 | 10000 | Building
1644 | INDENT-560/C BLDG/INT.PLASTER 1ST TO 12T FLOOR | 10 | Started | Material | (M)PERMA PLASTO-O-PROOF CHEMICAL | LTR | 120 | 236 | 28320 | 120 | 236 | 28320 | 12 | 236 | 2832 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 120 | 25488 | 28320 | Building
1645 | INDENT-560/C BLDG/INT.PLASTER 1ST TO 12T FLOOR | 10 | Started | Material | (M)SANLA-BADAM CHHAP | 12-15 KG/BAG | 657 | 120 | 78840 | 657 | 120 | 78840 | 66 | 120 | 7920 | 657 | 137.36 | 90247.9595 | 0 | 0 | 0 | 591 | 657 | 70920 | 78840 | Building
1646 | INDENT-560/C BLDG/INT.PLASTER 1ST TO 12T FLOOR | 10 | Started | Material | (M)Wishor | KG | 50 | 118 | 5900 | 50 | 118 | 5900 | 5 | 118 | 590 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 50 | 5310 | 5900 | Building
1647 | C BLDG PLASTER COVERING SHEET | 0 | Started | Material | (M)Tarpolin (Tadpatri) | NOS | 16 | 2596 | 41536 | 16 | 2596 | 41536 | 0 | 2596 | 0 | 8 | 2065 | 16520 | 0 | 0 | 0 | 16 | 16 | 41536 | 41536
1648 | INDENT-808/C BLDG EXTERNAL PLASTER | 0 | Started | Material | (M)Artificial Sand | BRASS | 188 | 5880 | 1105440 | 188 | 5880 | 1105440 | 0 | 5880 | 0 | 188 | 6300 | 1184400 | 0 | 0 | 0 | 188 | 188 | 1105440 | 1105440
1649 | INDENT-808/C BLDG EXTERNAL PLASTER | 0 | Started | Material | (M)CEMENT PPC 50KG | BAG | 3885 | 320 | 1243200 | 3885 | 320 | 1243200 | 0 | 320 | 0 | 2000 | 299.25 | 598504.85 | 0 | 0 | 0 | 3885 | 3885 | 1243200 | 1243200
1650 | INDENT-808/C BLDG EXTERNAL PLASTER | 0 | Started | Material | (M)CHIKAN MESH-6'' (20Mtr/Bundle) | BUNDLE | 135 | 153.4 | 20709 | 135 | 153.4 | 20709 | 0 | 153.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 135 | 20709 | 20709
1651 | INDENT-808/C BLDG EXTERNAL PLASTER | 0 | Started | Material | (M)MASTERBOND HACKAID (20 Ltr/Can) | LTR | 120 | 4484 | 538080 | 120 | 4484 | 538080 | 0 | 4484 | 0 | 120 | 223.61 | 26833.2 | 0 | 0 | 0 | 120 | 120 | 538080 | 538080
1652 | INDENT-808/C BLDG EXTERNAL PLASTER | 0 | Started | Material | (M)Nails 1 1/2" | KG | 50 | 100 | 5000 | 50 | 100 | 5000 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 5000 | 5000
1653 | INDENT-808/C BLDG EXTERNAL PLASTER | 0 | Started | Material | (M)PERMA PLASTO-O-PROOF CHEMICAL | LTR | 390 | 236 | 92040 | 390 | 236 | 92040 | 0 | 236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 390 | 390 | 92040 | 92040
1654 | INDENT-808/C BLDG EXTERNAL PLASTER | 0 | Started | Material | (M)SANLA-BADAM CHHAP | 12-15 KG/BAG | 74 | 120 | 8880 | 74 | 120 | 8880 | 0 | 120 | 0 | 43 | 140.06 | 6022.5155 | 0 | 0 | 0 | 74 | 74 | 8880 | 8880
1655 | INDENT-808/C BLDG EXTERNAL PLASTER | 0 | Started | Material | (M)Wishor | KG | 25 | 118 | 2950 | 25 | 118 | 2950 | 0 | 118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 25 | 2950 | 2950
1656 | INDENT-557/C BLDG/BLOCK WORK/7TH TO TERR | 10 | Started | Material | (M)AAC Block-125MM | CUM | 488 | 4200 | 2049600 | 488 | 4200 | 2049600 | 49 | 4200 | 205800 | 488 | 4156.49 | 2028369.2698 | 0 | 0 | 0 | 439 | 488 | 1843800 | 2049600
1657 | INDENT-557/C BLDG/BLOCK WORK/7TH TO TERR | 10 | Started | Material | (M)AAC Block-230MM | CUM | 89 | 4200 | 373800 | 89 | 4200 | 373800 | 9 | 4200 | 37800 | 89 | 4091.46 | 364139.8873 | 0 | 0 | 0 | 80 | 89 | 336000 | 373800
1658 | INDENT-557/C BLDG/BLOCK WORK/7TH TO TERR | 10 | Started | Material | (M)BLOCK ADHESIEVE | 40 KG/BAG | 528 | 400 | 211200 | 528 | 400 | 211200 | 53 | 400 | 21200 | 528 | 350 | 184799.8944 | 0 | 0 | 0 | 475 | 528 | 190000 | 211200
1659 | INDENT-557/C BLDG/BLOCK WORK/7TH TO TERR | 10 | Started | Material | (M)CEMENT PPC 50KG | BAG | 484 | 320 | 154880 | 484 | 320 | 154880 | 48 | 320 | 15360 | 484 | 300.01 | 145203.0976 | 0 | 0 | 0 | 436 | 484 | 139520 | 154880
1660 | INDENT-557/C BLDG/BLOCK WORK/7TH TO TERR | 10 | Started | Material | (M)Crush Sand | BRASS | 15.2 | 3675 | 55860 | 15.2 | 3675 | 55860 | 2 | 3675 | 7350 | 15.2 | 3360 | 51072 | 0 | 0 | 0 | 13.2 | 15.2 | 48510 | 55860
1661 | INDENT-557/C BLDG/BLOCK WORK/7TH TO TERR | 10 | Started | Material | (M)Metal No.III 20MM | BRASS | 19.1 | 3045 | 58159.5 | 19.1 | 3045 | 58159.5 | 2 | 3045 | 6090 | 0 | 0 | 0 | 0 | 0 | 0 | 17.1 | 19.1 | 52069.5 | 58159.5
1662 | INDENT-351/C BLDG/BLOCK WORK/1ST TO 6TH FLOOR | 10 | Started | Material | (M)AAC Block-125MM | CUM | 488 | 4200 | 2049600 | 451 | 4200 | 1894200 | 49 | 4200 | 205800 | 21.98 | 3900 | 85721.9363 | 0 | 0 | 0 | 439 | 488 | 1843800 | 2049600
1663 | INDENT-351/C BLDG/BLOCK WORK/1ST TO 6TH FLOOR | 10 | Started | Material | (M)AAC Block-230MM | CUM | 89 | 4200 | 373800 | 62 | 4200 | 260400 | 9 | 4200 | 37800 | 62 | 4149.58 | 257273.9583 | 0 | 0 | 0 | 80 | 89 | 336000 | 373800
1664 | INDENT-351/C BLDG/BLOCK WORK/1ST TO 6TH FLOOR | 10 | Started | Material | (M)BLOCK ADHESIEVE | 40 KG/BAG | 528 | 400 | 211200 | 456 | 400 | 182400 | 53 | 400 | 21200 | 0 | 0 | 0 | 0 | 0 | 0 | 475 | 528 | 190000 | 211200
1665 | INDENT-351/C BLDG/BLOCK WORK/1ST TO 6TH FLOOR | 10 | Started | Material | (M)CEMENT PPC 50KG | BAG | 484 | 320 | 154880 | 365 | 320 | 116800 | 48 | 320 | 15360 | 16 | 300.01 | 4800.1008 | 0 | 0 | 0 | 436 | 484 | 139520 | 154880
1666 | INDENT-351/C BLDG/BLOCK WORK/1ST TO 6TH FLOOR | 10 | Started | Material | (M)Crush Sand | BRASS | 15.2 | 3675 | 55860 | 13.5 | 3675 | 49612.5 | 2 | 3675 | 7350 | 0 | 0 | 0 | 0 | 0 | 0 | 13.2 | 15.2 | 48510 | 55860
1667 | INDENT-351/C BLDG/BLOCK WORK/1ST TO 6TH FLOOR | 10 | Started | Material | (M)Metal No.III 20MM | BRASS | 19.1 | 3045 | 58159.5 | 17 | 3045 | 51765 | 2 | 3045 | 6090 | 8.85 | 3045 | 26948.2527 | 0 | 0 | 0 | 17.1 | 19.1 | 52069.5 | 58159.5
1668 | a. C BLDG BBM-1ST FLOOR | 0 | Tentative | Labour | (L)BBM WORK | SQFT | 1489.5132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1489.5132 | 1489.5132 | 0 | 0
1669 | b. C BLDG BBM-2ND & 3RD FLOOR | 0 | Tentative | Labour | (L)BBM WORK | SQFT | 3085.4211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3085.4211 | 3085.4211 | 0 | 0
1670 | c. C BLDG BBM-4TH,5TH & 6TH FLOOR | 0 | Tentative | Labour | (L)BBM WORK | SQFT | 4787.7237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4787.7237 | 4787.7237 | 0 | 0
1671 | d. C BLDG BBM-7TH FLOOR | 0 | Tentative | Labour | (L)BBM WORK | SQFT | 1649.1053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1649.1053 | 1649.1053 | 0 | 0
1672 | e. C BLDG BBM-8TH & 9TH FLOOR | 0 | Tentative | Labour | (L)BBM WORK | SQFT | 3298.2105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3298.2105 | 3298.2105 | 0 | 0
1673 | f. C BLDG BBM-10TH & 11TH FLOOR | 0 | Tentative | Labour | (L)BBM WORK | SQFT | 3404.6053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3404.6053 | 3404.6053 | 0 | 0
1674 | g. C BLDG BBM-12TH FLOOR | 0 | Tentative | Labour | (L)BBM WORK | SQFT | 1755.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1755.5 | 1755.5 | 0 | 0
1675 | h. C BLDG BBM-TOP TERR. & ABOVE OHWT | 0 | Tentative | Labour | (L)BBM WORK | SQFT | 851.1579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 851.1579 | 851.1579 | 0 | 0
1676 | i. C BLDG BBM-LIFT, ELEVATION PIN & MISS. | 0 | Tentative | Labour | (L)BBM WORK | SQFT | 957.5526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 957.5526 | 957.5526 | 0 | 0
1677 | j. C BLDG BBM-CLEANING | 0 | Tentative | Labour | (L)CLEANING WORK | SQFT | 121.9079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121.9079 | 121.9079 | 0 | 0
1678 | k. INT.PLASTER-1,2,3,4 & 5TH FLOOR | 0 | Tentative | Labour | (L)INTERNAL PLASTER- | SQFT | 4152.8289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4152.8289 | 4152.8289 | 0 | 0
1679 | l. INT.PLASTER-6,7,8,9 & 10TH FLOOR | 0 | Tentative | Labour | (L)INTERNAL PLASTER- | SQFT | 4530.3289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4530.3289 | 4530.3289 | 0 | 0
1680 | m .INT.PLASTER-11TH & 12TH FLOOR | 0 | Tentative | Labour | (L)INTERNAL PLASTER- | SQFT | 1887.6316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1887.6316 | 1887.6316 | 0 | 0
1681 | n. INT.PLASTER-PASSAGE-1ST TO 12TH | 0 | Tentative | Labour | (L)INTERNAL PLASTER- | SQFT | 2038.6579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2038.6579 | 2038.6579 | 0 | 0
1682 | o. INT.PLASTER-ST CASE 1ST TO 12TH | 0 | Tentative | Labour | (L)INTERNAL PLASTER- | SQFT | 1094.8158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1094.8158 | 1094.8158 | 0 | 0
1683 | p. INT.PLASTER-LIFT WITH SCAFFOLDING | 0 | Tentative | Labour | (L)INTERNAL PLASTER- | SQFT | 755.0526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 755.0526 | 755.0526 | 0 | 0
1684 | q. INT.PLASTER-MISS.JAMB & BUT FILL. | 0 | Tentative | Labour | (L)INTERNAL PLASTER- | SQFT | 641.7895 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 641.7895 | 641.7895 | 0 | 0
1685 | r. INT.PLASTER-CLEANING 1ST TO 12TH | 0 | Tentative | Labour | (L)CLEANING WORK | SQFT | 121.9079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121.9079 | 121.9079 | 0 | 0
1686 | s. Ext.Plaster-F1 to F6 upto 12th floor | 0 | Tentative | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 4968.2632 | 89.68 | 445553.84 | 0 | 0 | 0 | 0 | 89.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4968.2632 | 4968.2632 | 445553.844 | 445553.8438
1687 | t. Ext.Plaster-F7 to F11 upto 12th floor | 0 | Tentative | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 4710.1579 | 89.68 | 422406.96 | 0 | 0 | 0 | 0 | 89.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4710.1579 | 4710.1579 | 422406.961 | 422406.9605
1688 | u. Ext.Plas-Toilet Duct F1,2,3 upto 12th | 0 | Tentative | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 1774.3816 | 89.68 | 159126.54 | 0 | 0 | 0 | 0 | 89.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1774.3816 | 1774.3816 | 159126.542 | 159126.5419
1689 | v. Ext.Plas-Toilet Duct F4,5,6 upto 12th | 0 | Tentative | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 1774.3816 | 89.68 | 159126.54 | 0 | 0 | 0 | 0 | 89.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1774.3816 | 1774.3816 | 159126.542 | 159126.5419
1690 | w. Ext.Plas-Toilet Duct F7,8,9 upto 12th | 0 | Tentative | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 1774.3816 | 89.68 | 159126.54 | 0 | 0 | 0 | 0 | 89.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1774.3816 | 1774.3816 | 159126.542 | 159126.5419
1691 | x. Ext.Plas-Toilet Duct F10 & F11 upto 12th | 0 | Tentative | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 1129.1447 | 89.68 | 101261.7 | 0 | 0 | 0 | 0 | 89.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1129.1447 | 1129.1447 | 101261.697 | 101261.6967
1692 | y. Ext.Plas-Main St.case uptu 12th | 0 | Tentative | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 1145.2895 | 89.68 | 102709.56 | 0 | 0 | 0 | 0 | 89.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1145.2895 | 1145.2895 | 102709.562 | 102709.5624
1693 | z. Ext.Plas-Fire St.case & lift uptu 12th | 0 | Tentative | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 1145.2895 | 89.68 | 102709.56 | 0 | 0 | 0 | 0 | 89.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1145.2895 | 1145.2895 | 102709.562 | 102709.5624
1694 | za. Ext.Plas-East side khata upto 12th | 0 | Tentative | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 3468.1184 | 89.68 | 311020.86 | 0 | 0 | 0 | 0 | 89.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3468.1184 | 3468.1184 | 311020.858 | 311020.8581
1695 | zb. Ext.Plas-West side khata upto 12th | 0 | Tentative | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 3468.1184 | 89.68 | 311020.86 | 0 | 0 | 0 | 0 | 89.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3468.1184 | 3468.1184 | 311020.858 | 311020.8581
1696 | zc. Ext.Plas-East side duct upto 12th | 0 | Tentative | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 1693.7237 | 89.68 | 151893.14 | 0 | 0 | 0 | 0 | 89.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1693.7237 | 1693.7237 | 151893.141 | 151893.1414
1697 | zd. Ext.Plas-West side duct upto 12th | 0 | Tentative | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 1693.7237 | 89.68 | 151893.14 | 0 | 0 | 0 | 0 | 89.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1693.7237 | 1693.7237 | 151893.141 | 151893.1414
1698 | ze. Ext.Plas-Electrical duct upto 12th | 0 | Tentative | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 322.6053 | 89.68 | 28931.24 | 0 | 0 | 0 | 0 | 89.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 322.6053 | 322.6053 | 28931.243 | 28931.2433
1699 | zf. Ext.Plas-Garbage & Fire duct upto 12th | 0 | Tentative | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 387.1316 | 89.68 | 34717.96 | 0 | 0 | 0 | 0 | 89.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 387.1316 | 387.1316 | 34717.962 | 34717.9619
1700 | zg. Ext.Plas-Parapet & OHWT | 0 | Tentative | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 1935.6842 | 89.68 | 173592.16 | 0 | 0 | 0 | 0 | 89.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1935.6842 | 1935.6842 | 173592.159 | 173592.1591
1701 | zh. Ext.Plas-Fire refuge area-1 & 2 | 0 | Tentative | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 387.1316 | 89.68 | 34717.96 | 0 | 0 | 0 | 0 | 89.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 387.1316 | 387.1316 | 34717.962 | 34717.9619
1702 | zi. Ext.Plas-Miss.work-50% & 100% | 0 | Tentative | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 483.9211 | 89.68 | 43398.04 | 0 | 0 | 0 | 0 | 89.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 483.9211 | 483.9211 | 43398.044 | 43398.0442
1703 | zj. Ext.Plas-Cleaning after plaster work | 0 | Tentative | Labour | (L)CLEANING WORK | SQFT | 122.2763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122.2763 | 122.2763 | 0 | 0
1704 | zk. PF Tappa | 0 | Tentative | Labour | (L)PF AMOUNT | SQFT | 549.1316 | 89.68 | 49246.12 | 0 | 0 | 0 | 0 | 89.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 549.1316 | 549.1316 | 49246.122 | 49246.1219
1705 | zl. RETENTION TAPPA | 0 | Tentative | Labour | (L)Retention Amount (BBM & PLASTER) | SQFT | 3660.8684 | 89.68 | 328306.68 | 0 | 0 | 0 | 0 | 89.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3660.8684 | 3660.8684 | 328306.678 | 328306.6781
1706 | C BLDG BBM-8TH & 9TH FLOOR | 0 | Started | Labour | (L)BBM WORK | SQFT | 3298.2105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3298.2105 | 89.68 | 295783.518 | 3298.2105 | 89.68 | 295783.52 | 3298.2105 | 0 | 0 | -295783.52
1707 | C BLDG BBM-ELEVATION PINS | 0 | Tentative | Labour | (L)BBM WORK | SQFT | 319.1842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 319.1842 | 89.68 | 28624.4392 | 0 | 0 | 0 | 319.1842 | 319.1842 | 0 | 0
1708 | C BLDG INT.PLASTER-DOOR JAMB UPTO 12TH | 0 | Tentative | Labour | (L)INTERNAL PLASTER- | SQFT | 188.7632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 188.7632 | 89.68 | 16928.2832 | 0 | 0 | 0 | 188.7632 | 188.7632 | 0 | 0
1709 | C BLGD Ext.Plaster-F1 to F6 upto 12th floor | 0 | Started | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 4968.2632 | 89.68 | 445553.84 | 0 | 0 | 0 | 0 | 89.68 | 0 | 4968.2632 | 89.68 | 445553.8432 | 1258.1974 | 89.68 | 112835.14 | 4968.2632 | 3710.0658 | 445553.844 | 332718.7038
1710 | C BLGD Ext.Plaster-F7 to F11 upto 12th floor | 0 | Started | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 4710.1579 | 89.68 | 422406.96 | 0 | 0 | 0 | 0 | 89.68 | 0 | 4710.1579 | 89.68 | 422406.9604 | 2419.6053 | 89.68 | 216990.2 | 4710.1579 | 2290.5526 | 422406.961 | 205416.7605
1711 | C BLGD Ext.Plas-Toilet Duct F1,2,3 upto 12th | 0 | Tentative | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 1774.3816 | 89.68 | 159126.54 | 0 | 0 | 0 | 0 | 89.68 | 0 | 1774.3816 | 89.68 | 159126.5416 | 0 | 0 | 0 | 1774.3816 | 1774.3816 | 159126.542 | 159126.5419
1712 | C BLGD Ext.Plas-Toilet Duct F4,5,6 upto 12th | 0 | Started | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 1774.3816 | 89.68 | 159126.54 | 0 | 0 | 0 | 0 | 89.68 | 0 | 1774.3816 | 89.68 | 159126.5416 | 967.8421 | 89.68 | 86796.08 | 1774.3816 | 806.5395 | 159126.542 | 72330.4619
1713 | C BLGD Ext.Plas-Toilet Duct F7,8,9 upto 12th | 0 | Started | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 1774.3816 | 89.68 | 159126.54 | 0 | 0 | 0 | 0 | 89.68 | 0 | 1774.3816 | 89.68 | 159126.5416 | 967.8421 | 89.68 | 86796.08 | 1774.3816 | 806.5395 | 159126.542 | 72330.4619
1714 | C BLGD Ext.Plas-Toilet Duct F10 & F11 upto 12th | 0 | Started | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 1129.1447 | 89.68 | 101261.7 | 0 | 0 | 0 | 0 | 89.68 | 0 | 1129.1447 | 89.68 | 101261.6972 | 645.2236 | 89.68 | 57863.65 | 1129.1447 | 483.9211 | 101261.697 | 43398.0467
1715 | C BLGD Ext.Plas-Main St.case uptu 12th | 0 | Started | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 1145.2895 | 89.68 | 102709.56 | 0 | 0 | 0 | 0 | 89.68 | 0 | 1145.2895 | 89.68 | 102709.562 | 0 | 0 | 0 | 1145.2895 | 1145.2895 | 102709.562 | 102709.5624
1716 | C BLGD Ext.Plas-Fire St.case & lift uptu 12th | 0 | Started | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 1145.2895 | 89.68 | 102709.56 | 0 | 0 | 0 | 0 | 89.68 | 0 | 1145.2895 | 89.68 | 102709.562 | 532.3158 | 89.68 | 47738.08 | 1145.2895 | 612.9737 | 102709.562 | 54971.4824
1717 | C BLGD Ext.Plas-East side khata upto 12th | 0 | Started | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 3468.1184 | 89.68 | 311020.86 | 0 | 0 | 0 | 0 | 89.68 | 0 | 3468.1184 | 89.68 | 311020.8584 | 3468.1184 | 89.68 | 311020.86 | 3468.1184 | 0 | 311020.858 | -0.0019
1718 | C BLGD Ext.Plas-West side khata upto 12th | 0 | Started | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 3468.1184 | 89.68 | 311020.86 | 0 | 0 | 0 | 0 | 89.68 | 0 | 3468.1184 | 89.68 | 311020.8584 | 1855.0394 | 89.68 | 166359.93 | 3468.1184 | 1613.079 | 311020.858 | 144660.9281
1719 | C BLGD Ext.Plas-East side duct upto 12th | 0 | Started | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 1693.7237 | 89.68 | 151893.14 | 0 | 0 | 0 | 0 | 89.68 | 0 | 1693.7237 | 89.68 | 151893.1412 | 1693.7237 | 89.68 | 151893.14 | 1693.7237 | 0 | 151893.141 | 0.0014
1720 | C BLGD Ext.Plas-West side duct upto 12th | 0 | Started | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 1693.7237 | 89.68 | 151893.14 | 0 | 0 | 0 | 0 | 89.68 | 0 | 1693.7237 | 89.68 | 151893.1412 | 806.5395 | 89.68 | 72330.46 | 1693.7237 | 887.1842 | 151893.141 | 79562.6814
1721 | C BLGD Ext.Plas-Electrical duct upto 12th | 0 | Started | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 322.6053 | 89.68 | 28931.24 | 0 | 0 | 0 | 0 | 89.68 | 0 | 322.6053 | 89.68 | 28931.2428 | 0 | 0 | 0 | 322.6053 | 322.6053 | 28931.243 | 28931.2433
1722 | C BLGD Ext.Plas-Garbage & Fire duct upto 12th | 0 | Started | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 387.1316 | 89.68 | 34717.96 | 0 | 0 | 0 | 0 | 89.68 | 0 | 387.1316 | 89.68 | 34717.9616 | 387.1316 | 89.68 | 34717.96 | 387.1316 | 0 | 34717.962 | 0.0019
1723 | C BLGD Ext.Plas-Parapet & OHWT | 0 | Started | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 1935.6842 | 89.68 | 173592.16 | 0 | 0 | 0 | 0 | 89.68 | 0 | 1935.6842 | 89.68 | 173592.1592 | 0 | 0 | 0 | 1935.6842 | 1935.6842 | 173592.159 | 173592.1591
1724 | C BLGD Ext.Plas-Fire refuge area-1 & 2 | 0 | Started | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 387.1316 | 89.68 | 34717.96 | 0 | 0 | 0 | 0 | 89.68 | 0 | 387.1316 | 89.68 | 34717.9616 | 193.5658 | 89.68 | 17358.98 | 387.1316 | 193.5658 | 34717.962 | 17358.9819
1725 | C BLGD Ext.Plas-Miss.work-50% & 100% | 0 | Started | Labour | (L)EXTERNAL PLASTER WORK | SQFT | 483.921 | 89.68 | 43398.04 | 0 | 0 | 0 | 0 | 89.68 | 0 | 483.921 | 89.68 | 43398.036 | 0 | 0 | 0 | 483.921 | 483.921 | 43398.035 | 43398.0353
1726 | C BLGD Ext.Plas-Cleaning after plaster work | 0 | Tentative | Labour | (L)CLEANING WORK | SQFT | 122.2763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122.2763 | 89.68 | 10965.7388 | 0 | 0 | 0 | 122.2763 | 122.2763 | 0 | 0
1727 | C BLGD PF-1 | 0 | Tentative | Labour | (L)PF AMOUNT | SQFT | 420.5658 | 89.68 | 37716.34 | 0 | 0 | 0 | 0 | 89.68 | 0 | 420.5658 | 89.68 | 37716.3408 | 0 | 0 | 0 | 420.5658 | 420.5658 | 37716.341 | 37716.3409
1728 | C BLDG BBM-1ST FLOOR | 0 | Tentative | Labour | (L)BBM WORK | SQFT | 1489.5132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1489.5132 | 76 | 113203.0032 | 0 | 0 | 0 | 1489.5132 | 1489.5132 | 0 | 0
1729 | C BLDG BBM-2ND & 3RD FLOOR | 0 | Tentative | Labour | (L)BBM WORK | SQFT | 3085.421 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3085.421 | 76 | 234491.996 | 0 | 0 | 0 | 3085.421 | 3085.421 | 0 | 0
1730 | C BLDG BBM-4TH,5TH & 6TH FLOOR | 0 | Tentative | Labour | (L)BBM WORK | SQFT | 4787.7237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4787.7237 | 76 | 363867.0012 | 0 | 0 | 0 | 4787.7237 | 4787.7237 | 0 | 0
1731 | C BLDG BBM-7TH FLOOR | 0 | Tentative | Labour | (L)BBM WORK | SQFT | 1649.1053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1649.1053 | 76 | 125332.0028 | 0 | 0 | 0 | 1649.1053 | 1649.1053 | 0 | 0
1732 | C BLDG BBM-10TH & 11TH FLOOR | 0 | Started | Labour | (L)BBM WORK | SQFT | 3404.6053 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3404.6053 | 76 | 258750.0028 | 3404.6053 | 76 | 258750 | 3404.6053 | 0 | 0 | -258750
1733 | C BLDG BBM-12TH FLOOR | 0 | Started | Labour | (L)BBM WORK | SQFT | 1755.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1755.5 | 76 | 133418 | 1755.5 | 76 | 133418 | 1755.5 | 0 | 0 | -133418
1734 | C BLDG BBM-TOP TERR. & ABOVE OHWT | 0 | Started | Labour | (L)BBM WORK | SQFT | 851.1579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 851.1579 | 76 | 64688.0004 | 744.7632 | 76 | 56602 | 851.1579 | 106.3947 | 0 | -56602
1735 | C BLDG BBM-LIFT & MISS. BBM | 0 | Tentative | Labour | (L)BBM WORK | SQFT | 638.3684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 638.3684 | 76 | 48515.9984 | 0 | 0 | 0 | 638.3684 | 638.3684 | 0 | 0
1736 | C BLDG BBM-CLEANING | 0 | Tentative | Labour | (L)CLEANING WORK | SQFT | 121.9079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121.9079 | 76 | 9265.0004 | 0 | 0 | 0 | 121.9079 | 121.9079 | 0 | 0
1737 | C BLDG INT.PLASTER-1,2,3,4 & 5TH FLOOR | 0 | Tentative | Labour | (L)INTERNAL PLASTER- | SQFT | 4152.829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4152.829 | 76 | 315615.004 | 0 | 0 | 0 | 4152.829 | 4152.829 | 0 | 0
1738 | C BLDG INT.PLASTER-6,7,8,9 & 10TH FLOOR | 0 | Started | Labour | (L)INTERNAL PLASTER- | SQFT | 4530.329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4530.329 | 76 | 344305.004 | 3624.2628 | 76 | 275443.97 | 4530.329 | 906.0662 | 0 | -275443.97
1739 | C BLDG INT.PLASTER-11TH & 12TH FLOOR | 0 | Started | Labour | (L)INTERNAL PLASTER- | SQFT | 1887.6316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1887.6316 | 76 | 143460.0016 | 1887.6316 | 76 | 143460 | 1887.6316 | 0 | 0 | -143460
1740 | C BLDG INT.PLASTER-PASSAGE-1ST TO 12TH | 0 | Started | Labour | (L)INTERNAL PLASTER- | SQFT | 2038.6579 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2038.6579 | 76 | 154938.0004 | 2038.6579 | 76 | 154938 | 2038.6579 | 0 | 0 | -154938
1741 | C BLDG INT.PLASTER-ST CASE 1ST TO 12TH | 0 | Tentative | Labour | (L)INTERNAL PLASTER- | SQFT | 1094.8158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1094.8158 | 76 | 83206.0008 | 0 | 0 | 0 | 1094.8158 | 1094.8158 | 0 | 0
1742 | C BLDG INT.PLASTER-LIFT WITH SCAFFOLDING | 0 | Tentative | Labour | (L)INTERNAL PLASTER- | SQFT | 755.0526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 755.0526 | 76 | 57383.9976 | 0 | 0 | 0 | 755.0526 | 755.0526 | 0 | 0
1743 | C BLDG INT.PLASTER-MISS. & BUT FILLING | 0 | Tentative | Labour | (L)INTERNAL PLASTER- | SQFT | 453.0263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 453.0263 | 76 | 34429.9988 | 0 | 0 | 0 | 453.0263 | 453.0263 | 0 | 0
1744 | C BLDG INT.PLASTER-CLEANING 1ST TO 12TH | 0 | Tentative | Labour | (L)CLEANING WORK | SQFT | 121.9079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 121.9079 | 76 | 9265.0004 | 0 | 0 | 0 | 121.9079 | 121.9079 | 0 | 0
1745 | C BLGD PF-2 | 0 | Tentative | Labour | (L)PF AMOUNT | SQFT | 128.5658 | 89.68 | 11529.78 | 0 | 0 | 0 | 0 | 89.68 | 0 | 128.5658 | 76 | 9771.0008 | 0 | 0 | 0 | 128.5658 | 128.5658 | 11529.781 | 11529.7809
1746 | C BLGD RETENTION | 0 | Tentative | Labour | (L)Retention Amount (BBM & PLASTER) | SQFT | 3660.8684 | 89.68 | 328306.68 | 0 | 0 | 0 | 0 | 89.68 | 0 | 3660.8684 | 76 | 278225.9984 | 0 | 0 | 0 | 3660.8684 | 3660.8684 | 328306.678 | 328306.6781
1747 | 13TH SLAB & ABOVE COLUMN CONCRETE-M25 | 10 | Started | Material | (M)CEMENT OPC 43 | BAG | 1172.16 | 378.88 | 444107.98 | 0 | 0 | 0 | 117 | 378.88 | 44328.96 | 0 | 0 | 0 | 125 | 345 | 43125 | 1055.16 | 1047.16 | 399779.021 | 400982.9808
1748 | 13TH SLAB & ABOVE COLUMN CONCRETE-M25 | 10 | Started | Material | (M)Crush Sand | BRASS | 45.584 | 3675 | 167521.2 | 0 | 0 | 0 | 5 | 3675 | 18375 | 0 | 0 | 0 | 0 | 0 | 0 | 40.584 | 45.584 | 149146.2 | 167521.2
1749 | 13TH SLAB & ABOVE COLUMN CONCRETE-M25 | 10 | Started | Material | (M)Metal No.III 20MM | BRASS | 70.4924 | 3045 | 214649.36 | 0 | 0 | 0 | 7 | 3045 | 21315 | 0 | 0 | 0 | 0 | 0 | 0 | 63.4924 | 70.4924 | 193334.358 | 214649.358
1750 | 13TH SLAB & ABOVE COLUMN 8MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 8mm (Fe 500, 0.395 KGS/Rm) | KG | 7500 | 59 | 442500 | 0 | 0 | 0 | 750 | 59 | 44250 | 0 | 0 | 0 | 0 | 0 | 0 | 6750 | 7500 | 398250 | 442500
1751 | 13TH SLAB & ABOVE COLUMN 10MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 10mm (Fe 500, 0.617 KGS/Rm) | KG | 2000 | 59 | 118000 | 0 | 0 | 0 | 200 | 59 | 11800 | 0 | 0 | 0 | 651.552 | 59.36 | 38674.3 | 1800 | 1348.448 | 106200 | 79325.7
1752 | 13TH SLAB & ABOVE COLUMN 12MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 12mm (Fe 500, 0.888 KGS/Rm) | KG | 4000 | 59 | 236000 | 0 | 0 | 0 | 400 | 59 | 23600 | 0 | 0 | 0 | 0 | 0 | 0 | 3600 | 4000 | 212400 | 236000
1753 | 13TH SLAB & ABOVE COLUMN 16MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 16mm (Fe 500, 1.58 KGS/Rm) | KG | 2000 | 59 | 118000 | 0 | 0 | 0 | 200 | 59 | 11800 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 2000 | 106200 | 118000
1754 | 13TH SLAB & ABOVE COLUMN 20MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 20mm (Fe 500, 2.47 KGS/Rm) | KG | 3000 | 59 | 177000 | 0 | 0 | 0 | 300 | 59 | 17700 | 0 | 0 | 0 | 100 | 60.47 | 6047.35 | 2700 | 2900 | 159300 | 170952.65
1755 | 13TH SLAB & ABOVE COLUMN 25MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 25mm (Fe 500, 3.85 KGS/Rm) | KG | 5000 | 59 | 295000 | 0 | 0 | 0 | 500 | 59 | 29500 | 0 | 0 | 0 | 0 | 0 | 0 | 4500 | 5000 | 265500 | 295000
1756 | 13TH SLAB & ABOVE COLUMN BINDING WIRE | 10 | Started | Material | (M)MS Binding Wire 18G | KG | 350 | 50 | 17500 | 0 | 0 | 0 | 35 | 50 | 1750 | 0 | 0 | 0 | 166.2 | 80.24 | 13335.89 | 315 | 183.8 | 15750 | 4164.11
1757 | 13TH SLAB & ABOVE COLUMN PERMA BOND SBR | 10 | Started | Material | (M)PERMA BOND SBR | LITRE | 25 | 291.08 | 7277 | 0 | 0 | 0 | 3 | 291.08 | 873.24 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 25 | 6403.76 | 7277
1758 | RCC WORK-14TH SLAB & ABOVE COLUMN CONCRETE-M25 | 10 | Started | Material | (M)CEMENT OPC 43 | BAG | 1172.16 | 378.88 | 444107.98 | 1172.16 | 378.88 | 444107.98 | 117 | 378.88 | 44328.96 | 600.4 | 350.01 | 210143.2 | 995 | 346.73 | 345000 | 1055.16 | 177.16 | 399779.021 | 99107.9808
1759 | RCC WORK-14TH SLAB & ABOVE COLUMN CONCRETE-M25 | 10 | Started | Material | (M)Crush Sand | BRASS | 45.584 | 3675 | 167521.2 | 45.584 | 3675 | 167521.2 | 5 | 3675 | 18375 | 45.584 | 3675 | 167521.2 | 0 | 0 | 0 | 40.584 | 45.584 | 149146.2 | 167521.2
1760 | RCC WORK-14TH SLAB & ABOVE COLUMN CONCRETE-M25 | 10 | Started | Material | (M)Metal No.III 20MM | BRASS | 70.4924 | 3045 | 214649.36 | 70.4924 | 3045 | 214649.36 | 7 | 3045 | 21315 | 70.4924 | 3360 | 236854.461 | 0 | 0 | 0 | 63.4924 | 70.4924 | 193334.358 | 214649.358
1761 | RCC WORK-OHWT CONCRETE-M25 | 10 | Started | Material | (M)CEMENT OPC 43 | BAG | 399.6 | 378.88 | 151400.45 | 399.6 | 378.88 | 151400.45 | 40 | 378.88 | 15155.2 | 399.6 | 358 | 143056.8 | 0 | 0 | 0 | 359.6 | 399.6 | 136245.248 | 151400.448
1762 | RCC WORK-OHWT CONCRETE-M25 | 10 | Started | Material | (M)Crush Sand | BRASS | 9.288 | 3675 | 34133.4 | 9.288 | 3675 | 34133.4 | 1 | 3675 | 3675 | 9.288 | 3675 | 34133.4 | 0 | 0 | 0 | 8.288 | 9.288 | 30458.4 | 34133.4
1763 | RCC WORK-OHWT CONCRETE-M25 | 10 | Started | Material | (M)Metal No.III 20MM | BRASS | 13.932 | 3045 | 42422.94 | 13.932 | 3045 | 42422.94 | 1 | 3045 | 3045 | 13.932 | 3360 | 46811.52 | 0 | 0 | 0 | 12.932 | 13.932 | 39377.94 | 42422.94
1764 | RCC WORK-OHWT CONCRETE-M25 | 10 | Started | Material | (M)RMC M-25 | CUM | 80 | 4600 | 368000 | 80 | 4600 | 368000 | 8 | 4600 | 36800 | 80 | 5729.37 | 458349.9721 | 0 | 0 | 0 | 72 | 80 | 331200 | 368000
1765 | RCC WORK-14TH SLAB & ABOVE COLUMN & OHWT 8MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 8mm (Fe 500, 0.395 KGS/Rm) | KG | 8000 | 59 | 472000 | 8000 | 59 | 472000 | 800 | 59 | 47200 | 8000 | 61.95 | 495600 | 5157.34 | 62.36 | 321596.62 | 7200 | 2842.66 | 424800 | 150403.38
1766 | RCC WORK-14TH SLAB & ABOVE COLUMN & OHWT 12MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 12mm (Fe 500, 0.888 KGS/Rm) | KG | 3000 | 59 | 177000 | 3000 | 59 | 177000 | 300 | 59 | 17700 | 3000 | 60.18 | 180540 | 512 | 60.06 | 30749.29 | 2700 | 2488 | 159300 | 146250.71
1767 | RCC WORK-14TH SLAB & ABOVE COLUMN & OHWT 16MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 16mm (Fe 500, 1.58 KGS/Rm) | KG | 3000 | 59 | 177000 | 3000 | 59 | 177000 | 300 | 59 | 17700 | 3000 | 60.18 | 180540 | 1137.75 | 60.83 | 69209.22 | 2700 | 1862.25 | 159300 | 107790.78
1768 | RCC WORK-14TH SLAB & ABOVE COLUMN & OHWT 20MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 20mm (Fe 500, 2.47 KGS/Rm) | KG | 1500 | 59 | 88500 | 1500 | 59 | 88500 | 150 | 59 | 8850 | 1500 | 60.18 | 90270 | 1500 | 60.47 | 90710.25 | 1350 | 0 | 79650 | -2210.25
1769 | RCC WORK-14TH SLAB & ABOVE COLUMN & OHWT 25MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 25mm (Fe 500, 3.85 KGS/Rm) | KG | 5000 | 59 | 295000 | 5000 | 59 | 295000 | 500 | 59 | 29500 | 5000 | 60.18 | 300900 | 3935.5 | 58.91 | 231852.9 | 4500 | 1064.5 | 265500 | 63147.1
1770 | RCC WORK-14TH SLAB & ABOVE COLUMN & OHWT PERMA BOND SBR | 10 | Started | Material | (M)PERMA BOND SBR | LITRE | 25 | 291.08 | 7277 | 25 | 291.08 | 7277 | 3 | 291.08 | 873.24 | 25 | 212.01 | 5300.27 | 0 | 0 | 0 | 22 | 25 | 6403.76 | 7277
1771 | INDENT-931/C WING/WOODEN DOOR FRAME | 0 | Started | Material | (M)BEDROOM DOOR FRAME (Redmaranty Wood) - 0.9M X 2.25M | SET | 132 | 3550 | 468600 | 132 | 3550 | 468600 | 0 | 3550 | 0 | 132 | 4309.94 | 568912.08 | 0 | 0 | 0 | 132 | 132 | 468600 | 468600
1772 | INDENT-931/C WING/WOODEN DOOR FRAME | 0 | Started | Material | (M)MAIN DOOR FRAME (Redmaranty Wood) - 1.05M X 2.25M | SET | 132 | 4700 | 620400 | 132 | 4700 | 620400 | 0 | 4700 | 0 | 132 | 5706.12 | 753207.84 | 0 | 0 | 0 | 132 | 132 | 620400 | 620400
1773 | C BLDG WOODEN FRAME BACK SIDE COATING WORK | 0 | Tentative | Material | (M)BLACK JAPAN-LIQUID | LTR | 20 | 200 | 4000 | 20 | 200 | 4000 | 0 | 200 | 0 | 20 | 140 | 2800.002 | 0 | 0 | 0 | 20 | 20 | 4000 | 4000
1774 | C BLDG WOODEN FRAME BACK SIDE COATING WORK | 0 | Tentative | Material | (M)PAINT ROLLER 4'' (BRUSH) | NOS | 4 | 47.2 | 188.8 | 4 | 47.2 | 188.8 | 0 | 47.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 188.8 | 188.8
1775 | C BLDG WOODEN FRAME BACK SIDE COATING WORK | 0 | Tentative | Material | (M)THINNER-LIQUID | LTR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1776 | C BLDG WOODEN FRAME BACK SIDE COATING WORK | 0 | Tentative | Material | (M)Turpentine Oil | LTR | 10 | 148.68 | 1486.8 | 10 | 148.68 | 1486.8 | 0 | 148.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 1486.8 | 1486.8
1777 | WOODEN DOOR SHUTTER SAMPLE FLAT-102 (INDENT-903) | 10 | Started | Material | (M)BEDROOM DOOR-32MM THK | NOS | 1 | 5175 | 5175 | 1 | 5175 | 5175 | 0 | 5175 | 0 | 1 | 6106.5 | 6106.5 | 0 | 0 | 0 | 1 | 1 | 5175 | 5175
1778 | WOODEN DOOR SHUTTER SAMPLE FLAT-102 (INDENT-903) | 10 | Started | Material | (M)MAIN DOOR-35MM THK | NOS | 1 | 6130 | 6130 | 1 | 6130 | 6130 | 0 | 6130 | 0 | 1 | 7233.4 | 7233.4 | 0 | 0 | 0 | 1 | 1 | 6130 | 6130
1779 | WOODEN DOOR SHUTTER SAMPLE FLAT-102 (INDENT-903) | 10 | Started | Material | (M)TOILET DOOR-32MM THK | NOS | 1 | 7729 | 7729 | 1 | 7729 | 7729 | 0 | 7729 | 0 | 1 | 5746.6 | 5746.6 | 0 | 0 | 0 | 1 | 1 | 7729 | 7729
1780 | C WING LGF & UGF SHOP TOILET DOOR SHUTTER-447 & 451 | 0 | Tentative | Material | (M)TOILET DOOR-32MM THK | NOS | 33 | 7729 | 255057 | 33 | 7729 | 255057 | 0 | 7729 | 0 | 33 | 6018 | 198594 | 0 | 0 | 0 | 33 | 33 | 255057 | 255057
1781 | C BLDG MD,C-BED & TOILET DOOR SHUTTER-1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)BEDROOM DOOR-32MM THK | NOS | 129 | 5175 | 667575 | 129 | 5175 | 667575 | 0 | 5175 | 0 | 129 | 4661 | 601269 | 0 | 0 | 0 | 129 | 129 | 667575 | 667575
1782 | C BLDG MD,C-BED & TOILET DOOR SHUTTER-1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)MAIN DOOR-35MM THK | NOS | 129 | 6130 | 790770 | 129 | 6130 | 790770 | 0 | 6130 | 0 | 129 | 5369 | 692601 | 0 | 0 | 0 | 129 | 129 | 790770 | 790770
1783 | C BLDG MD,C-BED & TOILET DOOR SHUTTER-1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)TOILET DOOR-32MM THK | NOS | 129 | 7729 | 997041 | 129 | 7729 | 997041 | 0 | 7729 | 0 | 129 | 4248 | 547992 | 0 | 0 | 0 | 129 | 129 | 997041 | 997041
1784 | C BLDG C.BED DOOR SHUTTER-HARDWARE (130 FLATS) | 10 | Started | Material | (M)Cylinderical Lock with Key-Bedroom | NOS | 131 | 1888 | 247328 | 131 | 1888 | 247328 | 13 | 1888 | 24544 | 0 | 0 | 0 | 0 | 0 | 0 | 118 | 131 | 222784 | 247328
1785 | C BLDG C.BED DOOR SHUTTER-HARDWARE (130 FLATS) | 10 | Started | Material | (M)Magnetic Door Catcher-3'' | NOS | 131 | 59 | 7729 | 131 | 59 | 7729 | 13 | 59 | 767 | 0 | 0 | 0 | 0 | 0 | 0 | 118 | 131 | 6962 | 7729
1786 | C BLDG C.BED DOOR SHUTTER-HARDWARE (130 FLATS) | 10 | Started | Material | (M)Screw 8 x 25mm | NOS | 20 | 1.18 | 23.6 | 20 | 1.18 | 23.6 | 2 | 1.18 | 2.36 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 20 | 21.24 | 23.6
1787 | C BLDG C.BED DOOR SHUTTER-HARDWARE (130 FLATS) | 10 | Started | Material | (M)SS Hinges - 4" | NOS | 394 | 100.3 | 39518.2 | 394 | 100.3 | 39518.2 | 39 | 100.3 | 3911.7 | 0 | 0 | 0 | 0 | 0 | 0 | 355 | 394 | 35606.5 | 39518.2
1788 | C BLDG C.BED DOOR SHUTTER-HARDWARE (130 FLATS) | 10 | Started | Material | (M)SS Screw 19 x 6 mm Full thread | NOS | 1080 | 2.36 | 2548.8 | 1080 | 2.36 | 2548.8 | 108 | 2.36 | 254.88 | 0 | 0 | 0 | 0 | 0 | 0 | 972 | 1080 | 2293.92 | 2548.8
1789 | C BLDG C.BED DOOR SHUTTER-HARDWARE (130 FLATS) | 10 | Started | Material | (M)SS Screw 25 x 6 mm Full thread | NOS | 560 | 1.18 | 660.8 | 560 | 1.18 | 660.8 | 56 | 1.18 | 66.08 | 0 | 0 | 0 | 0 | 0 | 0 | 504 | 560 | 594.72 | 660.8
1790 | C BLDG C.BED DOOR SHUTTER-HARDWARE (130 FLATS) | 10 | Started | Material | (M)SS Screw 38 x 8 mm Full thread (Nickel) | NOS | 560 | 1.18 | 660.8 | 560 | 1.18 | 660.8 | 56 | 1.18 | 66.08 | 0 | 0 | 0 | 0 | 0 | 0 | 504 | 560 | 594.72 | 660.8
1791 | C BLDG C.BED DOOR SHUTTER-HARDWARE (130 FLATS) | 10 | Started | Material | (M)SS Screw 8 x 32mm Full thread | NOS | 3336 | 2.07 | 6905.52 | 3336 | 2.07 | 6905.52 | 334 | 2.07 | 691.38 | 0 | 0 | 0 | 0 | 0 | 0 | 3002 | 3336 | 6214.14 | 6905.52
1792 | C BLDG C.BED DOOR SHUTTER-HARDWARE (130 FLATS) | 10 | Started | Material | (M)SS Tower Bolt-10" | NOS | 131 | 236 | 30916 | 131 | 236 | 30916 | 13 | 236 | 3068 | 0 | 0 | 0 | 0 | 0 | 0 | 118 | 131 | 27848 | 30916
1793 | C BLDG MAIN DOOR SHUTTER-HARDWARE (130 FLATS) | 10 | Started | Material | (M)Eye Viewer | NOS | 130 | 118 | 15340 | 130 | 118 | 15340 | 13 | 118 | 1534 | 0 | 0 | 0 | 0 | 0 | 0 | 117 | 130 | 13806 | 15340
1794 | C BLDG MAIN DOOR SHUTTER-HARDWARE (130 FLATS) | 10 | Started | Material | (M)Magnetic Door Catcher-3'' | NOS | 131 | 59 | 7729 | 131 | 59 | 7729 | 13 | 59 | 767 | 0 | 0 | 0 | 0 | 0 | 0 | 118 | 131 | 6962 | 7729
1795 | C BLDG MAIN DOOR SHUTTER-HARDWARE (130 FLATS) | 10 | Started | Material | (M)Mortise Lock with Key | NOS | 130 | 2065 | 268450 | 130 | 2065 | 268450 | 13 | 2065 | 26845 | 0 | 0 | 0 | 0 | 0 | 0 | 117 | 130 | 241605 | 268450
1796 | C BLDG MAIN DOOR SHUTTER-HARDWARE (130 FLATS) | 10 | Started | Material | (M)Screw 8 x 25mm | NOS | 24 | 1.18 | 28.32 | 24 | 1.18 | 28.32 | 2 | 1.18 | 2.36 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 24 | 25.96 | 28.32
1797 | C BLDG MAIN DOOR SHUTTER-HARDWARE (130 FLATS) | 10 | Started | Material | (M)SS Aldrop-10'' | NOS | 131 | 236 | 30916 | 131 | 236 | 30916 | 13 | 236 | 3068 | 0 | 0 | 0 | 0 | 0 | 0 | 118 | 131 | 27848 | 30916
1798 | C BLDG MAIN DOOR SHUTTER-HARDWARE (130 FLATS) | 10 | Started | Material | (M)SS Hinges - 5" | NOS | 524 | 100.3 | 52557.2 | 524 | 100.3 | 52557.2 | 52 | 100.3 | 5215.6 | 0 | 0 | 0 | 0 | 0 | 0 | 472 | 524 | 47341.6 | 52557.2
1799 | C BLDG MAIN DOOR SHUTTER-HARDWARE (130 FLATS) | 10 | Started | Material | (M)SS Screw 19 x 6 mm Full thread | NOS | 2080 | 2.36 | 4908.8 | 2080 | 2.36 | 4908.8 | 208 | 2.36 | 490.88 | 0 | 0 | 0 | 0 | 0 | 0 | 1872 | 2080 | 4417.92 | 4908.8
1800 | C BLDG MAIN DOOR SHUTTER-HARDWARE (130 FLATS) | 10 | Started | Material | (M)SS Screw 25 x 6 mm Full thread | NOS | 2080 | 1.18 | 2454.4 | 2080 | 1.18 | 2454.4 | 208 | 1.18 | 245.44 | 0 | 0 | 0 | 0 | 0 | 0 | 1872 | 2080 | 2208.96 | 2454.4
1801 | C BLDG MAIN DOOR SHUTTER-HARDWARE (130 FLATS) | 10 | Started | Material | (M)SS Screw 32 x 6 mm Full thread | NOS | 780 | 1.18 | 920.4 | 780 | 1.18 | 920.4 | 78 | 1.18 | 92.04 | 0 | 0 | 0 | 0 | 0 | 0 | 702 | 780 | 828.36 | 920.4
1802 | C BLDG MAIN DOOR SHUTTER-HARDWARE (130 FLATS) | 10 | Started | Material | (M)SS Screw 8 x 32mm Full thread | NOS | 5536 | 2.07 | 11459.52 | 5536 | 2.07 | 11459.52 | 554 | 2.07 | 1146.78 | 0 | 0 | 0 | 0 | 0 | 0 | 4982 | 5536 | 10312.74 | 11459.52
1803 | C BLDG MAIN DOOR SHUTTER-HARDWARE (130 FLATS) | 10 | Started | Material | (M)SS Tadi Patti-8'' | NOS | 131 | 88.5 | 11593.5 | 131 | 88.5 | 11593.5 | 13 | 88.5 | 1150.5 | 0 | 0 | 0 | 0 | 0 | 0 | 118 | 131 | 10443 | 11593.5
1804 | C BLDG MAIN DOOR SHUTTER-HARDWARE (130 FLATS) | 10 | Started | Material | (M)SS Tower Bolt-10" | NOS | 131 | 236 | 30916 | 131 | 236 | 30916 | 13 | 236 | 3068 | 0 | 0 | 0 | 0 | 0 | 0 | 118 | 131 | 27848 | 30916
1805 | C BLDG TOILET DOOR SHUTTER-HARDWARE (130 FLATS) | 10 | Started | Material | (M)Cylindrical Lock without Key-Toilet | NOS | 130 | 1947 | 253110 | 130 | 1947 | 253110 | 13 | 1947 | 25311 | 0 | 0 | 0 | 0 | 0 | 0 | 117 | 130 | 227799 | 253110
1806 | C BLDG TOILET DOOR SHUTTER-HARDWARE (130 FLATS) | 10 | Started | Material | (M)Nylon Buffer-3'' | NOS | 131 | 17.7 | 2318.7 | 131 | 17.7 | 2318.7 | 13 | 17.7 | 230.1 | 0 | 0 | 0 | 0 | 0 | 0 | 118 | 131 | 2088.6 | 2318.7
1807 | C BLDG TOILET DOOR SHUTTER-HARDWARE (130 FLATS) | 10 | Started | Material | (M)Raval Plug | NOS | 3516 | 1.18 | 4148.88 | 3516 | 1.18 | 4148.88 | 352 | 1.18 | 415.36 | 16 | 0.59 | 9.44 | 0 | 0 | 0 | 3164 | 3516 | 3733.52 | 4148.88
1808 | C BLDG TOILET DOOR SHUTTER-HARDWARE (130 FLATS) | 10 | Started | Material | (M)Screw 8 x 25mm | NOS | 12 | 1.18 | 14.16 | 12 | 1.18 | 14.16 | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 12 | 12.98 | 14.16
1809 | C BLDG TOILET DOOR SHUTTER-HARDWARE (130 FLATS) | 10 | Started | Material | (M)SS Hinges - 4" | NOS | 403 | 100.3 | 40420.9 | 403 | 100.3 | 40420.9 | 40 | 100.3 | 4012 | 0 | 0 | 0 | 0 | 0 | 0 | 363 | 403 | 36408.9 | 40420.9
1810 | C BLDG TOILET DOOR SHUTTER-HARDWARE (130 FLATS) | 10 | Started | Material | (M)SS Screw 19 x 6 mm Full thread | NOS | 560 | 2.36 | 1321.6 | 560 | 2.36 | 1321.6 | 56 | 2.36 | 132.16 | 0 | 0 | 0 | 0 | 0 | 0 | 504 | 560 | 1189.44 | 1321.6
1811 | C BLDG TOILET DOOR SHUTTER-HARDWARE (130 FLATS) | 10 | Started | Material | (M)SS Screw 8 x 32mm Full thread | NOS | 3516 | 2.07 | 7278.12 | 3516 | 2.07 | 7278.12 | 352 | 2.07 | 728.64 | 0 | 0 | 0 | 0 | 0 | 0 | 3164 | 3516 | 6549.48 | 7278.12
1812 | C BLDG TOILET DOOR SHUTTER-HARDWARE (130 FLATS) | 10 | Started | Material | (M)Tower Bolt - SS 4" | NOS | 131 | 59 | 7729 | 131 | 59 | 7729 | 13 | 59 | 767 | 0 | 0 | 0 | 0 | 0 | 0 | 118 | 131 | 6962 | 7729
1813 | INDENT-925, C WING/SAMPLE FLAT-102 INDENT-925 | 10 | Started | Material | (M)Angle Cock | NOS | 1 | 1239 | 1239 | 1 | 1239 | 1239 | 0 | 1239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1239 | 1239
1814 | INDENT-925, C WING/SAMPLE FLAT-102 INDENT-925 | 10 | Started | Material | (M)Basin Waste Coupling F/T | NOS | 1 | 307.49 | 307.49 | 1 | 307.49 | 307.49 | 0 | 307.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 307.49 | 307.49
1815 | INDENT-925, C WING/SAMPLE FLAT-102 INDENT-925 | 10 | Started | Material | (M)CP Ext. Piece - 1/2" x 1" | NOS | 2 | 29.5 | 59 | 2 | 29.5 | 59 | 0 | 29.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 59 | 59
1816 | INDENT-925, C WING/SAMPLE FLAT-102 INDENT-925 | 10 | Started | Material | (M)CP Nozzle Bib Cock | NOS | 1 | 697 | 697 | 1 | 697 | 697 | 0 | 697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 697 | 697
1817 | INDENT-925, C WING/SAMPLE FLAT-102 INDENT-925 | 10 | Started | Material | (M)CP Shower Arm | NOS | 1 | 344.4 | 344.4 | 1 | 344.4 | 344.4 | 0 | 344.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 344.4 | 344.4
1818 | INDENT-925, C WING/SAMPLE FLAT-102 INDENT-925 | 10 | Started | Material | (M)CP Wall Mixer | NOS | 1 | 3361.99 | 3361.99 | 1 | 3361.99 | 3361.99 | 0 | 3361.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3361.99 | 3361.99
1819 | INDENT-925, C WING/SAMPLE FLAT-102 INDENT-925 | 10 | Started | Material | (M)CPVC CONSEALED STOP COCK-1/2'' (ALD-CHR-083) | NOS | 1 | 2065 | 2065 | 1 | 2065 | 2065 | 0 | 2065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2065 | 2065
1820 | INDENT-925, C WING/SAMPLE FLAT-102 INDENT-925 | 10 | Started | Material | (M)Inlet Pipe - 1/2'' (Long-24") | NOS | 1 | 283.2 | 283.2 | 1 | 283.2 | 283.2 | 0 | 283.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 283.2 | 283.2
1821 | INDENT-925, C WING/SAMPLE FLAT-102 INDENT-925 | 10 | Started | Material | (M)Pillar Cock - FLR -CHR-5011N | NOS | 1 | 2300 | 2300 | 1 | 2300 | 2300 | 0 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2300 | 2300
1822 | INDENT-925, C WING/SAMPLE FLAT-102 INDENT-925 | 10 | Started | Material | (M)PVC FLOOR TRAP JALI-6'' (BROWN) | NOS | 1 | 59 | 59 | 1 | 59 | 59 | 0 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 59 | 59
1823 | INDENT-925, C WING/SAMPLE FLAT-102 INDENT-925 | 10 | Started | Material | (M)PVC FLOOR TRAP JALI-6'' (IVORY) | NOS | 1 | 59 | 59 | 1 | 59 | 59 | 0 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 59 | 59
1824 | INDENT-925, C WING/SAMPLE FLAT-102 INDENT-925 | 10 | Started | Material | (M)PVC Waste / Fiexible Pipe | NOS | 2 | 141.6 | 283.2 | 2 | 141.6 | 283.2 | 0 | 141.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 283.2 | 283.2
1825 | INDENT-925, C WING/SAMPLE FLAT-102 INDENT-925 | 10 | Started | Material | (M)Sink Cock Wall Mount -FLR-CHR-5347N | NOS | 2 | 2200 | 4400 | 0 | 0 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 4400 | 4400
1826 | INDENT-925, C WING/SAMPLE FLAT-102 INDENT-925 | 10 | Started | Material | (M)SS Sink Coupling | SET | 1 | 250 | 250 | 1 | 250 | 250 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 250 | 250
1827 | INDENT-925, C WING/SAMPLE FLAT-102 INDENT-925 | 10 | Started | Material | (M)Two Way Bib Cock | NOS | 1 | 1008.61 | 1008.61 | 1 | 1008.61 | 1008.61 | 0 | 1008.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1008.61 | 1008.61
1828 | INDENT-925, C WING/SAMPLE FLAT-102 INDENT-925 REVISED | 10 | Started | Material | (M)Angle Cock | NOS | 1 | 1239 | 1239 | 0 | 0 | 0 | 0 | 1239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1239 | 1239
1829 | INDENT-925, C WING/SAMPLE FLAT-102 INDENT-925 REVISED | 10 | Started | Material | (M)Basin Waste Coupling F/T | NOS | 1 | 307.49 | 307.49 | 0 | 0 | 0 | 0 | 307.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 307.49 | 307.49
1830 | INDENT-925, C WING/SAMPLE FLAT-102 INDENT-925 REVISED | 10 | Started | Material | (M)CP Ext. Piece - 1/2" x 1" | NOS | 2 | 29.5 | 59 | 0 | 0 | 0 | 0 | 29.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 59 | 59
1831 | INDENT-925, C WING/SAMPLE FLAT-102 INDENT-925 REVISED | 10 | Started | Material | (M)CP Nozzle Bib Cock | NOS | 1 | 697 | 697 | 0 | 0 | 0 | 0 | 697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 697 | 697
1832 | INDENT-925, C WING/SAMPLE FLAT-102 INDENT-925 REVISED | 10 | Started | Material | (M)CP Shower Arm | NOS | 1 | 344.4 | 344.4 | 0 | 0 | 0 | 0 | 344.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 344.4 | 344.4
1833 | INDENT-925, C WING/SAMPLE FLAT-102 INDENT-925 REVISED | 10 | Started | Material | (M)CP Sink Cock | NOS | 2 | 1459.61 | 2919.22 | 2 | 1459.61 | 2919.22 | 0 | 1459.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2919.22 | 2919.22
1834 | INDENT-925, C WING/SAMPLE FLAT-102 INDENT-925 REVISED | 10 | Started | Material | (M)CP Wall Mixer | NOS | 1 | 3361.99 | 3361.99 | 0 | 0 | 0 | 0 | 3361.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3361.99 | 3361.99
1835 | INDENT-925, C WING/SAMPLE FLAT-102 INDENT-925 REVISED | 10 | Started | Material | (M)CPVC CONSEALED STOP COCK-1/2'' (ALD-CHR-083) | NOS | 1 | 2065 | 2065 | 0 | 0 | 0 | 0 | 2065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2065 | 2065
1836 | INDENT-925, C WING/SAMPLE FLAT-102 INDENT-925 REVISED | 10 | Started | Material | (M)Inlet Pipe - 1/2'' (Long-24") | NOS | 1 | 283.2 | 283.2 | 0 | 0 | 0 | 0 | 283.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 283.2 | 283.2
1837 | INDENT-925, C WING/SAMPLE FLAT-102 INDENT-925 REVISED | 10 | Started | Material | (M)Pillar Cock - FLR -CHR-5011N | NOS | 1 | 2300 | 2300 | 0 | 0 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2300 | 2300
1838 | INDENT-925, C WING/SAMPLE FLAT-102 INDENT-925 REVISED | 10 | Started | Material | (M)PVC FLOOR TRAP JALI-6'' (BROWN) | NOS | 1 | 59 | 59 | 0 | 0 | 0 | 0 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 59 | 59
1839 | INDENT-925, C WING/SAMPLE FLAT-102 INDENT-925 REVISED | 10 | Started | Material | (M)PVC FLOOR TRAP JALI-6'' (IVORY) | NOS | 1 | 59 | 59 | 0 | 0 | 0 | 0 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 59 | 59
1840 | INDENT-925, C WING/SAMPLE FLAT-102 INDENT-925 REVISED | 10 | Started | Material | (M)PVC Waste / Fiexible Pipe | NOS | 2 | 141.6 | 283.2 | 0 | 0 | 0 | 0 | 141.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 283.2 | 283.2
1841 | INDENT-925, C WING/SAMPLE FLAT-102 INDENT-925 REVISED | 10 | Started | Material | (M)SS Sink Coupling | SET | 1 | 250 | 250 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 250 | 250
1842 | INDENT-925, C WING/SAMPLE FLAT-102 INDENT-925 REVISED | 10 | Started | Material | (M)Two Way Bib Cock | NOS | 1 | 1008.61 | 1008.61 | 0 | 0 | 0 | 0 | 1008.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1008.61 | 1008.61
1843 | INDENT-926, C WING/SAMPLE FLAT-102 INDENT-926, C WING/SAMPLE | 10 | Started | Material | (M)CP Flush Valve 32mm (1085-N) | NOS | 1 | 3599 | 3599 | 1 | 3599 | 3599 | 0 | 3599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3599 | 3599
1844 | INDENT-926, C WING/SAMPLE FLAT-102 INDENT-926, C WING/SAMPLE | 10 | Started | Material | (M)CP Health Faucet | NOS | 1 | 631.4 | 631.4 | 1 | 631.4 | 631.4 | 0 | 631.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 631.4 | 631.4
1845 | INDENT-926, C WING/SAMPLE FLAT-102 INDENT-926, C WING/SAMPLE | 10 | Started | Material | (M)DAFFODIL WASH BASIN 575 X 420 X 200 | NOS | 1 | 5310 | 5310 | 1 | 5310 | 5310 | 0 | 5310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 5310 | 5310
1846 | INDENT-926, C WING/SAMPLE FLAT-102 INDENT-926, C WING/SAMPLE | 10 | Started | Material | (M)GLASS LAMBI | KG | 1 | 118 | 118 | 1 | 118 | 118 | 0 | 118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 118 | 118
1847 | INDENT-926, C WING/SAMPLE FLAT-102 INDENT-926, C WING/SAMPLE | 10 | Started | Material | (M)M SEAL - 250 GM | NOS | 1 | 100 | 100 | 1 | 100 | 100 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 100 | 100
1848 | INDENT-926, C WING/SAMPLE FLAT-102 INDENT-926, C WING/SAMPLE | 10 | Started | Material | (M)Ruby Wall Hung Closet 500 x 350 x 335 | NOS | 1 | 5900 | 5900 | 1 | 5900 | 5900 | 0 | 5900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 5900 | 5900
1849 | INDENT-926, C WING/SAMPLE FLAT-102 INDENT-926, C WING/SAMPLE | 10 | Started | Material | (M)Teflon Tape | NOS | 5 | 19.48 | 97.4 | 5 | 19.48 | 97.4 | 1 | 19.48 | 19.48 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 77.92 | 97.4
1850 | OFFICE NO-01 & 24 CP & SANITRY WORK MATERIALS | 0 | Tentative | Material | (M)Angle Cock | NOS | 2 | 1239 | 2478 | 2 | 1239 | 2478 | 0 | 1239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2478 | 2478
1851 | OFFICE NO-01 & 24 CP & SANITRY WORK MATERIALS | 0 | Tentative | Material | (M)Basin Waste Coupling F/T | NOS | 2 | 307.49 | 614.98 | 2 | 307.49 | 614.98 | 0 | 307.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 614.98 | 614.98
1852 | OFFICE NO-01 & 24 CP & SANITRY WORK MATERIALS | 0 | Tentative | Material | (M)CP Ext. Piece - 1/2" x 1" | NOS | 10 | 29.5 | 295 | 10 | 29.5 | 295 | 0 | 29.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 295 | 295
1853 | OFFICE NO-01 & 24 CP & SANITRY WORK MATERIALS | 0 | Tentative | Material | (M)CP Health Faucet | NOS | 2 | 631.4 | 1262.8 | 2 | 631.4 | 1262.8 | 0 | 631.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 1262.8 | 1262.8
1854 | OFFICE NO-01 & 24 CP & SANITRY WORK MATERIALS | 0 | Tentative | Material | (M)CP Pillar Cock (DLX-CHR-508KN) | NOS | 2 | 1025 | 2050 | 2 | 1025 | 2050 | 0 | 1025 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2050 | 2050
1855 | OFFICE NO-01 & 24 CP & SANITRY WORK MATERIALS | 0 | Tentative | Material | (M)Inlet Pipe - 1/2'' (Long-24") | NOS | 2 | 283.2 | 566.4 | 2 | 283.2 | 566.4 | 0 | 283.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 566.4 | 566.4
1856 | OFFICE NO-01 & 24 CP & SANITRY WORK MATERIALS | 0 | Tentative | Material | (M)PVC Bottle Trap | NOS | 2 | 295 | 590 | 2 | 295 | 590 | 0 | 295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 590 | 590
1857 | OFFICE NO-01 & 24 CP & SANITRY WORK MATERIALS | 0 | Tentative | Material | (M)PVC FLOOR TRAP JALI-6'' (GRAY) | NOS | 2 | 59 | 118 | 2 | 59 | 118 | 0 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 118 | 118
1858 | OFFICE NO-01 & 24 CP & SANITRY WORK MATERIALS | 0 | Tentative | Material | (M)Ruby Topaz Seat Cover | NOS | 4 | 1770 | 7080 | 4 | 1770 | 7080 | 0 | 1770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 7080 | 7080
1859 | OFFICE NO-01 & 24 CP & SANITRY WORK MATERIALS | 0 | Tentative | Material | (M)Ruby Wall Hung Closet 500 x 350 x 335 | NOS | 4 | 5900 | 23600 | 4 | 5900 | 23600 | 0 | 5900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 23600 | 23600
1860 | OFFICE NO-01 & 24 CP & SANITRY WORK MATERIALS | 0 | Tentative | Material | (M)Teflon Tape | NOS | 10 | 19.48 | 194.8 | 10 | 19.48 | 194.8 | 0 | 19.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 194.8 | 194.8
1861 | OFFICE NO-01 & 24 CP & SANITRY WORK MATERIALS | 0 | Tentative | Material | (M)Two Way Bib Cock | NOS | 2 | 1008.61 | 2017.22 | 2 | 1008.61 | 2017.22 | 0 | 1008.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2017.22 | 2017.22
1862 | OFFICE NO-01 & 24 CP & SANITRY WORK MATERIALS | 0 | Tentative | Material | (M)Wall Mounted Basin 400 x 300mm | NOS | 2 | 2950 | 5900 | 2 | 2950 | 5900 | 0 | 2950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 5900 | 5900
1863 | OFFICE NO-01 & 24 CP & SANITRY WORK MATERIALS | 0 | Tentative | Material | (M)WHITE CEMENT (1Kg/Packet) | KG | 2 | 146.32 | 292.64 | 2 | 146.32 | 292.64 | 0 | 146.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 292.64 | 292.64
1864 | INDENT-959/C WING/UGF PVC DOWNTAKE | 10 | Started | Material | (M)Bullet Fastner - 10mm | NOS | 50 | 16.55 | 827.5 | 50 | 16.55 | 827.5 | 5 | 16.55 | 82.75 | 50 | 11.8 | 590 | 0 | 0 | 0 | 45 | 50 | 744.75 | 827.5
1865 | INDENT-959/C WING/UGF PVC DOWNTAKE | 10 | Started | Material | (M)GI U Clamp with Nut Bolt & Washer 3" | NOS | 60 | 17.7 | 1062 | 60 | 17.7 | 1062 | 6 | 17.7 | 106.2 | 60 | 15.93 | 955.8 | 0 | 0 | 0 | 54 | 60 | 955.8 | 1062
1866 | INDENT-959/C WING/UGF PVC DOWNTAKE | 10 | Started | Material | (M)GI U Clamp with Nut Bolt & Washer 4" | NOS | 60 | 19.12 | 1147.2 | 60 | 19.12 | 1147.2 | 6 | 19.12 | 114.72 | 60 | 19.12 | 1146.96 | 0 | 0 | 0 | 54 | 60 | 1032.48 | 1147.2
1867 | INDENT-959/C WING/UGF PVC DOWNTAKE | 10 | Started | Material | (M)Hanging Clamp (Regular) | NOS | 40 | 20 | 800 | 40 | 20 | 800 | 4 | 20 | 80 | 40 | 20.65 | 826 | 0 | 0 | 0 | 36 | 40 | 720 | 800
1868 | INDENT-959/C WING/UGF PVC DOWNTAKE | 10 | Started | Material | (M)Pvc Solution 473ml | NOS | 20 | 206.5 | 4130 | 20 | 206.5 | 4130 | 2 | 206.5 | 413 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 20 | 3717 | 4130
1869 | INDENT-959/C WING/UGF PVC DOWNTAKE | 10 | Started | Material | (M)Rubber Lubricant 500 gram | NOS | 10 | 332 | 3320 | 10 | 332 | 3320 | 1 | 332 | 332 | 10 | 90.27 | 902.7 | 0 | 0 | 0 | 9 | 10 | 2988 | 3320
1870 | INDENT-959/C WING/UGF PVC DOWNTAKE | 10 | Started | Material | (M)SWR Pipes 'B' type R/F 10ft long S/S 110mm | NOS | 30 | 885 | 26550 | 30 | 885 | 26550 | 3 | 885 | 2655 | 30 | 623.13 | 18694.041 | 0 | 0 | 0 | 27 | 30 | 23895 | 26550
1871 | INDENT-959/C WING/UGF PVC DOWNTAKE | 10 | Started | Material | (M)SWR Pipes 'B' type R/F 10ft long S/S 75mm | NOS | 55 | 417.93 | 22986.15 | 55 | 417.93 | 22986.15 | 6 | 417.93 | 2507.58 | 55 | 413 | 22715 | 0 | 0 | 0 | 49 | 55 | 20478.57 | 22986.15
1872 | INDENT-959/C WING/UGF PVC DOWNTAKE | 10 | Started | Material | (M)SWR Pipes 'B' type R/F 2ft long D/S 110mm | NOS | 30 | 200 | 6000 | 30 | 200 | 6000 | 3 | 200 | 600 | 30 | 163.88 | 4916.361 | 0 | 0 | 0 | 27 | 30 | 5400 | 6000
1873 | INDENT-959/C WING/UGF PVC DOWNTAKE | 10 | Started | Material | (M)SWR Plain Tee 75 mm | NOS | 30 | 59.03 | 1770.9 | 30 | 59.03 | 1770.9 | 3 | 59.03 | 177.09 | 30 | 58.15 | 1744.521 | 0 | 0 | 0 | 27 | 30 | 1593.81 | 1770.9
1874 | INDENT-959/C WING/UGF PVC DOWNTAKE | 10 | Started | Material | (M)SWR Plug Bend 75 mm | NOS | 50 | 80.24 | 4012 | 50 | 80.24 | 4012 | 5 | 80.24 | 401.2 | 50 | 51.54 | 2577.12 | 0 | 0 | 0 | 45 | 50 | 3610.8 | 4012
1875 | INDENT-959/C WING/UGF PVC DOWNTAKE | 10 | Started | Material | (M)SWR Shoe 110 mm | NOS | 40 | 82.6 | 3304 | 40 | 82.6 | 3304 | 4 | 82.6 | 330.4 | 40 | 64.1 | 2563.9 | 0 | 0 | 0 | 36 | 40 | 2973.6 | 3304
1876 | INDENT-959/C WING/UGF PVC DOWNTAKE | 10 | Started | Material | (M)SWR Shoe 75 mm | NOS | 40 | 70.8 | 2832 | 40 | 70.8 | 2832 | 4 | 70.8 | 283.2 | 40 | 38.33 | 1533.06 | 0 | 0 | 0 | 36 | 40 | 2548.8 | 2832
1877 | INDENT-959/C WING/UGF PVC DOWNTAKE | 10 | Started | Material | (M)SWR Single Y 110 mm | NOS | 35 | 177 | 6195 | 35 | 177 | 6195 | 4 | 177 | 708 | 35 | 142.07 | 4972.52 | 0 | 0 | 0 | 31 | 35 | 5487 | 6195
1878 | INDENT-959/C WING/UGF PVC DOWNTAKE | 10 | Started | Material | (M)SWR Single Y 75 mm | NOS | 60 | 135.7 | 8142 | 60 | 135.7 | 8142 | 6 | 135.7 | 814.2 | 60 | 75.99 | 4559.52 | 0 | 0 | 0 | 54 | 60 | 7327.8 | 8142
1879 | C BLDG PVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)GI C-Bracket 12" x 2" | NOS | 640 | 59 | 37760 | 640 | 59 | 37760 | 0 | 59 | 0 | 640 | 60.55 | 38751.232 | 0 | 0 | 0 | 640 | 640 | 37760 | 37760
1880 | C BLDG PVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)GI C-Bracket 3" x 2" | NOS | 330 | 29.5 | 9735 | 330 | 29.5 | 9735 | 0 | 29.5 | 0 | 330 | 31.52 | 10400.412 | 0 | 0 | 0 | 330 | 330 | 9735 | 9735
1881 | C BLDG PVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)GI C-Bracket 4" x 2" | NOS | 10 | 25.96 | 259.6 | 10 | 25.96 | 259.6 | 0 | 25.96 | 0 | 10 | 31.52 | 315.168 | 0 | 0 | 0 | 10 | 10 | 259.6 | 259.6
1882 | C BLDG PVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)GI C-Bracket 4" x 3" | NOS | 616 | 39.43 | 24288.88 | 616 | 39.43 | 24288.88 | 0 | 39.43 | 0 | 616 | 41.51 | 25569.4208 | 0 | 0 | 0 | 616 | 616 | 24288.88 | 24288.88
1883 | C BLDG PVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)GI C-Bracket 6" x 2" | NOS | 538 | 43.81 | 23569.78 | 538 | 43.81 | 23569.78 | 0 | 43.81 | 0 | 538 | 41.39 | 22270.1334 | 0 | 0 | 0 | 538 | 538 | 23569.78 | 23569.78
1884 | C BLDG PVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)GI C-Bracket 8" x 2" | NOS | 40 | 47.2 | 1888 | 40 | 47.2 | 1888 | 0 | 47.2 | 0 | 40 | 46.17 | 1846.7 | 0 | 0 | 0 | 40 | 40 | 1888 | 1888
1885 | C BLDG PVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)GI U Clamp with Nut Bolt & Washer 3" | NOS | 660 | 17.7 | 11682 | 660 | 17.7 | 11682 | 0 | 17.7 | 0 | 660 | 16.98 | 11209.968 | 0 | 0 | 0 | 660 | 660 | 11682 | 11682
1886 | C BLDG PVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)GI U Clamp with Nut Bolt & Washer 4" | NOS | 493 | 19.12 | 9426.16 | 493 | 19.12 | 9426.16 | 0 | 19.12 | 0 | 493 | 20.65 | 10180.943 | 0 | 0 | 0 | 493 | 493 | 9426.16 | 9426.16
1887 | C BLDG PVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)PVC Elbow 50 mm | NOS | 264 | 38.77 | 10235.28 | 264 | 38.77 | 10235.28 | 0 | 38.77 | 0 | 264 | 21.76 | 5744.2968 | 0 | 0 | 0 | 264 | 264 | 10235.28 | 10235.28
1888 | C BLDG PVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)PVC Equal Tee 50 mm | NOS | 42 | 15.34 | 644.28 | 42 | 15.34 | 644.28 | 0 | 15.34 | 0 | 42 | 32.86 | 1380.3258 | 0 | 0 | 0 | 42 | 42 | 644.28 | 644.28
1889 | C BLDG PVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)PVC Gray Pipes S/F 10ft long 50 mm (4Kg/Sqcm) | NOS | 140 | 306.8 | 42952 | 140 | 306.8 | 42952 | 0 | 306.8 | 0 | 140 | 167.72 | 23481.388 | 0 | 0 | 0 | 140 | 140 | 42952 | 42952
1890 | C BLDG PVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)PVC Shoe 40 mm | NOS | 85 | 17.81 | 1513.85 | 85 | 17.81 | 1513.85 | 0 | 17.81 | 0 | 85 | 17.61 | 1497.207 | 0 | 0 | 0 | 85 | 85 | 1513.85 | 1513.85
1891 | C BLDG PVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)SWR Nahani Trap without Jali 110 mm | NOS | 30 | 94.4 | 2832 | 30 | 94.4 | 2832 | 0 | 94.4 | 0 | 30 | 65.41 | 1962.177 | 0 | 0 | 0 | 30 | 30 | 2832 | 2832
1892 | C BLDG PVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)SWR Pipes 'B' type R/F 10ft long S/S 110mm | NOS | 240 | 885 | 212400 | 240 | 885 | 212400 | 0 | 885 | 0 | 240 | 630.1 | 151223.808 | 0 | 0 | 0 | 240 | 240 | 212400 | 212400
1893 | C BLDG PVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)SWR Pipes 'B' type R/F 10ft long S/S 75mm | NOS | 330 | 417.93 | 137916.9 | 330 | 417.93 | 137916.9 | 0 | 417.93 | 0 | 330 | 417.69 | 137838.261 | 0 | 0 | 0 | 330 | 330 | 137916.9 | 137916.9
1894 | C BLDG PVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)SWR Pipes 'B' type R/F 4ft long D/S 75mm | NOS | 66 | 354 | 23364 | 66 | 354 | 23364 | 0 | 354 | 0 | 66 | 189.09 | 12480.2238 | 0 | 0 | 0 | 66 | 66 | 23364 | 23364
1895 | C BLDG PVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)SWR Plain Tee 110 x 50 mm | NOS | 132 | 177 | 23364 | 132 | 177 | 23364 | 0 | 177 | 0 | 132 | 175.14 | 23118.3216 | 0 | 0 | 0 | 132 | 132 | 23364 | 23364
1896 | C BLDG PVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)SWR Plug Bend 110 mm | NOS | 125 | 177 | 22125 | 125 | 177 | 22125 | 0 | 177 | 0 | 125 | 90.01 | 11251.775 | 0 | 0 | 0 | 125 | 125 | 22125 | 22125
1897 | C BLDG PVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)SWR Plug Bend 75 mm | NOS | 105 | 80.24 | 8425.2 | 105 | 80.24 | 8425.2 | 0 | 80.24 | 0 | 105 | 51.16 | 5371.716 | 0 | 0 | 0 | 105 | 105 | 8425.2 | 8425.2
1898 | C BLDG PVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)SWR Plug Tee 75 mm | NOS | 124 | 106.2 | 13168.8 | 124 | 106.2 | 13168.8 | 0 | 106.2 | 0 | 124 | 69.94 | 8672.4484 | 0 | 0 | 0 | 124 | 124 | 13168.8 | 13168.8
1899 | C BLDG PVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)SWR Single Y 110 mm | NOS | 112 | 177 | 19824 | 112 | 177 | 19824 | 0 | 177 | 0 | 112 | 142.47 | 15956.4608 | 0 | 0 | 0 | 112 | 112 | 19824 | 19824
1900 | C BLDG PVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)SWR Single Y 75 mm | NOS | 112 | 135.7 | 15198.4 | 112 | 135.7 | 15198.4 | 0 | 135.7 | 0 | 112 | 76.41 | 8558.4464 | 0 | 0 | 0 | 112 | 112 | 15198.4 | 15198.4
1901 | C BLDG PVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)SWR ST. WC Connector with LIP Ring (2') 'B' type 110 mm | NOS | 66 | 236 | 15576 | 66 | 236 | 15576 | 0 | 236 | 0 | 66 | 181.32 | 11967.3378 | 0 | 0 | 0 | 66 | 66 | 15576 | 15576
1902 | C BLDG PVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)SWR Vent Cowl 75 mm | NOS | 22 | 29.5 | 649 | 22 | 29.5 | 649 | 0 | 29.5 | 0 | 22 | 11.66 | 256.4386 | 0 | 0 | 0 | 22 | 22 | 649 | 649
1903 | UPVC DOWNTAKE INDENT-960/C WING/UGF DOWNTAKE | 10 | Started | Material | (M)10MM THREAD ROD FOR FASTNER-2MTR | NOS | 20 | 130 | 2600 | 20 | 130 | 2600 | 2 | 130 | 260 | 20 | 153.4 | 3068 | 0 | 0 | 0 | 18 | 20 | 2340 | 2600
1904 | UPVC DOWNTAKE INDENT-960/C WING/UGF DOWNTAKE | 10 | Started | Material | (M)CPVC Transition Bushing 1/2" | NOS | 15 | 4.65 | 69.75 | 15 | 4.65 | 69.75 | 2 | 4.65 | 9.3 | 15 | 5.48 | 82.26 | 0 | 0 | 0 | 13 | 15 | 60.45 | 69.75
1905 | UPVC DOWNTAKE INDENT-960/C WING/UGF DOWNTAKE | 10 | Started | Material | (M)GI Z Bracket 3'' X 1Mtr | NOS | 40 | 190 | 7600 | 40 | 190 | 7600 | 4 | 190 | 760 | 40 | 224.2 | 8968 | 0 | 0 | 0 | 36 | 40 | 6840 | 7600
1906 | UPVC DOWNTAKE INDENT-960/C WING/UGF DOWNTAKE | 10 | Started | Material | (M)SWR Pipes 'B' type R/F 2ft long D/S 75mm | NOS | 15 | 88.48 | 1327.2 | 15 | 88.48 | 1327.2 | 2 | 88.48 | 176.96 | 15 | 104.41 | 1566.1005 | 0 | 0 | 0 | 13 | 15 | 1150.24 | 1327.2
1907 | UPVC DOWNTAKE INDENT-960/C WING/UGF DOWNTAKE | 10 | Started | Material | (M)UPVC Adhesives / Solvent (717) - 473ml | NOS | 20 | 535.72 | 10714.4 | 20 | 535.72 | 10714.4 | 2 | 535.72 | 1071.44 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 20 | 9642.96 | 10714.4
1908 | UPVC DOWNTAKE INDENT-960/C WING/UGF DOWNTAKE | 10 | Started | Material | (M)UPVC Coupler 1 1/4" | NOS | 65 | 25.48 | 1656.2 | 65 | 25.48 | 1656.2 | 7 | 25.48 | 178.36 | 65 | 14.27 | 927.758 | 0 | 0 | 0 | 58 | 65 | 1477.84 | 1656.2
1909 | UPVC DOWNTAKE INDENT-960/C WING/UGF DOWNTAKE | 10 | Started | Material | (M)UPVC Coupler 2" | NOS | 55 | 27.66 | 1521.3 | 55 | 27.66 | 1521.3 | 6 | 27.66 | 165.96 | 55 | 27.65 | 1520.9975 | 0 | 0 | 0 | 49 | 55 | 1355.34 | 1521.3
1910 | UPVC DOWNTAKE INDENT-960/C WING/UGF DOWNTAKE | 10 | Started | Material | (M)UPVC Elbow 1 1/4 (90 degree) | NOS | 118 | 23.61 | 2785.98 | 118 | 23.61 | 2785.98 | 12 | 23.61 | 283.32 | 118 | 20.68 | 2440.6058 | 0 | 0 | 0 | 106 | 118 | 2502.66 | 2785.98
1911 | UPVC DOWNTAKE INDENT-960/C WING/UGF DOWNTAKE | 10 | Started | Material | (M)UPVC Elbow 1/2" (90 degree) | NOS | 10 | 5.04 | 50.4 | 10 | 5.04 | 50.4 | 1 | 5.04 | 5.04 | 10 | 5.95 | 59.48 | 0 | 0 | 0 | 9 | 10 | 45.36 | 50.4
1912 | UPVC DOWNTAKE INDENT-960/C WING/UGF DOWNTAKE | 10 | Started | Material | (M)UPVC Pipe 1 1/4 X 3m long (SCH-40) | NOS | 75 | 465.33 | 34899.75 | 75 | 465.33 | 34899.75 | 8 | 465.33 | 3722.64 | 75 | 260.59 | 19543.98 | 0 | 0 | 0 | 67 | 75 | 31177.11 | 34899.75
1913 | UPVC DOWNTAKE INDENT-960/C WING/UGF DOWNTAKE | 10 | Started | Material | (M)UPVC Pipe 2" X 3m long (SCH-40) | NOS | 30 | 485.88 | 14576.4 | 30 | 485.88 | 14576.4 | 3 | 485.88 | 1457.64 | 30 | 417.2 | 12515.88 | 0 | 0 | 0 | 27 | 30 | 13118.76 | 14576.4
1914 | UPVC DOWNTAKE INDENT-960/C WING/UGF DOWNTAKE | 10 | Started | Material | (M)UPVC Reducer Tee 1 1/4" x 1/2" | NOS | 48 | 50 | 2400 | 48 | 50 | 2400 | 5 | 50 | 250 | 48 | 27.98 | 1343.2704 | 0 | 0 | 0 | 43 | 48 | 2150 | 2400
1915 | UPVC DOWNTAKE INDENT-960/C WING/UGF DOWNTAKE | 10 | Started | Material | (M)UPVC Reducer Tee 2" x 1 1/4" | NOS | 28 | 46 | 1288 | 28 | 46 | 1288 | 3 | 46 | 138 | 28 | 55.41 | 1551.4296 | 0 | 0 | 0 | 25 | 28 | 1150 | 1288
1916 | UPVC DOWNTAKE INDENT-960/C WING/UGF DOWNTAKE | 10 | Started | Material | (M)UPVC SHOE 1 1/4" | NOS | 20 | 17.94 | 358.8 | 20 | 17.94 | 358.8 | 2 | 17.94 | 35.88 | 20 | 17.94 | 358.82 | 0 | 0 | 0 | 18 | 20 | 322.92 | 358.8
1917 | UPVC DOWNTAKE INDENT-960/C WING/UGF DOWNTAKE | 10 | Started | Material | (M)UPVC SHOE 2" | NOS | 20 | 35.4 | 708 | 20 | 35.4 | 708 | 2 | 35.4 | 70.8 | 20 | 36.31 | 726.22 | 0 | 0 | 0 | 18 | 20 | 637.2 | 708
1918 | UPVC DOWNTAKE INDENT-961/C WING/UGF DOWNTAKE | 10 | Started | Material | (M)GI U Clamp with Nut Bolt & Washer 1 1/4" | NOS | 60 | 8.5 | 510 | 60 | 8.5 | 510 | 6 | 8.5 | 51 | 60 | 11.95 | 716.862 | 0 | 0 | 0 | 54 | 60 | 459 | 510
1919 | UPVC DOWNTAKE INDENT-961/C WING/UGF DOWNTAKE | 10 | Started | Material | (M)GI U Clamp with Nut Bolt & Washer 2" | NOS | 10 | 13.93 | 139.3 | 10 | 13.93 | 139.3 | 1 | 13.93 | 13.93 | 10 | 13.94 | 139.36 | 0 | 0 | 0 | 9 | 10 | 125.37 | 139.3
1920 | UPVC DOWNTAKE INDENT-961/C WING/UGF DOWNTAKE | 10 | Started | Material | (M)GI Z Bracket 2'' X 1Mtr | NOS | 20 | 170 | 3400 | 20 | 170 | 3400 | 2 | 170 | 340 | 20 | 200.6 | 4012 | 0 | 0 | 0 | 18 | 20 | 3060 | 3400
1921 | UPVC DOWNTAKE INDENT-961/C WING/UGF DOWNTAKE | 10 | Started | Material | (M)Plumbing Nails 2" | KG | 4 | 87 | 348 | 4 | 87 | 348 | 0 | 87 | 0 | 4 | 102.66 | 410.64 | 0 | 0 | 0 | 4 | 4 | 348 | 348
1922 | UPVC DOWNTAKE INDENT-961/C WING/UGF DOWNTAKE | 10 | Started | Material | (M)UPVC Ball Valves 1/2" | NOS | 22 | 44.24 | 973.28 | 22 | 44.24 | 973.28 | 2 | 44.24 | 88.48 | 22 | 52.2 | 1148.4792 | 0 | 0 | 0 | 20 | 22 | 884.8 | 973.28
1923 | UPVC DOWNTAKE INDENT-961/C WING/UGF DOWNTAKE | 10 | Started | Material | (M)UPVC Pipe 1/2" X 3m long (SCH-40) | NOS | 5 | 84.17 | 420.85 | 5 | 84.17 | 420.85 | 1 | 84.17 | 84.17 | 5 | 99.32 | 496.6 | 0 | 0 | 0 | 4 | 5 | 336.68 | 420.85
1924 | UPVC DOWNTAKE INDENT-961/C WING/UGF DOWNTAKE | 10 | Started | Material | (M)UPVC Tee 2" | NOS | 11 | 71.1 | 782.1 | 11 | 71.1 | 782.1 | 1 | 71.1 | 71.1 | 11 | 62.25 | 684.7093 | 0 | 0 | 0 | 10 | 11 | 711 | 782.1
1925 | C BLDG UPVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)CPVC Transition Bushing 1/2" | NOS | 396 | 4.65 | 1841.4 | 396 | 4.65 | 1841.4 | 0 | 4.65 | 0 | 396 | 5.25 | 2077.1784 | 0 | 0 | 0 | 396 | 396 | 1841.4 | 1841.4
1926 | C BLDG UPVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)GI U Clamp with Nut Bolt & Washer 1 1/2" | NOS | 176 | 13.5 | 2376 | 176 | 13.5 | 2376 | 0 | 13.5 | 0 | 176 | 11.95 | 2102.76 | 0 | 0 | 0 | 176 | 176 | 2376 | 2376
1927 | C BLDG UPVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)GI U Clamp with Nut Bolt & Washer 1 1/4" | NOS | 440 | 8.5 | 3740 | 440 | 8.5 | 3740 | 0 | 8.5 | 0 | 440 | 10.89 | 4789.62 | 0 | 0 | 0 | 440 | 440 | 3740 | 3740
1928 | C BLDG UPVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)GI U Clamp with Nut Bolt & Washer 1" | NOS | 330 | 17.7 | 5841 | 330 | 17.7 | 5841 | 0 | 17.7 | 0 | 330 | 9.74 | 3212.55 | 0 | 0 | 0 | 330 | 330 | 5841 | 5841
1929 | C BLDG UPVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)GI U Clamp with Nut Bolt & Washer 2" | NOS | 432 | 13.93 | 6017.76 | 432 | 13.93 | 6017.76 | 0 | 13.93 | 0 | 432 | 13.01 | 5620.104 | 0 | 0 | 0 | 432 | 432 | 6017.76 | 6017.76
1930 | C BLDG UPVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)GI U Clamp with Nut Bolt & Washer 3/4" | NOS | 352 | 11.8 | 4153.6 | 352 | 11.8 | 4153.6 | 0 | 11.8 | 0 | 352 | 8.67 | 3052.896 | 0 | 0 | 0 | 352 | 352 | 4153.6 | 4153.6
1931 | C BLDG UPVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)Pressure Reducing Valve 1 1/2" | NOS | 11 | 3555.22 | 39107.42 | 11 | 3555.22 | 39107.42 | 0 | 3555.22 | 0 | 11 | 3838.84 | 42227.1905 | 0 | 0 | 0 | 11 | 11 | 39107.42 | 39107.42
1932 | C BLDG UPVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)Pressure Reducing Valve 1" | NOS | 33 | 2792.65 | 92157.45 | 33 | 2792.65 | 92157.45 | 0 | 2792.65 | 0 | 33 | 3035.4 | 100168.2792 | 0 | 0 | 0 | 33 | 33 | 92157.45 | 92157.45
1933 | C BLDG UPVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)UPVC Ball Valves 1 1/2" | NOS | 33 | 198.24 | 6541.92 | 33 | 198.24 | 6541.92 | 0 | 198.24 | 0 | 33 | 194.28 | 6411.0816 | 0 | 0 | 0 | 33 | 33 | 6541.92 | 6541.92
1934 | C BLDG UPVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)UPVC Ball Valves 1 1/4" | NOS | 132 | 140.76 | 18580.32 | 132 | 140.76 | 18580.32 | 0 | 140.76 | 0 | 132 | 137.94 | 18207.4464 | 0 | 0 | 0 | 132 | 132 | 18580.32 | 18580.32
1935 | C BLDG UPVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)UPVC Ball Valves 1" | NOS | 79 | 104.4 | 8247.6 | 79 | 104.4 | 8247.6 | 0 | 104.4 | 0 | 79 | 102.32 | 8083.1299 | 0 | 0 | 0 | 79 | 79 | 8247.6 | 8247.6
1936 | C BLDG UPVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)UPVC Ball Valves 1/2" | NOS | 381 | 44.24 | 16855.44 | 381 | 44.24 | 16855.44 | 0 | 44.24 | 0 | 381 | 51.16 | 19493.7888 | 0 | 0 | 0 | 381 | 381 | 16855.44 | 16855.44
1937 | C BLDG UPVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)UPVC Coupler 1 1/2" | NOS | 33 | 19.56 | 645.48 | 33 | 19.56 | 645.48 | 0 | 19.56 | 0 | 33 | 17.16 | 566.3097 | 0 | 0 | 0 | 33 | 33 | 645.48 | 645.48
1938 | C BLDG UPVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)UPVC Coupler 1 1/4" | NOS | 20 | 25.48 | 509.6 | 20 | 25.48 | 509.6 | 0 | 25.48 | 0 | 20 | 14.31 | 286.23 | 0 | 0 | 0 | 20 | 20 | 509.6 | 509.6
1939 | C BLDG UPVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)UPVC Elbow 1 1/4 (90 degree) | NOS | 264 | 23.61 | 6233.04 | 264 | 23.61 | 6233.04 | 0 | 23.61 | 0 | 264 | 20.72 | 5470.7664 | 0 | 0 | 0 | 264 | 264 | 6233.04 | 6233.04
1940 | C BLDG UPVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)UPVC Elbow 1" (90 degree) | NOS | 66 | 15.2 | 1003.2 | 66 | 15.2 | 1003.2 | 0 | 15.2 | 0 | 66 | 13.34 | 880.4466 | 0 | 0 | 0 | 66 | 66 | 1003.2 | 1003.2
1941 | C BLDG UPVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)UPVC Elbow 1/2" (90 degree) | NOS | 672 | 5.04 | 3386.88 | 672 | 5.04 | 3386.88 | 0 | 5.04 | 0 | 672 | 5.96 | 4003.5744 | 0 | 0 | 0 | 672 | 672 | 3386.88 | 3386.88
1942 | C BLDG UPVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)UPVC End Cap 3/4" | NOS | 66 | 23.6 | 1557.6 | 66 | 23.6 | 1557.6 | 0 | 23.6 | 0 | 66 | 4.57 | 301.3164 | 0 | 0 | 0 | 66 | 66 | 1557.6 | 1557.6
1943 | C BLDG UPVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)UPVC MTA Brass Thread 1 1/2" | NOS | 7 | 325.9 | 2281.3 | 7 | 325.9 | 2281.3 | 0 | 325.9 | 0 | 7 | 226.46 | 1585.2298 | 0 | 0 | 0 | 7 | 7 | 2281.3 | 2281.3
1944 | C BLDG UPVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)UPVC MTA Brass Thread 1'' | NOS | 46 | 41.3 | 1899.8 | 46 | 41.3 | 1899.8 | 0 | 41.3 | 0 | 46 | 99.57 | 4580.0498 | 0 | 0 | 0 | 46 | 46 | 1899.8 | 1899.8
1945 | C BLDG UPVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)UPVC Pipe 1 1/2" X 3m long (SCH-40) | NOS | 99 | 236 | 23364 | 99 | 236 | 23364 | 0 | 236 | 0 | 99 | 314.14 | 31100.1669 | 0 | 0 | 0 | 99 | 99 | 23364 | 23364
1946 | C BLDG UPVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)UPVC Pipe 1 1/4 X 3m long (SCH-40) | NOS | 198 | 465.33 | 92135.34 | 198 | 465.33 | 92135.34 | 0 | 465.33 | 0 | 198 | 263.63 | 52198.9974 | 0 | 0 | 0 | 198 | 198 | 92135.34 | 92135.34
1947 | C BLDG UPVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)UPVC Pipe 1" X 3m long (SCH-40) | NOS | 182 | 177 | 32214 | 182 | 177 | 32214 | 0 | 177 | 0 | 182 | 196.12 | 35693.9674 | 0 | 0 | 0 | 182 | 182 | 32214 | 32214
1948 | C BLDG UPVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)UPVC Pipe 1/2" X 3m long (SCH-40) | NOS | 82 | 84.17 | 6901.94 | 82 | 84.17 | 6901.94 | 0 | 84.17 | 0 | 82 | 100.44 | 8236.1128 | 0 | 0 | 0 | 82 | 82 | 6901.94 | 6901.94
1949 | C BLDG UPVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)UPVC Pipe 2" X 3m long (SCH-40) | NOS | 78 | 485.88 | 37898.64 | 78 | 485.88 | 37898.64 | 0 | 485.88 | 0 | 78 | 422.06 | 32920.9062 | 0 | 0 | 0 | 78 | 78 | 37898.64 | 37898.64
1950 | C BLDG UPVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)UPVC Pipe 3/4" X 3m long (SCH-40) | NOS | 160 | 147.5 | 23600 | 160 | 147.5 | 23600 | 0 | 147.5 | 0 | 160 | 133.86 | 21416.88 | 0 | 0 | 0 | 160 | 160 | 23600 | 23600
1951 | C BLDG UPVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)UPVC Reducer Coupling 1 1/2" x 1 1/4" | NOS | 13 | 20.48 | 266.24 | 13 | 20.48 | 266.24 | 0 | 20.48 | 0 | 13 | 17.97 | 233.6191 | 0 | 0 | 0 | 13 | 13 | 266.24 | 266.24
1952 | C BLDG UPVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)UPVC Reducer Coupling 1 1/4" x 1" | NOS | 33 | 35.4 | 1168.2 | 33 | 35.4 | 1168.2 | 0 | 35.4 | 0 | 33 | 13.57 | 447.7077 | 0 | 0 | 0 | 33 | 33 | 1168.2 | 1168.2
1953 | C BLDG UPVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)UPVC Reducer Coupling 1" x 3/4" | NOS | 23 | 31.86 | 732.78 | 23 | 31.86 | 732.78 | 0 | 31.86 | 0 | 23 | 8.48 | 195.109 | 0 | 0 | 0 | 23 | 23 | 732.78 | 732.78
1954 | C BLDG UPVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)UPVC Reducer Coupling 2" x 1 1/2" | NOS | 11 | 41.3 | 454.3 | 11 | 41.3 | 454.3 | 0 | 41.3 | 0 | 11 | 27.26 | 299.8897 | 0 | 0 | 0 | 11 | 11 | 454.3 | 454.3
1955 | C BLDG UPVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)UPVC Reducer Tee 1 1/2" x 1 1/4" | NOS | 8 | 200.6 | 1604.8 | 8 | 200.6 | 1604.8 | 0 | 200.6 | 0 | 8 | 38.89 | 311.1 | 0 | 0 | 0 | 8 | 8 | 1604.8 | 1604.8
1956 | C BLDG UPVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)UPVC Reducer Tee 1 1/2" x 1/2" | NOS | 11 | 38 | 418 | 11 | 38 | 418 | 0 | 38 | 0 | 11 | 37.4 | 411.3901 | 0 | 0 | 0 | 11 | 11 | 418 | 418
1957 | C BLDG UPVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)UPVC Reducer Tee 1 1/4" x 1/2" | NOS | 74 | 50 | 3700 | 74 | 50 | 3700 | 0 | 50 | 0 | 74 | 28.04 | 2074.9748 | 0 | 0 | 0 | 74 | 74 | 3700 | 3700
1958 | C BLDG UPVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)UPVC Reducer Tee 1" x 1/2" | NOS | 133 | 30 | 3990 | 133 | 30 | 3990 | 0 | 30 | 0 | 133 | 17.06 | 2269.4987 | 0 | 0 | 0 | 133 | 133 | 3990 | 3990
1959 | C BLDG UPVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)UPVC Reducer Tee 2" x 1 1/4" | NOS | 25 | 46 | 1150 | 25 | 46 | 1150 | 0 | 46 | 0 | 25 | 55.5 | 1387.44 | 0 | 0 | 0 | 25 | 25 | 1150 | 1150
1960 | C BLDG UPVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)UPVC Reducer Tee 3/4" x 1/2" | NOS | 132 | 17.7 | 2336.4 | 132 | 17.7 | 2336.4 | 0 | 17.7 | 0 | 132 | 11.59 | 1530.0912 | 0 | 0 | 0 | 132 | 132 | 2336.4 | 2336.4
1961 | C BLDG UPVC DOWNTAKE 1ST TO 12TH FLOOR | 0 | Tentative | Material | (M)UPVC Tee 1" | NOS | 21 | 28.32 | 594.72 | 21 | 28.32 | 594.72 | 0 | 28.32 | 0 | 21 | 18.52 | 388.9305 | 0 | 0 | 0 | 21 | 21 | 594.72 | 594.72
1962 | INDENT-855/C BLDG/PLUMBING/INTERNAL CONCEALED | 0 | Started | Material | (M)Chair Bracket with nut bolt & wishor | NOS | 132 | 590 | 77880 | 132 | 590 | 77880 | 0 | 590 | 0 | 132 | 638.28 | 84252.96 | 0 | 0 | 0 | 132 | 132 | 77880 | 77880
1963 | INDENT-855/C BLDG/PLUMBING/INTERNAL CONCEALED | 0 | Started | Material | (M)CP Flush Valve 32mm (1085-N) | NOS | 132 | 3599 | 475068 | 132 | 3599 | 475068 | 0 | 3599 | 0 | 132 | 2808 | 370655.8416 | 0 | 0 | 0 | 132 | 132 | 475068 | 475068
1964 | INDENT-855/C BLDG/PLUMBING/INTERNAL CONCEALED | 0 | Started | Material | (M)CPVC Adhesives / Solvent - 237ml | NOS | 132 | 413 | 54516 | 132 | 413 | 54516 | 0 | 413 | 0 | 132 | 324.48 | 42831.096 | 0 | 0 | 0 | 132 | 132 | 54516 | 54516
1965 | INDENT-855/C BLDG/PLUMBING/INTERNAL CONCEALED | 0 | Started | Material | (M)CPVC Brass Elbow 1/2" | NOS | 1716 | 35.4 | 60746.4 | 1716 | 35.4 | 60746.4 | 0 | 35.4 | 0 | 1716 | 38.67 | 66353.6016 | 0 | 0 | 0 | 1716 | 1716 | 60746.4 | 60746.4
1966 | INDENT-855/C BLDG/PLUMBING/INTERNAL CONCEALED | 0 | Started | Material | (M)CPVC CONSEALED STOP COCK-1/2'' (ALD-CHR-083) | NOS | 132 | 2065 | 272580 | 132 | 2065 | 272580 | 0 | 2065 | 0 | 132 | 678.59 | 89574.3024 | 0 | 0 | 0 | 132 | 132 | 272580 | 272580
1967 | INDENT-855/C BLDG/PLUMBING/INTERNAL CONCEALED | 0 | Started | Material | (M)CPVC Elbow 1/2 (90 degree) | NOS | 1504 | 35.4 | 53241.6 | 1504 | 35.4 | 53241.6 | 0 | 35.4 | 0 | 1504 | 7.94 | 11943.5648 | 0 | 0 | 0 | 1504 | 1504 | 53241.6 | 53241.6
1968 | INDENT-855/C BLDG/PLUMBING/INTERNAL CONCEALED | 0 | Started | Material | (M)CPVC End Cap 1/2" | NOS | 528 | 5.9 | 3115.2 | 528 | 5.9 | 3115.2 | 0 | 5.9 | 0 | 528 | 4.68 | 2468.6112 | 0 | 0 | 0 | 528 | 528 | 3115.2 | 3115.2
1969 | INDENT-855/C BLDG/PLUMBING/INTERNAL CONCEALED | 0 | Started | Material | (M)CPVC End Plug Threaded 1/2'' (Long) | NOS | 1716 | 11.8 | 20248.8 | 1716 | 11.8 | 20248.8 | 0 | 11.8 | 0 | 1716 | 6.96 | 11943.36 | 0 | 0 | 0 | 1716 | 1716 | 20248.8 | 20248.8
1970 | INDENT-855/C BLDG/PLUMBING/INTERNAL CONCEALED | 0 | Started | Material | (M)CPVC Pipe 1/2 X 3m long (SDR-11) | NOS | 660 | 531 | 350460 | 660 | 531 | 350460 | 0 | 531 | 0 | 660 | 132.93 | 87731.952 | 0 | 0 | 0 | 660 | 660 | 350460 | 350460
1971 | INDENT-855/C BLDG/PLUMBING/INTERNAL CONCEALED | 0 | Started | Material | (M)CPVC Step Over Bend 1/2" | NOS | 132 | 35.4 | 4672.8 | 132 | 35.4 | 4672.8 | 0 | 35.4 | 0 | 132 | 30.23 | 3990.2148 | 0 | 0 | 0 | 132 | 132 | 4672.8 | 4672.8
1972 | INDENT-855/C BLDG/PLUMBING/INTERNAL CONCEALED | 0 | Started | Material | (M)CPVC Tee 1/2" | NOS | 924 | 17.7 | 16354.8 | 924 | 17.7 | 16354.8 | 0 | 17.7 | 0 | 924 | 10.98 | 10148.1072 | 0 | 0 | 0 | 924 | 924 | 16354.8 | 16354.8
1973 | INDENT-855/C BLDG/PLUMBING/INTERNAL CONCEALED | 0 | Started | Material | (M)UPVC Elbow 1 1/4 (90 degree) | NOS | 264 | 23.61 | 6233.04 | 264 | 23.61 | 6233.04 | 0 | 23.61 | 0 | 264 | 20.62 | 5443.3104 | 0 | 0 | 0 | 264 | 264 | 6233.04 | 6233.04
1974 | INDENT-855/C BLDG/PLUMBING/INTERNAL CONCEALED | 0 | Started | Material | (M)UPVC End Cap 1 1/4" | NOS | 132 | 29.5 | 3894 | 132 | 29.5 | 3894 | 0 | 29.5 | 0 | 132 | 10.95 | 1445.0568 | 0 | 0 | 0 | 132 | 132 | 3894 | 3894
1975 | INDENT-855/C BLDG/PLUMBING/INTERNAL CONCEALED | 0 | Started | Material | (M)UPVC FTA Brass Thread 1 1/4 | NOS | 132 | 236 | 31152 | 132 | 236 | 31152 | 0 | 236 | 0 | 132 | 132.43 | 17480.7336 | 0 | 0 | 0 | 132 | 132 | 31152 | 31152
1976 | INDENT-855/C BLDG/PLUMBING/INTERNAL CONCEALED | 0 | Started | Material | (M)UPVC MTA Brass Thread 1 1/4 | NOS | 132 | 315.71 | 41673.72 | 132 | 315.71 | 41673.72 | 0 | 315.71 | 0 | 132 | 176.33 | 23275.4544 | 0 | 0 | 0 | 132 | 132 | 41673.72 | 41673.72
1977 | INDENT-855/C BLDG/PLUMBING/INTERNAL CONCEALED | 0 | Started | Material | (M)UPVC Pipe 1 1/4 X 3m long (SCH-40) | NOS | 67 | 465.33 | 31177.11 | 67 | 465.33 | 31177.11 | 0 | 465.33 | 0 | 67 | 259.25 | 17369.7567 | 0 | 0 | 0 | 67 | 67 | 31177.11 | 31177.11
1978 | INDENT-855/C BLDG/PLUMBING/INTERNAL CONCEALED | 0 | Started | Material | (M)Upvc Solvent 237ml | NOS | 132 | 143.72 | 18971.04 | 132 | 143.72 | 18971.04 | 0 | 143.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132 | 132 | 18971.04 | 18971.04
1979 | INDENT-854/C BLDG/INTERNAL CONCEALED WORK | 0 | Started | Material | (M)GI C-Bracket 6" x 2" | NOS | 72 | 43.81 | 3154.32 | 72 | 43.81 | 3154.32 | 0 | 43.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 72 | 3154.32 | 3154.32 | Building
1980 | INDENT-854/C BLDG/INTERNAL CONCEALED WORK | 0 | Started | Material | (M)GI U Clamp with Nut Bolt & Washer 3" | NOS | 72 | 17.7 | 1274.4 | 72 | 17.7 | 1274.4 | 0 | 17.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 72 | 1274.4 | 1274.4 | Building
1981 | INDENT-854/C BLDG/INTERNAL CONCEALED WORK | 0 | Started | Material | (M)PVC BUSHING 50mm x 40 mm | NOS | 264 | 11.83 | 3123.12 | 264 | 11.83 | 3123.12 | 0 | 11.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 264 | 264 | 3123.12 | 3123.12 | Building
1982 | INDENT-854/C BLDG/INTERNAL CONCEALED WORK | 0 | Started | Material | (M)PVC Elbow 40 mm | NOS | 528 | 70.8 | 37382.4 | 528 | 70.8 | 37382.4 | 0 | 70.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 528 | 528 | 37382.4 | 37382.4 | Building
1983 | INDENT-854/C BLDG/INTERNAL CONCEALED WORK | 0 | Started | Material | (M)PVC End Cap 40mm | NOS | 264 | 7.44 | 1964.16 | 264 | 7.44 | 1964.16 | 0 | 7.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 264 | 264 | 1964.16 | 1964.16 | Building
1984 | INDENT-854/C BLDG/INTERNAL CONCEALED WORK | 0 | Started | Material | (M)PVC Equal Tee 40 mm | NOS | 132 | 17.98 | 2373.36 | 132 | 17.98 | 2373.36 | 0 | 17.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132 | 132 | 2373.36 | 2373.36 | Building
1985 | INDENT-854/C BLDG/INTERNAL CONCEALED WORK | 0 | Started | Material | (M)PVC Gray Pipes S/F 10ft long 40 mm (4Kg/Sqcm) | NOS | 132 | 281.81 | 37198.92 | 132 | 281.81 | 37198.92 | 0 | 281.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132 | 132 | 37198.92 | 37198.92 | Building
1986 | INDENT-854/C BLDG/INTERNAL CONCEALED WORK | 0 | Started | Material | (M)PVC Nahani Trap 75 mm | NOS | 156 | 66.49 | 10372.44 | 156 | 66.49 | 10372.44 | 0 | 66.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 156 | 156 | 10372.44 | 10372.44 | Building
1987 | INDENT-854/C BLDG/INTERNAL CONCEALED WORK | 0 | Started | Material | (M)PVC Shoe 40 mm | NOS | 396 | 17.81 | 7052.76 | 396 | 17.81 | 7052.76 | 0 | 17.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 396 | 396 | 7052.76 | 7052.76 | Building
1988 | INDENT-854/C BLDG/INTERNAL CONCEALED WORK | 0 | Started | Material | (M)PVC Solution 237ml | NOS | 132 | 176.29 | 23270.28 | 132 | 176.29 | 23270.28 | 0 | 176.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132 | 132 | 23270.28 | 23270.28 | Building
1989 | INDENT-854/C BLDG/INTERNAL CONCEALED WORK | 0 | Started | Material | (M)SWR Multi Floor Trap 4" Height 110 mm | NOS | 132 | 105.17 | 13882.44 | 132 | 105.17 | 13882.44 | 0 | 105.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132 | 132 | 13882.44 | 13882.44 | Building
1990 | INDENT-854/C BLDG/INTERNAL CONCEALED WORK | 0 | Started | Material | (M)SWR Pipes 'B' type R/F 10ft long S/S 75mm | NOS | 24 | 417.93 | 10030.32 | 24 | 417.93 | 10030.32 | 0 | 417.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 10030.32 | 10030.32 | Building
1991 | INDENT-854/C BLDG/INTERNAL CONCEALED WORK | 0 | Started | Material | (M)SWR Pipes 'B' type R/F 3ft long D/S 110mm | NOS | 67 | 234.77 | 15729.59 | 67 | 234.77 | 15729.59 | 0 | 234.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 67 | 15729.59 | 15729.59 | Building
1992 | INDENT-854/C BLDG/INTERNAL CONCEALED WORK | 0 | Started | Material | (M)SWR Pipes 'B' type R/F 3ft long D/S 75mm | NOS | 132 | 147.24 | 19435.68 | 132 | 147.24 | 19435.68 | 0 | 147.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 132 | 132 | 19435.68 | 19435.68 | Building
1993 | INDENT-854/C BLDG/INTERNAL CONCEALED WORK | 0 | Started | Material | (M)SWR Plain Tee 75 mm | NOS | 24 | 59.03 | 1416.72 | 24 | 59.03 | 1416.72 | 0 | 59.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 1416.72 | 1416.72 | Building
1994 | INTERNAL CONCEALED C WING OUTLET PLUMBING WORK | 0 | Started | Material | (M)CPVC Brass Elbow 1/2" | NOS | 2 | 35.4 | 70.8 | 2 | 35.4 | 70.8 | 0 | 35.4 | 0 | 2 | 43.46 | 86.92 | 0 | 0 | 0 | 2 | 2 | 70.8 | 70.8
1995 | INTERNAL CONCEALED C WING OUTLET PLUMBING WORK | 0 | Started | Material | (M)CPVC Coupling 1/2" | NOS | 2 | 11.8 | 23.6 | 2 | 11.8 | 23.6 | 0 | 11.8 | 0 | 2 | 6.7 | 13.4 | 0 | 0 | 0 | 2 | 2 | 23.6 | 23.6
1996 | INTERNAL CONCEALED C WING OUTLET PLUMBING WORK | 0 | Started | Material | (M)CPVC Elbow 1/2 (90 degree) | NOS | 6 | 35.4 | 212.4 | 6 | 35.4 | 212.4 | 0 | 35.4 | 0 | 6 | 8.99 | 53.9598 | 0 | 0 | 0 | 6 | 6 | 212.4 | 212.4
1997 | INTERNAL CONCEALED C WING OUTLET PLUMBING WORK | 0 | Started | Material | (M)CPVC Pipe 1/2 X 3m long (SDR-11) | NOS | 4 | 531 | 2124 | 4 | 531 | 2124 | 0 | 531 | 0 | 4 | 149.52 | 598.08 | 0 | 0 | 0 | 4 | 4 | 2124 | 2124
1998 | INTERNAL CONCEALED C WING OUTLET PLUMBING WORK | 0 | Started | Material | (M)PVC Equal Tee 40 mm | NOS | 30 | 17.98 | 539.4 | 30 | 17.98 | 539.4 | 0 | 17.98 | 0 | 30 | 24.34 | 730.239 | 0 | 0 | 0 | 30 | 30 | 539.4 | 539.4
1999 | INTERNAL CONCEALED C WING OUTLET PLUMBING WORK | 0 | Started | Material | (M)PVC Reducer Bush 40 x 50 mm | NOS | 60 | 23.6 | 1416 | 60 | 23.6 | 1416 | 0 | 23.6 | 0 | 60 | 12.94 | 776.22 | 0 | 0 | 0 | 60 | 60 | 1416 | 1416
2000 | INTERNAL CONCEALED C WING OUTLET PLUMBING WORK | 0 | Started | Material | (M)PVC Shoe 40 mm | NOS | 90 | 17.81 | 1602.9 | 90 | 17.81 | 1602.9 | 0 | 17.81 | 0 | 90 | 20.11 | 1809.495 | 0 | 0 | 0 | 90 | 90 | 1602.9 | 1602.9
2001 | INTERNAL CONCEALED C WING OUTLET PLUMBING WORK | 0 | Started | Material | (M)SWR Pipes 'B' type R/F 3ft long D/S 75mm | NOS | 120 | 147.24 | 17668.8 | 120 | 147.24 | 17668.8 | 0 | 147.24 | 0 | 120 | 167.59 | 20110.8 | 0 | 0 | 0 | 120 | 120 | 17668.8 | 17668.8
2002 | INTERNAL CONCEALED C WING OUTLET PLUMBING WORK | 0 | Started | Material | (M)SWR Shoe 75 mm | NOS | 180 | 70.8 | 12744 | 180 | 70.8 | 12744 | 0 | 70.8 | 0 | 180 | 43.72 | 7869.6 | 0 | 0 | 0 | 180 | 180 | 12744 | 12744
2003 | INTERNAL CONCEALED C WING OUTLET PLUMBING WORK | 0 | Started | Material | (M)Teflon Tape | NOS | 200 | 19.48 | 3896 | 200 | 19.48 | 3896 | 0 | 19.48 | 0 | 200 | 20.04 | 4008 | 0 | 0 | 0 | 200 | 200 | 3896 | 3896
2004 | INTERNAL CONCEALED C WING OUTLET PLUMBING WORK | 0 | Started | Material | (M)UPVC Coupler 1 1/4" | NOS | 3 | 25.48 | 76.44 | 3 | 25.48 | 76.44 | 0 | 25.48 | 0 | 3 | 16.32 | 48.96 | 0 | 0 | 0 | 3 | 3 | 76.44 | 76.44
2005 | INTERNAL CONCEALED C WING OUTLET PLUMBING WORK | 0 | Started | Material | (M)UPVC Elbow 1 1/4 (90 degree) | NOS | 4 | 23.61 | 94.44 | 4 | 23.61 | 94.44 | 0 | 23.61 | 0 | 4 | 23.68 | 94.72 | 0 | 0 | 0 | 4 | 4 | 94.44 | 94.44
2006 | INTERNAL CONCEALED C WING OUTLET PLUMBING WORK | 0 | Started | Material | (M)UPVC Pipe 1 1/4 X 3m long (SCH-40) | NOS | 4 | 465.33 | 1861.32 | 4 | 465.33 | 1861.32 | 0 | 465.33 | 0 | 4 | 300.89 | 1203.56 | 0 | 0 | 0 | 4 | 4 | 1861.32 | 1861.32
2007 | INTERNAL CONCEALED C WING OUTLET PLUMBING WORK | 0 | Started | Material | (M)UPVC SHOE 1 1/4" | NOS | 4 | 17.94 | 71.76 | 4 | 17.94 | 71.76 | 0 | 17.94 | 0 | 4 | 21.53 | 86.12 | 0 | 0 | 0 | 4 | 4 | 71.76 | 71.76
2008 | C Bldg: Toilet & Bathroom-Shop Concealed Work | 0 | Tentative | Labour | (L)Internal Concealed Work | NOS | 16344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16344 | 1 | 16344 | 0 | 0 | 0 | 16344 | 16344 | 0 | 0
2009 | C Bldg: Toilet & Bathroom-Office Concealed Work | 0 | Tentative | Labour | (L)Internal Concealed Work | NOS | 32688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32688 | 1 | 32688 | 0 | 0 | 0 | 32688 | 32688 | 0 | 0
2010 | C Bldg: Toilet & Bathroom-1,2,3,4 Floor Conc. Work | 0 | Started | Labour | (L)Internal Concealed Work | NOS | 88256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88256 | 1 | 88256 | 88256 | 1 | 88256 | 88256 | 0 | 0 | -88256
2011 | C Bldg: Toilet & Bathroom-5,6,7,8 Floor Conc. Work | 0 | Started | Labour | (L)Internal Concealed Work | NOS | 88256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88256 | 1 | 88256 | 88256 | 1 | 88256 | 88256 | 0 | 0 | -88256
2012 | C Bldg: Toilet & Bathroom-9,10,11,12 Floor Conc. Work | 0 | Started | Labour | (L)Internal Concealed Work | NOS | 101331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101331 | 1 | 101331 | 101331 | 1 | 101331 | 101331 | 0 | 0 | -101331
2013 | C Bldg: Pressure Testing & Levelling up to 12th | 0 | Started | Labour | (L)Internal Concealed Work | NOS | 26150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26150 | 1 | 26150 | 26150 | 1 | 26150 | 26150 | 0 | 0 | -26150
2014 | C Bldg: Kitchen Plumbing upto 12th Floor | 0 | Started | Labour | (L)Internal Concealed Work | NOS | 104600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 104600 | 1 | 104600 | 52300 | 1 | 52300 | 104600 | 52300 | 0 | -52300
2015 | C Bldg: P-Trap, N-Trap & Outlet Shop at LGF | 0 | Tentative | Labour | (L)Internal Concealed Work | NOS | 4707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4707 | 1 | 4707 | 0 | 0 | 0 | 4707 | 4707 | 0 | 0
2016 | C Bldg: P-Trap, N-Trap & Outlet Office at UGF | 0 | Tentative | Labour | (L)Internal Concealed Work | NOS | 9414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9414 | 1 | 9414 | 0 | 0 | 0 | 9414 | 9414 | 0 | 0
2017 | C Bldg: P-Trap, N-Trap & Outlet upto 4th Floor | 0 | Started | Labour | (L)Internal Concealed Work | NOS | 32949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32949 | 1 | 32949 | 32949 | 1 | 32949 | 32949 | 0 | 0 | -32949
2018 | C Bldg: P-Trap, N-Trap & Outlet upto 8th Floor | 0 | Started | Labour | (L)Internal Concealed Work | NOS | 32949 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32949 | 1 | 32949 | 32949 | 1 | 32949 | 32949 | 0 | 0 | -32949
2019 | C Bldg: P-Trap, N-Trap & Outlet upto 12th Floor | 0 | Tentative | Labour | (L)Internal Concealed Work | NOS | 37656 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37656 | 1 | 37656 | 0 | 0 | 0 | 37656 | 37656 | 0 | 0
2020 | C Bldg: Shop & Office PVC,UPVC Lines | 0 | Tentative | Labour | (L)External Plumbing Work | NOS | 18828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18828 | 1 | 18828 | 0 | 0 | 0 | 18828 | 18828 | 0 | 0
2021 | C Bldg: PVC line for duct F-1,2,3 upto 12th | 0 | Tentative | Labour | (L)External Plumbing Work | NOS | 31380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31380 | 1 | 31380 | 0 | 0 | 0 | 31380 | 31380 | 0 | 0
2022 | C Bldg: PVC line for duct F-4,5,6 upto 12th | 0 | Tentative | Labour | (L)External Plumbing Work | NOS | 31380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31380 | 1 | 31380 | 0 | 0 | 0 | 31380 | 31380 | 0 | 0
2023 | C Bldg: PVC line for duct F-7,8,9 upto 12th | 0 | Tentative | Labour | (L)External Plumbing Work | NOS | 31380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31380 | 1 | 31380 | 0 | 0 | 0 | 31380 | 31380 | 0 | 0
2024 | C Bldg: PVC line for duct F-10,11 upto 12th | 0 | Tentative | Labour | (L)External Plumbing Work | NOS | 21966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21966 | 1 | 21966 | 0 | 0 | 0 | 21966 | 21966 | 0 | 0
2025 | C Bldg: UPVC line for duct F-1,2,3 upto 12th | 0 | Tentative | Labour | (L)External Plumbing Work | NOS | 31380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31380 | 1 | 31380 | 0 | 0 | 0 | 31380 | 31380 | 0 | 0
2026 | C Bldg: UPVC line for duct F-4,5,6 upto 12th | 0 | Tentative | Labour | (L)External Plumbing Work | NOS | 31380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31380 | 1 | 31380 | 0 | 0 | 0 | 31380 | 31380 | 0 | 0
2027 | C Bldg: UPVC line for duct F-7,8,9 upto 12th | 0 | Tentative | Labour | (L)External Plumbing Work | NOS | 31380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31380 | 1 | 31380 | 0 | 0 | 0 | 31380 | 31380 | 0 | 0
2028 | C Bldg: UPVC line for duct F-10,11 upto 12th | 0 | Tentative | Labour | (L)External Plumbing Work | NOS | 21966 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21966 | 1 | 21966 | 0 | 0 | 0 | 21966 | 21966 | 0 | 0
2029 | C Bldg: Kit. line PVC,UPVC F-1,2,3 upto 12th | 0 | Tentative | Labour | (L)External Plumbing Work | NOS | 15690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15690 | 1 | 15690 | 0 | 0 | 0 | 15690 | 15690 | 0 | 0
2030 | C Bldg: Kit. line PVC,UPVC F-4,5,6 upto 12th | 0 | Tentative | Labour | (L)External Plumbing Work | NOS | 15690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15690 | 1 | 15690 | 0 | 0 | 0 | 15690 | 15690 | 0 | 0
2031 | C Bldg: Kit. line PVC,UPVC F-7,8,9 upto 12th | 0 | Tentative | Labour | (L)External Plumbing Work | NOS | 15690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15690 | 1 | 15690 | 0 | 0 | 0 | 15690 | 15690 | 0 | 0
2032 | C Bldg: Kit. line PVC,UPVC F-10,11 upto 12th | 0 | Tentative | Labour | (L)External Plumbing Work | NOS | 10983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10983 | 1 | 10983 | 0 | 0 | 0 | 10983 | 10983 | 0 | 0
2033 | C Bldg: Terr. line F-04 upto12th Floor | 0 | Tentative | Labour | (L)External Plumbing Work | NOS | 4707 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4707 | 1 | 4707 | 0 | 0 | 0 | 4707 | 4707 | 0 | 0
2034 | C Bldg: "Looping" Top Terr-100% Comp. | 0 | Tentative | Labour | (L)External Plumbing Work | NOS | 39225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39225 | 1 | 39225 | 0 | 0 | 0 | 39225 | 39225 | 0 | 0
2035 | C Bldg: All Sanitry Fitting upto 12th floor | 0 | Started | Labour | (L)Sanitry Work | NOS | 130750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130750 | 1 | 130750 | 19612 | 1 | 19612 | 130750 | 111138 | 0 | -19612
2036 | C Bldg: All CP Fitting upto 12th floor | 0 | Started | Labour | (L)CP WORK | NOS | 130750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130750 | 1 | 130750 | 19612 | 1 | 19612 | 130750 | 111138 | 0 | -19612
2037 | C Bldg: CP- Testing upto 12th Floor | 0 | Tentative | Labour | (L)CP WORK | NOS | 13075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13075 | 1 | 13075 | 0 | 0 | 0 | 13075 | 13075 | 0 | 0
2038 | C Bldg: "Parking" Drainage Line-100% Comp. | 0 | Tentative | Labour | (L)External Plumbing Work | NOS | 39225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39225 | 1 | 39225 | 0 | 0 | 0 | 39225 | 39225 | 0 | 0
2039 | C Bldg: "Retention" after comp. of work | 0 | Tentative | Labour | (L)Retention (Plumbing) | NOS | 65375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65375 | 1 | 65375 | 0 | 0 | 0 | 65375 | 65375 | 0 | 0
2040 | C BLDG OHWT SLEEVES-OUTLET,DRAIN & OVERFLOW | 0 | Tentative | Material | (M)GI SLEEVE ONE SIDE THREAD (OD -100MM, L-450MM) | NOS | 2 | 944 | 1888 | 2 | 944 | 1888 | 0 | 944 | 0 | 2 | 918.92 | 1837.84 | 0 | 0 | 0 | 2 | 2 | 1888 | 1888
2041 | C BLDG OHWT SLEEVES-OUTLET,DRAIN & OVERFLOW | 0 | Tentative | Material | (M)GI SLEEVE ONE SIDE THREAD (OD -65MM, L-450MM) | NOS | 11 | 708 | 7788 | 11 | 708 | 7788 | 0 | 708 | 0 | 11 | 513.07 | 5643.77 | 0 | 0 | 0 | 11 | 11 | 7788 | 7788
2042 | C BLDG OHWT SLEEVES-OUTLET,DRAIN & OVERFLOW | 0 | Tentative | Material | (M)GI SLEEVE ONE SIDE THREAD (OD -80MM, L-450MM) | NOS | 6 | 826 | 4956 | 6 | 826 | 4956 | 0 | 826 | 0 | 6 | 611.85 | 3671.1198 | 0 | 0 | 0 | 6 | 6 | 4956 | 4956
2043 | C BLDG OHWT SLEEVES-OUTLET,DRAIN & OVERFLOW | 0 | Tentative | Material | (M)SWR Pipes 'B' type S/F 10ft long S/S 160mm | NOS | 3 | 944 | 2832 | 2 | 944 | 1888 | 0 | 944 | 0 | 2 | 680.24 | 1360.48 | 0 | 0 | 0 | 3 | 3 | 2832 | 2832
2044 | C BLDG OHWT SLEEVES-OUTLET,DRAIN & OVERFLOW | 0 | Tentative | Material | (M)SWR Plain Bend 160 mm | NOS | 2 | 177 | 354 | 0 | 0 | 0 | 0 | 177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 354 | 354
2045 | C BLDG: MONOBLOCK PUMP SET FOR UGF TANK WATER RAISING | 0 | Tentative | Material | (M)1.5 Sqmm 3 Core Polycab Copper Flexible Cable | RMT | 50 | 41.3 | 2065 | 0 | 0 | 0 | 0 | 41.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 2065 | 2065
2046 | C BLDG: MONOBLOCK PUMP SET FOR UGF TANK WATER RAISING | 0 | Tentative | Material | (M)Curing Pipe 3/4" 30mtr Nylon Braided | NOS | 2 | 1947 | 3894 | 0 | 0 | 0 | 0 | 1947 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 3894 | 3894
2047 | C BLDG: MONOBLOCK PUMP SET FOR UGF TANK WATER RAISING | 0 | Tentative | Material | (M)Monoblock Pump 1 HP with foot valve | SET | 1 | 5900 | 5900 | 0 | 0 | 0 | 0 | 5900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 5900 | 5900
2048 | C BLDG: MONOBLOCK PUMP SET FOR UGF TANK WATER RAISING | 0 | Tentative | Material | (M)Water Tank 2000ltr Plasto | NOS | 1 | 11800 | 11800 | 0 | 0 | 0 | 0 | 11800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 11800 | 11800
2049 | FIRE EXIT DOOR C WING FIRE EXIT DOOR (INDENT-976) | 10 | Started | Material | (M)FIRE EXIT DOOR (1.5 M X 2.2 5M) | SET | 1 | 4500 | 4500 | 1 | 4500 | 4500 | 0 | 4500 | 0 | 1 | 16520 | 16520 | 0 | 0 | 0 | 1 | 1 | 4500 | 4500
2050 | 1 Loop Addressable Fire Alarm Control Panel [MONITIX] | 0 | Started | Labour | (L)Fire Detection System-Installation Charge | NOS | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1416 | 1416 | 1 | 1416 | 1416 | 1 | 0 | 1 | -1415
2051 | 1 Loop Addressable Fire Alarm Control Panel [MONITIX] | 0 | Started | Labour | (L)Fire Detection System-Supply Charge | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 32568 | 32568 | 1 | 32568 | 32568 | 1 | 0 | 1.18 | -32566.82
2052 | Addressable Smoke Detector | 0 | Started | Labour | (L)Fire Detection System-Installation Charge | NOS | 60 | 1 | 60 | 0 | 0 | 0 | 0 | 1 | 0 | 60 | 254.88 | 15292.8 | 60 | 254.88 | 15292.8 | 60 | 0 | 60 | -15232.8
2053 | Addressable Smoke Detector | 0 | Started | Labour | (L)Fire Detection System-Supply Charge | NOS | 60 | 1.18 | 70.8 | 0 | 0 | 0 | 0 | 1.18 | 0 | 60 | 1628.4 | 97704 | 60 | 1628.4 | 97704 | 60 | 0 | 70.8 | -97633.2
2054 | Addressable Manual Call Point | 0 | Started | Labour | (L)Fire Detection System-Installation Charge | NOS | 4 | 1 | 4 | 0 | 0 | 0 | 0 | 1 | 0 | 4 | 254.88 | 1019.52 | 4 | 254.88 | 1019.52 | 4 | 0 | 4 | -1015.52
2055 | Addressable Manual Call Point | 0 | Started | Labour | (L)Fire Detection System-Supply Charge | NOS | 4 | 1.18 | 4.72 | 0 | 0 | 0 | 0 | 1.18 | 0 | 4 | 1960.87 | 7843.46 | 4 | 1960.87 | 7843.46 | 4 | 0 | 4.72 | -7838.74
2056 | Sounder | 0 | Started | Labour | (L)Fire Detection System-Installation Charge | NOS | 4 | 1 | 4 | 0 | 0 | 0 | 0 | 1 | 0 | 4 | 254.88 | 1019.52 | 4 | 254.88 | 1019.52 | 4 | 0 | 4 | -1015.52
2057 | Sounder | 0 | Started | Labour | (L)Fire Detection System-Supply Charge | NOS | 4 | 1.18 | 4.72 | 0 | 0 | 0 | 0 | 1.18 | 0 | 4 | 2150.85 | 8603.38 | 4 | 2150.85 | 8603.38 | 4 | 0 | 4.72 | -8598.66
2058 | Addressable Moniter Module | 0 | Started | Labour | (L)Fire Detection System-Installation Charge | NOS | 2 | 1 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 254.88 | 509.76 | 0 | 0 | 0 | 2 | 2 | 2 | 2
2059 | Addressable Moniter Module | 0 | Started | Labour | (L)Fire Detection System-Supply Charge | NOS | 2 | 1.18 | 2.36 | 0 | 0 | 0 | 0 | 1.18 | 0 | 2 | 2340.83 | 4681.66 | 0 | 0 | 0 | 2 | 2 | 2.36 | 2.36
2060 | Fault Isolator Module | 0 | Started | Labour | (L)Fire Detection System-Installation Charge | NOS | 3 | 1 | 3 | 0 | 0 | 0 | 0 | 1 | 0 | 3 | 254.88 | 764.64 | 3 | 254.88 | 764.64 | 3 | 0 | 3 | -761.64
2061 | Fault Isolator Module | 0 | Started | Labour | (L)Fire Detection System-Supply Charge | NOS | 3 | 1.18 | 3.54 | 0 | 0 | 0 | 0 | 1.18 | 0 | 3 | 1743.74 | 5231.23 | 3 | 1743.74 | 5231.23 | 3 | 0 | 3.54 | -5227.69
2062 | Battery | 0 | Started | Labour | (L)Fire Detection System-Installation Charge | NOS | 2 | 1 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 254.88 | 509.76 | 2 | 254.88 | 509.76 | 2 | 0 | 2 | -507.76
2063 | Battery | 0 | Started | Labour | (L)Fire Detection System-Supply Charge | NOS | 2 | 1.18 | 2.36 | 0 | 0 | 0 | 0 | 1.18 | 0 | 2 | 1177.6 | 2355.2 | 2 | 1177.6 | 2355.2 | 2 | 0 | 2.36 | -2352.84
2064 | Metal Junction Box | 0 | Started | Labour | (L)Fire Detection System-Installation Charge | NOS | 60 | 1 | 60 | 0 | 0 | 0 | 0 | 1 | 0 | 60 | 42.48 | 2548.8 | 51 | 42.48 | 2166.48 | 60 | 9 | 60 | -2106.48
2065 | Metal Junction Box | 0 | Started | Labour | (L)Fire Detection System-Supply Charge | NOS | 60 | 1.18 | 70.8 | 0 | 0 | 0 | 0 | 1.18 | 0 | 60 | 81.42 | 4885.2 | 60 | 81.42 | 4885.2 | 60 | 0 | 70.8 | -4814.4
2066 | Flowswitch | 0 | Started | Labour | (L)Fire Detection System-Installation Charge | NOS | 2 | 1 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 254.88 | 509.76 | 0 | 0 | 0 | 2 | 2 | 2 | 2
2067 | Flowswitch | 0 | Started | Labour | (L)Fire Detection System-Supply Charge | NOS | 2 | 1.18 | 2.36 | 0 | 0 | 0 | 0 | 1.18 | 0 | 2 | 2239.05 | 4478.1 | 2 | 2239.05 | 4478.1 | 2 | 0 | 2.36 | -4475.74
2068 | 1.5 Sq. mm X 2 Core Copper Armoured FRLS RED Cable | 0 | Started | Labour | (L)Fire Detection System-Installation Charge (cable) | RMT | 820 | 1.18 | 967.6 | 0 | 0 | 0 | 0 | 1.18 | 0 | 820 | 42.48 | 34833.6 | 820 | 42.48 | 34833.6 | 820 | 0 | 967.6 | -33866
2069 | 1.5 Sq. mm X 2 Core Copper Armoured FRLS RED Cable | 0 | Started | Labour | (L)Fire Detection System-Supply Charge (cable) | RMT | 820 | 1.18 | 967.6 | 0 | 0 | 0 | 0 | 1.18 | 0 | 820 | 78.71 | 64538.92 | 633 | 78.71 | 49820.9 | 820 | 187 | 967.6 | -48853.3
2070 | HOUSE KEEPING/DEEP CLEANING INDENT-967/C WING/LGF & UGL TILE | 10 | Started | Material | (M)MULTI CLEAN (PERMA) 25LTR/BUCKET | BUCKET | 10 | 1550 | 15500 | 10 | 1550 | 15500 | 1 | 1550 | 1550 | 9 | 1894.56 | 17051.04 | 0 | 0 | 0 | 9 | 10 | 13950 | 15500
2071 | C WING TILE & STONE WORK INDENT-991/C WING/3RD ST CASE TAPPA | 10 | Started | Material | (M)Epoxy Resin Adhesive Araldite 1.8 kg | (1+0.8) KG/SET | 1 | 800 | 800 | 1 | 800 | 800 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 800 | 800
2072 | C WING TILE & STONE WORK INDENT-991/C WING/3RD ST CASE TAPPA | 10 | Started | Material | (M)STEEL GRAY GRANITE-60'' X 11'' TREAD | SQFT | 100 | 75 | 7500 | 100 | 75 | 7500 | 10 | 75 | 750 | 100 | 88.5 | 8850 | 0 | 0 | 0 | 90 | 100 | 6750 | 7500
2073 | C WING TILE & STONE WORK INDENT-991/C WING/3RD ST CASE TAPPA | 10 | Started | Material | (M)STELL GRAY GRANITE-60'' X 7'' RISER | SQFT | 75 | 75 | 5625 | 75 | 75 | 5625 | 8 | 75 | 600 | 75 | 88.5 | 6637.5 | 0 | 0 | 0 | 67 | 75 | 5025 | 5625
2074 | C WING TILE & STONE WORK INDENT-892/C WING/KITCHEN KADAPPA | 10 | Started | Material | (M)CEMENT PPC 50KG | BAG | 48 | 320 | 15360 | 48 | 320 | 15360 | 5 | 320 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 43 | 48 | 13760 | 15360 | Residencial
2075 | C WING TILE & STONE WORK INDENT-892/C WING/KITCHEN KADAPPA | 10 | Started | Material | (M)KADAPPA-DP 31'' X 25'' VERTICAL | SQFT | 975 | 45 | 43875 | 975 | 45 | 43875 | 98 | 45 | 4410 | 975 | 47.25 | 46068.75 | 0 | 0 | 0 | 877 | 975 | 39465 | 43875 | Residencial
2076 | C WING TILE & STONE WORK INDENT-892/C WING/KITCHEN KADAPPA | 10 | Started | Material | (M)KADAPPA-SP 31'' X 25'' VERTICAL | SQFT | 975 | 38 | 37050 | 975 | 38 | 37050 | 98 | 38 | 3724 | 975 | 39.9 | 38902.5 | 0 | 0 | 0 | 877 | 975 | 33326 | 37050 | Residencial
2077 | C WING TILE & STONE WORK INDENT-892/C WING/KITCHEN KADAPPA | 10 | Started | Material | (M)KADAPPA-SP 59'' X 25'' TOP | SQFT | 1475 | 38 | 56050 | 1475 | 38 | 56050 | 148 | 38 | 5624 | 1475 | 39.9 | 58852.5 | 0 | 0 | 0 | 1327 | 1475 | 50426 | 56050 | Residencial
2078 | C WING TILE & STONE WORK INDENT-892/C WING/KITCHEN KADAPPA | 10 | Started | Material | (M)KADAPPA-SP 71'' X 25'' TOP | SQFT | 2130 | 38 | 80940 | 2130 | 38 | 80940 | 213 | 38 | 8094 | 2130 | 39.9 | 84987 | 0 | 0 | 0 | 1917 | 2130 | 72846 | 80940 | Residencial
2079 | C WING TILE & STONE WORK INDENT-892/C WING/KITCHEN KADAPPA | 10 | Started | Material | (M)PVC LONG BEND 1 1/2'' | NOS | 130 | 15 | 1950 | 130 | 15 | 1950 | 13 | 15 | 195 | 0 | 0 | 0 | 0 | 0 | 0 | 117 | 130 | 1755 | 1950 | Residencial
2080 | C WING TILE & STONE WORK INDENT-990/C WING/LGF-LOBBY FLOORIN | 10 | Started | Material | (M)CEMENT PPC 50KG | BAG | 20 | 320 | 6400 | 20 | 320 | 6400 | 2 | 320 | 640 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 20 | 5760 | 6400
2081 | C WING TILE & STONE WORK INDENT-990/C WING/LGF-LOBBY FLOORIN | 10 | Started | Material | (M)Crush Sand | BRASS | 1.5 | 3675 | 5512.5 | 1.5 | 3675 | 5512.5 | 0 | 3675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 1.5 | 5512.5 | 5512.5
2082 | C WING TILE & STONE WORK INDENT-990/C WING/LGF-LOBBY FLOORIN | 10 | Started | Material | (M)Metal No.I 6mm (Grit) | BRASS | 1.5 | 3000 | 4500 | 1.5 | 3000 | 4500 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 1.5 | 4500 | 4500
2083 | C WING TILE & STONE WORK INDENT-990/C WING/LGF-LOBBY FLOORIN | 10 | Started | Material | (M)TRAPO DARK-600 X 600 (4 TILE/BOX) | BOX | 7 | 887.07 | 6209.49 | 7 | 887.07 | 6209.49 | 1 | 887.07 | 887.07 | 7 | 790.22 | 5531.5701 | 0 | 0 | 0 | 6 | 7 | 5322.42 | 6209.49
2084 | C WING TILE & STONE WORK INDENT-990/C WING/LGF-LOBBY FLOORIN | 10 | Started | Material | (M)TRAPO LIGHT-600 X 600 (4 TILE/BOX) | BOX | 58 | 887.07 | 51450.06 | 58 | 887.07 | 51450.06 | 6 | 887.07 | 5322.42 | 58 | 790.22 | 45833.021 | 0 | 0 | 0 | 52 | 58 | 46127.64 | 51450.06
2085 | INDENT-32/C WING ALL FLAT (130 FLAT) TILING WORK | 10 | Started | Material | (M)BOLAVIA MARFIL 300 x 450mm | BOX | 1200 | 339.56 | 407472 | 1200 | 339.56 | 407472 | 120 | 339.56 | 40747.2 | 1200 | 287.76 | 345312 | 0 | 0 | 0 | 1080 | 1200 | 366724.8 | 407472 | Building
2086 | INDENT-32/C WING ALL FLAT (130 FLAT) TILING WORK | 10 | Started | Material | (M)CEMENT PPC 50KG | BAG | 2542 | 320 | 813440 | 2542 | 320 | 813440 | 254 | 320 | 81280 | 1600 | 318.69 | 509900 | 0 | 0 | 0 | 2288 | 2542 | 732160 | 813440 | Building
2087 | INDENT-32/C WING ALL FLAT (130 FLAT) TILING WORK | 10 | Started | Material | (M)CHICAGO BROWN 300 x 300mm | BOX | 397 | 339.56 | 134805.32 | 397 | 339.56 | 134805.32 | 40 | 339.56 | 13582.4 | 397 | 287.76 | 114240.72 | 0 | 0 | 0 | 357 | 397 | 121222.92 | 134805.32 | Building
2088 | INDENT-32/C WING ALL FLAT (130 FLAT) TILING WORK | 10 | Started | Material | (M)CHICAGO BROWN 300 x 450mm | BOX | 548 | 339.56 | 186078.88 | 548 | 339.56 | 186078.88 | 55 | 339.56 | 18675.8 | 548 | 287.76 | 157692.48 | 0 | 0 | 0 | 493 | 548 | 167403.08 | 186078.88 | Building
2089 | INDENT-32/C WING ALL FLAT (130 FLAT) TILING WORK | 10 | Started | Material | (M)CHICAGO CREMA 300 x 450mm | BOX | 1478 | 339.56 | 501869.68 | 1478 | 339.56 | 501869.68 | 148 | 339.56 | 50254.88 | 1478 | 287.76 | 425309.28 | 0 | 0 | 0 | 1330 | 1478 | 451614.8 | 501869.68 | Building
2090 | INDENT-32/C WING ALL FLAT (130 FLAT) TILING WORK | 10 | Started | Material | (M)COTTO RED 400 x 400mm | BOX | 63 | 417.96 | 26331.48 | 63 | 417.96 | 26331.48 | 6 | 417.96 | 2507.76 | 63 | 354.2 | 22314.6 | 0 | 0 | 0 | 57 | 63 | 23823.72 | 26331.48 | Building
2091 | INDENT-32/C WING ALL FLAT (130 FLAT) TILING WORK | 10 | Started | Material | (M)Crush Sand | BRASS | 60 | 3675 | 220500 | 60 | 3675 | 220500 | 6 | 3675 | 22050 | 60 | 3675 | 220500 | 0 | 0 | 0 | 54 | 60 | 198450 | 220500 | Building
2092 | INDENT-32/C WING ALL FLAT (130 FLAT) TILING WORK | 10 | Started | Material | (M)Metal No.I 6mm (Grit) | BRASS | 60 | 3000 | 180000 | 60 | 3000 | 180000 | 6 | 3000 | 18000 | 60 | 3675 | 220500 | 0 | 0 | 0 | 54 | 60 | 162000 | 180000 | Building
2093 | INDENT-32/C WING ALL FLAT (130 FLAT) TILING WORK | 10 | Started | Material | (M)Vitrified Tile 600mm x 600mm | BOX | 3049 | 991.2 | 3022168.8 | 0 | 0 | 0 | 305 | 991.2 | 302316 | 0 | 0 | 0 | 0 | 0 | 0 | 2744 | 3049 | 2719852.8 | 3022168.8 | Building
2094 | INDENT-32/C WING ALL FLAT (130 FLAT) TILING WORK | 10 | Started | Material | (M)Vitrified Tile 800mm x 800mm (ZEST WHITE) | BOX | 2287 | 1180 | 2698660 | 2287 | 1180 | 2698660 | 229 | 1180 | 270220 | 2287 | 930.15 | 2127253.05 | 0 | 0 | 0 | 2058 | 2287 | 2428440 | 2698660 | Building
2095 | INDENT687/C BLDG/DOOR FRAME GRANITE | 10 | Started | Material | (M)Epoxy Resin Adhesive Araldite 1.8 kg | (1+0.8) KG/SET | 70 | 800 | 56000 | 70 | 800 | 56000 | 7 | 800 | 5600 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | 70 | 50400 | 56000
2096 | INDENT687/C BLDG/DOOR FRAME GRANITE | 10 | Started | Material | (M)GRANITE Steel Gray 16-18mm Thk | SQFT | 7493 | 88.5 | 663130.5 | 7493 | 88.5 | 663130.5 | 749 | 88.5 | 66286.5 | 7493 | 89.29 | 669049.97 | 0 | 0 | 0 | 6744 | 7493 | 596844 | 663130.5
2097 | INDENT687/C BLDG/DOOR FRAME GRANITE | 10 | Started | Material | (M)TILE ADHESIVE MYK 335/BAG-20KG | 20 KG/BAG | 340 | 300 | 102000 | 340 | 300 | 102000 | 34 | 300 | 10200 | 340 | 300 | 101999.966 | 0 | 0 | 0 | 306 | 340 | 91800 | 102000
2098 | C WING UGF OFFICE TILING WORK.(OFFICE-01,24,25) | 0 | Started | Material | (M)CEMENT PPC 50KG | BAG | 35 | 320 | 11200 | 35 | 320 | 11200 | 0 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 35 | 11200 | 11200
2099 | C WING UGF OFFICE TILING WORK.(OFFICE-01,24,25) | 0 | Started | Material | (M)CHICAGO BLANCO 300 x 450mm | BOX | 30 | 339.53 | 10185.9 | 30 | 339.53 | 10185.9 | 0 | 339.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 10185.9 | 10185.9
2100 | C WING UGF OFFICE TILING WORK.(OFFICE-01,24,25) | 0 | Started | Material | (M)CHICAGO GREY 300 x 300mm | BOX | 10 | 339.53 | 3395.3 | 10 | 339.53 | 3395.3 | 0 | 339.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 3395.3 | 3395.3
2101 | C WING UGF OFFICE TILING WORK.(OFFICE-01,24,25) | 0 | Started | Material | (M)CHICAGO GREY 300 x 450mm | BOX | 12 | 339.53 | 4074.36 | 12 | 339.53 | 4074.36 | 0 | 339.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 4074.36 | 4074.36
2102 | C WING UGF OFFICE TILING WORK.(OFFICE-01,24,25) | 0 | Started | Material | (M)Crush Sand | BRASS | 1.5 | 3675 | 5512.5 | 1.5 | 3675 | 5512.5 | 0 | 3675 | 0 | 1.5 | 3570 | 5355 | 0 | 0 | 0 | 1.5 | 1.5 | 5512.5 | 5512.5
2103 | C WING UGF OFFICE TILING WORK.(OFFICE-01,24,25) | 0 | Started | Material | (M)Metal No.I 6mm (Grit) | BRASS | 1.5 | 3000 | 4500 | 1.5 | 3000 | 4500 | 0 | 3000 | 0 | 1.5 | 3570 | 5355 | 0 | 0 | 0 | 1.5 | 1.5 | 4500 | 4500
2104 | C WING UGF OFFICE TILING WORK.(OFFICE-01,24,25) | 0 | Started | Material | (M)Vitrified Tile 600mm x 600mm | BOX | 90 | 991.2 | 89208 | 90 | 991.2 | 89208 | 0 | 991.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 90 | 89208 | 89208
2105 | INDENT-119/C WING/KITCHEN OTTA GRANITE | 0 | Started | Material | (M)CEMENT PPC 50KG | BAG | 110 | 320 | 35200 | 110 | 320 | 35200 | 0 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 110 | 35200 | 35200
2106 | INDENT-119/C WING/KITCHEN OTTA GRANITE | 0 | Started | Material | (M)Crush Sand | BRASS | 4 | 3675 | 14700 | 4 | 3675 | 14700 | 0 | 3675 | 0 | 4 | 3570 | 14280 | 0 | 0 | 0 | 4 | 4 | 14700 | 14700
2107 | INDENT-119/C WING/KITCHEN OTTA GRANITE | 0 | Started | Material | (M)Epoxy Resin Adhesive Araldite 1.8 kg | (1+0.8) KG/SET | 20 | 800 | 16000 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 16000 | 16000
2108 | INDENT-119/C WING/KITCHEN OTTA GRANITE | 0 | Started | Material | (M)Metal No.I 6mm (Grit) | BRASS | 4 | 3000 | 12000 | 4 | 3000 | 12000 | 0 | 3000 | 0 | 4 | 3570 | 14280 | 0 | 0 | 0 | 4 | 4 | 12000 | 12000
2109 | INDENT-119/C WING/KITCHEN OTTA GRANITE | 0 | Started | Material | (M)MYK Laticrete Grout 500 series | KG | 25 | 150 | 3750 | 25 | 150 | 3750 | 0 | 150 | 0 | 25 | 65 | 1625 | 0 | 0 | 0 | 25 | 25 | 3750 | 3750
2110 | INDENT-119/C WING/KITCHEN OTTA GRANITE | 0 | Started | Material | (M)NEW TEL.BLACK GRANITE-DP 48'' X 30'' (RIGHT SIDE) FULL MOUL | NOS | 70 | 2478 | 173460 | 70 | 2478 | 173460 | 0 | 2478 | 0 | 70 | 1960.75 | 137252.5 | 0 | 0 | 0 | 70 | 70 | 173460 | 173460
2111 | INDENT-119/C WING/KITCHEN OTTA GRANITE | 0 | Started | Material | (M)NEW TEL.BLACK GRANITE-DP 48'' X 30'' LEFT SIDE) FULL MOUL | NOS | 60 | 2478 | 148680 | 60 | 2478 | 148680 | 0 | 2478 | 0 | 60 | 1960.75 | 117645 | 0 | 0 | 0 | 60 | 60 | 148680 | 148680
2112 | INDENT-119/C WING/KITCHEN OTTA GRANITE | 0 | Started | Material | (M)NEW TEL.BLACK GRANITE-DP 48'' X 32'' | SQFT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2113 | INDENT-119/C WING/KITCHEN OTTA GRANITE | 0 | Started | Material | (M)NEW TEL.BLACK GRANITE-SP 30'' X 30'' | SQFT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2114 | INDENT-119/C WING/KITCHEN OTTA GRANITE | 0 | Started | Material | (M)NEW TEL.BLACK GRANITE-SP 45'' X 30'' | SQFT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2115 | INDENT-119/C WING/KITCHEN OTTA GRANITE | 0 | Started | Material | (M)NEW TEL.BLACK GRANITE-SP 45'' X 30'' (CUT.PCS) | NOS | 130 | 1829 | 237770 | 130 | 1829 | 237770 | 0 | 1829 | 0 | 130 | 1559.69 | 202759.7 | 0 | 0 | 0 | 130 | 130 | 237770 | 237770
2116 | INDENT-119/C WING/KITCHEN OTTA GRANITE | 0 | Started | Material | (M)NEW TEL.BLACK GRANITE-SP 84'' X 30'' | SQFT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2117 | INDENT-119/C WING/KITCHEN OTTA GRANITE | 0 | Started | Material | (M)NEW TEL.BLACK GRANITE-SP 84'' X 30'' (CUT.PCS) | NOS | 118 | 3407.84 | 402125.12 | 118 | 3407.84 | 402125.12 | 0 | 3407.84 | 0 | 118 | 2911.42 | 343547.56 | 0 | 0 | 0 | 118 | 118 | 402125.12 | 402125.12
2118 | INDENT-119/C WING/KITCHEN OTTA GRANITE | 0 | Started | Material | (M)NEW TEL.BLACK GRANITE-SP 96'' X 30'' | SQFT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2119 | INDENT-119/C WING/KITCHEN OTTA GRANITE | 0 | Started | Material | (M)NEW TEL.BLACK GRANITE-SP 96'' X 30'' (CUT. PCS) | NOS | 12 | 3894 | 46728 | 12 | 3894 | 46728 | 0 | 3894 | 0 | 12 | 3327.34 | 39928.08 | 0 | 0 | 0 | 12 | 12 | 46728 | 46728
2120 | INDENT-119/C WING/KITCHEN OTTA GRANITE | 0 | Started | Material | (M)SS Kitchen Sink with Coupling 22" X 18" | NOS | 129 | 4130 | 532770 | 129 | 4130 | 532770 | 0 | 4130 | 0 | 129 | 4168.94 | 537793.26 | 0 | 0 | 0 | 129 | 129 | 532770 | 532770
2121 | C WING ALL TILING WORK-GROUTE MATERIAL | 0 | Started | Material | (M)MYK Laticrete Grout 500 series | KG | 72 | 150 | 10800 | 72 | 150 | 10800 | 0 | 150 | 0 | 72 | 65 | 4680 | 0 | 0 | 0 | 72 | 72 | 10800 | 10800
2122 | C WING ALL TILING WORK-GROUTE MATERIAL | 0 | Started | Material | (M)SPACER 3MM | PACKET | 143 | 17.7 | 2531.1 | 143 | 17.7 | 2531.1 | 0 | 17.7 | 0 | 143 | 68.44 | 9786.92 | 0 | 0 | 0 | 143 | 143 | 2531.1 | 2531.1
2123 | C WING ALL TILING WORK-GROUTE MATERIAL | 0 | Started | Material | (M)TILE GROUT BRIGHT WHITE-644 | KG | 286 | 63.02 | 18023.72 | 286 | 63.02 | 18023.72 | 0 | 63.02 | 0 | 286 | 63.01 | 18021.432 | 0 | 0 | 0 | 286 | 286 | 18023.72 | 18023.72
2124 | C WING ALL TILING WORK-GROUTE MATERIAL | 0 | Started | Material | (M)TILE GROUT BURGENDY-6109 | KG | 160 | 63.02 | 10083.2 | 160 | 63.02 | 10083.2 | 0 | 63.02 | 0 | 160 | 63.01 | 10081.92 | 0 | 0 | 0 | 160 | 160 | 10083.2 | 10083.2
2125 | C WING ALL TILING WORK-GROUTE MATERIAL | 0 | Started | Material | (M)TILE GROUT IVORY | KG | 429 | 63.02 | 27035.58 | 429 | 63.02 | 27035.58 | 0 | 63.02 | 0 | 429 | 63.01 | 27032.148 | 0 | 0 | 0 | 429 | 429 | 27035.58 | 27035.58
2126 | C WING ALL TILING WORK-GROUTE MATERIAL | 0 | Started | Material | (M)TILE GROUT SILK-603 | KG | 143 | 63.02 | 9011.86 | 143 | 63.02 | 9011.86 | 0 | 63.02 | 0 | 143 | 62.89 | 8993.842 | 0 | 0 | 0 | 143 | 143 | 9011.86 | 9011.86
2127 | C BLDG: UGF OFFICE FLOORING WORK- 31.4% | 0 | Started | Labour | (L)Tiling Work | NOS | 98535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98535 | 1 | 98535 | 98535 | 1 | 98535 | 98535 | 0 | 0 | -98535
2128 | C BLDG: UGF OFFICE TOILET WALL DADO WORK- 13.20% | 0 | Started | Labour | (L)Tiling Work | NOS | 41422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41422 | 1 | 41422 | 41422 | 1 | 41422 | 41422 | 0 | 0 | -41422
2129 | C BLDG: UGF OFFICE TOILET FLOORING WORK- 4.30% | 0 | Started | Labour | (L)Tiling Work | NOS | 13494 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13494 | 1 | 13494 | 13494 | 1 | 13494 | 13494 | 0 | 0 | -13494
2130 | C BLDG: UGF OFFICE TOILET & OFFICE DOOR UMRA PATTI- 2.20% | 0 | Started | Labour | (L)Stone Work | NOS | 6904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6904 | 1 | 6904 | 6904 | 1 | 6904 | 6904 | 0 | 0 | -6904
2131 | C BLDG: UGF OFFICE & LOBBY, LGF LOBBY SKIRTING- 8.60% | 0 | Started | Labour | (L)Tiling Work | NOS | 26987 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26987 | 1 | 26987 | 26987 | 1 | 26987 | 26987 | 0 | 0 | -26987
2132 | C BLDG: UGF OFFICE TOILET DOOR FRAME WORK (20 NOS)- 12.30% | 0 | Started | Labour | (L)Stone Work | NOS | 38598 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38598 | 1 | 38598 | 0 | 0 | 0 | 38598 | 38598 | 0 | 0
2133 | C BLDG: UGF OFFICE TOILET DOOR FRAME WORK (4 NOS)- 1.10% | 0 | Started | Labour | (L)Stone Work | NOS | 3452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3452 | 1 | 3452 | 3452 | 1 | 3452 | 3452 | 0 | 0 | -3452
2134 | C BLDG: UGF OFFICE TOILET LOUVERS W. FRAME WORK - 3.10% | 0 | Started | Labour | (L)Stone Work | NOS | 9728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9728 | 1 | 9728 | 9728 | 1 | 9728 | 9728 | 0 | 0 | -9728
2135 | C BLDG: UGF OFFICE WINDOW FRAME WORK - 8.40% | 0 | Started | Labour | (L)Stone Work | NOS | 26360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26360 | 1 | 26360 | 26360 | 1 | 26360 | 26360 | 0 | 0 | -26360
2136 | C BLDG: UGF LOBBY AREA FLOORING WORK - 5.40% | 0 | Started | Labour | (L)Tiling Work | NOS | 16945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16945 | 1 | 16945 | 16945 | 1 | 16945 | 16945 | 0 | 0 | -16945
2137 | C BLDG: LGF LOBBY AREA FLOORING WORK - 3.0% | 0 | Started | Labour | (L)Tiling Work | NOS | 9414 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9414 | 1 | 9414 | 9414 | 1 | 9414 | 9414 | 0 | 0 | -9414
2138 | C BLDG: UGF & LGF ALL CLEANING WORK- 2.0% | 0 | Started | Labour | (L)Cleaning Work (Tiling & Stone work) | NOS | 6276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6276 | 1 | 6276 | 0 | 0 | 0 | 6276 | 6276 | 0 | 0
2139 | C BLDG: AFTER COMP.OF RETENTION PERIOD- 5.0% | 0 | Started | Labour | (L)Retention (Tiling & Stone work) | NOS | 15690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15690 | 1 | 15690 | 0 | 0 | 0 | 15690 | 15690 | 0 | 0
2140 | C BLDG COMMON TOILET WALL DADO WORK-1ST TO 12TH FLOOR | 0 | Started | Labour | (L)Tiling Work | NOS | 12 | 1 | 12 | 0 | 0 | 0 | 0 | 1 | 0 | 12 | 14166.2 | 169994.4156 | 9 | 14166.2 | 127495.81 | 12 | 3 | 12 | -127483.81
2141 | C BLDG KITCHEN WALL DADO WORK-1ST TO 12TH FLOOR | 0 | Started | Labour | (L)Tiling Work | NOS | 12 | 1 | 12 | 0 | 0 | 0 | 0 | 1 | 0 | 12 | 8499.72 | 101996.6496 | 6 | 8499.72 | 50998.32 | 12 | 6 | 12 | -50986.32
2142 | C BLDG COUNTER WB DADO WORK-1ST TO 12TH FLOOR | 0 | Tentative | Labour | (L)Tiling Work | NOS | 12 | 1 | 12 | 0 | 0 | 0 | 0 | 1 | 0 | 12 | 5666.48 | 67997.766 | 0 | 0 | 0 | 12 | 12 | 12 | 12
2143 | C BLDG FLAT FLOORING WORK-1ST TO 12TH FLOOR | 0 | Started | Labour | (L)Tiling Work | NOS | 12 | 1 | 12 | 0 | 0 | 0 | 0 | 1 | 0 | 12 | 62687.93 | 752255.106 | 6 | 62687.93 | 376127.55 | 12 | 6 | 12 | -376115.55
2144 | C BLDG TERRACE FLOORING WORK-1ST TO 12TH FLOOR | 0 | Tentative | Labour | (L)Tiling Work | NOS | 12 | 1 | 12 | 0 | 0 | 0 | 0 | 1 | 0 | 12 | 1279.35 | 15352.1448 | 0 | 0 | 0 | 12 | 12 | 12 | 12
2145 | C BLDG SKIRTING WORK-1ST TO 12TH FLOOR | 0 | Tentative | Labour | (L)Tiling Work | NOS | 12 | 1 | 12 | 0 | 0 | 0 | 0 | 1 | 0 | 12 | 11883.66 | 142603.8708 | 0 | 0 | 0 | 12 | 12 | 12 | 12
2146 | C BLDG UMRA PATTI FIXING WORK-1ST TO 12TH FLOOR | 0 | Tentative | Labour | (L)Tiling Work | NOS | 12 | 1 | 12 | 0 | 0 | 0 | 0 | 1 | 0 | 12 | 2428.02 | 29136.24 | 0 | 0 | 0 | 12 | 12 | 12 | 12
2147 | C BLDG KITCHEN WINDOW FIXING WORK-1ST TO 12TH FLOOR | 0 | Started | Labour | (L)Tiling Work | NOS | 12 | 1 | 12 | 0 | 0 | 0 | 0 | 1 | 0 | 12 | 5043.85 | 60526.1472 | 6 | 5043.85 | 30263.07 | 12 | 6 | 12 | -30251.07
2148 | C BLDG TOILET WINDOW FRAME WORK-1ST TO 12TH FLOOR | 0 | Started | Labour | (L)Tiling Work | NOS | 12 | 1 | 12 | 0 | 0 | 0 | 0 | 1 | 0 | 12 | 5043.85 | 60526.1472 | 6 | 5043.85 | 30263.07 | 12 | 6 | 12 | -30251.07
2149 | C BLDG HALL WINDOW FRAME WORK-1ST TO 12TH FLOOR | 0 | Started | Labour | (L)Tiling Work | NOS | 12 | 1 | 12 | 0 | 0 | 0 | 0 | 1 | 0 | 12 | 7441.62 | 89299.476 | 6 | 7441.62 | 44649.74 | 12 | 6 | 12 | -44637.74
2150 | C BLDG BEDROOM WINDOW FRAME WORK-1ST TO 12TH FLOOR | 0 | Started | Labour | (L)Tiling Work | NOS | 12 | 1 | 12 | 0 | 0 | 0 | 0 | 1 | 0 | 12 | 7441.62 | 89299.476 | 6 | 7441.62 | 44649.74 | 12 | 6 | 12 | -44637.74
2151 | C BLDG TOILET/WC FLOORING WORK-1ST TO 12TH FLOOR | 0 | Tentative | Labour | (L)Tiling Work | NOS | 12 | 1 | 12 | 0 | 0 | 0 | 0 | 1 | 0 | 12 | 5687.5 | 68250 | 0 | 0 | 0 | 12 | 12 | 12 | 12
2152 | C BLDG ACID WASH WORK-1ST TO 12TH FLOOR | 0 | Tentative | Labour | (L)Tiling Work | NOS | 12 | 1 | 12 | 0 | 0 | 0 | 0 | 1 | 0 | 12 | 7843.99 | 94127.8536 | 0 | 0 | 0 | 12 | 12 | 12 | 12
2153 | C BLDG CLEANING & MISC. WORK-1ST TO 12TH FLOOR | 0 | Tentative | Labour | (L)Tiling Work | NOS | 2 | 1 | 2 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 23531.96 | 47063.9268 | 0 | 0 | 0 | 2 | 2 | 2 | 2
2154 | C BLDG RETENTION-AFTER COMPLETION OF ALL TILING WORK | 0 | Tentative | Labour | (L)Tiling Work | NOS | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 94127.85 | 94127.8537 | 0 | 0 | 0 | 1 | 1 | 1 | 1
2155 | C BLDG TOILET DOOR FRAME (FLAT:01-11)-1,2,3 FLOOR | 0 | Started | Labour | (L)Toilet Door frames (Lab) | NOS | 496.0226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 496.0226 | 115 | 57042.599 | 496.0226 | 115 | 57042.6 | 496.0226 | 0 | 0 | -57042.6
2156 | C BLDG TOILET DOOR FRAME (FLAT:01-11)-4,5,6 FLOOR | 0 | Started | Labour | (L)Toilet Door frames (Lab) | NOS | 516.6902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 516.6902 | 115 | 59419.373 | 516.6902 | 115 | 59419.37 | 516.6902 | 0 | 0 | -59419.37
2157 | C BLDG TOILET DOOR FRAME (FLAT:01-11)-7,8,9 FLOOR | 0 | Started | Labour | (L)Toilet Door frames (Lab) | NOS | 516.6902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 516.6902 | 115 | 59419.373 | 516.6902 | 115 | 59419.37 | 516.6902 | 0 | 0 | -59419.37
2158 | C BLDG TOILET DOOR FRAME (FLAT:01-11)-10,11,12 FLOOR | 0 | Tentative | Labour | (L)Toilet Door frames (Lab) | NOS | 537.3578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 537.3578 | 115 | 61796.147 | 0 | 0 | 0 | 537.3578 | 537.3578 | 0 | 0
2159 | C BLDG KITCHEN KADAPPA (FLAT:01-11)-1,2,3 FLOOR | 0 | Started | Labour | (L)Kitchen Platform -(Lab) | RFT | 135.6987 | 440 | 59707.43 | 0 | 0 | 0 | 0 | 440 | 0 | 135.6987 | 440 | 59707.428 | 135.6987 | 440 | 59707.43 | 135.6987 | 0 | 59707.428 | -0.002
2160 | C BLDG KITCHEN KADAPPA (FLAT:01-11)-4,5,6 FLOOR | 0 | Started | Labour | (L)Kitchen Platform -(Lab) | RFT | 135.6987 | 440 | 59707.43 | 0 | 0 | 0 | 0 | 440 | 0 | 135.6987 | 440 | 59707.428 | 135.6987 | 440 | 59707.43 | 135.6987 | 0 | 59707.428 | -0.002
2161 | C BLDG KITCHEN KADAPPA (FLAT:01-11)-7,8,9 FLOOR | 0 | Started | Labour | (L)Kitchen Platform -(Lab) | RFT | 135.6987 | 440 | 59707.43 | 0 | 0 | 0 | 0 | 440 | 0 | 135.6987 | 440 | 59707.428 | 135.6987 | 440 | 59707.43 | 135.6987 | 0 | 59707.428 | -0.002
2162 | C BLDG KITCHEN KADAPPA (FLAT:01-11)-10,11,12 FLOOR | 0 | Started | Labour | (L)Kitchen Platform -(Lab) | RFT | 135.6987 | 440 | 59707.43 | 0 | 0 | 0 | 0 | 440 | 0 | 135.6987 | 440 | 59707.428 | 135.6987 | 440 | 59707.43 | 135.6987 | 0 | 59707.428 | -0.002
2163 | C BLDG KITCHEN GRANITE (FLAT:01-11)-1,2,3 FLOOR | 0 | Started | Labour | (L)Kitchen Platform -(Lab) | RFT | 172.7074 | 440 | 75991.26 | 0 | 0 | 0 | 0 | 440 | 0 | 172.7074 | 440 | 75991.256 | 172.7074 | 440 | 75991.26 | 172.7074 | 0 | 75991.256 | -0.004
2164 | C BLDG KITCHEN GRANITE (FLAT:01-11)-4,5,6 FLOOR | 0 | Started | Labour | (L)Kitchen Platform -(Lab) | RFT | 172.7074 | 440 | 75991.26 | 0 | 0 | 0 | 0 | 440 | 0 | 172.7074 | 440 | 75991.256 | 172.7074 | 440 | 75991.26 | 172.7074 | 0 | 75991.256 | -0.004
2165 | C BLDG KITCHEN GRANITE (FLAT:01-11)-7,8,9 FLOOR | 0 | Tentative | Labour | (L)Kitchen Platform -(Lab) | RFT | 172.7074 | 440 | 75991.26 | 0 | 0 | 0 | 0 | 440 | 0 | 172.7074 | 440 | 75991.256 | 0 | 0 | 0 | 172.7074 | 172.7074 | 75991.256 | 75991.256
2166 | C BLDG KITCHEN GRANITE (FLAT:01-11)-10,11,12 FLOOR | 0 | Tentative | Labour | (L)Kitchen Platform -(Lab) | RFT | 172.7074 | 440 | 75991.26 | 0 | 0 | 0 | 0 | 440 | 0 | 172.7074 | 440 | 75991.256 | 0 | 0 | 0 | 172.7074 | 172.7074 | 75991.256 | 75991.256
2167 | C BLDG TOILET DOOR FRAME (FLAT:01-11)-UP TO 12TH ''MISC.WORK | 0 | Tentative | Labour | (L)Toilet Door frames (Lab) | NOS | 33.515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.515 | 115 | 3854.225 | 0 | 0 | 0 | 33.515 | 33.515 | 0 | 0
2168 | C BLDG KITCHEN OTTA (FLAT:01-11)-UP TO 12TH ''MISC.WORK'' | 0 | Tentative | Labour | (L)Kitchen Platform -(Lab) | RFT | 20.0047 | 440 | 8802.07 | 0 | 0 | 0 | 0 | 440 | 0 | 20.0047 | 440 | 8802.068 | 0 | 0 | 0 | 20.0047 | 20.0047 | 8802.068 | 8802.068
2169 | C BLDG TOILET DOOR FRAME (FLAT:01-11)-UP TO 12TH CLEANING | 0 | Tentative | Labour | (L)Toilet Door frames (Lab) | NOS | 22.3434 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.3434 | 115 | 2569.491 | 0 | 0 | 0 | 22.3434 | 22.3434 | 0 | 0
2170 | C BLDG KITCHEN OTTA (FLAT:01-11)-UP TO 12TH CLEANING | 0 | Tentative | Labour | (L)Kitchen Platform -(Lab) | RFT | 13.3365 | 440 | 5868.06 | 0 | 0 | 0 | 0 | 440 | 0 | 13.3365 | 440 | 5868.06 | 0 | 0 | 0 | 13.3365 | 13.3365 | 5868.06 | 5868.06
2171 | C BLDG TOILET DOOR FRAME (FLAT:01-11)-UP TO 12TH, RETENTION | 0 | Tentative | Labour | (L)Toilet Door frames (Lab) | NOS | 111.7168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111.7168 | 115 | 12847.432 | 0 | 0 | 0 | 111.7168 | 111.7168 | 0 | 0
2172 | C BLDG KITCHEN OTTA (FLAT:01-11)-UP TO 12TH, RETENTION | 0 | Tentative | Labour | (L)Kitchen Platform -(Lab) | RFT | 66.6824 | 440 | 29340.26 | 0 | 0 | 0 | 0 | 440 | 0 | 66.6824 | 440 | 29340.256 | 0 | 0 | 0 | 66.6824 | 66.6824 | 29340.256 | 29340.256
2173 | C-WING PASSAGE & ST CASE TILING WORK-MATERIAL | 0 | Tentative | Material | (M)CEMENT PPC 50KG | BAG | 390 | 320 | 124800 | 390 | 320 | 124800 | 0 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 390 | 390 | 124800 | 124800
2174 | C-WING PASSAGE & ST CASE TILING WORK-MATERIAL | 0 | Tentative | Material | (M)Crush Sand | BRASS | 19 | 3675 | 69825 | 19 | 3675 | 69825 | 0 | 3675 | 0 | 19 | 3675 | 69825 | 0 | 0 | 0 | 19 | 19 | 69825 | 69825
2175 | C-WING PASSAGE & ST CASE TILING WORK-MATERIAL | 0 | Tentative | Material | (M)DUNKAN WHITE-600X600 (4 TILE/BOX or 15.5 SQFT) | BOX | 838.76 | 604 | 506611.04 | 838.76 | 604 | 506611.04 | 0 | 604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 838.76 | 838.76 | 506611.04 | 506611.04
2176 | C-WING PASSAGE & ST CASE TILING WORK-MATERIAL | 0 | Tentative | Material | (M)Metal No.I 6mm (Grit) | BRASS | 29 | 3000 | 87000 | 29 | 3000 | 87000 | 0 | 3000 | 0 | 29 | 3675 | 106575 | 0 | 0 | 0 | 29 | 29 | 87000 | 87000
2177 | C WING ELECTRICAL WORK INDENT-989/C WING/LGF & UGF LOBBY LIG | 10 | Started | Material | (M)LEGERO AVIO 12WT | NOS | 26 | 660 | 17160 | 26 | 660 | 17160 | 3 | 660 | 1980 | 26 | 826 | 21476 | 0 | 0 | 0 | 23 | 26 | 15180 | 17160
2178 | C WING ELECTRICAL WORK INDENT-989/C WING/LGF & UGF LOBBY LIG | 10 | Started | Material | (M)LEGERO AVIO 8WT | NOS | 18 | 537 | 9666 | 18 | 537 | 9666 | 2 | 537 | 1074 | 18 | 719.8 | 12956.4 | 0 | 0 | 0 | 16 | 18 | 8592 | 9666
2179 | C WING ELECTRICAL WORK INDENT-22/C WING/METER ROOM PLY WORK | 10 | Started | Material | (M)Backlight Sheet 8' x 4' x 3mm | NOS | 15 | 2000 | 30000 | 15 | 2000 | 30000 | 2 | 2000 | 4000 | 15 | 1125 | 16875 | 0 | 0 | 0 | 13 | 15 | 26000 | 30000
2180 | C WING ELECTRICAL WORK INDENT-22/C WING/METER ROOM PLY WORK | 10 | Started | Material | (M)Plywood 8' x 4' x 20mm (Waterproofing) | NOS | 15 | 2500 | 37500 | 15 | 2500 | 37500 | 2 | 2500 | 5000 | 15 | 2190.08 | 32851.2 | 0 | 0 | 0 | 13 | 15 | 32500 | 37500
2181 | INDENT-889/C BLDG/INT.ELEC.SUPPLY | 0 | Started | Material | (M)10 sq.mm x 4 core Aluminium Armoured Cable | RMT | 80 | 121.54 | 9723.2 | 80 | 121.54 | 9723.2 | 0 | 121.54 | 0 | 60 | 121.54 | 7292.4 | 0 | 0 | 0 | 80 | 80 | 9723.2 | 9723.2 | Building
2182 | INDENT-889/C BLDG/INT.ELEC.SUPPLY | 0 | Started | Material | (M)40 Amp 4 Pole MCB Schneider with Box | NOS | 6 | 3009 | 18054 | 6 | 3009 | 18054 | 0 | 3009 | 0 | 6 | 1733.42 | 10400.52 | 0 | 0 | 0 | 6 | 6 | 18054 | 18054 | Building
2183 | INDENT-889/C BLDG/INT.ELEC.SUPPLY | 0 | Started | Material | (M)63 Amp 4 Pole MCB Schneider with Box | NOS | 2 | 1866.76 | 3733.52 | 2 | 1866.76 | 3733.52 | 0 | 1866.76 | 0 | 1 | 2074.44 | 2074.44 | 0 | 0 | 0 | 2 | 2 | 3733.52 | 3733.52 | Building
2184 | INDENT-889/C BLDG/INT.ELEC.SUPPLY | 0 | Started | Material | (M)Industrial Socket 20 Amp 3 Pin | NOS | 18 | 123.9 | 2230.2 | 18 | 123.9 | 2230.2 | 0 | 123.9 | 0 | 18 | 123.9 | 2230.2 | 0 | 0 | 0 | 18 | 18 | 2230.2 | 2230.2 | Building
2185 | INDENT-889/C BLDG/INT.ELEC.SUPPLY | 0 | Started | Material | (M)Insulation Tape | NOS | 5 | 11.8 | 59 | 5 | 11.8 | 59 | 0 | 11.8 | 0 | 4 | 11.8 | 47.2 | 0 | 0 | 0 | 5 | 5 | 59 | 59 | Building
2186 | INDENT-889/C BLDG/INT.ELEC.SUPPLY | 0 | Started | Material | (M)LED Tubelight Fitting 10W x 2' long | NOS | 14 | 129.8 | 1817.2 | 14 | 129.8 | 1817.2 | 0 | 129.8 | 0 | 14 | 129.8 | 1817.2 | 0 | 0 | 0 | 14 | 14 | 1817.2 | 1817.2 | Building
2187 | INDENT-889/C BLDG/INT.ELEC.SUPPLY | 0 | Started | Material | (M)MCB 10Amp Single Pole with box | NOS | 1 | 224.2 | 224.2 | 1 | 224.2 | 224.2 | 0 | 224.2 | 0 | 1 | 224.2 | 224.2 | 0 | 0 | 0 | 1 | 1 | 224.2 | 224.2 | Building
2188 | INDENT-889/C BLDG/INT.ELEC.SUPPLY | 0 | Started | Material | (M)Raval Plug | NOS | 50 | 1.18 | 59 | 50 | 1.18 | 59 | 0 | 1.18 | 0 | 50 | 0.47 | 23.6 | 0 | 0 | 0 | 50 | 50 | 59 | 59 | Building
2189 | INDENT-889/C BLDG/INT.ELEC.SUPPLY | 0 | Started | Material | (M)Screw-75 x 8 | NOS | 100 | 1.42 | 142 | 100 | 1.42 | 142 | 0 | 1.42 | 0 | 100 | 1.42 | 141.6 | 0 | 0 | 0 | 100 | 100 | 142 | 142 | Building
2190 | C WING UGF SAMPLE OFFICE LIGHT | 0 | Started | Material | (M)CEILING FAN | NOS | 1 | 1770 | 1770 | 1 | 1770 | 1770 | 0 | 1770 | 0 | 1 | 1652 | 1652 | 0 | 0 | 0 | 1 | 1 | 1770 | 1770
2191 | C WING UGF SAMPLE OFFICE LIGHT | 0 | Started | Material | (M)LED Panel Light Fitting 15w | NOS | 7 | 590 | 4130 | 7 | 590 | 4130 | 0 | 590 | 0 | 7 | 641.75 | 4492.2799 | 0 | 0 | 0 | 7 | 7 | 4130 | 4130
2192 | C WING UGF SAMPLE OFFICE LIGHT | 0 | Started | Material | (M)LED Panel Light Fitting 6w | NOS | 4 | 472 | 1888 | 4 | 472 | 1888 | 0 | 472 | 0 | 4 | 429.25 | 1717 | 0 | 0 | 0 | 4 | 4 | 1888 | 1888
2193 | C WING METER ROOM ELECTRICAL WORK | 0 | Started | Material | (M)125Amp BUSBAR (16KA for 1sec) With 100A TP+NL MCCB | NOS | 2 | 12000 | 24000 | 2 | 12000 | 24000 | 0 | 12000 | 0 | 2 | 14361.13 | 28722.26 | 0 | 0 | 0 | 2 | 2 | 24000 | 24000
2194 | C WING METER ROOM ELECTRICAL WORK | 0 | Started | Material | (M)4 MM NUT BOLT & WASHER | NOS | 200 | 10 | 2000 | 200 | 10 | 2000 | 0 | 10 | 0 | 200 | 11.97 | 2394 | 0 | 0 | 0 | 200 | 200 | 2000 | 2000
2195 | C WING METER ROOM ELECTRICAL WORK | 0 | Started | Material | (M)4 SQMM PVC COATED COPPER LUGS | NOS | 200 | 6 | 1200 | 100 | 6 | 600 | 0 | 6 | 0 | 100 | 7.18 | 718 | 0 | 0 | 0 | 200 | 200 | 1200 | 1200
2196 | C WING METER ROOM ELECTRICAL WORK | 0 | Started | Material | (M)40 Amp 2 Pole MCB Schneider With Enclosure | NOS | 33 | 1416 | 46728 | 33 | 1416 | 46728 | 0 | 1416 | 0 | 33 | 789.86 | 26065.38 | 0 | 0 | 0 | 33 | 33 | 46728 | 46728
2197 | C WING METER ROOM ELECTRICAL WORK | 0 | Started | Material | (M)6 SQMM RING TYPE COPPER LUGS | NOS | 200 | 8 | 1600 | 100 | 8 | 800 | 0 | 8 | 0 | 100 | 9.57 | 957 | 0 | 0 | 0 | 200 | 200 | 1600 | 1600
2198 | C WING METER ROOM ELECTRICAL WORK | 0 | Started | Material | (M)Cable Tie-150mm | PACKET | 5 | 350 | 1750 | 5 | 350 | 1750 | 0 | 350 | 0 | 5 | 418.87 | 2094.35 | 0 | 0 | 0 | 5 | 5 | 1750 | 1750
2199 | C WING METER ROOM ELECTRICAL WORK | 0 | Started | Material | (M)FERRULE (0TO9) | NOS | 10 | 45 | 450 | 10 | 45 | 450 | 0 | 45 | 0 | 10 | 53.85 | 538.5 | 0 | 0 | 0 | 10 | 10 | 450 | 450
2200 | C WING METER ROOM ELECTRICAL WORK | 0 | Started | Material | (M)FLEXIBLE PIPE GREY COLOUR (25MTR/BUND.) | BUNDLE | 1 | 300 | 300 | 1 | 300 | 300 | 0 | 300 | 0 | 1 | 359.03 | 359.03 | 0 | 0 | 0 | 1 | 1 | 300 | 300
2201 | C WING METER ROOM ELECTRICAL WORK | 0 | Started | Material | (M)GI STRIP 25x3 MM | Mtr. | 40 | 85 | 3400 | 40 | 85 | 3400 | 0 | 85 | 0 | 40 | 101.72 | 4068.8 | 0 | 0 | 0 | 40 | 40 | 3400 | 3400
2202 | C WING METER ROOM ELECTRICAL WORK | 0 | Started | Material | (M)Insulation Tape | NOS | 20 | 11.8 | 236 | 20 | 11.8 | 236 | 0 | 11.8 | 0 | 20 | 11.97 | 239.4 | 0 | 0 | 0 | 20 | 20 | 236 | 236
2203 | C WING METER ROOM ELECTRICAL WORK | 0 | Started | Material | (M)PVC GLAND 20mm | NOS | 1 | 25 | 25 | 1 | 25 | 25 | 0 | 25 | 0 | 1 | 29.92 | 29.92 | 0 | 0 | 0 | 1 | 1 | 25 | 25
2204 | C WING METER ROOM ELECTRICAL WORK | 0 | Started | Material | (M)PVC SUPPORTER PATTI | NOS | 50 | 25 | 1250 | 50 | 25 | 1250 | 0 | 25 | 0 | 50 | 29.92 | 1496 | 0 | 0 | 0 | 50 | 50 | 1250 | 1250
2205 | C WING METER ROOM ELECTRICAL WORK | 0 | Started | Material | (M)PVC TRAY 100X100 MM | Mtr. | 30 | 300 | 9000 | 30 | 300 | 9000 | 0 | 300 | 0 | 30 | 359.03 | 10770.9 | 0 | 0 | 0 | 30 | 30 | 9000 | 9000
2206 | C WING METER ROOM ELECTRICAL WORK | 0 | Started | Material | (M)PVC TRAY 65X165 MM | Mtr. | 265 | 150 | 39750 | 265 | 150 | 39750 | 0 | 150 | 0 | 265 | 179.51 | 47570.15 | 0 | 0 | 0 | 265 | 265 | 39750 | 39750
2207 | C WING METER ROOM ELECTRICAL WORK | 0 | Started | Material | (M)SS Screw 19 x 6 mm Full thread | NOS | 1000 | 2.36 | 2360 | 1000 | 2.36 | 2360 | 0 | 2.36 | 0 | 1000 | 0.36 | 364 | 0 | 0 | 0 | 1000 | 1000 | 2360 | 2360
2208 | C BLDG METER ROOM CABLE TRAY INSTALLATION WORK | 0 | Started | Material | (M)C Channel 35x15x15x2 mm for Cable Support - 2.5 Mtr Long | NOS | 10 | 177 | 1770 | 10 | 177 | 1770 | 0 | 177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 1770 | 1770
2209 | C BLDG METER ROOM CABLE TRAY INSTALLATION WORK | 0 | Started | Material | (M)M12 Bullet Fastner | NOS | 50 | 10.04 | 502 | 50 | 10.04 | 502 | 0 | 10.04 | 0 | 50 | 13.28 | 664 | 0 | 0 | 0 | 50 | 50 | 502 | 502
2210 | C BLDG METER ROOM CABLE TRAY INSTALLATION WORK | 0 | Started | Material | (M)M12 Nut | NOS | 100 | 2.96 | 296 | 100 | 2.96 | 296 | 0 | 2.96 | 0 | 100 | 3.91 | 391 | 0 | 0 | 0 | 100 | 100 | 296 | 296
2211 | C BLDG METER ROOM CABLE TRAY INSTALLATION WORK | 0 | Started | Material | (M)M12 Threaded Rod - 2 Mtr Long | NOS | 25 | 218.3 | 5457.5 | 25 | 218.3 | 5457.5 | 0 | 218.3 | 0 | 25 | 289.15 | 7228.75 | 0 | 0 | 0 | 25 | 25 | 5457.5 | 5457.5
2212 | C BLDG METER ROOM CABLE TRAY INSTALLATION WORK | 0 | Started | Material | (M)M8 x 25 Nut Bolt & Washer | SET | 50 | 4.14 | 207 | 50 | 4.14 | 207 | 0 | 4.14 | 0 | 50 | 5.47 | 273.5 | 0 | 0 | 0 | 50 | 50 | 207 | 207
2213 | C BLDG METER ROOM CABLE TRAY INSTALLATION WORK | 0 | Started | Material | (M)Perforated Cable Tray 600 x 75 x 2.0 mm Thick | Mtr. | 30 | 1215.4 | 36462 | 30 | 1215.4 | 36462 | 0 | 1215.4 | 0 | 30 | 1609.84 | 48295.2 | 0 | 0 | 0 | 30 | 30 | 36462 | 36462
2214 | C BLDG (AUTO CHANGEOVER PANEL & SUB DIST. PANEL) | 0 | Tentative | Material | (M)10_Sub Dist. Panel-5 Common (Locn-C Wing Meter Room) | SET | 1 | 64900 | 64900 | 1 | 64900 | 64900 | 0 | 64900 | 0 | 1 | 45726.18 | 45726.18 | 0 | 0 | 0 | 1 | 1 | 64900 | 64900
2215 | C BLDG (AUTO CHANGEOVER PANEL & SUB DIST. PANEL) | 0 | Tentative | Material | (M)15A_Common Area Changeover Panel (D.G Set to C Wing Meter ) | SET | 1 | 70800 | 70800 | 1 | 70800 | 70800 | 0 | 70800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 70800 | 70800
2216 | C BLDG (AUTO CHANGEOVER PANEL & SUB DIST. PANEL) | 0 | Tentative | Material | (M)15B_Common Area Changeover Panel (D.G Set to C Wing Meter) | SET | 1 | 70800 | 70800 | 1 | 70800 | 70800 | 0 | 70800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 70800 | 70800
2217 | C BLDG (AUTO CHANGEOVER PANEL & SUB DIST. PANEL) | 0 | Tentative | Material | (M)6_Sub Dist. Panel-4 (Locn-C Wing Meter Room) | SET | 1 | 70800 | 70800 | 1 | 70800 | 70800 | 0 | 70800 | 0 | 1 | 56079.5 | 56079.5 | 0 | 0 | 0 | 1 | 1 | 70800 | 70800
2218 | C WING BOTH LIFT SHAFT ELECTRICAL MATERIAL | 0 | Tentative | Material | (M)1 Model Modular box | NOS | 2 | 59 | 118 | 2 | 59 | 118 | 0 | 59 | 0 | 2 | 23.6 | 47.2 | 0 | 0 | 0 | 2 | 2 | 118 | 118
2219 | C WING BOTH LIFT SHAFT ELECTRICAL MATERIAL | 0 | Tentative | Material | (M)16 amp 2-way SP switch-1module | NOS | 8 | 130 | 1040 | 8 | 130 | 1040 | 0 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 1040 | 1040
2220 | C WING BOTH LIFT SHAFT ELECTRICAL MATERIAL | 0 | Tentative | Material | (M)16amp 4 Pole MCB-Type C | NOS | 2 | 1020 | 2040 | 2 | 1020 | 2040 | 0 | 1020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2040 | 2040
2221 | C WING BOTH LIFT SHAFT ELECTRICAL MATERIAL | 0 | Tentative | Material | (M)2.5 sq.mm x 3 core Copper Armoured Cable | RMT | 281 | 136 | 38216 | 281 | 136 | 38216 | 0 | 136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 281 | 281 | 38216 | 38216
2222 | C WING BOTH LIFT SHAFT ELECTRICAL MATERIAL | 0 | Tentative | Material | (M)20W LED Tubelight-4 Ft | NOS | 38 | 190.1 | 7223.8 | 38 | 190.1 | 7223.8 | 0 | 190.1 | 0 | 38 | 141.6 | 5380.8 | 0 | 0 | 0 | 38 | 38 | 7223.8 | 7223.8
2223 | C WING BOTH LIFT SHAFT ELECTRICAL MATERIAL | 0 | Tentative | Material | (M)25amp 2 Pole MCB-Type C | NOS | 2 | 750 | 1500 | 2 | 750 | 1500 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 1500 | 1500
2224 | C WING BOTH LIFT SHAFT ELECTRICAL MATERIAL | 0 | Tentative | Material | (M)4 sq.mm x 4 core Copper Armoured Cable | RMT | 159 | 198 | 31482 | 159 | 198 | 31482 | 0 | 198 | 0 | 159 | 247.8 | 39400.2 | 0 | 0 | 0 | 159 | 159 | 31482 | 31482
2225 | C WING BOTH LIFT SHAFT ELECTRICAL MATERIAL | 0 | Tentative | Material | (M)6A Sockets | NOS | 38 | 177 | 6726 | 38 | 177 | 6726 | 0 | 177 | 0 | 38 | 35.4 | 1345.2 | 0 | 0 | 0 | 38 | 38 | 6726 | 6726
2226 | C WING BOTH LIFT SHAFT ELECTRICAL MATERIAL | 0 | Tentative | Material | (M)6A Switches | NOS | 76 | 41.3 | 3138.8 | 76 | 41.3 | 3138.8 | 0 | 41.3 | 0 | 76 | 16.52 | 1255.52 | 0 | 0 | 0 | 76 | 76 | 3138.8 | 3138.8
2227 | C WING BOTH LIFT SHAFT ELECTRICAL MATERIAL | 0 | Tentative | Material | (M)8 Gauge Copper wire | RMT | 318 | 469 | 149142 | 318 | 469 | 149142 | 0 | 469 | 0 | 318 | 147.69 | 46963.989 | 0 | 0 | 0 | 318 | 318 | 149142 | 149142
2228 | C WING BOTH LIFT SHAFT ELECTRICAL MATERIAL | 0 | Tentative | Material | (M)Flexible Cable 2.5 sq.mm x 2 core | RMT | 300 | 100 | 30000 | 300 | 100 | 30000 | 0 | 100 | 0 | 300 | 73.63 | 22089.6 | 0 | 0 | 0 | 300 | 300 | 30000 | 30000
2229 | C WING BOTH LIFT SHAFT ELECTRICAL MATERIAL | 0 | Tentative | Material | (M)Insulation Tape | NOS | 20 | 11.8 | 236 | 20 | 11.8 | 236 | 0 | 11.8 | 0 | 20 | 11.8 | 236 | 0 | 0 | 0 | 20 | 20 | 236 | 236
2230 | C WING BOTH LIFT SHAFT ELECTRICAL MATERIAL | 0 | Tentative | Material | (M)MS Saddle 3/4" | NOS | 441 | 8 | 3528 | 441 | 8 | 3528 | 0 | 8 | 0 | 441 | 1.49 | 654.885 | 0 | 0 | 0 | 441 | 441 | 3528 | 3528
2231 | C WING BOTH LIFT SHAFT ELECTRICAL MATERIAL | 0 | Tentative | Material | (M)PVC Conduits Pipe 20mm-3mtr | NOS | 147 | 35 | 5145 | 147 | 35 | 5145 | 0 | 35 | 0 | 147 | 46.02 | 6764.94 | 0 | 0 | 0 | 147 | 147 | 5145 | 5145
2232 | C WING BOTH LIFT SHAFT ELECTRICAL MATERIAL | 0 | Tentative | Material | (M)Raval Plug | NOS | 1033 | 1.18 | 1218.94 | 1033 | 1.18 | 1218.94 | 0 | 1.18 | 0 | 1033 | 0.46 | 471.9777 | 0 | 0 | 0 | 1033 | 1033 | 1218.94 | 1218.94
2233 | C WING BOTH LIFT SHAFT ELECTRICAL MATERIAL | 0 | Tentative | Material | (M)RCBO 16amp - FP - 300mA (B-Type) | NOS | 2 | 3127 | 6254 | 2 | 3127 | 6254 | 0 | 3127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 6254 | 6254
2234 | C WING BOTH LIFT SHAFT ELECTRICAL MATERIAL | 0 | Tentative | Material | (M)RCBO 25amp - DP - 30mA (A-Type) | NOS | 2 | 3351.2 | 6702.4 | 2 | 3351.2 | 6702.4 | 0 | 3351.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 6702.4 | 6702.4
2235 | C WING BOTH LIFT SHAFT ELECTRICAL MATERIAL | 0 | Tentative | Material | (M)Screw 8 x 25mm | NOS | 152 | 1.18 | 179.36 | 152 | 1.18 | 179.36 | 0 | 1.18 | 0 | 152 | 2.17 | 330.4024 | 0 | 0 | 0 | 152 | 152 | 179.36 | 179.36
2236 | C WING BOTH LIFT SHAFT ELECTRICAL MATERIAL | 0 | Tentative | Material | (M)Screw 8 x 35mm | NOS | 882 | 0.77 | 679.14 | 882 | 0.77 | 679.14 | 0 | 0.77 | 0 | 882 | 0.78 | 690.3414 | 0 | 0 | 0 | 882 | 882 | 679.14 | 679.14
2237 | C WING BOTH LIFT SHAFT ELECTRICAL MATERIAL | 0 | Tentative | Material | (M)Sunmike Board 8'' x 10'' | NOS | 38 | 150 | 5700 | 38 | 150 | 5700 | 0 | 150 | 0 | 38 | 118 | 4484 | 0 | 0 | 0 | 38 | 38 | 5700 | 5700
2238 | C BLDG LGF & UGF- SLAB & WALL PIPING WORK-(MAT) | 0 | Started | Labour | (L)ELECTRICAL WORK. | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 134236.8 | 134236.8 | 1 | 134236.8 | 134236.8 | 1 | 0 | 0 | -134236.8
2239 | C BLDG LGF & UGF- INTERNAL WIRING WORK-(MAT) | 0 | Started | Labour | (L)ELECTRICAL WORK. | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 134236.8 | 134236.8 | 1 | 134236.8 | 134236.8 | 1 | 0 | 0 | -134236.8
2240 | C BLDG LGF & UGF- SWITCHES, SOCKET & PLATE FITTING-(MAT) | 0 | Started | Labour | (L)ELECTRICAL WORK. | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 134236.8 | 134236.8 | 1 | 134236.8 | 134236.8 | 1 | 0 | 0 | -134236.8
2241 | C BLDG LGF & UGF- MISC. WORK & TESTING WORK.-(MAT) | 0 | Tentative | Labour | (L)ELECTRICAL WORK. | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 22372.8 | 22372.8 | 0 | 0 | 0 | 1 | 1 | 0 | 0
2242 | C BLDG LGF & UGF- ELECTRICAL WORK RETENTION-(MAT) | 0 | Tentative | Labour | (L)ELECTRICAL WORK. | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 22372.8 | 22372.8 | 0 | 0 | 0 | 1 | 1 | 0 | 0
2243 | C BLDG LGF & UGF- SLAB & WALL PIPING WORK-(LAB) | 0 | Started | Labour | (L)ELECTRICAL WORK. | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 42859 | 42859 | 1 | 42859 | 42859 | 1 | 0 | 0 | -42859
2244 | C BLDG LGF & UGF- INTERNAL WIRING WORK-(LAB) | 0 | Started | Labour | (L)ELECTRICAL WORK. | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 42859 | 42859 | 1 | 42859 | 42859 | 1 | 0 | 0 | -42859
2245 | C BLDG LGF & UGF- SWITCHES, SOCKET & PLATE FITTING--(LAB) | 0 | Started | Labour | (L)ELECTRICAL WORK. | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 42859 | 42859 | 1 | 42859 | 42859 | 1 | 0 | 0 | -42859
2246 | C BLDG LGF & UGF- MISC. WORK & TESTING WORK-(LAB) | 0 | Tentative | Labour | (L)ELECTRICAL WORK. | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 7143 | 7143 | 0 | 0 | 0 | 1 | 1 | 0 | 0
2247 | C BLDG LGF & UGF- ELECTRICAL WORK RETENTION-(LAB) | 0 | Tentative | Labour | (L)ELECTRICAL WORK. | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 7143 | 7143 | 0 | 0 | 0 | 1 | 1 | 0 | 0
2248 | C Bldg Toilet, Kitchen with Passage & Balcony (24 N0S) WP W | 0 | Started | Labour | (L)BASE COAT (WP WORK) | NOS | 130 | 1 | 130 | 0 | 0 | 0 | 0 | 1 | 0 | 130 | 525.46 | 68309.995 | 105.3001 | 525.46 | 55331.15 | 130 | 24.6999 | 130 | -55201.15
2249 | C Bldg Toilet, Kitchen with Passage & Balcony (24 N0S) WP W | 0 | Started | Labour | (L)BRICK BAT (WP WORK) | NOS | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130 | 597.12 | 77625.002 | 105.2991 | 597.12 | 62875.71 | 130 | 24.7009 | 0 | -62875.71
2250 | C Bldg Toilet, Kitchen with Passage & Balcony (24 N0S) WP W | 0 | Started | Labour | (L)CHEMICAL COAT (WP WORK) | NOS | 130 | 1 | 130 | 0 | 0 | 0 | 0 | 1 | 0 | 130 | 286.62 | 37260.002 | 105.2982 | 286.62 | 30180.09 | 130 | 24.7018 | 130 | -30050.09
2251 | C Bldg Toilet, Kitchen with Passage & Balcony (24 N0S) WP W | 0 | Started | Labour | (L)FINISHING (WP WORK) | NOS | 130 | 1 | 130 | 0 | 0 | 0 | 0 | 1 | 0 | 130 | 843.13 | 109606.497 | 105.2996 | 843.13 | 88780.93 | 130 | 24.7004 | 130 | -88650.93
2252 | C Bldg Toilet, Kitchen with Passage & Balcony (24 N0S) WP W | 0 | Started | Labour | (L)KIT.KATTA & CLEANING (WP WORK) | NOS | 130 | 1 | 130 | 0 | 0 | 0 | 0 | 1 | 0 | 130 | 136.14 | 17698.499 | 0 | 0 | 0 | 130 | 130 | 130 | 130
2253 | C Bldg Toilet, Kitchen with Passage & Balcony (24 N0S) WP W | 0 | Started | Labour | (L)RETENTION (WP WORK) | NOS | 130 | 1 | 130 | 0 | 0 | 0 | 0 | 1 | 0 | 130 | 265.38 | 34499.998 | 0 | 0 | 0 | 130 | 130 | 130 | 130
2254 | INDENT-809/C BLDG/OFFICE SLIDING WINDOW/Mat.+Lab. | 0 | Started | Labour | (L)3 Track Aluminum Sliding Window (M+L) | SQFT | 1200 | 295 | 354000 | 0 | 0 | 0 | 0 | 295 | 0 | 1200 | 295 | 354000 | 191.667 | 295 | 56541.77 | 1200 | 1008.333 | 354000 | 297458.23
2255 | INDENT-809/C BLDG/OFFICE SLIDING WINDOW/Mat.+Lab. | 0 | Started | Labour | (L)Alu.Window Louver Toilet (M+L) 3' x 2' | SQFT | 138 | 224.2 | 30939.6 | 0 | 0 | 0 | 0 | 224.2 | 0 | 138 | 224.2 | 30939.6 | 0 | 0 | 0 | 138 | 138 | 30939.6 | 30939.6
2256 | SAFETY WORK: C BLDG/SAFETY WORK/INDENT-467 | 0 | Started | Labour | (L)SAFETY NET FIXING | SQFT | 37014.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27760.8 | 2.25 | 62461.8 | 14364.556 | 2.25 | 32320.25 | 37014.4 | 22649.844 | 0 | -32320.25
2257 | SAFETY WORK: C BLDG/SAFETY WORK/INDENT-467 | 0 | Started | Labour | (L)SAFETY NET REMOVING WORK | SQFT | 37014.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37014.4 | 1.25 | 46268 | 25902.2 | 1.25 | 32377.75 | 37014.4 | 11112.2 | 0 | -32377.75
2258 | C BLDG UGF OFFICE WINDOW INVISIBLE GRILL-23 NOS | 0 | Started | Labour | (L)INVISIBLE GRILL (LABOUR)-25% | SQFT | 1060.76 | 45 | 47734.2 | 0 | 0 | 0 | 0 | 45 | 0 | 1060.76 | 45 | 47734.2 | 1060.76 | 45 | 47734.2 | 1060.76 | 0 | 47734.2 | 0
2259 | C BLDG UGF OFFICE WINDOW INVISIBLE GRILL-23 NOS | 0 | Started | Labour | (L)INVISIBLE GRILL (MATERIAL)-70% | SQFT | 1060.76 | 148.68 | 157713.8 | 0 | 0 | 0 | 0 | 148.68 | 0 | 1060.76 | 148.68 | 157713.8 | 1060.76 | 148.68 | 157713.8 | 1060.76 | 0 | 157713.797 | -0.0032
2260 | C BLDG UGF OFFICE WINDOW INVISIBLE GRILL-23 NOS | 0 | Started | Labour | (L)INVISIBLE GRILL (RETENTION)-5% | SQFT | 1060.76 | 9 | 9546.84 | 0 | 0 | 0 | 0 | 9 | 0 | 1060.76 | 9 | 9546.84 | 1060.76 | 9 | 9546.84 | 1060.76 | 0 | 9546.84 | 0
2261 | C BLDG UGF OFFICE WINDOW INVISIBLE GRILL-LABOUR@25% | 0 | Started | Labour | (L)INVISIBLE GRILL (MATERIAL)-70% | SQFT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2262 | C BLDG UGF OFFICE WINDOW INVISIBLE GRILL-RETENTION@5% | 0 | Tentative | Labour | (L)INVISIBLE GRILL (MATERIAL)-70% | SQFT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2263 | C Bldg-Ceiling Gypsum (Mat+Lab)- 1st & 2nd Floor | 0 | Started | Labour | (L)Ceiling Gypsum Work | SQFT | 4401.0137 | 14.16 | 62318.35 | 0 | 0 | 0 | 0 | 14.16 | 0 | 4401.0137 | 12 | 52812.1644 | 4401.0137 | 12 | 52812.16 | 4401.0137 | 0 | 62318.354 | 9506.194
2264 | C Bldg-Ceiling Gypsum (Mat+Lab)-- 3rd & 4th Floor | 0 | Started | Labour | (L)Ceiling Gypsum Work | SQFT | 4401.0137 | 14.16 | 62318.35 | 0 | 0 | 0 | 0 | 14.16 | 0 | 4401.0137 | 12 | 52812.1644 | 4401.0137 | 12 | 52812.16 | 4401.0137 | 0 | 62318.354 | 9506.194
2265 | C Bldg-Ceiling Gypsum (Mat+Lab)- 5th & 6th Floor | 0 | Started | Labour | (L)Ceiling Gypsum Work | SQFT | 4567.0897 | 14.16 | 64669.99 | 0 | 0 | 0 | 0 | 14.16 | 0 | 4567.0897 | 12 | 54805.0764 | 4567.0897 | 12 | 54805.08 | 4567.0897 | 0 | 64669.99 | 9864.9102
2266 | C Bldg-Ceiling Gypsum (Mat+Lab)- 7th & 8th Floor | 0 | Tentative | Labour | (L)Ceiling Gypsum Work | SQFT | 4567.0897 | 14.16 | 64669.99 | 0 | 0 | 0 | 0 | 14.16 | 0 | 4567.0897 | 12 | 54805.0764 | 0 | 0 | 0 | 4567.0897 | 4567.0897 | 64669.99 | 64669.9902
2267 | C Bldg-Ceiling Gypsum (Mat+Lab)- 9th & 10th Floor | 0 | Tentative | Labour | (L)Ceiling Gypsum Work | SQFT | 4567.0897 | 14.16 | 64669.99 | 0 | 0 | 0 | 0 | 14.16 | 0 | 4567.0897 | 12 | 54805.0764 | 0 | 0 | 0 | 4567.0897 | 4567.0897 | 64669.99 | 64669.9902
2268 | C Bldg-Ceiling Gypsum (Mat+Lab)- 11th & 12th Floor | 0 | Tentative | Labour | (L)Ceiling Gypsum Work | SQFT | 4567.0897 | 14.16 | 64669.99 | 0 | 0 | 0 | 0 | 14.16 | 0 | 4567.0897 | 12 | 54805.0764 | 0 | 0 | 0 | 4567.0897 | 4567.0897 | 64669.99 | 64669.9902
2269 | C Bldg-Pass.Ceiling Gyp. (Mat+Lab)- 1st, 2nd & 3rd Floor | 0 | Started | Labour | (L)Ceiling Gypsum Work | SQFT | 1494.6839 | 14.16 | 21164.72 | 0 | 0 | 0 | 0 | 14.16 | 0 | 1494.6839 | 12 | 17936.2068 | 1494.6839 | 12 | 17936.21 | 1494.6839 | 0 | 21164.724 | 3228.514
2270 | C Bldg-Pass.Ceiling Gyp. (Mat+Lab)- 4th,5th & 6th Floor | 0 | Tentative | Labour | (L)Ceiling Gypsum Work | SQFT | 1494.6839 | 14.16 | 21164.72 | 0 | 0 | 0 | 0 | 14.16 | 0 | 1494.6839 | 12 | 17936.2068 | 0 | 0 | 0 | 1494.6839 | 1494.6839 | 21164.724 | 21164.724
2271 | C Bldg-Pass.Ceiling Gyp. (Mat+Lab)- 7th,8th & 9th Floor | 0 | Tentative | Labour | (L)Ceiling Gypsum Work | SQFT | 1577.7219 | 14.16 | 22340.54 | 0 | 0 | 0 | 0 | 14.16 | 0 | 1577.7219 | 12 | 18932.6628 | 0 | 0 | 0 | 1577.7219 | 1577.7219 | 22340.542 | 22340.5421
2272 | C Bldg-Pass.Ceiling Gyp. (Mat+Lab)- 10th,11th & 12th Floor | 0 | Tentative | Labour | (L)Ceiling Gypsum Work | SQFT | 1577.7219 | 14.16 | 22340.54 | 0 | 0 | 0 | 0 | 14.16 | 0 | 1577.7219 | 12 | 18932.6628 | 0 | 0 | 0 | 1577.7219 | 1577.7219 | 22340.542 | 22340.5421
2273 | C Bldg- Wall Gypsum. (Mat+Lab)- 1st & 2nd Floor | 0 | Started | Labour | (L)Wall Gypsum Work | SQFT | 13314.0497 | 27.14 | 361343.31 | 0 | 0 | 0 | 0 | 27.14 | 0 | 13314.0497 | 23.75 | 316208.6804 | 13314.0497 | 23.75 | 316208.68 | 13314.0497 | 0 | 361343.309 | 45134.6289
2274 | C Bldg- Wall Gypsum. (Mat+Lab)- 3rd & 4th Floor | 0 | Started | Labour | (L)Wall Gypsum Work | SQFT | 13314.0497 | 27.14 | 361343.31 | 0 | 0 | 0 | 0 | 27.14 | 0 | 13314.0497 | 23.75 | 316208.6804 | 13314.0497 | 23.75 | 316208.68 | 13314.0497 | 0 | 361343.309 | 45134.6289
2275 | C Bldg- Wall Gypsum. (Mat+Lab)- 5th & 6th Floor | 0 | Started | Labour | (L)Wall Gypsum Work | SQFT | 14265.0533 | 27.14 | 387153.55 | 0 | 0 | 0 | 0 | 27.14 | 0 | 14265.0533 | 23.75 | 338795.0159 | 14265.0533 | 23.75 | 338795.02 | 14265.0533 | 0 | 387153.547 | 48358.5266
2276 | C Bldg- Wall Gypsum. (Mat+Lab)- 7th & 8th Floor | 0 | Tentative | Labour | (L)Wall Gypsum Work | SQFT | 14265.0533 | 27.14 | 387153.55 | 0 | 0 | 0 | 0 | 27.14 | 0 | 14265.0533 | 23.75 | 338795.0159 | 0 | 0 | 0 | 14265.0533 | 14265.0533 | 387153.547 | 387153.5466
2277 | C Bldg- Wall Gypsum. (Mat+Lab)- 9th & 10th Floor | 0 | Tentative | Labour | (L)Wall Gypsum Work | SQFT | 15216.0569 | 27.14 | 412963.78 | 0 | 0 | 0 | 0 | 27.14 | 0 | 15216.0569 | 23.75 | 361381.3514 | 0 | 0 | 0 | 15216.0569 | 15216.0569 | 412963.784 | 412963.7843
2278 | C Bldg- Wall Gypsum. (Mat+Lab)- 11th & 12th Floor | 0 | Tentative | Labour | (L)Wall Gypsum Work | SQFT | 15216.0569 | 27.14 | 412963.78 | 0 | 0 | 0 | 0 | 27.14 | 0 | 15216.0569 | 23.75 | 361381.3514 | 0 | 0 | 0 | 15216.0569 | 15216.0569 | 412963.784 | 412963.7843
2279 | C Bldg- But. Filling Gypsum. (Mat+Lab)- 1st to 6th Floor | 0 | Tentative | Labour | (L)Wall Gypsum Work | SQFT | 4755.0178 | 27.14 | 129051.18 | 0 | 0 | 0 | 0 | 27.14 | 0 | 4755.0178 | 23.75 | 112931.6728 | 0 | 0 | 0 | 4755.0178 | 4755.0178 | 129051.183 | 129051.1831
2280 | C Bldg- But. Filling Gypsum. (Mat+Lab)- 7th to 12th Floor | 0 | Tentative | Labour | (L)Wall Gypsum Work | SQFT | 4755.0178 | 27.14 | 129051.18 | 0 | 0 | 0 | 0 | 27.14 | 0 | 4755.0178 | 23.75 | 112931.6728 | 0 | 0 | 0 | 4755.0178 | 4755.0178 | 129051.183 | 129051.1831
2281 | C Bldg- Wall Gypsum. (Lab)- Cleaning:60% | 0 | Tentative | Labour | (L)Wall Gypsum Work | SQFT | 1081.3627 | 27.14 | 29348.18 | 0 | 0 | 0 | 0 | 27.14 | 0 | 1081.3627 | 23.75 | 25682.3641 | 0 | 0 | 0 | 1081.3627 | 1081.3627 | 29348.184 | 29348.1837
2282 | C Bldg- Ceiling Gypsum. (Lab)- Cleaning:40% | 0 | Tentative | Labour | (L)Ceiling Gypsum Work | SQFT | 1431.3297 | 14.16 | 20267.63 | 0 | 0 | 0 | 0 | 14.16 | 0 | 1431.3297 | 12 | 17175.9564 | 0 | 0 | 0 | 1431.3297 | 1431.3297 | 20267.629 | 20267.6286
2283 | C Bldg- Wall Gypsum (Lab)- Misc.Work:60% | 0 | Tentative | Labour | (L)Wall Gypsum Work | SQFT | 360.4542 | 27.14 | 9782.73 | 0 | 0 | 0 | 0 | 27.14 | 0 | 360.4542 | 23.75 | 8560.7873 | 0 | 0 | 0 | 360.4542 | 360.4542 | 9782.727 | 9782.727
2284 | C Bldg- Ceiling Gypsum. (Lab)- Misc.Work:40% | 0 | Tentative | Labour | (L)Ceiling Gypsum Work | SQFT | 477.1099 | 14.16 | 6755.88 | 0 | 0 | 0 | 0 | 14.16 | 0 | 477.1099 | 12 | 5725.3188 | 0 | 0 | 0 | 477.1099 | 477.1099 | 6755.876 | 6755.8762
2285 | C Bldg- Wall Gypsum (Mat+Lab)-Retention | 0 | Tentative | Labour | (L)Wall Gypsum Work | SQFT | 3604.5422 | 27.14 | 97827.28 | 0 | 0 | 0 | 0 | 27.14 | 0 | 3604.5422 | 23.75 | 85607.8773 | 0 | 0 | 0 | 3604.5422 | 3604.5422 | 97827.275 | 97827.2753
2286 | C Bldg- Ceiling Gypsum. (Mat+Lab)- Retention | 0 | Tentative | Labour | (L)Ceiling Gypsum Work | SQFT | 4771.0989 | 14.16 | 67558.76 | 0 | 0 | 0 | 0 | 14.16 | 0 | 4771.0989 | 12 | 57253.1868 | 0 | 0 | 0 | 4771.0989 | 4771.0989 | 67558.76 | 67558.7604
2287 | C BLDG LGF LOBBY & UGF OFFICE, PASSAGE FALSE CEILING WORK | 0 | Started | Labour | (L)False Ceiling (Mat. + Lab.) | SQFT | 1480.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1480.48 | 65 | 96231.2 | 1480.48 | 65 | 96231.2 | 1480.48 | 0 | 0 | -96231.2
2288 | C BLDG LGF LOBBY & UGF OFFICE, PASSAGE FALSE CEILING WORK | 0 | Started | Labour | (L)Vertical Patta False Ceiling (M+L) | RFT | 79.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79.04 | 55 | 4347.2 | 79.04 | 55 | 4347.2 | 79.04 | 0 | 0 | -4347.2
2289 | C BLDG UGF WALL PUNNING-OFFICE:01-07 (MAT+LAB) | 0 | Tentative | Labour | (L)Wall Gypsum Work | SQFT | 2573.0526 | 27.14 | 69832.65 | 0 | 0 | 0 | 0 | 27.14 | 0 | 2573.0526 | 23.75 | 61109.9993 | 0 | 0 | 0 | 2573.0526 | 2573.0526 | 69832.648 | 69832.6476
2290 | C BLDG UGF WALL PUNNING-OFFICE: 08-11 (MAT+LAB) | 0 | Tentative | Labour | (L)Wall Gypsum Work | SQFT | 1583.4105 | 27.14 | 42973.76 | 0 | 0 | 0 | 0 | 27.14 | 0 | 1583.4105 | 23.75 | 37605.9994 | 0 | 0 | 0 | 1583.4105 | 1583.4105 | 42973.761 | 42973.761
2291 | C BLDG UGF WALL PUNNING-OFFICE: 12-17 (MAT+LAB) | 0 | Tentative | Labour | (L)Wall Gypsum Work | SQFT | 2276.1684 | 27.14 | 61775.21 | 0 | 0 | 0 | 0 | 27.14 | 0 | 2276.1684 | 23.75 | 54058.9995 | 0 | 0 | 0 | 2276.1684 | 2276.1684 | 61775.21 | 61775.2104
2292 | C BLDG UGF WALL PUNNING-OFFICE: 18-23 (MAT+LAB) | 0 | Tentative | Labour | (L)Wall Gypsum Work | SQFT | 3463.7053 | 27.14 | 94004.96 | 0 | 0 | 0 | 0 | 27.14 | 0 | 3463.7053 | 23.75 | 82263.0009 | 0 | 0 | 0 | 3463.7053 | 3463.7053 | 94004.962 | 94004.9618
2293 | C BLDG UGF WALL PUNNING- BUT. FILLING (MAT+LAB) | 0 | Started | Labour | (L)Wall Gypsum Work | SQFT | 634.3579 | 27.14 | 17216.47 | 0 | 0 | 0 | 0 | 27.14 | 0 | 634.3579 | 23.75 | 15066.0001 | 634.3579 | 23.75 | 15066 | 634.3579 | 0 | 17216.473 | 2150.4734
2294 | C BLDG UGF WALL PUNNING- MISC. WORK (MAT+LAB) | 0 | Started | Labour | (L)Wall Gypsum Work | SQFT | 255.3043 | 27.14 | 6928.96 | 0 | 0 | 0 | 0 | 27.14 | 0 | 255.3043 | 23.75 | 6063.4771 | 255.3043 | 23.75 | 6063.48 | 255.3043 | 0 | 6928.959 | 865.4787
2295 | C BLDG UGF WALL PUNNING- CLEANING WORK (MAT+LAB) | 0 | Started | Labour | (L)Wall Gypsum Work | SQFT | 183.0058 | 27.14 | 4966.78 | 0 | 0 | 0 | 0 | 27.14 | 0 | 183.0058 | 23.75 | 4346.3878 | 183.0058 | 23.75 | 4346.39 | 183.0058 | 0 | 4966.777 | 620.3874
2296 | C BLDG UGF WALL PUNNING- RETENTION (MAT+LAB) | 0 | Tentative | Labour | (L)Wall Gypsum Work | SQFT | 457.5426 | 27.14 | 12417.71 | 0 | 0 | 0 | 0 | 27.14 | 0 | 457.5426 | 23.75 | 10866.6368 | 0 | 0 | 0 | 457.5426 | 457.5426 | 12417.706 | 12417.7062
2297 | C BLDG UGF CEILING PUNNING-OFFICE:01-07 (MAT+LAB) | 0 | Tentative | Labour | (L)Ceiling Gypsum Work | SQFT | 895.3469 | 14.16 | 12678.11 | 0 | 0 | 0 | 0 | 14.16 | 0 | 895.3469 | 12.25 | 10967.9995 | 0 | 0 | 0 | 895.3469 | 895.3469 | 12678.112 | 12678.1121
2298 | C BLDG UGF CEILING PUNNING-OFFICE: 08-11 (MAT+LAB) | 0 | Tentative | Labour | (L)Ceiling Gypsum Work | SQFT | 551.0204 | 14.16 | 7802.45 | 0 | 0 | 0 | 0 | 14.16 | 0 | 551.0204 | 12.25 | 6749.9999 | 0 | 0 | 0 | 551.0204 | 551.0204 | 7802.449 | 7802.4489
2299 | C BLDG UGF CEILING PUNNING-OFFICE: 12-17 (MAT+LAB) | 0 | Tentative | Labour | (L)Ceiling Gypsum Work | SQFT | 792.0816 | 14.16 | 11215.88 | 0 | 0 | 0 | 0 | 14.16 | 0 | 792.0816 | 12.25 | 9702.9996 | 0 | 0 | 0 | 792.0816 | 792.0816 | 11215.876 | 11215.8755
2300 | C BLDG UGF CEILING PUNNING-OFFICE: 18-23 (MAT+LAB) | 0 | Tentative | Labour | (L)Ceiling Gypsum Work | SQFT | 1205.3061 | 14.16 | 17067.13 | 0 | 0 | 0 | 0 | 14.16 | 0 | 1205.3061 | 12.25 | 14764.9997 | 0 | 0 | 0 | 1205.3061 | 1205.3061 | 17067.134 | 17067.1344
2301 | C BLDG UGF CEILING PUNNING- MISC. WORK (MAT+LAB) | 0 | Started | Labour | (L)Ceiling Gypsum Work | SQFT | 242.9814 | 14.16 | 3440.62 | 0 | 0 | 0 | 0 | 14.16 | 0 | 242.9814 | 12.25 | 2976.5222 | 242.9814 | 12.25 | 2976.52 | 242.9814 | 0 | 3440.617 | 464.0966
2302 | C BLDG UGF CEILING PUNNING- CLEANING WORK (MAT+LAB) | 0 | Started | Labour | (L)Ceiling Gypsum Work | SQFT | 174.1725 | 14.16 | 2466.28 | 0 | 0 | 0 | 0 | 14.16 | 0 | 174.1725 | 12.25 | 2133.6131 | 174.1725 | 12.25 | 2133.61 | 174.1725 | 0 | 2466.283 | 332.6726
2303 | C BLDG UGF CEILING PUNNING- RETENTION (MAT+LAB) | 0 | Tentative | Labour | (L)Ceiling Gypsum Work | SQFT | 435.4581 | 14.16 | 6166.09 | 0 | 0 | 0 | 0 | 14.16 | 0 | 435.4581 | 12.25 | 5334.3617 | 0 | 0 | 0 | 435.4581 | 435.4581 | 6166.087 | 6166.0867
2304 | C BLDG GYPSUM WORK 6TH TO 12TH FLOOR-FIBER MESH (IND-205) | 0 | Tentative | Material | (M)Fibre Mesh-50 Mtr/Bundle (width-6'') | BUNDLE | 38 | 177 | 6726 | 38 | 177 | 6726 | 0 | 177 | 0 | 38 | 260.22 | 9888.36 | 0 | 0 | 0 | 38 | 38 | 6726 | 6726
2305 | C BLDG LGF SHOP ROLLING SHUTTER-COVER | 0 | Started | Labour | (L)Fare Charges Transportation - | NOS | 1499.9985 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1499.9985 | 1 | 1499.9985 | 1499.9985 | 1 | 1500 | 1499.9985 | 0 | 0 | -1500
2306 | C BLDG LGF SHOP ROLLING SHUTTER-COVER | 0 | Started | Labour | (L)Rolling Shutter Top Cover | RFT | 92.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92.5 | 150 | 13875 | 92.5 | 150 | 13875 | 92.5 | 0 | 0 | -13875
2307 | C Bldg-Window Grill 1st & 2nd Floor | 0 | Started | Labour | (L)M.S.Grill (Mat.+Lab.) | SQFT | 446.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 446.35 | 100 | 44635 | 446.35 | 100 | 44635 | 446.35 | 0 | 0 | -44635
2308 | C Bldg-Window Grill 3rd & 4th Floor | 0 | Started | Labour | (L)M.S.Grill (Mat.+Lab.) | SQFT | 476.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 476.11 | 100 | 47611 | 476.11 | 100 | 47611 | 476.11 | 0 | 0 | -47611
2309 | C Bldg-Window Grill 5th & 6th Floor | 0 | Started | Labour | (L)M.S.Grill (Mat.+Lab.) | SQFT | 476.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 476.11 | 100 | 47611 | 476.11 | 100 | 47611 | 476.11 | 0 | 0 | -47611
2310 | C Bldg-Window Grill 7th & 8th Floor | 0 | Tentative | Labour | (L)M.S.Grill (Mat.+Lab.) | SQFT | 505.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 505.87 | 100 | 50587 | 0 | 0 | 0 | 505.87 | 505.87 | 0 | 0
2311 | C Bldg-Window Grill 9th & 10th Floor | 0 | Started | Labour | (L)M.S.Grill (Mat.+Lab.) | SQFT | 505.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 505.87 | 100 | 50587 | 0 | 0 | 0 | 505.87 | 505.87 | 0 | 0
2312 | C Bldg-Window Grill 11th & 12th Floor | 0 | Tentative | Labour | (L)M.S.Grill (Mat.+Lab.) | SQFT | 565.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 565.38 | 100 | 56538 | 0 | 0 | 0 | 565.38 | 565.38 | 0 | 0
2313 | C Bldg-Terrace Railing up to 6th Floor | 0 | Started | Labour | (L)M.S. Railing (Mat.+Lab.) | SQFT | 255.4348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255.4348 | 115 | 29375.002 | 255.4348 | 115 | 29375 | 255.4348 | 0 | 0 | -29375
2314 | C Bldg-Terrace Railing up to 12th Floor | 0 | Started | Labour | (L)M.S. Railing (Mat.+Lab.) | SQFT | 474.3826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 474.3826 | 115 | 54553.999 | 474.3826 | 115 | 54554 | 474.3826 | 0 | 0 | -54554
2315 | C Bldg-Window Grill Misc.Work | 0 | Tentative | Labour | (L)M.S.Grill (Mat.+Lab.) | SQFT | 75.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75.77 | 100 | 7577 | 0 | 0 | 0 | 75.77 | 75.77 | 0 | 0
2316 | C Bldg-Terrace Railing Misc.Work | 0 | Tentative | Labour | (L)M.S. Railing (Mat.+Lab.) | SQFT | 5.4522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.4522 | 115 | 627.003 | 0 | 0 | 0 | 5.4522 | 5.4522 | 0 | 0
2317 | C Bldg-Window Grill Retention | 0 | Tentative | Labour | (L)M.S.Grill (Mat.+Lab.) | SQFT | 175.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 175.11 | 100 | 17511 | 0 | 0 | 0 | 175.11 | 175.11 | 0 | 0
2318 | C Bldg-Terrace Railing Retention | 0 | Tentative | Labour | (L)M.S. Railing (Mat.+Lab.) | SQFT | 26.087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.087 | 115 | 3000.005 | 0 | 0 | 0 | 26.087 | 26.087 | 0 | 0
2319 | C Bldg-Window Grill 1st & 2nd Floor | 0 | Tentative | Labour | (L)M.S.Grill (Mat.+Lab.) | SQFT | 707.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 707.03 | 100 | 70703 | 0 | 0 | 0 | 707.03 | 707.03 | 0 | 0
2320 | C Bldg-Window Grill 3rd & 4th Floor | 0 | Tentative | Labour | (L)M.S.Grill (Mat.+Lab.) | SQFT | 754.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 754.17 | 100 | 75417 | 0 | 0 | 0 | 754.17 | 754.17 | 0 | 0
2321 | C Bldg-Window Grill 5th & 6th Floor | 0 | Tentative | Labour | (L)M.S.Grill (Mat.+Lab.) | SQFT | 754.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 754.17 | 100 | 75417 | 0 | 0 | 0 | 754.17 | 754.17 | 0 | 0
2322 | C Bldg-Window Grill 7th & 8th Floor | 0 | Tentative | Labour | (L)M.S.Grill (Mat.+Lab.) | SQFT | 801.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 801.3 | 100 | 80130 | 0 | 0 | 0 | 801.3 | 801.3 | 0 | 0
2323 | C Bldg-Window Grill 9th & 10th Floor | 0 | Started | Labour | (L)M.S.Grill (Mat.+Lab.) | SQFT | 801.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 801.3 | 100 | 80130 | 801.3 | 100 | 80130 | 801.3 | 0 | 0 | -80130
2324 | C Bldg-Window Grill 11th & 12th Floor | 0 | Tentative | Labour | (L)M.S.Grill (Mat.+Lab.) | SQFT | 895.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 895.57 | 100 | 89557 | 0 | 0 | 0 | 895.57 | 895.57 | 0 | 0
2325 | C Bldg-Window Grill Misc.Work | 0 | Tentative | Labour | (L)M.S.Grill (Mat.+Lab.) | SQFT | 101.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101.37 | 100 | 10137 | 0 | 0 | 0 | 101.37 | 101.37 | 0 | 0
2326 | C Bldg-Window Grill Retention | 0 | Tentative | Labour | (L)M.S.Grill (Mat.+Lab.) | SQFT | 253.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 253.42 | 100 | 25342 | 0 | 0 | 0 | 253.42 | 253.42 | 0 | 0
2327 | C WING MISC.FABRIACTION WORK | 0 | Started | Labour | (L)Cement sheet covering LG and UG | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 33000 | 33000 | 1 | 33000 | 33000 | 1 | 0 | 0 | -33000
2328 | C WING MISC.FABRIACTION WORK | 0 | Started | Labour | (L)SAFETY DOOR | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 8900 | 8900 | 1 | 8900 | 8900 | 1 | 0 | 0 | -8900
2329 | C WING MISC.FABRIACTION WORK | 0 | Started | Labour | (L)Small Door below Staircase | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2700 | 2700 | 1 | 2700 | 2700 | 1 | 0 | 0 | -2700
2330 | C WING MISC.FABRIACTION WORK | 0 | Started | Labour | (L)WATER TANK STAND 7'x7' & LADDER | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 10000 | 10000 | 1 | 10000 | 10000 | 1 | 0 | 0 | -10000
2331 | C WING ST-CASE & LIFT TOP & A BLDG GODOWN FRAMING & PATRA FI | 0 | Started | Labour | (L)G.I. Sheet Fixing | SQFT | 1954.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1954.6 | 10 | 19546 | 1879.805 | 10 | 18798.05 | 1954.6 | 74.795 | 0 | -18798.05
2332 | C WING 2ND SLAB LEVELFRAME MAKING & PATRA FIXING WORK | 0 | Started | Labour | (L)G.I. Sheet Fixing | SQFT | 967.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 967.9 | 12 | 11614.8 | 967.89 | 12 | 11614.68 | 967.9 | 0.01 | 0 | -11614.68
2333 | C WING 6M ROAD SIDE,SHOP FRONT TOP, A BLDG GODOWN PATRA REM | 0 | Started | Labour | (L)Patra (Tin sheet) Removing work | SQFT | 1224.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1224.53 | 5 | 6122.65 | 1149.7 | 5 | 5748.5 | 1224.53 | 74.83 | 0 | -5748.5
2334 | A & C-wing Lift Barriacating Grill Making | 0 | Started | Labour | (L)MC-LABOUR | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2335 | A & C-wing Lift Barriacating Grill Making | 0 | Started | Labour | (L)SKILLED (FABRICATION) | NOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2336 | A,B & C-Wing lift grill making work & B-Wing lift smoke wind | 0 | Started | Labour | (L)Lift front barricading grill-7' x 4' | NOS | 52 | 295 | 15340 | 0 | 0 | 0 | 0 | 295 | 0 | 52 | 269.24 | 14000.48 | 52 | 269.24 | 14000.48 | 52 | 0 | 15340 | 1339.52
2337 | A,B & C-Wing lift grill making work & B-Wing lift smoke wind | 0 | Started | Labour | (L)Smoke window -2' x 2' | NOS | 1 | 2124 | 2124 | 0 | 0 | 0 | 0 | 2124 | 0 | 1 | 1800 | 1800 | 1 | 1800 | 1800 | 1 | 0 | 2124 | 324
2338 | INDENT-695/C WING/WATERPROOFING WORK | 0 | Started | Material | (M)Artificial Sand | BRASS | 26 | 5880 | 152880 | 26 | 5880 | 152880 | 0 | 5880 | 0 | 26 | 6300 | 163800 | 0 | 0 | 0 | 26 | 26 | 152880 | 152880
2339 | INDENT-695/C WING/WATERPROOFING WORK | 0 | Started | Material | (M)CEMENT PPC 50KG | BAG | 455 | 320 | 145600 | 455 | 320 | 145600 | 0 | 320 | 0 | 455 | 305 | 138775.0455 | 0 | 0 | 0 | 455 | 455 | 145600 | 145600
2340 | INDENT-695/C WING/WATERPROOFING WORK | 0 | Started | Material | (M)Dr.Fixit LW+ 50Ltr Drum | DRUM | 2 | 3800 | 7600 | 0 | 0 | 0 | 0 | 3800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 7600 | 7600
2341 | INDENT-695/C WING/WATERPROOFING WORK | 0 | Started | Material | (M)Pidifin - 2k - 15kg | PACKET | 111 | 1465 | 162615 | 0 | 0 | 0 | 0 | 1465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 111 | 111 | 162615 | 162615
2342 | INDENT-695/C WING/WATERPROOFING WORK | 0 | Started | Material | (M)Red Bricks 4" | NOS | 17540 | 8.5 | 149090 | 17540 | 8.5 | 149090 | 0 | 8.5 | 0 | 17540 | 8.96 | 157158.4 | 0 | 0 | 0 | 17540 | 17540 | 149090 | 149090
2343 | C BLDG SKIRTING LEVEL CEMENT SLURRY & DPS-WATERPROOFING WORK | 0 | Tentative | Material | (M)Perma Bond Sbr - 25 Lit | BUCKET | 6 | 5500 | 33000 | 6 | 5500 | 33000 | 0 | 5500 | 0 | 6 | 5300.01 | 31800.0402 | 0 | 0 | 0 | 6 | 6 | 33000 | 33000
2344 | C BLDG SKIRTING LEVEL CEMENT SLURRY & DPS-WATERPROOFING WORK | 0 | Tentative | Material | (M)PERMA DPS 25 LTR BUCKET | BUCKET | 75 | 7139 | 535425 | 75 | 7139 | 535425 | 0 | 7139 | 0 | 75 | 275.33 | 20649.75 | 0 | 0 | 0 | 75 | 75 | 535425 | 535425
2345 | C BLDG APPLICATION OF DPS IN SKIRTING AREA (PER FLAT) | 0 | Started | Labour | (L)1 BHK-DPS Chemical Coating-Labour | NOS | 130 | 700 | 91000 | 0 | 0 | 0 | 0 | 700 | 0 | 130 | 700 | 91000 | 55 | 700 | 38500 | 130 | 75 | 91000 | 52500
2346 | C BLDG/TOP TERRACE & OHWT WP WORK-MATERIAL | 0 | Tentative | Material | (M)Artificial Sand | BRASS | 26 | 5880 | 152880 | 26 | 5880 | 152880 | 0 | 5880 | 0 | 26 | 6300 | 163800 | 0 | 0 | 0 | 26 | 26 | 152880 | 152880
2347 | C BLDG/TOP TERRACE & OHWT WP WORK-MATERIAL | 0 | Tentative | Material | (M)CEMENT PPC 50KG | BAG | 421 | 320 | 134720 | 421 | 320 | 134720 | 0 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 421 | 421 | 134720 | 134720
2348 | C BLDG/TOP TERRACE & OHWT WP WORK-MATERIAL | 0 | Tentative | Material | (M)Dr. Fixit URP 20 LTR Bucket | LITRE | 220 | 231.68 | 50969.6 | 220 | 231.68 | 50969.6 | 0 | 231.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 220 | 50969.6 | 50969.6
2349 | C BLDG/TOP TERRACE & OHWT WP WORK-MATERIAL | 0 | Tentative | Material | (M)Dr.Fixit LW+ 50Ltr Drum | DRUM | 2 | 3800 | 7600 | 2 | 3800 | 7600 | 0 | 3800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 7600 | 7600
2350 | C BLDG/TOP TERRACE & OHWT WP WORK-MATERIAL | 0 | Tentative | Material | (M)Pidifin - 2k - 15kg | PACKET | 46 | 1465 | 67390 | 46 | 1465 | 67390 | 0 | 1465 | 0 | 46 | 1705.1 | 78434.6 | 0 | 0 | 0 | 46 | 46 | 67390 | 67390
2351 | C BLDG/TOP TERRACE & OHWT WP WORK-MATERIAL | 0 | Tentative | Material | (M)Red Bricks 4" | NOS | 20700 | 8.5 | 175950 | 20700 | 8.5 | 175950 | 0 | 8.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20700 | 20700 | 175950 | 175950
2352 | C BLDG SIGNAGE BOARD/NAME PLATES | 0 | Tentative | Material | (M)Directory Board-6' x 4' | NOS | 1 | 29736 | 29736 | 1 | 29736 | 29736 | 0 | 29736 | 0 | 1 | 29736 | 29736 | 0 | 0 | 0 | 1 | 1 | 29736 | 29736
2353 | C BLDG SIGNAGE BOARD/NAME PLATES | 0 | Tentative | Material | (M)Office Number Plates- 6'' x 6'' | NOS | 25 | 177 | 4425 | 25 | 177 | 4425 | 0 | 177 | 0 | 25 | 127.44 | 3186 | 0 | 0 | 0 | 25 | 25 | 4425 | 4425
2354 | C BLDG 3RD ST-CASE RAILLING WORK (M+L) | 0 | Started | Labour | (L)SS PIPE RAILLING (M+L) | RFT | 22 | 767 | 16874 | 0 | 0 | 0 | 0 | 767 | 0 | 22 | 767 | 16874 | 22 | 767 | 16874 | 22 | 0 | 16874 | 0
2355 | C Wing CAR Policy: 1st Installments (at policy inception) | 0 | Started | Labour | (L)CAR Policy-Premium | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 286506.36 | 286506.36 | 1 | 286506.36 | 286506.36 | 1 | 0 | 1.18 | -286505.18
2356 | C Wing CAR Policy: 2nd Installments | 0 | Tentative | Labour | (L)CAR Policy-Premium | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 22495.52 | 22495.52 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
2357 | C Wing CAR Policy: 3rd Installments | 0 | Tentative | Labour | (L)CAR Policy-Premium | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 22495.52 | 22495.52 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
2358 | DELETED | 0 | Tentative | Labour | (L)CAR Policy-Premium | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
2359 | DELETED | 0 | Tentative | Labour | (L)CAR Policy-Premium | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
2360 | DELETED | 0 | Tentative | Labour | (L)CAR Policy-Premium | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
2361 | DELETED | 0 | Tentative | Labour | (L)CAR Policy-Premium | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
2362 | DELETED | 0 | Tentative | Labour | (L)CAR Policy-Premium | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
2363 | DELETED | 0 | Tentative | Labour | (L)CAR Policy-Premium | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
2364 | C BLDG CORE CUTTING WORK -DEPTH-5'' | 0 | Started | Labour | (L)Core Cutting Dia-100mm | Inches | 270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270 | 45 | 12150 | 270 | 45 | 12150 | 270 | 0 | 0 | -12150
2365 | C BLDG CORE CUTTING WORK -DEPTH-5'' | 0 | Started | Labour | (L)Core Cutting Dia-125mm | Inches | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 50 | 9000 | 180 | 50 | 9000 | 180 | 0 | 0 | -9000
2366 | C BLDG CORE CUTTING WORK -DEPTH-5'' | 0 | Started | Labour | (L)Core Cutting Dia-50mm | Inches | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 30 | 2100 | 70 | 30 | 2100 | 70 | 0 | 0 | -2100
2367 | C BLDG CORE CUTTING WORK -DEPTH-5'' | 0 | Started | Labour | (L)Core Cutting Dia-75mm | Inches | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 35 | 2450 | 70 | 35 | 2450 | 70 | 0 | 0 | -2450
2368 | C BLDG CORE CUTTING WORK -DEPTH-9'' | 0 | Started | Labour | (L)Core Cutting Dia-100mm | Inches | 189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 189 | 45 | 8505 | 189 | 45 | 8505 | 189 | 0 | 0 | -8505
2369 | C BLDG CORE CUTTING WORK -DEPTH-9'' | 0 | Started | Labour | (L)Core Cutting Dia-125mm | Inches | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 50 | 1350 | 27 | 50 | 1350 | 27 | 0 | 0 | -1350
2370 | C BLDG CORE CUTTING WORK -DEPTH-9'' | 0 | Started | Labour | (L)Core Cutting Dia-75mm | Inches | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 35 | 1260 | 36 | 35 | 1260 | 36 | 0 | 0 | -1260
2371 | C BLDG BALC.& TOILET CORE CUTTING WORK. | 0 | Started | Labour | (L)Core Cutting Dia-100mm | Inches | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 45 | 5625 | 0 | 0 | 0 | 125 | 125 | 0 | 0
2372 | C BLDG BALC.& TOILET CORE CUTTING WORK. | 0 | Started | Labour | (L)Core Cutting Dia-50mm | Inches | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 30 | 150 | 0 | 0 | 0 | 5 | 5 | 0 | 0
2373 | C BLDG CORE CUTTING & OHWT PARDI BAR REBARING WORK | 0 | Started | Labour | (L)Core Cutting Dia-100mm | Inches | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 45 | 1215 | 27 | 45 | 1215 | 27 | 0 | 0 | -1215
2374 | C BLDG CORE CUTTING & OHWT PARDI BAR REBARING WORK | 0 | Started | Labour | (L)Rebaring Work Dia 10 mm | NOS | 30 | 50 | 1500 | 0 | 0 | 0 | 0 | 50 | 0 | 30 | 60 | 1800 | 28 | 60 | 1680 | 30 | 2 | 1500 | -180
2375 | CBLDG LOWER GROUNG FLOOR SHOP-23 TO 31 | 0 | Started | Labour | (L)LGF SHOPS-ACID WASH (BIG) | NOS | 7 | 830 | 5810 | 0 | 0 | 0 | 0 | 830 | 0 | 7 | 830 | 5810 | 0 | 0 | 0 | 7 | 7 | 5810 | 5810
2376 | CBLDG LOWER GROUNG FLOOR SHOP-23 TO 31 | 0 | Started | Labour | (L)LGF SHOPS-ACID WASH (SMALL) | NOS | 2 | 500 | 1000 | 0 | 0 | 0 | 0 | 500 | 0 | 2 | 500 | 1000 | 0 | 0 | 0 | 2 | 2 | 1000 | 1000
2377 | CBLDG UPPER GROUNG FLOOR OFFICES-01 TO 25 | 0 | Started | Labour | (L)UGF OFFICES-ACID WASH (BIG) | NOS | 6 | 725 | 4350 | 0 | 0 | 0 | 0 | 725 | 0 | 6 | 725 | 4350 | 6 | 725 | 4350 | 6 | 0 | 4350 | 0
2378 | CBLDG UPPER GROUNG FLOOR OFFICES-01 TO 25 | 0 | Started | Labour | (L)UGF OFFICES-ACID WASH (SMALL) | NOS | 19 | 500 | 9500 | 0 | 0 | 0 | 0 | 500 | 0 | 19 | 500 | 9500 | 19 | 500 | 9500 | 19 | 0 | 9500 | 0
2379 | C BLDG UGF OFFICE & LOBBY OBD PAINT (MAT.)-PUTTY 2 COAT | 0 | Started | Labour | (L)INTERNAL OBD PAINT (WALL & CEILING) | FLOORS | 3214.8147 | 1.18 | 3793.48 | 0 | 0 | 0 | 0 | 1.18 | 0 | 3214.8147 | 8.85 | 28451.1103 | 3214.8147 | 8.85 | 28451.11 | 3214.8147 | 0 | 3793.481 | -24657.6287
2380 | C BLDG UGF OFFICE & LOBBY OBD PAINT (MAT.)-1ST COAT PAINT | 0 | Started | Labour | (L)INTERNAL OBD PAINT (WALL & CEILING) | FLOORS | 2755.5555 | 1.18 | 3251.56 | 0 | 0 | 0 | 0 | 1.18 | 0 | 2755.5555 | 8.85 | 24386.6663 | 2755.5555 | 8.85 | 24386.67 | 2755.5555 | 0 | 3251.556 | -21135.1145
2381 | C BLDG UGF OFFICE & LOBBY OBD PAINT (MAT.)-2ND COAT PAINT | 0 | Started | Labour | (L)INTERNAL OBD PAINT (WALL & CEILING) | FLOORS | 3214.8147 | 1.18 | 3793.48 | 0 | 0 | 0 | 0 | 1.18 | 0 | 3214.8147 | 8.85 | 28451.1103 | 3214.8147 | 8.85 | 28451.11 | 3214.8147 | 0 | 3793.481 | -24657.6287
2382 | C BLDG LGF LOBBY & ST CASE OBD PAINT (MAT.)-PUTTY 2 COAT | 0 | Started | Labour | (L)INTERNAL OBD PAINT (WALL & CEILING) | FLOORS | 310.5838 | 1.18 | 366.49 | 0 | 0 | 0 | 0 | 1.18 | 0 | 310.5838 | 8.85 | 2748.6585 | 310.5838 | 8.85 | 2748.66 | 310.5838 | 0 | 366.489 | -2382.1711
2383 | C BLDG LGF LOBBY & ST CASE OBD PAINT (MAT.)-1ST COAT PAINT | 0 | Started | Labour | (L)INTERNAL OBD PAINT (WALL & CEILING) | FLOORS | 221.8456 | 1.18 | 261.78 | 0 | 0 | 0 | 0 | 1.18 | 0 | 221.8456 | 8.85 | 1963.342 | 221.8456 | 8.85 | 1963.34 | 221.8456 | 0 | 261.778 | -1701.5622
2384 | C BLDG LGF LOBBY & ST CASE OBD PAINT (MAT.)-2ND COAT PAINT | 0 | Started | Labour | (L)INTERNAL OBD PAINT (WALL & CEILING) | FLOORS | 207.0559 | 1.18 | 244.33 | 0 | 0 | 0 | 0 | 1.18 | 0 | 207.0559 | 8.85 | 1832.4393 | 207.0559 | 8.85 | 1832.44 | 207.0559 | 0 | 244.326 | -1588.114
2385 | C BLDG LGF LOBBY WALL TEXTURE , PAINTING WORK-(MAT.) | 0 | Started | Labour | (L)TEXTURE WITH 2-COAT PAINT | SQFT | 504.5221 | 27 | 13622.1 | 0 | 0 | 0 | 0 | 27 | 0 | 504.5221 | 31.86 | 16074.0767 | 504.5221 | 31.86 | 16074.08 | 504.5221 | 0 | 13622.097 | -2451.9833
2386 | C BLDG UGF OFFICE & LOBBY OBD PAINT (LAB.)-PUTTY 2 COAT | 0 | Started | Labour | (L)INTERNAL OBD PAINT (WALL & CEILING) | FLOORS | 3214.8147 | 1.18 | 3793.48 | 0 | 0 | 0 | 0 | 1.18 | 0 | 3214.8147 | 7.5 | 24111.1103 | 3214.8147 | 7.5 | 24111.11 | 3214.8147 | 0 | 3793.481 | -20317.6287
2387 | C BLDG UGF OFFICE & LOBBY OBD PAINT (LAB.)-1ST COAT PAINT | 0 | Started | Labour | (L)INTERNAL OBD PAINT (WALL & CEILING) | FLOORS | 2755.5555 | 1.18 | 3251.56 | 0 | 0 | 0 | 0 | 1.18 | 0 | 2755.5555 | 7.5 | 20666.6663 | 2755.5555 | 7.5 | 20666.67 | 2755.5555 | 0 | 3251.556 | -17415.1145
2388 | C BLDG UGF OFFICE & LOBBY OBD PAINT (LAB.)-2ND COAT PAINT | 0 | Started | Labour | (L)INTERNAL OBD PAINT (WALL & CEILING) | FLOORS | 3214.8147 | 1.18 | 3793.48 | 0 | 0 | 0 | 0 | 1.18 | 0 | 3214.8147 | 7.5 | 24111.1103 | 3214.8147 | 7.5 | 24111.11 | 3214.8147 | 0 | 3793.481 | -20317.6287
2389 | C BLDG LGF LOBBY & ST CASE OBD PAINT (MAT.)-PUTTY 2 COAT | 0 | Started | Labour | (L)INTERNAL OBD PAINT (WALL & CEILING) | FLOORS | 310.5838 | 1.18 | 366.49 | 0 | 0 | 0 | 0 | 1.18 | 0 | 310.5838 | 7.5 | 2329.3785 | 310.5838 | 7.5 | 2329.38 | 310.5838 | 0 | 366.489 | -1962.8911
2390 | C BLDG LGF LOBBY & ST CASE OBD PAINT (MAT.)-1ST COAT PAINT | 0 | Started | Labour | (L)INTERNAL OBD PAINT (WALL & CEILING) | FLOORS | 221.8456 | 1.18 | 261.78 | 0 | 0 | 0 | 0 | 1.18 | 0 | 221.8456 | 7.5 | 1663.842 | 221.8456 | 7.5 | 1663.84 | 221.8456 | 0 | 261.778 | -1402.0622
2391 | C BLDG LGF LOBBY & ST CASE OBD PAINT (MAT.)-2ND COAT PAINT | 0 | Started | Labour | (L)INTERNAL OBD PAINT (WALL & CEILING) | FLOORS | 207.0559 | 1.18 | 244.33 | 0 | 0 | 0 | 0 | 1.18 | 0 | 207.0559 | 7.5 | 1552.9193 | 207.0559 | 7.5 | 1552.92 | 207.0559 | 0 | 244.326 | -1308.594
2392 | C BLDG LGF LOBBY WALL TEXTURE , PAINTING WORK (LAB) | 0 | Started | Labour | (L)TEXTURE WITH 2-COAT PAINT | SQFT | 504.5221 | 27 | 13622.1 | 0 | 0 | 0 | 0 | 27 | 0 | 504.5221 | 27 | 13622.0967 | 504.5221 | 27 | 13622.1 | 504.5221 | 0 | 13622.097 | -0.0033
2393 | CLEANING.MISC. & PF-UGF OFFICE & LOBBY INTERNAL PAINT | 0 | Started | Labour | (L)INTERNAL OBD PAINT (WALL & CEILING) | FLOORS | 916.722 | 1.18 | 1081.73 | 0 | 0 | 0 | 0 | 1.18 | 0 | 916.722 | 7.5 | 6875.415 | 916.722 | 7.5 | 6875.42 | 916.722 | 0 | 1081.732 | -5793.688
2394 | CLEANING.MISC. & PF-LGF LOBBY & ST CASE INTERNAL PAINT | 0 | Started | Labour | (L)INTERNAL OBD PAINT (WALL & CEILING) | FLOORS | 72.6863 | 1.18 | 85.77 | 0 | 0 | 0 | 0 | 1.18 | 0 | 72.6863 | 7.5 | 545.1473 | 72.6863 | 7.5 | 545.15 | 72.6863 | 0 | 85.77 | -459.3802
2395 | CLEANING.MISC. & PF-LGF GF LOBBY TEXTURE PAINT | 0 | Started | Labour | (L)TEXTURE WITH 2-COAT PAINT | SQFT | 49.5 | 27 | 1336.5 | 0 | 0 | 0 | 0 | 27 | 0 | 49.5 | 27 | 1336.5 | 49.5 | 27 | 1336.5 | 49.5 | 0 | 1336.5 | 0
2396 | RETENTION-UGF OFFICE & LOBBY INTERNAL PAINT | 0 | Tentative | Labour | (L)INTERNAL OBD PAINT (WALL & CEILING) | FLOORS | 1018.58 | 1.18 | 1201.92 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1018.58 | 7.5 | 7639.35 | 0 | 0 | 0 | 1018.58 | 1018.58 | 1201.924 | 1201.9244
2397 | RETENTION-LGF LOBBY & ST CASE INTERNAL PAINT | 0 | Tentative | Labour | (L)INTERNAL OBD PAINT (WALL & CEILING) | FLOORS | 80.7625 | 1.18 | 95.3 | 0 | 0 | 0 | 0 | 1.18 | 0 | 80.7625 | 7.5 | 605.7188 | 0 | 0 | 0 | 80.7625 | 80.7625 | 95.3 | 95.2998
2398 | RETENTION-LGF GF LOBBY TEXTURE PAINT | 0 | Tentative | Labour | (L)TEXTURE WITH 2-COAT PAINT | SQFT | 55 | 27 | 1485 | 0 | 0 | 0 | 0 | 27 | 0 | 55 | 27 | 1485 | 0 | 0 | 0 | 55 | 55 | 1485 | 1485
2399 | AMENITY PLOT RET.WALL RCC WORK | 0 | Started | Material | (M)BOULDER (Medium Size) | BRASS | 41 | 3150 | 129150 | 41 | 3150 | 129150 | 0 | 3150 | 0 | 41 | 1890 | 77490 | 0 | 0 | 0 | 41 | 41 | 129150 | 129150
2400 | AMENITY PLOT RET.WALL RCC WORK | 0 | Started | Material | (M)CONNECTOR SOCEKT 2'' (HOSE PIPE) | NOS | 6 | 50 | 300 | 6 | 50 | 300 | 0 | 50 | 0 | 6 | 70.8 | 424.8 | 0 | 0 | 0 | 6 | 6 | 300 | 300
2401 | AMENITY PLOT RET.WALL RCC WORK | 0 | Started | Material | (M)CONNECTOR SOCEKT 3'' (HOSE PIPE) | NOS | 3 | 35.4 | 106.2 | 3 | 35.4 | 106.2 | 0 | 35.4 | 0 | 3 | 165.2 | 495.6 | 0 | 0 | 0 | 3 | 3 | 106.2 | 106.2
2402 | AMENITY PLOT RET.WALL RCC WORK | 0 | Started | Material | (M)COTTON HOSE PIPE 2'' x 30 mtr | BUNDLE | 11 | 3500 | 38500 | 11 | 3500 | 38500 | 0 | 3500 | 0 | 11 | 2419 | 26609 | 0 | 0 | 0 | 11 | 11 | 38500 | 38500
2403 | AMENITY PLOT RET.WALL RCC WORK | 0 | Started | Material | (M)COTTON HOSE PIPE 3'' x 30 MTR | BUNDLE | 4 | 4720 | 18880 | 4 | 4720 | 18880 | 0 | 4720 | 0 | 4 | 2891 | 11564 | 0 | 0 | 0 | 4 | 4 | 18880 | 18880
2404 | AMENITY PLOT RET.WALL RCC WORK | 0 | Started | Material | (M)Curing Pipe 3/4" 30mtr Nylon Braided | NOS | 5 | 1947 | 9735 | 5 | 1947 | 9735 | 0 | 1947 | 0 | 5 | 1593 | 7965 | 0 | 0 | 0 | 5 | 5 | 9735 | 9735
2405 | AMENITY PLOT RET.WALL RCC WORK | 0 | Started | Material | (M)Perma Grout -60 (GP-2) | BAG | 5 | 531 | 2655 | 5 | 531 | 2655 | 0 | 531 | 0 | 5 | 531 | 2655 | 0 | 0 | 0 | 5 | 5 | 2655 | 2655
2406 | AMENITY PLOT RET.WALL RCC WORK | 0 | Started | Material | (M)RMC M-15 | CUM | 25 | 3500 | 87500 | 23 | 3500 | 80500 | 0 | 3500 | 0 | 23 | 4700 | 108100.0092 | 0 | 0 | 0 | 25 | 25 | 87500 | 87500
2407 | AMENITY PLOT RET.WALL RCC WORK | 0 | Started | Material | (M)RMC M-20 | CUM | 141 | 3800 | 535800 | 141 | 3800 | 535800 | 0 | 3800 | 0 | 68 | 5025 | 341699.9864 | 0 | 0 | 0 | 141 | 141 | 535800 | 535800
2408 | AMENITY PLOT RET.WALL RCC WORK | 0 | Started | Material | (M)SWR Pipes 'A' type S/F 10ft long S/S 110mm | NOS | 30 | 472 | 14160 | 30 | 472 | 14160 | 0 | 472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 14160 | 14160
2409 | AMENITY PLOT RET.WALL RCC WORK | 0 | Started | Material | (M)SWR Plain Bend 110 mm | NOS | 80 | 159.3 | 12744 | 80 | 159.3 | 12744 | 0 | 159.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 80 | 12744 | 12744
2410 | MACHINERY-DIESEL PUMP RENTAL SERVICES | 0 | Started | Labour | (L)5HP DIESEL PUMP | DAY | 60 | 1770 | 106200 | 0 | 0 | 0 | 0 | 1770 | 0 | 60 | 708 | 42480 | 60 | 708 | 42480 | 60 | 0 | 106200 | 63720
2411 | MACHINERY-DIESEL PUMP RENTAL SERVICES | 0 | Started | Labour | (L)Fare Charges Transportation - | NOS | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1770 | 3540 | 2 | 1770 | 3540 | 2 | 0 | 0 | -3540
2412 | MACHINERY-DIESEL PUMP RENTAL SERVICES | 0 | Started | Labour | (L)LOADING/UNLOADING CHARGE | NOS | 1 | 236 | 236 | 0 | 0 | 0 | 0 | 236 | 0 | 1 | 236 | 236 | 1 | 236 | 236 | 1 | 0 | 236 | 0
2413 | MACHINERY-PETROL HONDA PUMP RENTAL SERVICES | 0 | Started | Labour | (L)Fare Charges Transportation - | NOS | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1003 | 4012 | 2 | 1003 | 2006 | 4 | 2 | 0 | -2006
2414 | MACHINERY-PETROL HONDA PUMP RENTAL SERVICES | 0 | Started | Labour | (L)PETROL HONDA PUMP-EN5672 | DAY | 55 | 826 | 45430 | 0 | 0 | 0 | 0 | 826 | 0 | 55 | 826 | 45430 | 53 | 826 | 43778 | 55 | 2 | 45430 | 1652
2415 | MACHINERY-PETROL HONDA PUMP RENTAL SERVICES | 0 | Started | Labour | (L)PETROL HONDA PUMP-EN5673 | DAY | 30 | 826 | 24780 | 0 | 0 | 0 | 0 | 826 | 0 | 30 | 826 | 24780 | 17 | 826 | 14042 | 30 | 13 | 24780 | 10738
2416 | DEWATERING MUD PUMP ON RENT DAY WISE-1 | 0 | Started | Labour | (L)3HP MUD PUMP-DEWATERING | DAY | 70 | 500 | 35000 | 0 | 0 | 0 | 0 | 500 | 0 | 70 | 500 | 35000 | 63 | 500 | 31500 | 70 | 7 | 35000 | 3500
2417 | DEWATERING MUD PUMP ON RENT DAY WISE-2 | 0 | Started | Labour | (L)1.5HP MUD PUMP-DEWATERING | DAY | 40 | 350 | 14000 | 0 | 0 | 0 | 0 | 350 | 0 | 40 | 350 | 14000 | 0 | 0 | 0 | 40 | 40 | 14000 | 14000
2418 | DEWATERING MUD PUMP ON RENT DAY WISE-2 | 0 | Started | Labour | (L)3HP MUD PUMP-DEWATERING | DAY | 88 | 500 | 44000 | 0 | 0 | 0 | 0 | 500 | 0 | 88 | 450 | 39600 | 47 | 450 | 21150 | 88 | 41 | 44000 | 22850
2419 | DEWATERING MUD PUMP ON RENT DAY WISE-2 | 0 | Started | Labour | (L)5HP MUD PUMP-DEWATERING | DAY | 68 | 550 | 37400 | 0 | 0 | 0 | 0 | 550 | 0 | 68 | 550 | 37400 | 68 | 550 | 37400 | 68 | 0 | 37400 | 0
2420 | DEWATERING MUD PUMP ON RENT DAY WISE-2 | 0 | Started | Labour | (L)Fare Charges Transportation - | NOS | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 600 | 1200 | 2 | 600 | 1200 | 2 | 0 | 0 | -1200
2421 | UGWT RAFT PCC RMC-M15 | 10 | Started | Material | (M)RMC M-15 | CUM | 40 | 3500 | 140000 | 40 | 3500 | 140000 | 4 | 3500 | 14000 | 40 | 4100.03 | 164001.12 | 0 | 0 | 0 | 36 | 40 | 126000 | 140000
2422 | UGWT RAFT PCC SOLING-METAL 60MM | 10 | Started | Material | (M)METAL-60MM | BRASS | 9 | 3200 | 28800 | 9 | 3200 | 28800 | 1 | 3200 | 3200 | 9 | 3045 | 27405 | 0 | 0 | 0 | 8 | 9 | 25600 | 28800
2423 | UGWT RAFT RMC-M25 | 10 | Started | Material | (M)RMC M-25 | CUM | 85 | 4600 | 391000 | 85 | 4600 | 391000 | 9 | 4600 | 41400 | 85 | 4811.76 | 408999.7073 | 0 | 0 | 0 | 76 | 85 | 349600 | 391000
2424 | UGWT RAFT 10MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 10mm (Fe 500, 0.617 KGS/Rm) | KG | 4400 | 59 | 259600 | 4400 | 59 | 259600 | 440 | 59 | 25960 | 4400 | 60.18 | 264792 | 6271.62 | 59.36 | 372265.8 | 3960 | -1871.62 | 233640 | -112665.8
2425 | UGWT RAFT RMC-M25 | 10 | Started | Material | (M)RMC M-25 | CUM | 60 | 4600 | 276000 | 60 | 4600 | 276000 | 6 | 4600 | 27600 | 60 | 4700.24 | 282014.1 | 0 | 0 | 0 | 54 | 60 | 248400 | 276000
2426 | INDENT-25/UGWT/RCC WORK- COL.& COL.FOOTING | 10 | Started | Material | (M)CEMENT OPC 43 | BAG | 200 | 378.88 | 75776 | 200 | 378.88 | 75776 | 20 | 378.88 | 7577.6 | 79 | 365 | 28835 | 80 | 354.38 | 28350 | 180 | 120 | 68198.4 | 47426
2427 | INDENT-25/UGWT/RCC WORK- COL.& COL.FOOTING | 10 | Started | Material | (M)Crush Sand | BRASS | 6 | 3675 | 22050 | 6 | 3675 | 22050 | 1 | 3675 | 3675 | 6 | 3360 | 20160 | 0 | 0 | 0 | 5 | 6 | 18375 | 22050
2428 | INDENT-25/UGWT/RCC WORK- COL.& COL.FOOTING | 10 | Started | Material | (M)Metal No.III 20MM | BRASS | 7.42 | 3045 | 22593.9 | 7.42 | 3045 | 22593.9 | 1 | 3045 | 3045 | 7.42 | 3045 | 22593.9 | 0 | 0 | 0 | 6.42 | 7.42 | 19548.9 | 22593.9
2429 | INDENT-25/UGWT/RCC WORK- COL.& COL.FOOTING | 10 | Started | Material | (M)MS Binding Wire 18G | KG | 150 | 50 | 7500 | 150 | 50 | 7500 | 15 | 50 | 750 | 150 | 80.24 | 12036 | 302.85 | 80.24 | 24300.68 | 135 | -152.85 | 6750 | -16800.68
2430 | INDENT-25/UGWT/RCC WORK- COL.& COL.FOOTING | 10 | Started | Material | (M)PERMA BOND SBR 25 LTR BUCKET | BUCKET | 1 | 4491.75 | 4491.75 | 1 | 4491.75 | 4491.75 | 0 | 4491.75 | 0 | 1 | 5299.99 | 5299.99 | 0 | 0 | 0 | 1 | 1 | 4491.75 | 4491.75
2431 | INDENT-25/UGWT/RCC WORK- COL.& COL.FOOTING | 10 | Started | Material | (M)T.M.T.Bar 10mm (Fe 500, 0.617 KGS/Rm) | KG | 2000 | 59 | 118000 | 2000 | 59 | 118000 | 200 | 59 | 11800 | 2000 | 61.71 | 123428 | 0 | 0 | 0 | 1800 | 2000 | 106200 | 118000
2432 | INDENT-25/UGWT/RCC WORK- COL.& COL.FOOTING | 10 | Started | Material | (M)T.M.T.Bar 12mm (Fe 500, 0.888 KGS/Rm) | KG | 2000 | 59 | 118000 | 2000 | 59 | 118000 | 200 | 59 | 11800 | 2000 | 61.71 | 123428 | 0 | 0 | 0 | 1800 | 2000 | 106200 | 118000
2433 | INDENT-25/UGWT/RCC WORK- COL.& COL.FOOTING | 10 | Started | Material | (M)T.M.T.Bar 16mm (Fe 500, 1.58 KGS/Rm) | KG | 1000 | 59 | 59000 | 1000 | 59 | 59000 | 100 | 59 | 5900 | 1000 | 61.71 | 61714 | 1075.85 | 60.83 | 65443.85 | 900 | -75.85 | 53100 | -6443.85
2434 | INDENT-25/UGWT/RCC WORK- COL.& COL.FOOTING | 10 | Started | Material | (M)T.M.T.Bar 20mm (Fe 500, 2.47 KGS/Rm) | KG | 2000 | 59 | 118000 | 2000 | 59 | 118000 | 200 | 59 | 11800 | 2000 | 61.71 | 123428 | 888.9 | 60.47 | 53754.89 | 1800 | 1111.1 | 106200 | 64245.11
2435 | INDENT-25/UGWT/RCC WORK- COL.& COL.FOOTING | 10 | Started | Material | (M)T.M.T.Bar 25mm (Fe 500, 3.85 KGS/Rm) | KG | 2000 | 59 | 118000 | 2000 | 59 | 118000 | 200 | 59 | 11800 | 2000 | 61.71 | 123428 | 1389 | 58.91 | 81830.43 | 1800 | 611 | 106200 | 36169.57
2436 | INDENT-25/UGWT/RCC WORK- COL.& COL.FOOTING | 10 | Started | Material | (M)T.M.T.Bar 8mm (Fe 500, 0.395 KGS/Rm) | KG | 2500 | 59 | 147500 | 2500 | 59 | 147500 | 250 | 59 | 14750 | 2500 | 63.48 | 158710 | 0 | 0 | 0 | 2250 | 2500 | 132750 | 147500
2437 | UGWT PARDI CONCRETE-M25 | 10 | Started | Material | (M)CEMENT OPC 43 | BAG | 1400 | 378.88 | 530432 | 1400 | 378.88 | 530432 | 140 | 378.88 | 53043.2 | 0 | 0 | 0 | 71 | 351.97 | 24990 | 1260 | 1329 | 477388.8 | 505442
2438 | UGWT PARDI CONCRETE-M25 | 10 | Started | Material | (M)Crush Sand | BRASS | 40.65 | 3675 | 149388.75 | 40.65 | 3675 | 149388.75 | 4 | 3675 | 14700 | 40.65 | 3675 | 149388.7598 | 0 | 0 | 0 | 36.65 | 40.65 | 134688.75 | 149388.75
2439 | UGWT PARDI CONCRETE-M25 | 10 | Started | Material | (M)Metal No.III 20MM | BRASS | 49.5 | 3045 | 150727.5 | 49.5 | 3045 | 150727.5 | 5 | 3045 | 15225 | 49.5 | 3360 | 166320 | 0 | 0 | 0 | 44.5 | 49.5 | 135502.5 | 150727.5
2440 | UGWT PARDI CONCRETE-M25 | 10 | Started | Material | (M)RMC M-25 | CUM | 185 | 4600 | 851000 | 185 | 4600 | 851000 | 19 | 4600 | 87400 | 183.5 | 4968.8 | 911775.0968 | 0 | 0 | 0 | 166 | 185 | 763600 | 851000
2441 | UGWT PARDI 8MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 8mm (Fe 500, 0.395 KGS/Rm) | KG | 10000 | 59 | 590000 | 10000 | 59 | 590000 | 1000 | 59 | 59000 | 10000 | 64.07 | 640740 | 3464.94 | 61.77 | 214041.58 | 9000 | 6535.06 | 531000 | 375958.42
2442 | UGWT PARDI 10MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 10mm (Fe 500, 0.617 KGS/Rm) | KG | 600 | 59 | 35400 | 600 | 59 | 35400 | 60 | 59 | 3540 | 600 | 60.18 | 36108 | 0 | 0 | 0 | 540 | 600 | 31860 | 35400
2443 | UGWT PARDI 12MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 12mm (Fe 500, 0.888 KGS/Rm) | KG | 7800 | 59 | 460200 | 7800 | 59 | 460200 | 780 | 59 | 46020 | 7800 | 60.18 | 469404 | 6314.52 | 60.06 | 379231.97 | 7020 | 1485.48 | 414180 | 80968.03
2444 | UGWT PARDI 16MM STEEL | 10 | Started | Material | (M)T.M.T.Bar 16mm (Fe 500, 1.58 KGS/Rm) | KG | 4000 | 59 | 236000 | 4000 | 59 | 236000 | 400 | 59 | 23600 | 4000 | 60.18 | 240720 | 5447.25 | 60.83 | 331356.01 | 3600 | -1447.25 | 212400 | -95356.01
2445 | UGWT PARDI PERMA BOND SBR | 10 | Started | Material | (M)PERMA BOND SBR | LITRE | 50 | 291.08 | 14554 | 50 | 291.08 | 14554 | 5 | 291.08 | 1455.4 | 50 | 212.01 | 10600.54 | 0 | 0 | 0 | 45 | 50 | 13098.6 | 14554
2446 | INDENT-26/UGWT/RCC WORK- SLAB & BEAM | 10 | Started | Material | (M)CEMENT OPC 43 | BAG | 221 | 378.88 | 83732.48 | 221 | 378.88 | 83732.48 | 22 | 378.88 | 8335.36 | 221 | 365 | 80665 | 4 | 360 | 1440 | 199 | 217 | 75397.12 | 82292.48
2447 | INDENT-26/UGWT/RCC WORK- SLAB & BEAM | 10 | Started | Material | (M)Crush Sand | BRASS | 5.3 | 3675 | 19477.5 | 5.3 | 3675 | 19477.5 | 1 | 3675 | 3675 | 5.3 | 3360 | 17808 | 0 | 0 | 0 | 4.3 | 5.3 | 15802.5 | 19477.5
2448 | INDENT-26/UGWT/RCC WORK- SLAB & BEAM | 10 | Started | Material | (M)Metal No.III 20MM | BRASS | 7.8 | 3045 | 23751 | 7.8 | 3045 | 23751 | 1 | 3045 | 3045 | 7.8 | 3045 | 23751 | 0 | 0 | 0 | 6.8 | 7.8 | 20706 | 23751
2449 | INDENT-26/UGWT/RCC WORK- SLAB & BEAM | 10 | Started | Material | (M)MS Binding Wire 18G | KG | 50 | 50 | 2500 | 50 | 50 | 2500 | 5 | 50 | 250 | 50 | 76.7 | 3835 | 79 | 80.24 | 6338.96 | 45 | -29 | 2250 | -3838.96
2450 | INDENT-26/UGWT/RCC WORK- SLAB & BEAM | 10 | Started | Material | (M)PERMA BOND SBR 25 LTR BUCKET | BUCKET | 1 | 4491.75 | 4491.75 | 1 | 4491.75 | 4491.75 | 0 | 4491.75 | 0 | 1 | 5299.99 | 5299.99 | 0 | 0 | 0 | 1 | 1 | 4491.75 | 4491.75
2451 | INDENT-26/UGWT/RCC WORK- SLAB & BEAM | 10 | Started | Material | (M)RMC M-25 | CUM | 10 | 4600 | 46000 | 10 | 4600 | 46000 | 1 | 4600 | 4600 | 10 | 5100 | 50999.999 | 0 | 0 | 0 | 9 | 10 | 41400 | 46000
2452 | INDENT-26/UGWT/RCC WORK- SLAB & BEAM | 10 | Started | Material | (M)T.M.T.Bar 10mm (Fe 500, 0.617 KGS/Rm) | KG | 1500 | 59 | 88500 | 1500 | 59 | 88500 | 150 | 59 | 8850 | 0 | 0 | 0 | 1222.2 | 59.36 | 72546.37 | 1350 | 277.8 | 79650 | 15953.63
2453 | INDENT-26/UGWT/RCC WORK- SLAB & BEAM | 10 | Started | Material | (M)T.M.T.Bar 12mm (Fe 500, 0.888 KGS/Rm) | KG | 500 | 59 | 29500 | 500 | 59 | 29500 | 50 | 59 | 2950 | 0 | 0 | 0 | 0 | 0 | 0 | 450 | 500 | 26550 | 29500
2454 | INDENT-26/UGWT/RCC WORK- SLAB & BEAM | 10 | Started | Material | (M)T.M.T.Bar 20mm (Fe 500, 2.47 KGS/Rm) | KG | 1000 | 59 | 59000 | 1000 | 59 | 59000 | 100 | 59 | 5900 | 0 | 0 | 0 | 0 | 0 | 0 | 900 | 1000 | 53100 | 59000
2455 | INDENT-26/UGWT/RCC WORK- SLAB & BEAM | 10 | Started | Material | (M)T.M.T.Bar 8mm (Fe 500, 0.395 KGS/Rm) | KG | 1000 | 59 | 59000 | 1000 | 59 | 59000 | 100 | 59 | 5900 | 0 | 0 | 0 | 0 | 0 | 0 | 900 | 1000 | 53100 | 59000
2456 | INDENT-31/215/UGWT/UGWT PARDI SHAHABAD WP WORK | 10 | Started | Material | (M)Artificial Sand | BRASS | 1.76 | 5880 | 10348.8 | 1.76 | 5880 | 10348.8 | 0 | 5880 | 0 | 1.76 | 6300 | 11088 | 0 | 0 | 0 | 1.76 | 1.76 | 10348.8 | 10348.8
2457 | INDENT-31/215/UGWT/UGWT PARDI SHAHABAD WP WORK | 10 | Started | Material | (M)CEMENT PPC 50KG | BAG | 140 | 320 | 44800 | 140 | 320 | 44800 | 14 | 320 | 4480 | 0 | 0 | 0 | 0 | 0 | 0 | 126 | 140 | 40320 | 44800
2458 | INDENT-31/215/UGWT/UGWT PARDI SHAHABAD WP WORK | 10 | Started | Material | (M)Crush Sand | BRASS | 1 | 3675 | 3675 | 1 | 3675 | 3675 | 0 | 3675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3675 | 3675
2459 | INDENT-31/215/UGWT/UGWT PARDI SHAHABAD WP WORK | 10 | Started | Material | (M)Dr. Fixit URP 20 LTR Bucket | LITRE | 50 | 231.68 | 11584 | 50 | 231.68 | 11584 | 5 | 231.68 | 1158.4 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 50 | 10425.6 | 11584
2460 | INDENT-31/215/UGWT/UGWT PARDI SHAHABAD WP WORK | 10 | Started | Material | (M)Shahabad Tile 2'x1'6" | SQFT | 3580 | 20.2 | 72316 | 3580 | 20.2 | 72316 | 358 | 20.2 | 7231.6 | 3580 | 17.85 | 63903 | 0 | 0 | 0 | 3222 | 3580 | 65084.4 | 72316
2461 | INDENT-31/215/UGWT/UGWT PARDI SHAHABAD WP WORK | 10 | Started | Labour | (L)Rough Shahabad W/P (Lab) | SQFT | 4335 | 0 | 0 | 0 | 0 | 0 | 434 | 0 | 0 | 4335 | 23 | 99705 | 3853.32 | 23 | 88626.36 | 3901 | 481.68 | 0 | -88626.36
2462 | INDENT-823/034/215/UGWT RAFT PCC SHAHABAD WP WORK | 0 | Started | Material | (M)Artificial Sand | BRASS | 3 | 5880 | 17640 | 3 | 5880 | 17640 | 0 | 5880 | 0 | 3 | 6300 | 18900 | 0 | 0 | 0 | 3 | 3 | 17640 | 17640
2463 | INDENT-823/034/215/UGWT RAFT PCC SHAHABAD WP WORK | 0 | Started | Material | (M)CEMENT PPC 50KG | BAG | 102 | 320 | 32640 | 102 | 320 | 32640 | 0 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 102 | 32640 | 32640
2464 | INDENT-823/034/215/UGWT RAFT PCC SHAHABAD WP WORK | 0 | Started | Material | (M)PERMA PLASTO-O-PROOF CHEMICAL | LTR | 25 | 236 | 5900 | 25 | 236 | 5900 | 0 | 236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 25 | 5900 | 5900
2465 | INDENT-823/034/215/UGWT RAFT PCC SHAHABAD WP WORK | 0 | Started | Material | (M)Shahabad Tile 2'x1'6" | SQFT | 2400 | 20.2 | 48480 | 2400 | 20.2 | 48480 | 0 | 20.2 | 0 | 2400 | 19.34 | 46420.2 | 0 | 0 | 0 | 2400 | 2400 | 48480 | 48480
2466 | INDENT-823/034/215/UGWT RAFT PCC SHAHABAD WP WORK | 0 | Started | Labour | (L)Rough Shahabad W/P (Lab) | SQFT | 4250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4250 | 20 | 85000 | 3811.97 | 20 | 76239.4 | 4250 | 438.03 | 0 | -76239.4
2467 | UGWT RAFT : COMPLETION OF RAFT RCC WORK-60% | 0 | Started | Labour | (L)UGWT RCC WORK (RATE/LTR) | LTR | 155763.293 | 3.42 | 532710.46 | 0 | 0 | 0 | 0 | 3.42 | 0 | 155763.293 | 3.42 | 533021.9897 | 155763.293 | 3.42 | 533021.99 | 155763.293 | 0 | 532710.462 | -311.5279
2468 | UGWT PARDI : COMPLETION OF 50% OF WORK | 0 | Started | Labour | (L)UGWT RCC WORK (RATE/LTR) | LTR | 111259.495 | 3.42 | 380507.47 | 0 | 0 | 0 | 0 | 3.42 | 0 | 111259.495 | 3.42 | 380729.9955 | 111259.495 | 3.42 | 380730 | 111259.495 | 0 | 380507.473 | -222.5271
2469 | UGWT SLAB & ST-CASE : COMPLETION OF 50% OF WORK | 0 | Tentative | Labour | (L)UGWT RCC WORK (RATE/LTR) | LTR | 103842.196 | 3.42 | 355140.31 | 0 | 0 | 0 | 0 | 3.42 | 0 | 103842.196 | 3.42 | 355347.9884 | 0 | 0 | 0 | 103842.196 | 103842.196 | 355140.31 | 355140.3103
2470 | UGWT RAFT : COMPLETION OF RAFT RCC WORK-40% | 0 | Started | Labour | (L)UGWT RCC WORK (RATE/LTR) | LTR | 103842.196 | 3.42 | 355140.31 | 0 | 0 | 0 | 0 | 3.42 | 0 | 103842.196 | 2.9 | 301142.3684 | 103842.196 | 2.9 | 301142.37 | 103842.196 | 0 | 355140.31 | 53997.9403
2471 | UGWT PARDI : COMPLETION OF BAL. PARDI RCC WORK-50% | 0 | Tentative | Labour | (L)UGWT RCC WORK (RATE/LTR) | LTR | 111259.495 | 3.42 | 380507.47 | 0 | 0 | 0 | 0 | 3.42 | 0 | 111259.495 | 2.9 | 322652.5355 | 0 | 0 | 0 | 111259.495 | 111259.495 | 380507.473 | 380507.4729
2472 | UGWT SLAB : COMPLETION OF BAL. SLAB RCC WORK-50% | 0 | Started | Labour | (L)UGWT RCC WORK (RATE/LTR) | LTR | 103842.196 | 3.42 | 355140.31 | 0 | 0 | 0 | 0 | 3.42 | 0 | 103842.196 | 2.9 | 301142.3684 | 103842.196 | 2.9 | 301142.37 | 103842.196 | 0 | 355140.31 | 53997.9403
2473 | UGWT COMPLETION OF ALL HACKING & DESHUTTERING WORK-100% | 0 | Started | Labour | (L)UGWT RCC WORK (RATE/LTR) | LTR | 37086.498 | 3.42 | 126835.82 | 0 | 0 | 0 | 0 | 3.42 | 0 | 37086.498 | 2.9 | 107550.8442 | 37086.498 | 2.9 | 107550.84 | 37086.498 | 0 | 126835.823 | 19284.9832
2474 | UGWT COMPLETION OF ALL MISC. & CLEANING WORK-100% | 0 | Started | Labour | (L)UGWT RCC WORK (RATE/LTR) | LTR | 14834.599 | 3.42 | 50734.33 | 0 | 0 | 0 | 0 | 3.42 | 0 | 14834.599 | 2.9 | 43020.3371 | 14834.599 | 2.9 | 43020.34 | 14834.599 | 0 | 50734.329 | 7713.9886
2475 | DEVELOPEMENT FLY ASH-6'' | 10 | Started | Material | (M)Flyash Bricks 6" | NOS | 22500 | 8.96 | 201600 | 22500 | 8.96 | 201600 | 2250 | 8.96 | 20160 | 22500 | 9.24 | 207900 | 0 | 0 | 0 | 20250 | 22500 | 181440 | 201600
2476 | DEVELOPEMENT FLY ASH-6'' | 10 | Started | Labour | (L)BBM 6" thick | BRASS | 50 | 0 | 0 | 50 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 50 | 0 | 0
2477 | CLUB HOUSE BAMBOO SCAFFOLDING WORK | 0 | Started | Labour | (L)Bamboo scafoilding | SQFT | 5597 | 0 | 0 | 5597 | 0 | 0 | 0 | 0 | 0 | 5597 | 5 | 27985 | 5597 | 5 | 27985 | 5597 | 0 | 0 | -27985 | Club House
2478 | CLUB HOUSE CLUB HOUSE PCC BREAKING | 0 | Started | Labour | (L)Hand Breaker With Oprator | DAY | 1 | 1200 | 1200 | 1 | 1200 | 1200 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1200 | 1200
2479 | CLUB HOUSE CLUB HOUSE DPC WATERPROOFING | 0 | Started | Labour | (L)DPC WATERPROOFING (CHEMICAL COATING) | RFT | 285.19 | 0 | 0 | 285.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285.19 | 285.19 | 0 | 0
2480 | CLUB HOUSE CLUB HOUSE ROUND COLUMN CONCRETING | 0 | Started | Labour | (L)ROUND COLUMN GABRI CONCRETING WORK | NOS | 6 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0
2481 | INDENT-910/CLUB HOUSE/ELECTRICAL SUPPLY LINE | 10 | Started | Material | (M)PVC Agri Pipes R/F 20ft long (4KGS/Grade A) 110 mm - 4" | NOS | 18 | 862.87 | 15531.66 | 18 | 862.87 | 15531.66 | 2 | 862.87 | 1725.74 | 18 | 1049.18 | 18885.1806 | 0 | 0 | 0 | 16 | 18 | 13805.92 | 15531.66
2482 | INDENT-910/CLUB HOUSE/ELECTRICAL SUPPLY LINE | 10 | Started | Material | (M)PVC Agri Pipes R/F 20ft long (4KGS/Grade A) 160 mm - 6" | NOS | 18 | 1845.27 | 33214.86 | 18 | 1845.27 | 33214.86 | 2 | 1845.27 | 3690.54 | 18 | 2243.69 | 40386.4002 | 0 | 0 | 0 | 16 | 18 | 29524.32 | 33214.86
2483 | INDENT-910/CLUB HOUSE/ELECTRICAL SUPPLY LINE | 10 | Started | Material | (M)PVC Pipe 40mm X 10ft | NOS | 6 | 281.81 | 1690.86 | 6 | 281.81 | 1690.86 | 1 | 281.81 | 281.81 | 6 | 109.49 | 656.94 | 0 | 0 | 0 | 5 | 6 | 1409.05 | 1690.86
2484 | INDENT-910/CLUB HOUSE/ELECTRICAL SUPPLY LINE | 10 | Started | Labour | (L)Chamber 1'' x 1.5'' Electrical | NOS | 12 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 12 | 1200 | 14400 | 12 | 1200 | 14400 | 11 | 0 | 0 | -14400
2485 | INDENT-910/CLUB HOUSE/ELECTRICAL SUPPLY LINE | 10 | Started | Labour | (L)Chamber 2 X 2 ft Drainage | NOS | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1650 | 3300 | 2 | 1650 | 3300 | 2 | 0 | 0 | -3300
2486 | INDENT-910/CLUB HOUSE/ELECTRICAL SUPPLY LINE | 10 | Started | Labour | (L)PVC Line 3 or 4 inch | RFT | 297 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 297 | 5 | 1485 | 297 | 5 | 1485 | 267 | 0 | 0 | -1485
2487 | INDENT-910/CLUB HOUSE/ELECTRICAL SUPPLY LINE | 10 | Started | Labour | (L)PVC Line 8 inch | RFT | 317 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 317 | 8 | 2536 | 317 | 8 | 2536 | 285 | 0 | 0 | -2536
2488 | CLUB HOUSE INDENT-964/CLUB HOUSE/COUNTER & URINAL | 10 | Started | Material | (M)KADAPPA-SP 31'' X 24'' VERTICAL | SQFT | 11 | 45 | 495 | 11 | 45 | 495 | 1 | 45 | 45 | 11 | 63.51 | 698.61 | 0 | 0 | 0 | 10 | 11 | 450 | 495
2489 | CLUB HOUSE INDENT-964/CLUB HOUSE/COUNTER & URINAL | 10 | Started | Material | (M)KADAPPA-SP 42'' X 24'' TOP | SQFT | 8 | 45 | 360 | 8 | 45 | 360 | 1 | 45 | 45 | 8 | 63.51 | 508.08 | 0 | 0 | 0 | 7 | 8 | 315 | 360
2490 | CLUB HOUSE INDENT-964/CLUB HOUSE/COUNTER & URINAL | 10 | Started | Material | (M)KADAPPA-SP 72'' X 24'' TOP | SQFT | 13 | 45 | 585 | 13 | 45 | 585 | 1 | 45 | 45 | 13 | 63.51 | 825.63 | 0 | 0 | 0 | 12 | 13 | 540 | 585
2491 | CLUB HOUSE INDENT-964/CLUB HOUSE/COUNTER & URINAL | 10 | Started | Material | (M)NEW TEL.BLACK GRANITE TOP - 42'' X 27'' | SQFT | 8.5 | 140 | 1190 | 8.5 | 140 | 1190 | 1 | 140 | 140 | 8.5 | 197.6 | 1679.6 | 0 | 0 | 0 | 7.5 | 8.5 | 1050 | 1190
2492 | CLUB HOUSE INDENT-964/CLUB HOUSE/COUNTER & URINAL | 10 | Started | Material | (M)NEW TEL.BLACK GRANITE TOP - 72'' X 27'' | SQFT | 13.5 | 140 | 1890 | 13.5 | 140 | 1890 | 1 | 140 | 140 | 13.5 | 197.6 | 2667.6 | 0 | 0 | 0 | 12.5 | 13.5 | 1750 | 1890
2493 | CLUB HOUSE INDENT-964/CLUB HOUSE/COUNTER & URINAL | 10 | Started | Material | (M)NEW TEL.BLACK GRANITE-DP 48'' X 27'' VERTICAL | SQFT | 18 | 165 | 2970 | 18 | 165 | 2970 | 2 | 165 | 330 | 18 | 232.88 | 4191.84 | 0 | 0 | 0 | 16 | 18 | 2640 | 2970
2494 | CLUB HOUSE INDENT-964/CLUB HOUSE/COUNTER & URINAL | 10 | Started | Material | (M)NEW TEL.BLACK GRANITE-DP 66'' X 24'' VERTICAL | SQFT | 33 | 165 | 5445 | 33 | 165 | 5445 | 3 | 165 | 495 | 33 | 232.88 | 7685.04 | 0 | 0 | 0 | 30 | 33 | 4950 | 5445
2495 | CLUB HOUSE INDENT-985/CLUB HOUSE/KITCHEN | 10 | Started | Material | (M)KADAPPA-DP 31'' X 21'' VERTICAL | SQFT | 9.62 | 45 | 432.9 | 9.62 | 45 | 432.9 | 1 | 45 | 45 | 9.62 | 62.2 | 598.3621 | 0 | 0 | 0 | 8.62 | 9.62 | 387.9 | 432.9
2496 | CLUB HOUSE INDENT-985/CLUB HOUSE/KITCHEN | 10 | Started | Material | (M)KADAPPA-SP 31'' X 21'' VERTICAL | SQFT | 4.81 | 38 | 182.78 | 4.81 | 38 | 182.78 | 0 | 38 | 0 | 4.81 | 52.53 | 252.6688 | 0 | 0 | 0 | 4.81 | 4.81 | 182.78 | 182.78
2497 | CLUB HOUSE INDENT-985/CLUB HOUSE/KITCHEN | 10 | Started | Material | (M)KADAPPA-SP 63'' X 21'' TOP | SQFT | 9.18 | 38 | 348.84 | 9.18 | 38 | 348.84 | 1 | 38 | 38 | 9.18 | 52.53 | 482.2346 | 0 | 0 | 0 | 8.18 | 9.18 | 310.84 | 348.84
2498 | CLUB HOUSE INDENT-985/CLUB HOUSE/KITCHEN | 10 | Started | Material | (M)KADAPPA-SP 72'' X 21'' TOP | SQFT | 10.5 | 38 | 399 | 10.5 | 38 | 399 | 1 | 38 | 38 | 10.5 | 52.53 | 551.565 | 0 | 0 | 0 | 9.5 | 10.5 | 361 | 399
2499 | CLUB HOUSE INDENT-985/CLUB HOUSE/KITCHEN | 10 | Started | Material | (M)NEW TEL.BLACK GRANITE-DP 48'' X 24'' VERTICAL | SQFT | 8 | 165 | 1320 | 8 | 165 | 1320 | 1 | 165 | 165 | 8 | 228.08 | 1824.64 | 0 | 0 | 0 | 7 | 8 | 1155 | 1320
2500 | CLUB HOUSE INDENT-985/CLUB HOUSE/KITCHEN | 10 | Started | Material | (M)NEW TEL.BLACK GRANITE-SP 63'' X 24'' TOP | SQFT | 10.5 | 140 | 1470 | 10.5 | 140 | 1470 | 1 | 140 | 140 | 10.5 | 193.52 | 2031.96 | 0 | 0 | 0 | 9.5 | 10.5 | 1330 | 1470
2501 | CLUB HOUSE INDENT-985/CLUB HOUSE/KITCHEN | 10 | Started | Material | (M)NEW TEL.BLACK GRANITE-SP 72'' X 24'' TOP | SQFT | 12 | 140 | 1680 | 12 | 140 | 1680 | 1 | 140 | 140 | 12 | 193.52 | 2322.24 | 0 | 0 | 0 | 11 | 12 | 1540 | 1680
2502 | CLUB HOUSE INDENT-985/CLUB HOUSE/KITCHEN | 10 | Started | Material | (M)SS Sink with Coupling Small size | NOS | 2 | 2000 | 4000 | 2 | 2000 | 4000 | 0 | 2000 | 0 | 2 | 3221.5 | 6443.0094 | 0 | 0 | 0 | 2 | 2 | 4000 | 4000
2503 | INDENT-13/CLUB HOUSE/INTERIOR WORK | 10 | Started | Material | (M)Abro Tape | BOX | 6 | 259.6 | 1557.6 | 6 | 259.6 | 1557.6 | 1 | 259.6 | 259.6 | 6 | 266.38 | 1598.28 | 0 | 0 | 0 | 5 | 6 | 1298 | 1557.6
2504 | INDENT-13/CLUB HOUSE/INTERIOR WORK | 10 | Started | Material | (M)Black Board 8' x 4' x 18mm | NOS | 4 | 2500 | 10000 | 4 | 2500 | 10000 | 0 | 2500 | 0 | 4 | 2881.75 | 11527 | 0 | 0 | 0 | 4 | 4 | 10000 | 10000
2505 | INDENT-13/CLUB HOUSE/INTERIOR WORK | 10 | Started | Material | (M)Edge Patti-20mm width (Dark Brown) | RFT | 400 | 30 | 12000 | 400 | 30 | 12000 | 40 | 30 | 1200 | 400 | 2.36 | 944.4 | 0 | 0 | 0 | 360 | 400 | 10800 | 12000
2506 | INDENT-13/CLUB HOUSE/INTERIOR WORK | 10 | Started | Material | (M)Fevicol | KG | 30 | 247.8 | 7434 | 30 | 247.8 | 7434 | 3 | 247.8 | 743.4 | 30 | 242.16 | 7264.8 | 0 | 0 | 0 | 27 | 30 | 6690.6 | 7434
2507 | INDENT-13/CLUB HOUSE/INTERIOR WORK | 10 | Started | Material | (M)Laminates 8' x 4' x 1mm (Off wite) | NOS | 17 | 485 | 8245 | 17 | 485 | 8245 | 2 | 485 | 970 | 17 | 581.19 | 9880.23 | 0 | 0 | 0 | 15 | 17 | 7275 | 8245
2508 | INDENT-13/CLUB HOUSE/INTERIOR WORK | 10 | Started | Material | (M)Laminates 8' x 4' x 1mm (Shade-10380) | NOS | 13 | 850 | 11050 | 13 | 850 | 11050 | 1 | 850 | 850 | 13 | 1347.92 | 17522.96 | 0 | 0 | 0 | 12 | 13 | 10200 | 11050
2509 | INDENT-13/CLUB HOUSE/INTERIOR WORK | 10 | Started | Material | (M)Plywood 8' x 4' x 18mm | NOS | 15 | 2176 | 32640 | 15 | 2176 | 32640 | 2 | 2176 | 4352 | 15 | 2247.28 | 33709.2 | 0 | 0 | 0 | 13 | 15 | 28288 | 32640
2510 | INDENT-13/CLUB HOUSE/INTERIOR WORK | 10 | Started | Material | (M)SS Autoclose Hinges | NOS | 12 | 177 | 2124 | 12 | 177 | 2124 | 1 | 177 | 177 | 12 | 254.27 | 3051.24 | 0 | 0 | 0 | 11 | 12 | 1947 | 2124
2511 | INDENT-13/CLUB HOUSE/INTERIOR WORK | 10 | Started | Material | (M)SS Handle-3'' | NOS | 10 | 50 | 500 | 10 | 50 | 500 | 1 | 50 | 50 | 10 | 115.03 | 1150.3 | 0 | 0 | 0 | 9 | 10 | 450 | 500
2512 | INDENT-13/CLUB HOUSE/INTERIOR WORK | 10 | Started | Material | (M)SS L-Hinges 3'' | NOS | 40 | 75 | 3000 | 40 | 75 | 3000 | 4 | 75 | 300 | 40 | 10.29 | 411.6 | 0 | 0 | 0 | 36 | 40 | 2700 | 3000
2513 | CLUB HOUSE INDENT-873/CLUB HOUSE/DOOR FITTING | 10 | Started | Material | (M)Cylinderical Lock with Key-Bedroom | NOS | 6 | 1888 | 11328 | 6 | 1888 | 11328 | 1 | 1888 | 1888 | 6 | 2183 | 13098 | 0 | 0 | 0 | 5 | 6 | 9440 | 11328
2514 | CLUB HOUSE INDENT-873/CLUB HOUSE/DOOR FITTING | 10 | Started | Material | (M)Cylindrical Lock without Key-Toilet | NOS | 5 | 1947 | 9735 | 5 | 1947 | 9735 | 1 | 1947 | 1947 | 5 | 2112.2 | 10561 | 0 | 0 | 0 | 4 | 5 | 7788 | 9735
2515 | CLUB HOUSE INDENT-873/CLUB HOUSE/DOOR FITTING | 10 | Started | Material | (M)Door Stopper with Rubber-5'' | NOS | 4 | 59 | 236 | 4 | 59 | 236 | 0 | 59 | 0 | 4 | 330.4 | 1321.6 | 0 | 0 | 0 | 4 | 4 | 236 | 236
2516 | CLUB HOUSE INDENT-873/CLUB HOUSE/DOOR FITTING | 10 | Started | Material | (M)Drawer Closer Magnet | NOS | 40 | 41.3 | 1652 | 40 | 41.3 | 1652 | 4 | 41.3 | 165.2 | 40 | 76.7 | 3068 | 0 | 0 | 0 | 36 | 40 | 1486.8 | 1652
2517 | CLUB HOUSE INDENT-873/CLUB HOUSE/DOOR FITTING | 10 | Started | Material | (M)Laminates 8' x 4' x 1mm (Shade-10380) | NOS | 30 | 850 | 25500 | 30 | 850 | 25500 | 3 | 850 | 2550 | 30 | 1003 | 30090 | 0 | 0 | 0 | 27 | 30 | 22950 | 25500
2518 | CLUB HOUSE INDENT-873/CLUB HOUSE/DOOR FITTING | 10 | Started | Material | (M)Nylon Buffer-3'' | NOS | 11 | 17.7 | 194.7 | 11 | 17.7 | 194.7 | 1 | 17.7 | 17.7 | 11 | 35.4 | 389.4 | 0 | 0 | 0 | 10 | 11 | 177 | 194.7
2519 | CLUB HOUSE INDENT-873/CLUB HOUSE/DOOR FITTING | 10 | Started | Material | (M)Round Door Knob-Brass | NOS | 40 | 70.8 | 2832 | 40 | 70.8 | 2832 | 4 | 70.8 | 283.2 | 40 | 53.1 | 2124 | 0 | 0 | 0 | 36 | 40 | 2548.8 | 2832
2520 | CLUB HOUSE INDENT-873/CLUB HOUSE/DOOR FITTING | 10 | Started | Material | (M)SS L-Hinges 3'' | NOS | 40 | 75 | 3000 | 40 | 75 | 3000 | 4 | 75 | 300 | 40 | 88.5 | 3540 | 0 | 0 | 0 | 36 | 40 | 2700 | 3000
2521 | CLUB HOUSE INDENT-873/CLUB HOUSE/DOOR FITTING | 10 | Started | Material | (M)SS Table Chain - 8'' | NOS | 40 | 59 | 2360 | 40 | 59 | 2360 | 4 | 59 | 236 | 40 | 53.1 | 2124 | 0 | 0 | 0 | 36 | 40 | 2124 | 2360
2522 | CLUB HOUSE INDENT-873/CLUB HOUSE/DOOR FITTING | 10 | Started | Labour | (L)Labour Charges for Carpentary | NOS | 59259 | 0 | 0 | 0 | 0 | 0 | 5926 | 0 | 0 | 59259 | 1 | 59259 | 59259 | 1 | 59259 | 53333 | 0 | 0 | -59259
2523 | CLUB HOUSE INDENT-873/CLUB HOUSE/DOOR FITTING | 10 | Started | Labour | (L)Misc. Carpentary | NOS | 3119 | 0 | 0 | 0 | 0 | 0 | 312 | 0 | 0 | 3119 | 1 | 3119 | 0 | 0 | 0 | 2807 | 3119 | 0 | 0
2524 | CLUB HOUSE INDENT-863/CLUB HOUSE DOORS | 10 | Started | Material | (M)Raval Plug | NOS | 100 | 1.18 | 118 | 100 | 1.18 | 118 | 10 | 1.18 | 11.8 | 100 | 0.59 | 59 | 0 | 0 | 0 | 90 | 100 | 106.2 | 118 | Club House
2525 | CLUB HOUSE INDENT-863/CLUB HOUSE DOORS | 10 | Started | Material | (M)SS Hinges - 4" | NOS | 44 | 100.3 | 4413.2 | 44 | 100.3 | 4413.2 | 4 | 100.3 | 401.2 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 44 | 4012 | 4413.2 | Club House
2526 | CLUB HOUSE INDENT-863/CLUB HOUSE DOORS | 10 | Started | Material | (M)SS Screw 8 x 32mm Full thread | NOS | 400 | 2.07 | 828 | 400 | 2.07 | 828 | 40 | 2.07 | 82.8 | 0 | 0 | 0 | 0 | 0 | 0 | 360 | 400 | 745.2 | 828 | Club House
2527 | CLUB HOUSE INDENT-863/CLUB HOUSE DOORS | 10 | Started | Material | (M)TOILET DOOR WPC-30MM THK | NOS | 2 | 6195 | 12390 | 2 | 6195 | 12390 | 0 | 6195 | 0 | 2 | 6195 | 12390 | 0 | 0 | 0 | 2 | 2 | 12390 | 12390 | Club House
2528 | CLUB HOUSE INDENT-863/CLUB HOUSE DOORS | 10 | Started | Material | (M)TOILET DOOR-32MM THK | NOS | 5 | 7729 | 38645 | 5 | 7729 | 38645 | 1 | 7729 | 7729 | 5 | 7729 | 38645 | 0 | 0 | 0 | 4 | 5 | 30916 | 38645 | Club House
2529 | INDENT-678/CLUB HOUSE/STONE WORK & TILING WORK | 10 | Started | Material | (M)Crush Sand | BRASS | 6 | 3675 | 22050 | 6 | 3675 | 22050 | 1 | 3675 | 3675 | 6 | 3570 | 21420 | 0 | 0 | 0 | 5 | 6 | 18375 | 22050
2530 | INDENT-678/CLUB HOUSE/STONE WORK & TILING WORK | 10 | Started | Material | (M)Metal No.I 6mm (Grit) | BRASS | 9 | 3000 | 27000 | 9 | 3000 | 27000 | 1 | 3000 | 3000 | 9 | 3570 | 32130 | 0 | 0 | 0 | 8 | 9 | 24000 | 27000
2531 | INDENT-678/CLUB HOUSE/STONE WORK & TILING WORK | 10 | Started | Material | (M)PRETTA BIANCO TILE-600X600 | BOX | 65 | 488.03 | 31721.95 | 65 | 488.03 | 31721.95 | 7 | 488.03 | 3416.21 | 65 | 559.75 | 36383.5083 | 0 | 0 | 0 | 58 | 65 | 28305.74 | 31721.95
2532 | CLUB HOUSE INDENT-874/CLUB HOUSE/INDOOR LIGHTING | 10 | Started | Material | (M)COB Down Light-12W | NOS | 20 | 501.5 | 10030 | 20 | 501.5 | 10030 | 2 | 501.5 | 1003 | 20 | 501.5 | 10030 | 0 | 0 | 0 | 18 | 20 | 9027 | 10030 | Club House
2533 | CLUB HOUSE INDENT-874/CLUB HOUSE/INDOOR LIGHTING | 10 | Started | Material | (M)COB Down Light-6W | NOS | 16 | 354 | 5664 | 16 | 354 | 5664 | 2 | 354 | 708 | 16 | 354 | 5664 | 0 | 0 | 0 | 14 | 16 | 4956 | 5664 | Club House
2534 | CLUB HOUSE INDENT-874/CLUB HOUSE/INDOOR LIGHTING | 10 | Started | Material | (M)COB Down Light-9W | NOS | 21 | 413 | 8673 | 21 | 413 | 8673 | 2 | 413 | 826 | 21 | 413 | 8673 | 0 | 0 | 0 | 19 | 21 | 7847 | 8673 | Club House
2535 | CLUB HOUSE INDENT-874/CLUB HOUSE/INDOOR LIGHTING | 10 | Started | Material | (M)Core LED Strip Light-8W | NOS | 8 | 737.5 | 5900 | 8 | 737.5 | 5900 | 1 | 737.5 | 737.5 | 8 | 737.5 | 5900 | 0 | 0 | 0 | 7 | 8 | 5162.5 | 5900 | Club House
2536 | CLUB HOUSE INDENT-874/CLUB HOUSE/INDOOR LIGHTING | 10 | Started | Material | (M)DRIVER-96W | NOS | 4 | 1357 | 5428 | 4 | 1357 | 5428 | 0 | 1357 | 0 | 4 | 1357 | 5428 | 0 | 0 | 0 | 4 | 4 | 5428 | 5428 | Club House
2537 | CLUB HOUSE INDENT-874/CLUB HOUSE/INDOOR LIGHTING | 10 | Started | Material | (M)Foot Light-5W | NOS | 19 | 2401.3 | 45624.7 | 19 | 2401.3 | 45624.7 | 2 | 2401.3 | 4802.6 | 19 | 2401.3 | 45624.7 | 0 | 0 | 0 | 17 | 19 | 40822.1 | 45624.7 | Club House
2538 | CLUB HOUSE INDENT-874/CLUB HOUSE/INDOOR LIGHTING | 10 | Started | Material | (M)PANEL-12W | NOS | 7 | 418.9 | 2932.3 | 7 | 418.9 | 2932.3 | 1 | 418.9 | 418.9 | 7 | 418.9 | 2932.3 | 0 | 0 | 0 | 6 | 7 | 2513.4 | 2932.3 | Club House
2539 | CLUB HOUSE INDENT-874/CLUB HOUSE/INDOOR LIGHTING | 10 | Started | Material | (M)PANEL-6W | NOS | 2 | 430.7 | 861.4 | 2 | 430.7 | 861.4 | 0 | 430.7 | 0 | 2 | 430.7 | 861.4 | 0 | 0 | 0 | 2 | 2 | 861.4 | 861.4 | Club House
2540 | CLUB HOUSE INDENT-874/CLUB HOUSE/INDOOR LIGHTING | 10 | Started | Material | (M)Surface Light | NOS | 4 | 513.3 | 2053.2 | 4 | 513.3 | 2053.2 | 0 | 513.3 | 0 | 4 | 513.3 | 2053.2 | 0 | 0 | 0 | 4 | 4 | 2053.2 | 2053.2 | Club House
2541 | CLUB HOUSE INDENT-874/CLUB HOUSE/INDOOR LIGHTING | 10 | Started | Material | (M)Tube Light-20W | NOS | 2 | 171.1 | 342.2 | 2 | 171.1 | 342.2 | 0 | 171.1 | 0 | 2 | 171.1 | 342.2 | 0 | 0 | 0 | 2 | 2 | 342.2 | 342.2 | Club House
2542 | CLUB HOUSE INDENT-875/CLUB HOUSE/OUTDOOR LIGHTING | 10 | Started | Material | (M)4 Way Light | NOS | 1 | 501.5 | 501.5 | 1 | 501.5 | 501.5 | 0 | 501.5 | 0 | 1 | 501.5 | 501.5 | 0 | 0 | 0 | 1 | 1 | 501.5 | 501.5 | Club House
2543 | CLUB HOUSE INDENT-875/CLUB HOUSE/OUTDOOR LIGHTING | 10 | Started | Material | (M)Aluminum Profile-1Mtr | NOS | 66 | 649 | 42834 | 66 | 649 | 42834 | 7 | 649 | 4543 | 66 | 649 | 42834 | 0 | 0 | 0 | 59 | 66 | 38291 | 42834 | Club House
2544 | CLUB HOUSE INDENT-875/CLUB HOUSE/OUTDOOR LIGHTING | 10 | Started | Material | (M)Aluminum Profile-1Mtr (Local Make) | NOS | 50 | 118 | 5900 | 50 | 118 | 5900 | 5 | 118 | 590 | 50 | 47.2 | 2360 | 0 | 0 | 0 | 45 | 50 | 5310 | 5900 | Club House
2545 | CLUB HOUSE INDENT-875/CLUB HOUSE/OUTDOOR LIGHTING | 10 | Started | Material | (M)Ground Burial-10W | NOS | 3 | 2914.6 | 8743.8 | 3 | 2914.6 | 8743.8 | 0 | 2914.6 | 0 | 3 | 2914.6 | 8743.8 | 0 | 0 | 0 | 3 | 3 | 8743.8 | 8743.8 | Club House
2546 | CLUB HOUSE INDENT-875/CLUB HOUSE/OUTDOOR LIGHTING | 10 | Started | Material | (M)LED Driver Chock | NOS | 10 | 1652 | 16520 | 10 | 1652 | 16520 | 1 | 1652 | 1652 | 10 | 1652 | 16520 | 0 | 0 | 0 | 9 | 10 | 14868 | 16520 | Club House
2547 | CLUB HOUSE INDENT-875/CLUB HOUSE/OUTDOOR LIGHTING | 10 | Started | Material | (M)Meanwell Power Supply-200W (DC Products) | NOS | 5 | 4130 | 20650 | 5 | 4130 | 20650 | 1 | 4130 | 4130 | 5 | 4130 | 20650 | 0 | 0 | 0 | 4 | 5 | 16520 | 20650 | Club House
2548 | CLUB HOUSE INDENT-875/CLUB HOUSE/OUTDOOR LIGHTING | 10 | Started | Material | (M)Neon Flex-12W/Mtr (5M/Roll) | NOS | 14 | 21240 | 297360 | 14 | 21240 | 297360 | 1 | 21240 | 21240 | 14 | 21240 | 297360 | 0 | 0 | 0 | 13 | 14 | 276120 | 297360 | Club House
2549 | CLUB HOUSE INDENT-875/CLUB HOUSE/OUTDOOR LIGHTING | 10 | Started | Material | (M)Spike Light-8W | NOS | 3 | 1846.7 | 5540.1 | 3 | 1846.7 | 5540.1 | 0 | 1846.7 | 0 | 3 | 1846.7 | 5540.1 | 0 | 0 | 0 | 3 | 3 | 5540.1 | 5540.1 | Club House
2550 | CLUB HOUSE INDENT-875/CLUB HOUSE/OUTDOOR LIGHTING | 10 | Started | Material | (M)Strip Light-15W IP 65 (5M/Roll) | NOS | 10 | 1239 | 12390 | 10 | 1239 | 12390 | 1 | 1239 | 1239 | 10 | 1239 | 12390 | 0 | 0 | 0 | 9 | 10 | 11151 | 12390 | Club House
2551 | CLUB HOUSE INDENT-875/CLUB HOUSE/OUTDOOR LIGHTING | 10 | Started | Material | (M)Updown light-6WX2 | NOS | 8 | 2112.2 | 16897.6 | 8 | 2112.2 | 16897.6 | 1 | 2112.2 | 2112.2 | 8 | 2112.2 | 16897.6 | 0 | 0 | 0 | 7 | 8 | 14785.4 | 16897.6 | Club House
2552 | CLUB HOUSE INDENT-600/CLUB HOUSE/WP-MATERIAL | 0 | Started | Material | (M)Artificial Sand | BRASS | 4 | 5880 | 23520 | 4 | 5880 | 23520 | 0 | 5880 | 0 | 4 | 6300 | 25200 | 0 | 0 | 0 | 4 | 4 | 23520 | 23520
2553 | CLUB HOUSE INDENT-600/CLUB HOUSE/WP-MATERIAL | 0 | Started | Material | (M)CEMENT PPC 50KG | BAG | 100 | 320 | 32000 | 100 | 320 | 32000 | 0 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 32000 | 32000
2554 | CLUB HOUSE INDENT-600/CLUB HOUSE/WP-MATERIAL | 0 | Started | Material | (M)Pidifin - 2k - 15kg | PACKET | 20 | 1465 | 29300 | 20 | 1465 | 29300 | 0 | 1465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 29300 | 29300
2555 | CLUB HOUSE INDENT-600/CLUB HOUSE/WP-MATERIAL | 0 | Started | Material | (M)Red Bricks 4" | NOS | 18000 | 8.5 | 153000 | 18000 | 8.5 | 153000 | 0 | 8.5 | 0 | 18000 | 8.74 | 157248 | 0 | 0 | 0 | 18000 | 18000 | 153000 | 153000
2556 | INDENT-833/CLUB HOUSE CP MATERIAL | 0 | Started | Material | (M)Angle Cock | NOS | 5 | 1239 | 6195 | 5 | 1239 | 6195 | 0 | 1239 | 0 | 5 | 1071.99 | 5359.97 | 0 | 0 | 0 | 5 | 5 | 6195 | 6195
2557 | INDENT-833/CLUB HOUSE CP MATERIAL | 0 | Started | Material | (M)Basin Waste Coupling F/T | NOS | 5 | 307.49 | 1537.45 | 5 | 307.49 | 1537.45 | 0 | 307.49 | 0 | 5 | 448 | 2240 | 0 | 0 | 0 | 5 | 5 | 1537.45 | 1537.45
2558 | INDENT-833/CLUB HOUSE CP MATERIAL | 0 | Started | Material | (M)CP Bottle Trap | NOS | 5 | 177 | 885 | 5 | 177 | 885 | 0 | 177 | 0 | 5 | 952 | 4760 | 0 | 0 | 0 | 5 | 5 | 885 | 885
2559 | INDENT-833/CLUB HOUSE CP MATERIAL | 0 | Started | Material | (M)CP Ext. Piece - 1/2" x 1" | NOS | 20 | 29.5 | 590 | 20 | 29.5 | 590 | 0 | 29.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 590 | 590
2560 | INDENT-833/CLUB HOUSE CP MATERIAL | 0 | Started | Material | (M)CP Health Faucet | NOS | 4 | 631.4 | 2525.6 | 4 | 631.4 | 2525.6 | 0 | 631.4 | 0 | 4 | 1128 | 4511.98 | 0 | 0 | 0 | 4 | 4 | 2525.6 | 2525.6
2561 | INDENT-833/CLUB HOUSE CP MATERIAL | 0 | Started | Material | (M)CP Pillar Cock (DLX-CHR-508KN) | NOS | 5 | 1025 | 5125 | 5 | 1025 | 5125 | 0 | 1025 | 0 | 5 | 1584 | 7919.99 | 0 | 0 | 0 | 5 | 5 | 5125 | 5125
2562 | INDENT-833/CLUB HOUSE CP MATERIAL | 0 | Started | Material | (M)CP Urinal Push Flush Valve | NOS | 3 | 1808 | 5424 | 3 | 1808 | 5424 | 0 | 1808 | 0 | 3 | 1807.99 | 5423.9799 | 0 | 0 | 0 | 3 | 3 | 5424 | 5424
2563 | INDENT-833/CLUB HOUSE CP MATERIAL | 0 | Started | Material | (M)GLASS LAMBI | KG | 8 | 118 | 944 | 8 | 118 | 944 | 0 | 118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 944 | 944
2564 | INDENT-833/CLUB HOUSE CP MATERIAL | 0 | Started | Material | (M)Inlet Pipe - 1/2'' (Long-24") | NOS | 5 | 283.2 | 1416 | 5 | 283.2 | 1416 | 0 | 283.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 1416 | 1416
2565 | INDENT-833/CLUB HOUSE CP MATERIAL | 0 | Started | Material | (M)Teflon Tape | NOS | 20 | 19.48 | 389.6 | 20 | 19.48 | 389.6 | 0 | 19.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 389.6 | 389.6
2566 | INDENT-833/CLUB HOUSE CP MATERIAL | 0 | Started | Material | (M)Two Way Bib Cock | NOS | 5 | 1008.61 | 5043.05 | 5 | 1008.61 | 5043.05 | 0 | 1008.61 | 0 | 4 | 3376.01 | 13504.02 | 0 | 0 | 0 | 5 | 5 | 5043.05 | 5043.05
2567 | CLUB HOUSE/VERANDAH & PATHWAY TAPPA WORK | 0 | Started | Material | (M)CEMENT PPC 50KG | BAG | 100 | 320 | 32000 | 100 | 320 | 32000 | 0 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 32000 | 32000 | Club House
2568 | CLUB HOUSE/VERANDAH & PATHWAY TAPPA WORK | 0 | Started | Material | (M)Crush Sand | BRASS | 6 | 3675 | 22050 | 6 | 3675 | 22050 | 0 | 3675 | 0 | 6 | 3360 | 20160 | 0 | 0 | 0 | 6 | 6 | 22050 | 22050 | Club House
2569 | CLUB HOUSE/VERANDAH & PATHWAY TAPPA WORK | 0 | Started | Material | (M)FLY ASH BRICKS 6 INCH | NOS | 3000 | 9.52 | 28560 | 3000 | 9.52 | 28560 | 0 | 9.52 | 0 | 3000 | 8.96 | 26880 | 0 | 0 | 0 | 3000 | 3000 | 28560 | 28560 | Club House
2570 | CLUB HOUSE/VERANDAH & PATHWAY TAPPA WORK | 0 | Started | Material | (M)Flyash Bricks 5 inch | NOS | 2500 | 8.4 | 21000 | 2500 | 8.4 | 21000 | 0 | 8.4 | 0 | 2500 | 8.4 | 21000 | 0 | 0 | 0 | 2500 | 2500 | 21000 | 21000 | Club House
2571 | CLUB HOUSE/VERANDAH & PATHWAY TAPPA WORK | 0 | Started | Material | (M)GRANITE - Telephonic Black 16-18mm Thk | SQFT | 535 | 165.2 | 88382 | 535 | 165.2 | 88382 | 0 | 165.2 | 0 | 285 | 170.17 | 48498.45 | 0 | 0 | 0 | 535 | 535 | 88382 | 88382 | Club House
2572 | CLUB HOUSE/VERANDAH & PATHWAY TAPPA WORK | 0 | Started | Material | (M)KERB STONE (350 X 200 X125) 1MTR | NOS | 90 | 501.5 | 45135 | 90 | 501.5 | 45135 | 0 | 501.5 | 0 | 90 | 579.31 | 52137.9 | 0 | 0 | 0 | 90 | 90 | 45135 | 45135 | Club House
2573 | CLUB HOUSE/VERANDAH & PATHWAY TAPPA WORK | 0 | Started | Material | (M)Metal No.I 6mm (Grit) | BRASS | 3 | 3000 | 9000 | 3 | 3000 | 9000 | 0 | 3000 | 0 | 3 | 3360 | 10080 | 0 | 0 | 0 | 3 | 3 | 9000 | 9000 | Club House
2574 | CLUB HOUSE/VERANDAH & PATHWAY TAPPA WORK | 0 | Started | Material | (M)Metal No.III 20MM | BRASS | 4 | 3045 | 12180 | 4 | 3045 | 12180 | 0 | 3045 | 0 | 4 | 3045 | 12180 | 0 | 0 | 0 | 4 | 4 | 12180 | 12180 | Club House
2575 | CLUB HOUSE/VERANDAH & PATHWAY TAPPA WORK | 0 | Started | Material | (M)NEW TEL.BLACK GRANITE-SP 84'' X 30'' (CUT.PCS) | NOS | 3 | 3407.84 | 10223.52 | 3 | 3407.84 | 10223.52 | 0 | 3407.84 | 0 | 3 | 3013.67 | 9041.01 | 0 | 0 | 0 | 3 | 3 | 10223.52 | 10223.52 | Club House
2576 | CLUB HOUSE/VERANDAH & PATHWAY TAPPA WORK | 0 | Started | Material | (M)NEW TEL.BLACK GRANITE-SP 96'' X 30'' (CUT. PCS) | NOS | 10 | 3894 | 38940 | 10 | 3894 | 38940 | 0 | 3894 | 0 | 10 | 3444.2 | 34442 | 0 | 0 | 0 | 10 | 10 | 38940 | 38940 | Club House
2577 | CLUB HOUSE/VERANDAH & PATHWAY TAPPA WORK | 0 | Started | Material | (M)Paver Blocks 60 mm 12" x 18" White | SQFT | 1100 | 59 | 64900 | 1100 | 59 | 64900 | 0 | 59 | 0 | 1100 | 63.36 | 69696 | 0 | 0 | 0 | 1100 | 1100 | 64900 | 64900 | Club House
2578 | CLUB HOUSE/VERANDAH & PATHWAY TAPPA WORK | 0 | Started | Material | (M)Paver Blocks 60 mm 6" x 6" Black | SQFT | 100 | 59 | 5900 | 100 | 59 | 5900 | 0 | 59 | 0 | 100 | 52.5 | 5250 | 0 | 0 | 0 | 100 | 100 | 5900 | 5900 | Club House
2579 | CLUB HOUSE/VERANDAH & PATHWAY TAPPA WORK | 0 | Started | Material | (M)Paver Blocks 60 mm 6" x 6" Gray | SQFT | 100 | 177 | 17700 | 100 | 177 | 17700 | 0 | 177 | 0 | 100 | 52.5 | 5250 | 0 | 0 | 0 | 100 | 100 | 17700 | 17700 | Club House
2580 | INDENT-94/CLUB HOUSE/INTERIOR WORK-Fitting | 0 | Started | Material | (M)Abro Tape | BOX | 4 | 259.6 | 1038.4 | 4 | 259.6 | 1038.4 | 0 | 259.6 | 0 | 4 | 284.05 | 1136.2 | 0 | 0 | 0 | 4 | 4 | 1038.4 | 1038.4
2581 | INDENT-94/CLUB HOUSE/INTERIOR WORK-Fitting | 0 | Started | Material | (M)DRAWER LOCK-EUROPA | SET | 7 | 1180 | 8260 | 7 | 1180 | 8260 | 0 | 1180 | 0 | 7 | 251.77 | 1762.39 | 0 | 0 | 0 | 7 | 7 | 8260 | 8260
2582 | INDENT-94/CLUB HOUSE/INTERIOR WORK-Fitting | 0 | Started | Material | (M)Fevicol | KG | 20 | 247.8 | 4956 | 20 | 247.8 | 4956 | 0 | 247.8 | 0 | 15 | 271.14 | 4067.1 | 0 | 0 | 0 | 20 | 20 | 4956 | 4956
2583 | INDENT-94/CLUB HOUSE/INTERIOR WORK-Fitting | 0 | Started | Material | (M)Laminates 8' x 4' x 1mm (Off wite) | NOS | 4 | 485 | 1940 | 4 | 485 | 1940 | 0 | 485 | 0 | 3 | 581.01 | 1743.03 | 0 | 0 | 0 | 4 | 4 | 1940 | 1940
2584 | INDENT-94/CLUB HOUSE/INTERIOR WORK-Fitting | 0 | Started | Material | (M)Round Door Knob-Brass | NOS | 25 | 70.8 | 1770 | 25 | 70.8 | 1770 | 0 | 70.8 | 0 | 25 | 6.46 | 161.5 | 0 | 0 | 0 | 25 | 25 | 1770 | 1770
2585 | INDENT-94/CLUB HOUSE/INTERIOR WORK-Fitting | 0 | Started | Material | (M)SS Autoclose Hinges | NOS | 8 | 177 | 1416 | 8 | 177 | 1416 | 0 | 177 | 0 | 4 | 271.14 | 1084.56 | 0 | 0 | 0 | 8 | 8 | 1416 | 1416
2586 | INDENT-94/CLUB HOUSE/INTERIOR WORK-Fitting | 0 | Started | Material | (M)SS Handle-3'' | NOS | 4 | 50 | 200 | 4 | 50 | 200 | 0 | 50 | 0 | 4 | 125.24 | 500.96 | 0 | 0 | 0 | 4 | 4 | 200 | 200
2587 | INDENT-94/CLUB HOUSE/INTERIOR WORK-Fitting | 0 | Started | Material | (M)Tower Bolt - Brass 6" (L-Type) | NOS | 12 | 177 | 2124 | 12 | 177 | 2124 | 0 | 177 | 0 | 12 | 271.14 | 3253.68 | 0 | 0 | 0 | 12 | 12 | 2124 | 2124
2588 | INDEN-670/CLUB HOUSE H FRAME SCAFFOLDING (M+L) for ACP WORK | 0 | Started | Labour | (L)MS.H FRAME ON RENT | SET | 100 | 295 | 29500 | 0 | 0 | 0 | 0 | 295 | 0 | 100 | 295 | 29500 | 0 | 0 | 0 | 100 | 100 | 29500 | 29500
2589 | INDEN-670/CLUB HOUSE H FRAME SCAFFOLDING (M+L) for ACP WORK | 0 | Started | Labour | (L)Scaffolding (Lab) | SET | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 10000 | 100 | 100 | 10000 | 100 | 0 | 0 | -10000
2590 | Club House RCC- PLINTH-Comp.of Footing, Col. upto P.Beam | 0 | Started | Labour | (L)RCC Work (Mat+Lab) | SQFT | 565.4372 | 855.5 | 483731.52 | 0 | 0 | 0 | 0 | 855.5 | 0 | 565.4372 | 725 | 409941.97 | 0 | 0 | 0 | 565.4372 | 565.4372 | 483731.525 | 483731.5246
2591 | Club House RCC- PLINTH- Comp.of Plinth B, Murum Filling | 0 | Started | Labour | (L)RCC Work (Mat+Lab) | SQFT | 565.4372 | 855.5 | 483731.52 | 0 | 0 | 0 | 0 | 855.5 | 0 | 565.4372 | 725 | 409941.97 | 0 | 0 | 0 | 565.4372 | 565.4372 | 483731.525 | 483731.5246
2592 | Club House RCC- PLINTH-Soling & PCC | 0 | Started | Labour | (L)RCC Work (Mat+Lab) | SQFT | 282.7186 | 855.5 | 241865.76 | 0 | 0 | 0 | 0 | 855.5 | 0 | 282.7186 | 725 | 204970.985 | 0 | 0 | 0 | 282.7186 | 282.7186 | 241865.762 | 241865.7623
2593 | Club House RCC- 1ST SLAB- Slab Shutt. & R/F | 0 | Started | Labour | (L)RCC Work (Mat+Lab) | SQFT | 901.7738 | 855.5 | 771467.49 | 0 | 0 | 0 | 0 | 855.5 | 0 | 901.7738 | 725 | 653786.005 | 0 | 0 | 0 | 901.7738 | 901.7738 | 771467.486 | 771467.4859
2594 | Club House RCC- 1ST SLAB- Slab Casting | 0 | Started | Labour | (L)RCC Work (Mat+Lab) | SQFT | 811.5972 | 855.5 | 694321.4 | 0 | 0 | 0 | 0 | 855.5 | 0 | 811.5972 | 725 | 588407.97 | 0 | 0 | 0 | 811.5972 | 811.5972 | 694321.405 | 694321.4046
2595 | Club House RCC- 1ST SLAB- Hacking & Deshuttering | 0 | Started | Labour | (L)RCC Work (Mat+Lab) | SQFT | 90.1779 | 855.5 | 77147.19 | 0 | 0 | 0 | 0 | 855.5 | 0 | 90.1779 | 725 | 65378.9775 | 0 | 0 | 0 | 90.1779 | 90.1779 | 77147.194 | 77147.1935
2596 | Club House RCC- 2ND SLAB- Slab Shutt. & R/F | 0 | Started | Labour | (L)RCC Work (Mat+Lab) | SQFT | 828.6579 | 855.5 | 708916.83 | 0 | 0 | 0 | 0 | 855.5 | 0 | 828.6579 | 725 | 600776.9775 | 0 | 0 | 0 | 828.6579 | 828.6579 | 708916.834 | 708916.8335
2597 | Club House RCC- 2ND SLAB- Slab Casting | 0 | Started | Labour | (L)RCC Work (Mat+Lab) | SQFT | 745.7917 | 855.5 | 638024.8 | 0 | 0 | 0 | 0 | 855.5 | 0 | 745.7917 | 725 | 540698.9825 | 0 | 0 | 0 | 745.7917 | 745.7917 | 638024.799 | 638024.7994
2598 | Club House RCC- 2ND SLAB- Hacking & Deshuttering | 0 | Started | Labour | (L)RCC Work (Mat+Lab) | SQFT | 82.8662 | 855.5 | 70892.03 | 0 | 0 | 0 | 0 | 855.5 | 0 | 82.8662 | 725 | 60077.995 | 0 | 0 | 0 | 82.8662 | 82.8662 | 70892.034 | 70892.0341
2599 | Club House RCC- MISC.WORK- After Comp of All RCC Work | 0 | Started | Labour | (L)RCC Work (Mat+Lab) | SQFT | 52.4138 | 855.5 | 44840.01 | 0 | 0 | 0 | 0 | 855.5 | 0 | 52.4138 | 725 | 38000.005 | 0 | 0 | 0 | 52.4138 | 52.4138 | 44840.006 | 44840.0059
2600 | Club House RCC- CLEANING- After Comp of Cleaning Work | 0 | Started | Labour | (L)RCC Work (Mat+Lab) | SQFT | 52.4138 | 855.5 | 44840.01 | 0 | 0 | 0 | 0 | 855.5 | 0 | 52.4138 | 725 | 38000.005 | 52.4138 | 725 | 38000.01 | 52.4138 | 0 | 44840.006 | 6839.9959
2601 | Club House RCC- RETENTION- After Comp of 12th Month | 0 | Started | Labour | (L)RCC Work (Mat+Lab) | SQFT | 262.0676 | 855.5 | 224198.83 | 0 | 0 | 0 | 0 | 855.5 | 0 | 262.0676 | 725 | 189999.01 | 0 | 0 | 0 | 262.0676 | 262.0676 | 224198.832 | 224198.8318
2602 | Club House (Mat.)-Multipurpose hall & Gym Fix Window Glass W | 0 | Started | Labour | (L)Fix Wind. Glass Work (without glass) | SQFT | 233.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 233.1 | 106.2 | 24755.22 | 205.016 | 106.2 | 21772.7 | 233.1 | 28.084 | 0 | -21772.7
2603 | Club House (Mat.)-Indoor Games Fix Window Glass Work | 0 | Started | Labour | (L)Fix Wind. Glass Work (with glass) | SQFT | 109.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109.9 | 401.2 | 44091.88 | 109.9 | 401.2 | 44091.9 | 109.9 | 0 | 0 | -44091.9
2604 | Club House (Mat.)-Multi.P hall, Gym & Indoor Games Glass Doo | 0 | Started | Labour | (L)Glass Door Work (Openable) | SQFT | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140 | 885 | 123900 | 137.6836 | 885 | 121849.98 | 140 | 2.3164 | 0 | -121849.98
2605 | Club House (Mat.)-Multi.P hall & Gym Glass Door Work | 0 | Started | Labour | (L)Glass Door Work (Fix Glass) | SQFT | 53.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53.2 | 401.2 | 21343.84 | 53.2 | 401.2 | 21343.84 | 53.2 | 0 | 0 | -21343.84
2606 | Club House (Mat.)-Terrace Glass Railing-1st floor Terr. | 0 | Started | Labour | (L)Terrace Glass Railing (Top-1200mm) | RFT | 81.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81.9 | 1711 | 140130.9 | 79.698 | 1711 | 136363.28 | 81.9 | 2.202 | 0 | -136363.28
2607 | Club House (Mat.)-ST Case S.S Glass Railing | 0 | Started | Labour | (L)Staircase Glass Railing (Top-1150mm) M+L | RFT | 17.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.5 | 1711 | 29942.5 | 17.5 | 1711 | 29942.5 | 17.5 | 0 | 0 | -29942.5
2608 | Club House (Mat.)-All Toilet,Green,Storage,Janitor Room | 0 | Started | Labour | (L)Louver Window | SQFT | 44.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44.1 | 224.2 | 9887.22 | 44.1 | 224.2 | 9887.22 | 44.1 | 0 | 0 | -9887.22
2609 | Club House (Lab.)-Multipurpose hall & Gym Fix Window Glass W | 0 | Started | Labour | (L)Fix Wind. Glass Work (without glass) | SQFT | 99.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99.9 | 90 | 8991 | 99.9 | 90 | 8991 | 99.9 | 0 | 0 | -8991
2610 | Club House (Lab.)-Indoor Games Fix Window Glass Work | 0 | Started | Labour | (L)Fix Wind. Glass Work (with glass) | SQFT | 47.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47.1 | 340 | 16014 | 47.1 | 340 | 16014 | 47.1 | 0 | 0 | -16014
2611 | Club House (Lab.)-Multi.P hall, Gym & Indoor Games Glass Doo | 0 | Started | Labour | (L)Glass Door Work (Openable) | SQFT | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 750 | 45000 | 56.2514 | 750 | 42188.55 | 60 | 3.7486 | 0 | -42188.55
2612 | Club House (Lab.)-Multi.P hall & Gym Glass Door Work | 0 | Started | Labour | (L)Glass Door Work (Fix Glass) | SQFT | 22.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.8 | 340 | 7752 | 22.8 | 340 | 7752 | 22.8 | 0 | 0 | -7752
2613 | Club House (Lab.)-Terrace Glass Railing-1st floor Terr. | 0 | Started | Labour | (L)Terrace Glass Railing (Top-1200mm) | RFT | 35.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35.1 | 1450 | 50895 | 35.1 | 1450 | 50895 | 35.1 | 0 | 0 | -50895
2614 | Club House (Lab)-ST Case S.S Glass Railing | 0 | Started | Labour | (L)Staircase Glass Railing (Top-1150mm) M+L | RFT | 7.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 1450 | 10875 | 7.5 | 1450 | 10875 | 7.5 | 0 | 0 | -10875
2615 | Club House (Lab.)-All Toilet,Green,Storage,Janitor Room | 0 | Started | Labour | (L)Louver Window | SQFT | 18.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.9 | 190 | 3591 | 16.875 | 190 | 3206.25 | 18.9 | 2.025 | 0 | -3206.25
2616 | Club House: Multi P.Hall Flooring & Skirting | 0 | Started | Labour | (L)Tiling Work | NOS | 19435 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19435 | 1 | 19435 | 19435 | 1 | 19435 | 19435 | 0 | 0 | -19435
2617 | Club House: Indoor Games Flooring & Skirting | 0 | Started | Labour | (L)Tiling Work | NOS | 12076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12076 | 1 | 12076 | 12076 | 1 | 12076 | 12076 | 0 | 0 | -12076
2618 | Club House: Gym Flooring & Skirting | 0 | Started | Labour | (L)Tiling Work | NOS | 17169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17169 | 1 | 17169 | 17169 | 1 | 17169 | 17169 | 0 | 0 | -17169
2619 | Club House: Terrace Flooring & Skirting | 0 | Started | Labour | (L)Tiling Work | NOS | 16311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16311 | 1 | 16311 | 16311 | 1 | 16311 | 16311 | 0 | 0 | -16311
2620 | Club House: GF. Passage Flooring & Skirting | 0 | Tentative | Labour | (L)Tiling Work | NOS | 11049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11049 | 1 | 11049 | 0 | 0 | 0 | 11049 | 11049 | 0 | 0
2621 | Club House: Open Courtyard Flooring & Skirting | 0 | Tentative | Labour | (L)Tiling Work | NOS | 2331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2331 | 1 | 2331 | 0 | 0 | 0 | 2331 | 2331 | 0 | 0
2622 | Club House: Verandah & Pathway Flooring & Skirting | 0 | Tentative | Labour | (L)Tiling Work | NOS | 17862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17862 | 1 | 17862 | 0 | 0 | 0 | 17862 | 17862 | 0 | 0
2623 | Club House:All Toilets,Janitor,Storage & Green Room Flooring | 0 | Started | Labour | (L)Tiling Work | NOS | 7161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7161 | 1 | 7161 | 7161 | 1 | 7161 | 7161 | 0 | 0 | -7161
2624 | Club House: Staircase Tappa Work | 0 | Started | Labour | (L)Stone Work | NOS | 15173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15173 | 1 | 15173 | 15173 | 1 | 15173 | 15173 | 0 | 0 | -15173
2625 | Club House: Pathway Tappa Work | 0 | Tentative | Labour | (L)Stone Work | NOS | 33706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33706 | 1 | 33706 | 0 | 0 | 0 | 33706 | 33706 | 0 | 0
2626 | Club House:All Toilets,Janitor,Storage & Green Room D.Frame | 0 | Started | Labour | (L)Stone Work | NOS | 14876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14876 | 1 | 14876 | 14876 | 1 | 14876 | 14876 | 0 | 0 | -14876
2627 | Club House:All Toilets,Janitor,Storage & Green Room W.Frame | 0 | Started | Labour | (L)Stone Work | NOS | 4472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4472 | 1 | 4472 | 4472 | 1 | 4472 | 4472 | 0 | 0 | -4472
2628 | Club House: All Fix Wind, Glass Door, Wind. Sill & Terr. Sil | 0 | Started | Labour | (L)Stone Work | NOS | 25517 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25517 | 1 | 25517 | 25517 | 1 | 25517 | 25517 | 0 | 0 | -25517
2629 | Club House: Open Courtyard Seating | 0 | Started | Labour | (L)Stone Work | NOS | 6086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6086 | 1 | 6086 | 6086 | 1 | 6086 | 6086 | 0 | 0 | -6086
2630 | Club House:All Toilets,Janitor,Storage & Gr. Room Wall Dado | 0 | Started | Labour | (L)Tiling Work | NOS | 28172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28172 | 1 | 28172 | 28172 | 1 | 28172 | 28172 | 0 | 0 | -28172
2631 | Club House: All Counter for Basin & Urinal Partition | 0 | Tentative | Labour | (L)Stone Work | NOS | 8942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8942 | 1 | 8942 | 0 | 0 | 0 | 8942 | 8942 | 0 | 0
2632 | Club House: Ladies & Gents Toilet Changing Room Partition | 0 | Tentative | Labour | (L)Stone Work | NOS | 2296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2296 | 1 | 2296 | 0 | 0 | 0 | 2296 | 2296 | 0 | 0
2633 | Club House: Retention after Comp.of all work | 0 | Tentative | Labour | (L)Retention (Tiling & Stone work) | NOS | 13944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13944 | 1 | 13944 | 0 | 0 | 0 | 13944 | 13944 | 0 | 0
2634 | Club House: Comp. of Acid Wash Work | 0 | Tentative | Labour | (L)Cleaning Work (Tiling & Stone work) | NOS | 13944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13944 | 1 | 13944 | 0 | 0 | 0 | 13944 | 13944 | 0 | 0
2635 | Club House: After Comp. of Misc. Work & Cleaning work | 0 | Tentative | Labour | (L)Miss. Work (Tiling & Stone work) | NOS | 8366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8366 | 1 | 8366 | 0 | 0 | 0 | 8366 | 8366 | 0 | 0
2636 | CLUB HOUSE-INDOOR,STORAGE &JANITOR ROOM INTERIOR WORK | 0 | Started | Material | (M)Drawer Closer Magnet | NOS | 20 | 41.3 | 826 | 20 | 41.3 | 826 | 0 | 41.3 | 0 | 20 | 53.1 | 1062 | 0 | 0 | 0 | 20 | 20 | 826 | 826
2637 | CLUB HOUSE-INDOOR,STORAGE &JANITOR ROOM INTERIOR WORK | 0 | Started | Material | (M)Fevicol | KG | 15 | 247.8 | 3717 | 15 | 247.8 | 3717 | 0 | 247.8 | 0 | 15 | 236 | 3540 | 0 | 0 | 0 | 15 | 15 | 3717 | 3717
2638 | CLUB HOUSE-INDOOR,STORAGE &JANITOR ROOM INTERIOR WORK | 0 | Started | Material | (M)Laminates 8' x 4' x 1mm (Off wite) | NOS | 6 | 485 | 2910 | 6 | 485 | 2910 | 0 | 485 | 0 | 6 | 531 | 3186 | 0 | 0 | 0 | 6 | 6 | 2910 | 2910
2639 | CLUB HOUSE-INDOOR,STORAGE &JANITOR ROOM INTERIOR WORK | 0 | Started | Material | (M)Nails 12 no x 2" | KG | 0.5 | 177 | 88.5 | 0.5 | 177 | 88.5 | 0 | 177 | 0 | 0.5 | 283.2 | 141.6 | 0 | 0 | 0 | 0.5 | 0.5 | 88.5 | 88.5
2640 | CLUB HOUSE-INDOOR,STORAGE &JANITOR ROOM INTERIOR WORK | 0 | Started | Material | (M)Nails 14 no x 1 1/2" | KG | 1 | 236 | 236 | 1 | 236 | 236 | 0 | 236 | 0 | 1 | 141.6 | 141.6 | 0 | 0 | 0 | 1 | 1 | 236 | 236
2641 | CLUB HOUSE-INDOOR,STORAGE &JANITOR ROOM INTERIOR WORK | 0 | Started | Material | (M)Nails 14 no x 1" | KG | 1 | 236 | 236 | 1 | 236 | 236 | 0 | 236 | 0 | 1 | 141.6 | 141.6 | 0 | 0 | 0 | 1 | 1 | 236 | 236
2642 | CLUB HOUSE-INDOOR,STORAGE &JANITOR ROOM INTERIOR WORK | 0 | Started | Material | (M)Nails 17 no x 1" | KG | 1 | 212.4 | 212.4 | 1 | 212.4 | 212.4 | 0 | 212.4 | 0 | 1 | 165.2 | 165.2 | 0 | 0 | 0 | 1 | 1 | 212.4 | 212.4
2643 | CLUB HOUSE-INDOOR,STORAGE &JANITOR ROOM INTERIOR WORK | 0 | Started | Material | (M)Nails 19 no x 1" | KG | 1 | 236 | 236 | 1 | 236 | 236 | 0 | 236 | 0 | 1 | 188.8 | 188.8 | 0 | 0 | 0 | 1 | 1 | 236 | 236
2644 | CLUB HOUSE-INDOOR,STORAGE &JANITOR ROOM INTERIOR WORK | 0 | Started | Material | (M)SS Autoclose Hinges | NOS | 24 | 177 | 4248 | 24 | 177 | 4248 | 0 | 177 | 0 | 24 | 247.8 | 5947.2 | 0 | 0 | 0 | 24 | 24 | 4248 | 4248
2645 | CLUB HOUSE-INDOOR,STORAGE &JANITOR ROOM INTERIOR WORK | 0 | Started | Material | (M)SS Handle-3'' | NOS | 12 | 50 | 600 | 12 | 50 | 600 | 0 | 50 | 0 | 12 | 88.5 | 1062 | 0 | 0 | 0 | 12 | 12 | 600 | 600
2646 | CLUB HOUSE-INDOOR,STORAGE &JANITOR ROOM INTERIOR WORK | 0 | Started | Material | (M)SS Screw 19 x 6 mm Full thread | NOS | 500 | 2.36 | 1180 | 500 | 2.36 | 1180 | 0 | 2.36 | 0 | 500 | 0.66 | 330.4 | 0 | 0 | 0 | 500 | 500 | 1180 | 1180
2647 | CLUB HOUSE-INDOOR,STORAGE &JANITOR ROOM INTERIOR WORK | 0 | Started | Material | (M)SS Screw 75 x10 Full Thread | BOX | 1 | 501.5 | 501.5 | 1 | 501.5 | 501.5 | 0 | 501.5 | 0 | 1 | 442.5 | 442.5 | 0 | 0 | 0 | 1 | 1 | 501.5 | 501.5
2648 | CLUB HOUSE-INDOOR,STORAGE &JANITOR ROOM INTERIOR WORK | 0 | Started | Labour | (L)Labour Charges for Carpentary | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 39796.64 | 39796.64 | 1 | 39796.64 | 39796.64 | 1 | 0 | 0 | -39796.64
2649 | CLUB HOUSE-INDOOR,STORAGE &JANITOR ROOM INTERIOR WORK | 0 | Started | Labour | (L)Misc. Carpentary | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2094.56 | 2094.56 | 0 | 0 | 0 | 1 | 1 | 0 | 0
2650 | CLUB HOUSE ACP WORK MATERIAL-60% | 0 | Started | Labour | (L)Aluminum Composite Panel (ACP) M+L | SQFT | 2831.83 | 250.16 | 708410.59 | 0 | 0 | 0 | 0 | 250.16 | 0 | 2828.55 | 250.16 | 707590.06 | 677.05 | 250.16 | 169370.82 | 2831.83 | 2154.78 | 708410.593 | 539039.7728
2651 | CLUB HOUSE ACP WORK LABOUR-40% | 0 | Started | Labour | (L)Aluminum Composite Panel (ACP) M+L | SQFT | 1887.89 | 250.16 | 472274.56 | 0 | 0 | 0 | 0 | 250.16 | 0 | 1885.7 | 212 | 399768.4 | 1885.7 | 212 | 399768.4 | 1887.89 | 2.19 | 472274.562 | 72506.1624
2652 | CLUB HOUSE EXTERNAL WALL BUBBLE TEXTURE-MATERIAL 50% | 0 | Started | Labour | (L)Bubble Texture (M+L) | SQFT | 1594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1594 | 35 | 55790 | 0 | 0 | 0 | 1594 | 1594 | 0 | 0
2653 | CLUB HOUSE EXTERNAL WALL BUBBLE TEXTURE-LABOUR 45% | 0 | Started | Labour | (L)Bubble Texture (M+L) | SQFT | 1434.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1434.6 | 35 | 50211 | 0 | 0 | 0 | 1434.6 | 1434.6 | 0 | 0
2654 | CLUB HOUSE EXTERNAL WALL BUBBLE TEXTURE-RETENTION 5% | 0 | Started | Labour | (L)Bubble Texture (M+L) | SQFT | 159.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159.4 | 35 | 5579 | 0 | 0 | 0 | 159.4 | 159.4 | 0 | 0
2655 | CLUB HOUSE MATERIAL-INT.PAINT,PUTTY & BASE COAT | 0 | Started | Labour | (L)Royal luxery Paint (Putty-2,Sanding,Base Coat-1,Paint-2) | SQFT | 517.7154 | 23 | 11907.45 | 0 | 0 | 0 | 0 | 23 | 0 | 517.7154 | 27.14 | 14050.7942 | 517.7154 | 27.14 | 14050.79 | 517.7154 | 0 | 11907.454 | -2143.3358
2656 | CLUB HOUSE MATERIAL-INT.PAINT 1ST CAOT | 0 | Started | Labour | (L)Royal luxery Paint (Putty-2,Sanding,Base Coat-1,Paint-2) | SQFT | 443.7561 | 23 | 10206.39 | 0 | 0 | 0 | 0 | 23 | 0 | 443.7561 | 27.14 | 12043.5503 | 443.7561 | 27.14 | 12043.55 | 443.7561 | 0 | 10206.39 | -1837.1597
2657 | CLUB HOUSE MATERIAL-INT.PAINT 2ND CAOT | 0 | Started | Labour | (L)Royal luxery Paint (Putty-2,Sanding,Base Coat-1,Paint-2) | SQFT | 517.7154 | 23 | 11907.45 | 0 | 0 | 0 | 0 | 23 | 0 | 517.7154 | 27.14 | 14050.7942 | 0 | 0 | 0 | 517.7154 | 517.7154 | 11907.454 | 11907.4542
2658 | CLUB HOUSE MATERIAL-EXT.PAINT PRIMER,CRACK,AQUATEC | 0 | Started | Labour | (L)Elastomeric Paint (Primer, Crackfill,Basecoat,Paint-2 coat) | SQFT | 1009.1532 | 20.06 | 20243.61 | 0 | 0 | 0 | 0 | 20.06 | 0 | 1009.1532 | 20.06 | 20243.6044 | 1009.1532 | 20.06 | 20243.6 | 1009.1532 | 0 | 20243.613 | 0.0132
2659 | CLUB HOUSE MATERIAL-EXT.PAINT 1ST COAT ELASTOMERIC | 0 | Started | Labour | (L)Elastomeric Paint (Primer, Crackfill,Basecoat,Paint-2 coat) | SQFT | 720.8237 | 20.06 | 14459.72 | 0 | 0 | 0 | 0 | 20.06 | 0 | 720.8237 | 20.06 | 14459.7229 | 720.8237 | 20.06 | 14459.72 | 720.8237 | 0 | 14459.723 | 0.0034
2660 | CLUB HOUSE MATERIAL-EXT.PAINT 2ND COAT ELASTOMERIC | 0 | Tentative | Labour | (L)Elastomeric Paint (Primer, Crackfill,Basecoat,Paint-2 coat) | SQFT | 672.7688 | 20.06 | 13495.74 | 0 | 0 | 0 | 0 | 20.06 | 0 | 672.7688 | 20.06 | 13495.7496 | 0 | 0 | 0 | 672.7688 | 672.7688 | 13495.742 | 13495.7421
2661 | CLUB HOUSE MATERIAL-M.S PERGOLA PAINT 2 COAT EPOXY PRIMER | 0 | Started | Labour | (L)Epoxy Paint (Cleaning,Primer-1,Paint-2 coat) | SQFT | 574.5867 | 25 | 14364.67 | 0 | 0 | 0 | 0 | 25 | 0 | 574.5867 | 29.5 | 16950.3075 | 574.5867 | 29.5 | 16950.31 | 574.5867 | 0 | 14364.668 | -2585.6425
2662 | CLUB HOUSE MATERIAL-M.S PERGOLA PAINT 1ST COAT EPOXY PAINT | 0 | Started | Labour | (L)Epoxy Paint (Cleaning,Primer-1,Paint-2 coat) | SQFT | 430.94 | 25 | 10773.5 | 0 | 0 | 0 | 0 | 25 | 0 | 430.94 | 29.5 | 12712.74 | 430.94 | 29.5 | 12712.74 | 430.94 | 0 | 10773.5 | -1939.24
2663 | CLUB HOUSE MATERIAL-M.S PERGOLA PAINT 2ND COAT EPOXY PAINT | 0 | Started | Labour | (L)Epoxy Paint (Cleaning,Primer-1,Paint-2 coat) | SQFT | 430.94 | 25 | 10773.5 | 0 | 0 | 0 | 0 | 25 | 0 | 430.94 | 29.5 | 12712.74 | 430.94 | 29.5 | 12712.74 | 430.94 | 0 | 10773.5 | -1939.24
2664 | CLUB HOUSE LABOUR-INT.PAINT,PUTTY & BASE COAT | 0 | Started | Labour | (L)Royal luxery Paint (Putty-2,Sanding,Base Coat-1,Paint-2) | SQFT | 517.7154 | 23 | 11907.45 | 0 | 0 | 0 | 0 | 23 | 0 | 517.7154 | 23 | 11907.4542 | 517.7154 | 23 | 11907.45 | 517.7154 | 0 | 11907.454 | 0.0042
2665 | CLUB HOUSE LABOUR-INT.PAINT 1ST CAOT | 0 | Started | Labour | (L)Royal luxery Paint (Putty-2,Sanding,Base Coat-1,Paint-2) | SQFT | 443.7561 | 23 | 10206.39 | 0 | 0 | 0 | 0 | 23 | 0 | 443.7561 | 23 | 10206.3903 | 443.7561 | 23 | 10206.39 | 443.7561 | 0 | 10206.39 | 0.0003
2666 | CLUB HOUSE LABOUR-INT.PAINT 2ND CAOT | 0 | Started | Labour | (L)Royal luxery Paint (Putty-2,Sanding,Base Coat-1,Paint-2) | SQFT | 517.7154 | 23 | 11907.45 | 0 | 0 | 0 | 0 | 23 | 0 | 517.7154 | 23 | 11907.4542 | 0 | 0 | 0 | 517.7154 | 517.7154 | 11907.454 | 11907.4542
2667 | CLUB HOUSE LABOUR-EXT.PAINT PRIMER,CRACK,AQUATEC | 0 | Started | Labour | (L)Elastomeric Paint (Primer, Crackfill,Basecoat,Paint-2 coat) | SQFT | 1009.1532 | 20.06 | 20243.61 | 0 | 0 | 0 | 0 | 20.06 | 0 | 1009.1532 | 17 | 17155.6044 | 1009.1532 | 17 | 17155.6 | 1009.1532 | 0 | 20243.613 | 3088.0132
2668 | CLUB HOUSE LABOUR-EXT.PAINT 1ST COAT ELASTOMERIC | 0 | Started | Labour | (L)Elastomeric Paint (Primer, Crackfill,Basecoat,Paint-2 coat) | SQFT | 720.8237 | 20.06 | 14459.72 | 0 | 0 | 0 | 0 | 20.06 | 0 | 720.8237 | 17 | 12254.0029 | 720.8237 | 17 | 12254 | 720.8237 | 0 | 14459.723 | 2205.7234
2669 | CLUB HOUSE LABOUR-EXT.PAINT 2ND COAT ELASTOMERIC | 0 | Tentative | Labour | (L)Elastomeric Paint (Primer, Crackfill,Basecoat,Paint-2 coat) | SQFT | 672.7688 | 20.06 | 13495.74 | 0 | 0 | 0 | 0 | 20.06 | 0 | 672.7688 | 17 | 11437.0696 | 0 | 0 | 0 | 672.7688 | 672.7688 | 13495.742 | 13495.7421
2670 | CLUB HOUSE LABOUR-M.S PERGOLA PAINT 2 COAT EPOXY PRIMER | 0 | Started | Labour | (L)Epoxy Paint (Cleaning,Primer-1,Paint-2 coat) | SQFT | 574.5867 | 25 | 14364.67 | 0 | 0 | 0 | 0 | 25 | 0 | 574.5867 | 25 | 14364.6675 | 574.5867 | 25 | 14364.67 | 574.5867 | 0 | 14364.668 | -0.0025
2671 | CLUB HOUSE LABOUR-M.S PERGOLA PAINT 1ST COAT EPOXY PAINT | 0 | Started | Labour | (L)Epoxy Paint (Cleaning,Primer-1,Paint-2 coat) | SQFT | 430.94 | 25 | 10773.5 | 0 | 0 | 0 | 0 | 25 | 0 | 430.94 | 25 | 10773.5 | 430.94 | 25 | 10773.5 | 430.94 | 0 | 10773.5 | 0
2672 | CLUB HOUSE LABOUR-M.S PERGOLA PAINT 2ND COAT EPOXY PAINT | 0 | Started | Labour | (L)Epoxy Paint (Cleaning,Primer-1,Paint-2 coat) | SQFT | 430.94 | 25 | 10773.5 | 0 | 0 | 0 | 0 | 25 | 0 | 430.94 | 25 | 10773.5 | 430.94 | 25 | 10773.5 | 430.94 | 0 | 10773.5 | 0
2673 | CLUB HOUSE LABOUR-INTERNAL PAINT MISC. WORK | 0 | Tentative | Labour | (L)Royal luxery Paint (Putty-2,Sanding,Base Coat-1,Paint-2) | SQFT | 79.9561 | 23 | 1838.99 | 0 | 0 | 0 | 0 | 23 | 0 | 79.9561 | 23 | 1838.9903 | 0 | 0 | 0 | 79.9561 | 79.9561 | 1838.99 | 1838.9903
2674 | CLUB HOUSE LABOUR-EXTERNAL PAINT MISC. WORK | 0 | Tentative | Labour | (L)Elastomeric Paint (Primer, Crackfill,Basecoat,Paint-2 coat) | SQFT | 129.8781 | 20.06 | 2605.35 | 0 | 0 | 0 | 0 | 20.06 | 0 | 129.8781 | 17 | 2207.9277 | 0 | 0 | 0 | 129.8781 | 129.8781 | 2605.355 | 2605.3547
2675 | CLUB HOUSE LABOUR-M.S PERGOLA PAINT MISC. WORK | 0 | Tentative | Labour | (L)Epoxy Paint (Cleaning,Primer-1,Paint-2 coat) | SQFT | 77.6469 | 25 | 1941.17 | 0 | 0 | 0 | 0 | 25 | 0 | 77.6469 | 25 | 1941.1725 | 0 | 0 | 0 | 77.6469 | 77.6469 | 1941.173 | 1941.1725
2676 | CLUB HOUSE LABOUR-INTERNAL PAINT RETENTION | 0 | Tentative | Labour | (L)Royal luxery Paint (Putty-2,Sanding,Base Coat-1,Paint-2) | SQFT | 159.9121 | 23 | 3677.98 | 0 | 0 | 0 | 0 | 23 | 0 | 159.9121 | 23 | 3677.9783 | 0 | 0 | 0 | 159.9121 | 159.9121 | 3677.978 | 3677.9783
2677 | CLUB HOUSE LABOUR-EXTERNAL PAINT RETENTION | 0 | Tentative | Labour | (L)Elastomeric Paint (Primer, Crackfill,Basecoat,Paint-2 coat) | SQFT | 259.7563 | 20.06 | 5210.71 | 0 | 0 | 0 | 0 | 20.06 | 0 | 259.7563 | 17 | 4415.8571 | 0 | 0 | 0 | 259.7563 | 259.7563 | 5210.711 | 5210.7114
2678 | CLUB HOUSE LABOUR-M.S PERGOLA PAINT RETENTION | 0 | Tentative | Labour | (L)Epoxy Paint (Cleaning,Primer-1,Paint-2 coat) | SQFT | 155.2937 | 25 | 3882.34 | 0 | 0 | 0 | 0 | 25 | 0 | 155.2937 | 25 | 3882.3425 | 0 | 0 | 0 | 155.2937 | 155.2937 | 3882.343 | 3882.3425
2679 | CLUB HOUSE-ELECTRICAL SUPPLY CABLE WORK | 0 | Tentative | Material | (M)16 Sqmm Single core Copper Flexible Cable-Black | RMT | 5 | 188.8 | 944 | 0 | 0 | 0 | 0 | 188.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 944 | 944
2680 | CLUB HOUSE-ELECTRICAL SUPPLY CABLE WORK | 0 | Tentative | Material | (M)16 Sqmm Single core Copper Flexible Cable-Blue | RMT | 5 | 188.8 | 944 | 0 | 0 | 0 | 0 | 188.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 944 | 944
2681 | CLUB HOUSE-ELECTRICAL SUPPLY CABLE WORK | 0 | Tentative | Material | (M)16 Sqmm Single core Copper Flexible Cable-Red | RMT | 5 | 188.8 | 944 | 0 | 0 | 0 | 0 | 188.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 944 | 944
2682 | CLUB HOUSE-ELECTRICAL SUPPLY CABLE WORK | 0 | Tentative | Material | (M)16 Sqmm Single core Copper Flexible Cable-Yellow | RMT | 5 | 188.8 | 944 | 0 | 0 | 0 | 0 | 188.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 944 | 944
2683 | CLUB HOUSE-ELECTRICAL SUPPLY CABLE WORK | 0 | Tentative | Material | (M)25 sq.mm x 3.5 core Aluminium Armoured XLPE Cable | RMT | 215 | 177 | 38055 | 215 | 177 | 38055 | 0 | 177 | 0 | 215 | 207.24 | 44555.912 | 0 | 0 | 0 | 215 | 215 | 38055 | 38055
2684 | CLUB HOUSE-ELECTRICAL SUPPLY CABLE WORK | 0 | Tentative | Material | (M)63AMP 4 WAY CONNECTOR | NOS | 1 | 590 | 590 | 0 | 0 | 0 | 0 | 590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 590 | 590
2685 | Club House: Internal Concealed Plumbing Work | 0 | Started | Labour | (L)Internal Concealed Work | NOS | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 22722.5 | 22722.5 | 1 | 22722.5 | 22722.5 | 1 | 0 | 1 | -22721.5
2686 | Club House: External Downtake Plumbing Work | 0 | Started | Labour | (L)External Plumbing Work | NOS | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 3725 | 3725 | 1 | 3725 | 3725 | 1 | 0 | 1 | -3724
2687 | Club House: Water Tank Fixing on Terrace & Pipe Connection | 0 | Started | Labour | (L)External Plumbing Work | NOS | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 3725 | 3725 | 1 | 3725 | 3725 | 1 | 0 | 1 | -3724
2688 | Club House: Sanitry Fitting | 0 | Tentative | Labour | (L)Sanitry Work | NOS | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 2607.5 | 2607.5 | 0 | 0 | 0 | 1 | 1 | 1 | 1
2689 | Club House: CP Fitting | 0 | Tentative | Labour | (L)CP WORK | NOS | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 2607.5 | 2607.5 | 0 | 0 | 0 | 1 | 1 | 1 | 1
2690 | Club House: Retention (After Comp.of Retention Period) | 0 | Tentative | Labour | (L)Retention (Plumbing) | NOS | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1862.5 | 1862.5 | 0 | 0 | 0 | 1 | 1 | 1 | 1
2691 | CLUB HOUSE & ROW HOUSE FLEX SONE LABOUR (RED TILE PATTERN) | 0 | Started | Labour | (L)FLEX STONE-INSTALLATION (LABOUR) | SQFT | 1540 | 76.7 | 118118 | 0 | 0 | 0 | 0 | 76.7 | 0 | 1510 | 76.7 | 115817 | 1510 | 76.7 | 115817 | 1540 | 30 | 118118 | 2301
2692 | CLUB HOUSE-GYM & M.P HALL WOODEN FALSE CEILING-VEENER POLISH | 0 | Started | Labour | (L)Labour Charges for Melamine Polish- Misc.work | SQFT | 805 | 4.25 | 3421.25 | 0 | 0 | 0 | 0 | 4.25 | 0 | 805 | 4.25 | 3421.25 | 0 | 0 | 0 | 805 | 805 | 3421.25 | 3421.25
2693 | CLUB HOUSE-GYM & M.P HALL WOODEN FALSE CEILING-VEENER POLISH | 0 | Started | Labour | (L)Labour Charges for Melamine Polish-1st coat | SQFT | 805 | 35 | 28175 | 0 | 0 | 0 | 0 | 35 | 0 | 805 | 35 | 28175 | 804 | 35 | 28140 | 805 | 1 | 28175 | 35
2694 | CLUB HOUSE-GYM & M.P HALL WOODEN FALSE CEILING-VEENER POLISH | 0 | Started | Labour | (L)Labour Charges for Melamine Polish-2nd coat | SQFT | 805 | 45.75 | 36828.75 | 0 | 0 | 0 | 0 | 45.75 | 0 | 805 | 45.75 | 36828.75 | 0 | 0 | 0 | 805 | 805 | 36828.75 | 36828.75
2695 | ROW HOUSE-16 FRENCH DOOR & FRAME-LABOUR | 0 | Started | Labour | (L)FOLDING DOORS (M+L) - 3.25' x 7.5' | SQFT | 32 | 354 | 11328 | 32 | 354 | 11328 | 0 | 354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 11328 | 11328
2696 | ROW HOUSE-16 INDENT-966/ROW HOUSE-16/LIGHTING MAT. | 10 | Started | Material | (M)LEGERO LED 12W NOVA (WW-3424120086) | NOS | 21 | 725 | 15225 | 21 | 725 | 15225 | 2 | 725 | 1450 | 21 | 855.5 | 17965.5 | 0 | 0 | 0 | 19 | 21 | 13775 | 15225
2697 | ROW HOUSE-16 INDENT-966/ROW HOUSE-16/LIGHTING MAT. | 10 | Started | Material | (M)LEGERO LED 3W CLARA (WW-FDLBLGR LUM00788) | NOS | 20 | 165 | 3300 | 20 | 165 | 3300 | 2 | 165 | 330 | 20 | 194.7 | 3894 | 0 | 0 | 0 | 18 | 20 | 2970 | 3300
2698 | ROW HOUSE-16 INDENT-966/ROW HOUSE-16/LIGHTING MAT. | 10 | Started | Material | (M)LEGERO LED 7W NOVA (WW-342407003D) | NOS | 28 | 565 | 15820 | 28 | 565 | 15820 | 3 | 565 | 1695 | 28 | 666.7 | 18667.6 | 0 | 0 | 0 | 25 | 28 | 14125 | 15820
2699 | ROW HOUSE-16 FRENCH DOOR & FRAME-MATERIAL | 10 | Started | Material | (M)FRENCH DOOR WITH FRAME-SINGLE FOLD SHUTTER | SQFT | 24 | 354 | 8496 | 24 | 354 | 8496 | 2 | 354 | 708 | 24 | 236 | 5664 | 0 | 0 | 0 | 22 | 24 | 7788 | 8496
2700 | ROW HOUSE-16 FRENCH DOOR & FRAME-MATERIAL | 10 | Started | Labour | (L)FOLDING DOORS (M+L) - 3.25' x 7.5' | SQFT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2701 | ROW HOUSE-16 ROW HOUSE/DB BOX TO MAIN SUPPLY/WIRING | 0 | Started | Material | (M)10 sq.mm copper flexible cable (black) | RMT | 30 | 118 | 3540 | 30 | 118 | 3540 | 0 | 118 | 0 | 30 | 111 | 3330.081 | 0 | 0 | 0 | 30 | 30 | 3540 | 3540
2702 | ROW HOUSE-16 ROW HOUSE/DB BOX TO MAIN SUPPLY/WIRING | 0 | Started | Material | (M)10 sq.mm copper flexible cable (blue) | RMT | 30 | 118 | 3540 | 30 | 118 | 3540 | 0 | 118 | 0 | 30 | 111 | 3330.081 | 0 | 0 | 0 | 30 | 30 | 3540 | 3540
2703 | ROW HOUSE-16 ROW HOUSE/DB BOX TO MAIN SUPPLY/WIRING | 0 | Started | Material | (M)10 sq.mm copper flexible cable (red) | RMT | 30 | 100 | 3000 | 30 | 100 | 3000 | 0 | 100 | 0 | 30 | 111 | 3330.081 | 0 | 0 | 0 | 30 | 30 | 3000 | 3000
2704 | ROW HOUSE-16 ROW HOUSE/DB BOX TO MAIN SUPPLY/WIRING | 0 | Started | Material | (M)10 sq.mm copper flexible cable (yellow) | RMT | 30 | 118 | 3540 | 30 | 118 | 3540 | 0 | 118 | 0 | 30 | 111 | 3330.081 | 0 | 0 | 0 | 30 | 30 | 3540 | 3540
2705 | ROW HOUSE-16 ROW HOUSE/DB BOX TO MAIN SUPPLY/WIRING | 0 | Started | Material | (M)10 sq.mm x 4 core Aluminium Armoured Cable | RMT | 40 | 121.54 | 4861.6 | 40 | 121.54 | 4861.6 | 0 | 121.54 | 0 | 40 | 161.66 | 6466.4 | 0 | 0 | 0 | 40 | 40 | 4861.6 | 4861.6
2706 | ROW HOUSE-16 ROW HOUSE/DB BOX TO MAIN SUPPLY/WIRING | 0 | Started | Material | (M)3W LED FOOT LAMP (DAY LIGHT) BLACK BODY OUTDOOR | NOS | 11 | 885 | 9735 | 11 | 885 | 9735 | 0 | 885 | 0 | 11 | 397.02 | 4367.2596 | 0 | 0 | 0 | 11 | 11 | 9735 | 9735
2707 | ROW HOUSE-16 ROW HOUSE/DB BOX TO MAIN SUPPLY/WIRING | 0 | Started | Material | (M)4 sq.mm copper flexible cables (Green) | RMT | 25 | 94.4 | 2360 | 25 | 94.4 | 2360 | 0 | 94.4 | 0 | 25 | 50.01 | 1250.22 | 0 | 0 | 0 | 25 | 25 | 2360 | 2360
2708 | ROW HOUSE-16 ROW HOUSE/DB BOX TO MAIN SUPPLY/WIRING | 0 | Started | Material | (M)4" Round Plate | NOS | 16 | 59 | 944 | 16 | 59 | 944 | 0 | 59 | 0 | 16 | 5.9 | 94.4 | 0 | 0 | 0 | 16 | 16 | 944 | 944
2709 | ROW HOUSE-16 ROW HOUSE/DB BOX TO MAIN SUPPLY/WIRING | 0 | Started | Material | (M)40 Amp 4 Pole MCB Schneider with Box | NOS | 1 | 3009 | 3009 | 1 | 3009 | 3009 | 0 | 3009 | 0 | 1 | 1323.96 | 1323.96 | 0 | 0 | 0 | 1 | 1 | 3009 | 3009
2710 | ROW HOUSE-16 ROW HOUSE/DB BOX TO MAIN SUPPLY/WIRING | 0 | Started | Material | (M)6 sq.mm copper flexible cables (black) | RMT | 10 | 94.4 | 944 | 10 | 94.4 | 944 | 0 | 94.4 | 0 | 10 | 74 | 739.98 | 0 | 0 | 0 | 10 | 10 | 944 | 944
2711 | ROW HOUSE-16 ROW HOUSE/DB BOX TO MAIN SUPPLY/WIRING | 0 | Started | Material | (M)6 sq.mm copper flexible cables (Red) | RMT | 20 | 94.4 | 1888 | 20 | 94.4 | 1888 | 0 | 94.4 | 0 | 20 | 74 | 1479.96 | 0 | 0 | 0 | 20 | 20 | 1888 | 1888
2712 | ROW HOUSE-16 ROW HOUSE/DB BOX TO MAIN SUPPLY/WIRING | 0 | Started | Material | (M)Aluminium Cable Lugs 10 sq mm | NOS | 6 | 47.2 | 283.2 | 6 | 47.2 | 283.2 | 0 | 47.2 | 0 | 6 | 9.44 | 56.64 | 0 | 0 | 0 | 6 | 6 | 283.2 | 283.2
2713 | ROW HOUSE-16 ROW HOUSE/DB BOX TO MAIN SUPPLY/WIRING | 0 | Started | Material | (M)Angle Holder | NOS | 9 | 59 | 531 | 9 | 59 | 531 | 0 | 59 | 0 | 9 | 30 | 269.9604 | 0 | 0 | 0 | 9 | 9 | 531 | 531
2714 | ROW HOUSE-16 ROW HOUSE/DB BOX TO MAIN SUPPLY/WIRING | 0 | Started | Material | (M)Celling Rose | NOS | 6 | 11.8 | 70.8 | 6 | 11.8 | 70.8 | 0 | 11.8 | 0 | 6 | 20 | 120 | 0 | 0 | 0 | 6 | 6 | 70.8 | 70.8
2715 | ROW HOUSE-16 ROW HOUSE/DB BOX TO MAIN SUPPLY/WIRING | 0 | Started | Material | (M)Insulation Tape | NOS | 30 | 11.8 | 354 | 30 | 11.8 | 354 | 0 | 11.8 | 0 | 30 | 9.99 | 299.841 | 0 | 0 | 0 | 30 | 30 | 354 | 354
2716 | ROW HOUSE-16 ROW HOUSE/DB BOX TO MAIN SUPPLY/WIRING | 0 | Started | Material | (M)MCB 10amp - SP - 10ka 'C' Curve | NOS | 7 | 590 | 4130 | 7 | 590 | 4130 | 0 | 590 | 0 | 7 | 128.62 | 900.34 | 0 | 0 | 0 | 7 | 7 | 4130 | 4130
2717 | ROW HOUSE-16 ROW HOUSE/DB BOX TO MAIN SUPPLY/WIRING | 0 | Started | Material | (M)MCB 16amp - SP - 10ka 'C' Curve | NOS | 8 | 885 | 7080 | 8 | 885 | 7080 | 0 | 885 | 0 | 8 | 128.62 | 1028.96 | 0 | 0 | 0 | 8 | 8 | 7080 | 7080
2718 | ROW HOUSE-16 ROW HOUSE/DB BOX TO MAIN SUPPLY/WIRING | 0 | Started | Material | (M)MCB 20amp - SP - 10ka 'C' Curve | NOS | 5 | 1770 | 8850 | 5 | 1770 | 8850 | 0 | 1770 | 0 | 5 | 128.62 | 643.1 | 0 | 0 | 0 | 5 | 5 | 8850 | 8850
2719 | ROW HOUSE-16 ROW HOUSE/DB BOX TO MAIN SUPPLY/WIRING | 0 | Started | Material | (M)RCCB 40amp - FP - 30mA | NOS | 1 | 1770 | 1770 | 1 | 1770 | 1770 | 0 | 1770 | 0 | 1 | 2417.82 | 2417.82 | 0 | 0 | 0 | 1 | 1 | 1770 | 1770
2720 | ROW HOUSE-16 ROW HOUSE/DB BOX TO MAIN SUPPLY/WIRING | 0 | Started | Material | (M)Video Door Phone (VDP) | SET | 1 | 5900 | 5900 | 1 | 5900 | 5900 | 0 | 5900 | 0 | 1 | 9735 | 9735 | 0 | 0 | 0 | 1 | 1 | 5900 | 5900
2721 | Row House:Internal Concealed & Testing Work | 0 | Tentative | Labour | (L)Internal Concealed Work | NOS | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000 | 1 | 15000 | 0 | 0 | 0 | 15000 | 15000 | 0 | 0
2722 | Row House:External PVC & UPVC Downtake & Terr.Looping | 0 | Tentative | Labour | (L)External Plumbing Work | NOS | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 1 | 10000 | 0 | 0 | 0 | 10000 | 10000 | 0 | 0
2723 | Row House: CP Fitting Work | 0 | Started | Labour | (L)CP WORK | NOS | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 1 | 3500 | 3500 | 1 | 3500 | 3500 | 0 | 0 | -3500
2724 | Row House: Sanitry Fitting Work | 0 | Started | Labour | (L)Sanitry Work | NOS | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 1 | 3500 | 3500 | 1 | 3500 | 3500 | 0 | 0 | -3500
2725 | Row House: Miscellaneous Work | 0 | Started | Labour | (L)Miss. Work (Plumbing) | NOS | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250 | 1 | 1250 | 1250 | 1 | 1250 | 1250 | 0 | 0 | -1250
2726 | Row House: Retention after comp. of work | 0 | Tentative | Labour | (L)Retention (Plumbing) | NOS | 1750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1750 | 1 | 1750 | 0 | 0 | 0 | 1750 | 1750 | 0 | 0
2727 | Row House: Chamber (18'' x 24'') | 0 | Tentative | Labour | (L)External Plumbing Work | NOS | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1100 | 4400 | 0 | 0 | 0 | 4 | 4 | 0 | 0
2728 | Row House: Gully Trap | 0 | Tentative | Labour | (L)External Plumbing Work | NOS | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 500 | 2000 | 0 | 0 | 0 | 4 | 4 | 0 | 0
2729 | Row House: PVC line 4'' | 0 | Tentative | Labour | (L)External Plumbing Work | NOS | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 5 | 90 | 0 | 0 | 0 | 18 | 18 | 0 | 0
2730 | Row House: Round Chamber-21'' | 0 | Tentative | Labour | (L)External Plumbing Work | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1100 | 1100 | 0 | 0 | 0 | 1 | 1 | 0 | 0
2731 | ROW HOUSE RAILLING WORK (M+L) | 0 | Started | Labour | (L)SS PIPE HANDLE (M+L) | RFT | 18.5 | 354 | 6549 | 0 | 0 | 0 | 0 | 354 | 0 | 18.5 | 354 | 6549 | 18.5 | 354 | 6549 | 18.5 | 0 | 6549 | 0
2732 | ROW HOUSE RAILLING WORK (M+L) | 0 | Started | Labour | (L)Staircase Glass Railing (Top-1150mm) M+L | RFT | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 1947 | 112926 | 58 | 1947 | 112926 | 58 | 0 | 0 | -112926
2733 | ROW HOUSE TILING WORK LABOUR-82% (INDENT-630) | 0 | Tentative | Labour | (L)Tiling Work | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 96877 | 96877 | 0 | 0 | 0 | 1 | 1 | 0 | 0
2734 | ROW HOUSE TILING WORK ACID WASH-10% (INDENT-630) | 0 | Started | Labour | (L)Tiling Work | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 11814 | 11814 | 1 | 11814 | 11814 | 1 | 0 | 0 | -11814
2735 | ROW HOUSE TILING WORK CLEANING-3% (INDENT-630) | 0 | Started | Labour | (L)Tiling Work | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3544 | 3544 | 1 | 3544 | 3544 | 1 | 0 | 0 | -3544
2736 | ROW HOUSE TILING WORK RETENTION-5% (INDENT-630) | 0 | Started | Labour | (L)Tiling Work | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5907 | 5907 | 1 | 5907 | 5907 | 1 | 0 | 0 | -5907
2737 | ROW HOUSE RCC PLINTH: COMP OF PLINTH BEAM | 0 | Tentative | Labour | (L)RCC Work (Mat+Lab) | SQFT | 564.2414 | 855.5 | 482708.52 | 0 | 0 | 0 | 0 | 855.5 | 0 | 564.2414 | 660.4 | 372625.0206 | 0 | 0 | 0 | 564.2414 | 564.2414 | 482708.518 | 482708.5177
2738 | ROW HOUSE RCC PLINTH: SOLING,PCC | 0 | Tentative | Labour | (L)RCC Work (Mat+Lab) | SQFT | 76.9428 | 855.5 | 65824.57 | 0 | 0 | 0 | 0 | 855.5 | 0 | 76.9428 | 660.4 | 50813.0251 | 0 | 0 | 0 | 76.9428 | 76.9428 | 65824.565 | 65824.5654
2739 | ROW HOUSE RCC 1ST SLAB: SLAB CASTING | 0 | Tentative | Labour | (L)RCC Work (Mat+Lab) | SQFT | 627.0397 | 855.5 | 536432.46 | 0 | 0 | 0 | 0 | 855.5 | 0 | 627.0397 | 660.4 | 414097.0179 | 0 | 0 | 0 | 627.0397 | 627.0397 | 536432.463 | 536432.4634
2740 | ROW HOUSE RCC 1ST SLAB: HACK,DESHUTT. | 0 | Tentative | Labour | (L)RCC Work (Mat+Lab) | SQFT | 33.0027 | 855.5 | 28233.81 | 0 | 0 | 0 | 0 | 855.5 | 0 | 33.0027 | 660.4 | 21794.9831 | 0 | 0 | 0 | 33.0027 | 33.0027 | 28233.81 | 28233.8099
2741 | ROW HOUSE RCC 2ND SLAB: SLAB CASTING | 0 | Tentative | Labour | (L)RCC Work (Mat+Lab) | SQFT | 555.3786 | 855.5 | 475126.39 | 0 | 0 | 0 | 0 | 855.5 | 0 | 555.3786 | 660.4 | 366772.0274 | 0 | 0 | 0 | 555.3786 | 555.3786 | 475126.392 | 475126.3923
2742 | ROW HOUSE RCC 2ND SLAB: HACK,DESHUTT. | 0 | Tentative | Labour | (L)RCC Work (Mat+Lab) | SQFT | 29.2308 | 855.5 | 25006.95 | 0 | 0 | 0 | 0 | 855.5 | 0 | 29.2308 | 660.4 | 19304.0203 | 0 | 0 | 0 | 29.2308 | 29.2308 | 25006.949 | 25006.9494
2743 | ROW HOUSE RCC 3RD SLAB: SLAB CASTING | 0 | Tentative | Labour | (L)RCC Work (Mat+Lab) | SQFT | 394.1399 | 855.5 | 337186.68 | 0 | 0 | 0 | 0 | 855.5 | 0 | 394.1399 | 660.4 | 260289.99 | 0 | 0 | 0 | 394.1399 | 394.1399 | 337186.685 | 337186.6845
2744 | ROW HOUSE RCC 3RD SLAB: HACK,DESHUTT. | 0 | Tentative | Labour | (L)RCC Work (Mat+Lab) | SQFT | 20.7435 | 855.5 | 17746.06 | 0 | 0 | 0 | 0 | 855.5 | 0 | 20.7435 | 660.4 | 13699.0074 | 0 | 0 | 0 | 20.7435 | 20.7435 | 17746.064 | 17746.0643
2745 | ROW HOUSE RCC ST CASE PARAPET GHABRI: SLAB CASTING | 0 | Tentative | Labour | (L)RCC Work (Mat+Lab) | SQFT | 89.5775 | 855.5 | 76633.55 | 0 | 0 | 0 | 0 | 855.5 | 0 | 89.5775 | 660.4 | 59156.981 | 0 | 0 | 0 | 89.5775 | 89.5775 | 76633.551 | 76633.5513
2746 | ROW HOUSE RCC ST CASE PARAPET GHABRI: HACK,DESHUTT. | 0 | Tentative | Labour | (L)RCC Work (Mat+Lab) | SQFT | 4.7153 | 855.5 | 4033.94 | 0 | 0 | 0 | 0 | 855.5 | 0 | 4.7153 | 660.4 | 3113.9841 | 0 | 0 | 0 | 4.7153 | 4.7153 | 4033.939 | 4033.9392
2747 | ROW HOUSE RCC MISC.WORK | 0 | Tentative | Labour | (L)RCC Work (Mat+Lab) | SQFT | 25.6154 | 855.5 | 21913.97 | 0 | 0 | 0 | 0 | 855.5 | 0 | 25.6154 | 660.4 | 16916.4102 | 0 | 0 | 0 | 25.6154 | 25.6154 | 21913.975 | 21913.9747
2748 | ROW HOUSE RCC CLEANING WORK | 0 | Tentative | Labour | (L)RCC Work (Mat+Lab) | SQFT | 12.8077 | 855.5 | 10956.99 | 0 | 0 | 0 | 0 | 855.5 | 0 | 12.8077 | 660.4 | 8458.2051 | 0 | 0 | 0 | 12.8077 | 12.8077 | 10956.987 | 10956.9874
2749 | ROW HOUSE RCC RETENTION | 0 | Tentative | Labour | (L)RCC Work (Mat+Lab) | SQFT | 128.076 | 855.5 | 109569.02 | 0 | 0 | 0 | 0 | 855.5 | 0 | 128.076 | 660.4 | 84581.3904 | 0 | 0 | 0 | 128.076 | 128.076 | 109569.018 | 109569.018
2750 | ROW HOUSE BBM WORK GROUND & 1ST FLOOR | 0 | Tentative | Labour | (L)BBM & PLASTER WORK (M+L) | SQFT | 492.1259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 492.1259 | 379.6 | 186810.9916 | 0 | 0 | 0 | 492.1259 | 492.1259 | 0 | 0
2751 | ROW HOUSE BBM WORK 2ND & TERRACE FLOOR | 0 | Tentative | Labour | (L)BBM & PLASTER WORK (M+L) | SQFT | 295.2766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295.2766 | 379.6 | 112086.9974 | 0 | 0 | 0 | 295.2766 | 295.2766 | 0 | 0
2752 | ROW HOUSE BBM WORK ST. CAP AND ABOVE ST.CASE | 0 | Tentative | Labour | (L)BBM & PLASTER WORK (M+L) | SQFT | 49.2123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49.2123 | 379.6 | 18680.9891 | 0 | 0 | 0 | 49.2123 | 49.2123 | 0 | 0
2753 | ROW HOUSE BBM WORK FOR DOUBLE WALL-GR,1ST,2ND,TERR. FLOOR | 0 | Tentative | Labour | (L)BBM & PLASTER WORK (M+L) | SQFT | 147.637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147.637 | 379.6 | 56043.0052 | 0 | 0 | 0 | 147.637 | 147.637 | 0 | 0
2754 | ROW HOUSE INTERNAL PLASTER WORK- GR,1ST FLOOR | 0 | Tentative | Labour | (L)BBM & PLASTER WORK (M+L) | SQFT | 270.6691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270.6691 | 379.6 | 102745.9904 | 0 | 0 | 0 | 270.6691 | 270.6691 | 0 | 0
2755 | ROW HOUSE INTERNAL PLASTER WORK- 2ND FLOOR | 0 | Tentative | Labour | (L)BBM & PLASTER WORK (M+L) | SQFT | 147.637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147.637 | 379.6 | 56043.0052 | 0 | 0 | 0 | 147.637 | 147.637 | 0 | 0
2756 | ROW HOUSE INTERNAL PLASTER WORK- STAIRCASE | 0 | Tentative | Labour | (L)BBM & PLASTER WORK (M+L) | SQFT | 73.8198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73.8198 | 379.6 | 28021.9961 | 0 | 0 | 0 | 73.8198 | 73.8198 | 0 | 0
2757 | ROW HOUSE EXTERNAL PLASTER WORK- EAST SIDE | 0 | Tentative | Labour | (L)BBM & PLASTER WORK (M+L) | SQFT | 174.5416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174.5416 | 379.6 | 66255.9914 | 0 | 0 | 0 | 174.5416 | 174.5416 | 0 | 0
2758 | ROW HOUSE EXTERNAL PLASTER WORK- WEST SIDE | 0 | Tentative | Labour | (L)BBM & PLASTER WORK (M+L) | SQFT | 174.5416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 174.5416 | 379.6 | 66255.9914 | 0 | 0 | 0 | 174.5416 | 174.5416 | 0 | 0
2759 | ROW HOUSE EXTERNAL PLASTER WORK- NORTH SIDE | 0 | Tentative | Labour | (L)BBM & PLASTER WORK (M+L) | SQFT | 257.2181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 257.2181 | 379.6 | 97639.9908 | 0 | 0 | 0 | 257.2181 | 257.2181 | 0 | 0
2760 | ROW HOUSE EXTERNAL PLASTER WORK- SOUTH SIDE | 0 | Tentative | Labour | (L)BBM & PLASTER WORK (M+L) | SQFT | 257.2181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 257.2181 | 379.6 | 97639.9908 | 0 | 0 | 0 | 257.2181 | 257.2181 | 0 | 0
2761 | ROW HOUSE EXTERNAL PLASTER WORK- PARAPET,ST. CAP | 0 | Tentative | Labour | (L)BBM & PLASTER WORK (M+L) | SQFT | 55.1185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55.1185 | 379.6 | 20922.9826 | 0 | 0 | 0 | 55.1185 | 55.1185 | 0 | 0
2762 | ROW HOUSE BBM & PLASTER WORK-MISC. WORK | 0 | Tentative | Labour | (L)BBM & PLASTER WORK (M+L) | SQFT | 25.6154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25.6154 | 379.6 | 9723.6058 | 0 | 0 | 0 | 25.6154 | 25.6154 | 0 | 0
2763 | ROW HOUSE BBM & PLASTER WORK-CLEANING WORK | 0 | Tentative | Labour | (L)BBM & PLASTER WORK (M+L) | SQFT | 12.8077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.8077 | 379.6 | 4861.8029 | 0 | 0 | 0 | 12.8077 | 12.8077 | 0 | 0
2764 | ROW HOUSE BBM & PLASTER WORK-RETENTION | 0 | Tentative | Labour | (L)BBM & PLASTER WORK (M+L) | SQFT | 128.076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 128.076 | 379.6 | 48617.6496 | 0 | 0 | 0 | 128.076 | 128.076 | 0 | 0
2765 | ROW HOUSE WOODEN FLASE CEILING WORK | 0 | Started | Labour | (L)Labour Charges for Carpentary | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 46265.4 | 46265.4 | 0 | 0 | 0 | 1 | 1 | 0 | 0
2766 | ROW HOUSE WOODEN FLASE CEILING WORK | 0 | Started | Labour | (L)Misc. Carpentary | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5140.6 | 5140.6 | 1 | 5140.6 | 5140.6 | 1 | 0 | 0 | -5140.6
2767 | ROW HOUSE-16 FAN & LIGHT ELECTRICAL WORK | 0 | Tentative | Material | (M)12W Surface Light (Round) | NOS | 1 | 590 | 590 | 1 | 590 | 590 | 0 | 590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 590 | 590
2768 | ROW HOUSE-16 FAN & LIGHT ELECTRICAL WORK | 0 | Tentative | Material | (M)40 Amp 4 Pole MCB Schneider with Box | NOS | 1 | 3009 | 3009 | 1 | 3009 | 3009 | 0 | 3009 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3009 | 3009
2769 | ROW HOUSE-16 FAN & LIGHT ELECTRICAL WORK | 0 | Tentative | Material | (M)Ceiling Fan 24'' | NOS | 2 | 1652 | 3304 | 2 | 1652 | 3304 | 0 | 1652 | 0 | 2 | 3600.18 | 7200.36 | 0 | 0 | 0 | 2 | 2 | 3304 | 3304
2770 | ROW HOUSE-16 FAN & LIGHT ELECTRICAL WORK | 0 | Tentative | Material | (M)Ceiling Fan 48" | NOS | 6 | 1770 | 10620 | 6 | 1770 | 10620 | 0 | 1770 | 0 | 6 | 3600.18 | 21601.08 | 0 | 0 | 0 | 6 | 6 | 10620 | 10620
2771 | ROW HOUSE-16 FAN & LIGHT ELECTRICAL WORK | 0 | Tentative | Material | (M)Exhuast Fan 10'' x 10'' | NOS | 5 | 1180 | 5900 | 5 | 1180 | 5900 | 0 | 1180 | 0 | 5 | 1249.62 | 6248.1 | 0 | 0 | 0 | 5 | 5 | 5900 | 5900
2772 | ROW HOUSE-16 FAN & LIGHT ELECTRICAL WORK | 0 | Tentative | Material | (M)METER BOX LOCKABLE 18'' x 18'' DEEP-200MM | NOS | 1 | 944 | 944 | 1 | 944 | 944 | 0 | 944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 944 | 944
2773 | ROW HOUSE-16: ROW HOUSE CP PLUMBING MATERIAL | 0 | Tentative | Material | (M)CP Nozzle Bib Cock | NOS | 1 | 697 | 697 | 1 | 697 | 697 | 0 | 697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 697 | 697
2774 | ROW HOUSE-16: ROW HOUSE CP PLUMBING MATERIAL | 0 | Tentative | Material | (M)CP SPOUT | NOS | 2 | 590 | 1180 | 2 | 590 | 1180 | 0 | 590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 1180 | 1180
2775 | ROW HOUSE-16: ROW HOUSE CP PLUMBING MATERIAL | 0 | Tentative | Material | (M)Single Lever Tall Body Spout (FUS-CHR-2900NB) | NOS | 1 | 7080 | 7080 | 1 | 7080 | 7080 | 0 | 7080 | 0 | 1 | 4949.49 | 4949.49 | 0 | 0 | 0 | 1 | 1 | 7080 | 7080
2776 | STP STP EXPANSION SHEET INDENT-930 | 10 | Started | Material | (M)25MM EXPANSION SHEET-4' X 6' | SHEET | 20 | 365 | 7300 | 20 | 365 | 7300 | 2 | 365 | 730 | 20 | 380.63 | 7612.6 | 0 | 0 | 0 | 18 | 20 | 6570 | 7300
2777 | STP STP EXPANSION SHEET INDENT-930 | 10 | Started | Material | (M)50MM EXPANSION SHEET-4' X 6' | SHEET | 6 | 500 | 3000 | 6 | 500 | 3000 | 1 | 500 | 500 | 6 | 761.25 | 4567.5 | 0 | 0 | 0 | 5 | 6 | 2500 | 3000
2778 | STP INDENT-696,697,698 & 699/STP RCC WORK | 0 | Started | Material | (M)MS Binding Wire 18G | KG | 497 | 50 | 24850 | 497 | 50 | 24850 | 0 | 50 | 0 | 0 | 0 | 0 | 147 | 80.24 | 11795.28 | 497 | 350 | 24850 | 13054.72
2779 | STP INDENT-696,697,698 & 699/STP RCC WORK | 0 | Started | Material | (M)Perma Grout -60 (GP-2) | BAG | 10 | 531 | 5310 | 10 | 531 | 5310 | 0 | 531 | 0 | 10 | 578.2 | 5782 | 0 | 0 | 0 | 10 | 10 | 5310 | 5310
2780 | STP INDENT-696,697,698 & 699/STP RCC WORK | 0 | Started | Material | (M)RMC M-15 | CUM | 29 | 3500 | 101500 | 29 | 3500 | 101500 | 0 | 3500 | 0 | 27 | 4100 | 110699.9892 | 0 | 0 | 0 | 29 | 29 | 101500 | 101500
2781 | STP INDENT-696,697,698 & 699/STP RCC WORK | 0 | Started | Material | (M)RMC M-25 | CUM | 285 | 4600 | 1311000 | 285 | 4600 | 1311000 | 0 | 4600 | 0 | 285 | 4862.67 | 1385860.7207 | 0 | 0 | 0 | 285 | 285 | 1311000 | 1311000
2782 | STP INDENT-696,697,698 & 699/STP RCC WORK | 0 | Started | Material | (M)T.M.T.Bar 10mm (Fe 500, 0.617 KGS/Rm) | KG | 4127 | 59 | 243493 | 4127 | 59 | 243493 | 0 | 59 | 0 | 0 | 0 | 0 | 1547.4363 | 59.36 | 91851.49 | 4127 | 2579.5637 | 243493 | 151641.51
2783 | STP INDENT-696,697,698 & 699/STP RCC WORK | 0 | Started | Material | (M)T.M.T.Bar 12mm (Fe 500, 0.888 KGS/Rm) | KG | 9972 | 59 | 588348 | 9972 | 59 | 588348 | 0 | 59 | 0 | 0 | 0 | 0 | 2815.89 | 60.06 | 169114.35 | 9972 | 7156.11 | 588348 | 419233.65
2784 | STP INDENT-696,697,698 & 699/STP RCC WORK | 0 | Started | Material | (M)T.M.T.Bar 16mm (Fe 500, 1.58 KGS/Rm) | KG | 6932 | 59 | 408988 | 6932 | 59 | 408988 | 0 | 59 | 0 | 0 | 0 | 0 | 606.27 | 60.83 | 36879.39 | 6932 | 6325.73 | 408988 | 372108.61
2785 | STP INDENT-696,697,698 & 699/STP RCC WORK | 0 | Started | Material | (M)T.M.T.Bar 20mm (Fe 500, 2.47 KGS/Rm) | KG | 2243 | 59 | 132337 | 2243 | 59 | 132337 | 0 | 59 | 0 | 0 | 0 | 0 | 88.89 | 60.47 | 5375.49 | 2243 | 2154.11 | 132337 | 126961.51
2786 | STP INDENT-696,697,698 & 699/STP RCC WORK | 0 | Started | Material | (M)T.M.T.Bar 25mm (Fe 500, 3.85 KGS/Rm) | KG | 1412 | 59 | 83308 | 1412 | 59 | 83308 | 0 | 59 | 0 | 0 | 0 | 0 | 2222.4 | 58.91 | 130928.6 | 1412 | -810.4 | 83308 | -47620.6
2787 | STP INDENT-696,697,698 & 699/STP RCC WORK | 0 | Started | Material | (M)T.M.T.Bar 8mm (Fe 500, 0.395 KGS/Rm) | KG | 4136 | 59 | 244024 | 4136 | 59 | 244024 | 0 | 59 | 0 | 0 | 0 | 0 | 2739.72 | 61.77 | 169242.15 | 4136 | 1396.28 | 244024 | 74781.85
2788 | STP - RAFT COMP. OF 1ST STAGE OF RAFT (TANK-1,2,3,4) | 0 | Started | Labour | (L)STP RCC WORK (RATE/LTR) | LTR | 66557.334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66557.334 | 3 | 199672.002 | 66557.334 | 3 | 199672 | 66557.334 | 0 | 0 | -199672
2789 | STP - RAFT COMP. OF 2ND STAGE OF RAFT (TANK-5,6,7,8) | 0 | Started | Labour | (L)STP RCC WORK (RATE/LTR) | LTR | 99836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99836 | 3 | 299508 | 0 | 0 | 0 | 99836 | 99836 | 0 | 0
2790 | STP - PARDI COMP. OF TANK-1,2,3,4 SIDE PORTION 50% OF WORK | 0 | Started | Labour | (L)STP RCC WORK (RATE/LTR) | LTR | 33445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33445 | 3 | 100335 | 0 | 0 | 0 | 33445 | 33445 | 0 | 0
2791 | STP - PARDI COMP. OF TANK-1,2,3,4 SIDE PORTION 100% OF WORK | 0 | Started | Labour | (L)STP RCC WORK (RATE/LTR) | LTR | 40877.334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40877.334 | 3 | 122632.002 | 40877.334 | 3 | 122632 | 40877.334 | 0 | 0 | -122632
2792 | STP - PARDI COMP. OF TANK-5,6,7,8 SIDE PORTION UPTO 50% HT | 0 | Started | Labour | (L)STP RCC WORK (RATE/LTR) | LTR | 52025.667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52025.667 | 3 | 156077.001 | 52025.667 | 3 | 156077 | 52025.667 | 0 | 0 | -156077
2793 | STP - PARDI COMP. OF TANK-5,6,7,8 SIDE PORTION UPTO 100% HT | 0 | Started | Labour | (L)STP RCC WORK (RATE/LTR) | LTR | 59458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59458 | 3 | 178374 | 59458 | 3 | 178374 | 59458 | 0 | 0 | -178374
2794 | STP - SLAB COMP. OF TANK-1,2,3,4 SIDE PORTION 50% OF WORK | 0 | Started | Labour | (L)STP RCC WORK (RATE/LTR) | LTR | 49918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49918 | 3 | 149754 | 49918 | 3 | 149754 | 49918 | 0 | 0 | -149754
2795 | STP - SLAB COMP. OF BAL. SLAB | 0 | Started | Labour | (L)STP RCC WORK (RATE/LTR) | LTR | 116475.334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 116475.334 | 3 | 349426.002 | 0 | 0 | 0 | 116475.334 | 116475.334 | 0 | 0
2796 | STP - HACKING & DESHUT. WORK. (COMP. OF HACK.& DESHUTTERING) | 0 | Started | Labour | (L)STP RCC WORK (RATE/LTR) | LTR | 27732.334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27732.334 | 3 | 83197.002 | 27732.334 | 3 | 83197 | 27732.334 | 0 | 0 | -83197
2797 | STP - MISC. WORKS (COMP. OF ALL MISC. WORK) | 0 | Started | Labour | (L)STP RCC WORK (RATE/LTR) | LTR | 8319.667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8319.667 | 3 | 24959.001 | 900 | 3 | 2700 | 8319.667 | 7419.667 | 0 | -2700
2798 | STP - CLEANING (COMP. OF CLEANING & MISC. WORK) | 0 | Started | Labour | (L)STP RCC WORK (RATE/LTR) | LTR | 11928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11928 | 3 | 35784 | 0 | 0 | 0 | 11928 | 11928 | 0 | 0
2799 | STP - RETENTION (AFTER COMP. OF 6 MONTH OF WORK) | 0 | Started | Labour | (L)STP RCC WORK (RATE/LTR) | LTR | 29819.667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29819.667 | 3 | 89459.001 | 0 | 0 | 0 | 29819.667 | 29819.667 | 0 | 0
2800 | STP TANK EXCAVATION WORK | 0 | Started | Labour | (L)EXTRA HARD MURUM EXCAVATION | CUM | 223.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223.26 | 350 | 78141 | 223.26 | 350 | 78141 | 223.26 | 0 | 0 | -78141
2801 | STP TANK EXCAVATION WORK | 0 | Started | Labour | (L)HARD MURUM EXCAVATION | CUM | 269.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 269.8 | 250 | 67450 | 269.8 | 250 | 67450 | 269.8 | 0 | 0 | -67450
2802 | STP TANK EXCAVATION WORK | 0 | Started | Labour | (L)SOFT MURUM EXCAVATION | CUM | 659.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 659.6 | 150 | 98940 | 659.6 | 150 | 98940 | 659.6 | 0 | 0 | -98940
2803 | INDENT-127 CHAMBER (STORM & ELEC.) & STP SEPTIC TANK BBM-9" | 0 | Tentative | Material | (M)Artificial Sand | BRASS | 3 | 5880 | 17640 | 3 | 5880 | 17640 | 0 | 5880 | 0 | 3 | 6300 | 18900 | 0 | 0 | 0 | 3 | 3 | 17640 | 17640
2804 | INDENT-127 CHAMBER (STORM & ELEC.) & STP SEPTIC TANK BBM-9" | 0 | Tentative | Material | (M)CEMENT PPC 50KG | BAG | 20 | 320 | 6400 | 20 | 320 | 6400 | 0 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 6400 | 6400
2805 | INDENT-127 CHAMBER (STORM & ELEC.) & STP SEPTIC TANK BBM-9" | 0 | Tentative | Material | (M)Crush Sand | BRASS | 3 | 3675 | 11025 | 3 | 3675 | 11025 | 0 | 3675 | 0 | 3 | 3570 | 10710 | 0 | 0 | 0 | 3 | 3 | 11025 | 11025
2806 | INDENT-127 CHAMBER (STORM & ELEC.) & STP SEPTIC TANK BBM-9" | 0 | Tentative | Material | (M)Flyash Bricks 6" | NOS | 6000 | 8.96 | 53760 | 6000 | 8.96 | 53760 | 0 | 8.96 | 0 | 6000 | 9.24 | 55440 | 0 | 0 | 0 | 6000 | 6000 | 53760 | 53760
2807 | STP PUMP ROOM-PLINTH COMPLETION-15% | 0 | Started | Labour | (L)RCC WORK-LABOUR | SQFT | 167.25 | 197.06 | 32958.29 | 0 | 0 | 0 | 0 | 197.06 | 0 | 167.25 | 135 | 22578.75 | 167.25 | 135 | 22578.75 | 167.25 | 0 | 32958.285 | 10379.535
2808 | STP PUMP ROOM-COLUMN UPTO BEAM BOTTOM-30% | 0 | Started | Labour | (L)RCC WORK-LABOUR | SQFT | 334.5 | 197.06 | 65916.57 | 0 | 0 | 0 | 0 | 197.06 | 0 | 334.5 | 135 | 45157.5 | 334.5 | 135 | 45157.5 | 334.5 | 0 | 65916.57 | 20759.07
2809 | STP PUMP ROOM-1ST SLAB LEVEL BEAM-45% | 0 | Started | Labour | (L)RCC WORK-LABOUR | SQFT | 501.75 | 197.06 | 98874.86 | 0 | 0 | 0 | 0 | 197.06 | 0 | 501.75 | 135 | 67736.25 | 501.75 | 135 | 67736.25 | 501.75 | 0 | 98874.855 | 31138.605
2810 | STP PUMP ROOM-1ST SLAB LEVEL CHHAJA & MISC.WORK-10% | 0 | Started | Labour | (L)RCC WORK-LABOUR | SQFT | 111.5 | 197.06 | 21972.19 | 0 | 0 | 0 | 0 | 197.06 | 0 | 111.5 | 135 | 15052.5 | 111.5 | 135 | 15052.5 | 111.5 | 0 | 21972.19 | 6919.69
2811 | STP PUMP ROOM,EXTENSION COM.WALL & ABOVE STP TANK-BBM & PLAS | 0 | Started | Material | (M)AAC Block-125MM | CUM | 32 | 4200 | 134400 | 32 | 4200 | 134400 | 0 | 4200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 134400 | 134400
2812 | STP PUMP ROOM,EXTENSION COM.WALL & ABOVE STP TANK-BBM & PLAS | 0 | Started | Material | (M)Artificial Sand | BRASS | 10 | 5880 | 58800 | 10 | 5880 | 58800 | 0 | 5880 | 0 | 10 | 6300 | 63000 | 0 | 0 | 0 | 10 | 10 | 58800 | 58800
2813 | STP PUMP ROOM,EXTENSION COM.WALL & ABOVE STP TANK-BBM & PLAS | 0 | Started | Material | (M)BLOCK ADHESIEVE | 40 KG/BAG | 32 | 400 | 12800 | 32 | 400 | 12800 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 12800 | 12800
2814 | STP PUMP ROOM,EXTENSION COM.WALL & ABOVE STP TANK-BBM & PLAS | 0 | Started | Material | (M)CEMENT PPC 50KG | BAG | 197 | 320 | 63040 | 197 | 320 | 63040 | 0 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 197 | 197 | 63040 | 63040
2815 | STP PUMP ROOM,EXTENSION COM.WALL & ABOVE STP TANK-BBM & PLAS | 0 | Started | Material | (M)Crush Sand | BRASS | 1 | 3675 | 3675 | 1 | 3675 | 3675 | 0 | 3675 | 0 | 1 | 3675 | 3675 | 0 | 0 | 0 | 1 | 1 | 3675 | 3675
2816 | STP PUMP ROOM,EXTENSION COM.WALL & ABOVE STP TANK-BBM & PLAS | 0 | Started | Material | (M)Metal No.III 20MM | BRASS | 1 | 3045 | 3045 | 1 | 3045 | 3045 | 0 | 3045 | 0 | 1 | 3360 | 3360 | 0 | 0 | 0 | 1 | 1 | 3045 | 3045
2817 | STP PUMP ROOM BBM,PATALI,DPC,INTERNAL & EXTERNAL PLASTER | 0 | Started | Labour | (L)BBM WORK-125MM (ABOVE CHAJJA) | SQFT | 194 | 25 | 4850 | 0 | 0 | 0 | 0 | 25 | 0 | 194 | 25 | 4850 | 168.76 | 25 | 4219 | 194 | 25.24 | 4850 | 631
2818 | STP PUMP ROOM BBM,PATALI,DPC,INTERNAL & EXTERNAL PLASTER | 0 | Started | Labour | (L)BBM WORK-125MM (UPTO BEAM BOTT.) | SQFT | 475 | 22 | 10450 | 0 | 0 | 0 | 0 | 22 | 0 | 475 | 22 | 10450 | 413.22 | 22 | 9090.84 | 475 | 61.78 | 10450 | 1359.16
2819 | STP PUMP ROOM BBM,PATALI,DPC,INTERNAL & EXTERNAL PLASTER | 0 | Started | Labour | (L)BBM WORK-125MM (UPTO PATALI) | SQFT | 764 | 20 | 15280 | 0 | 0 | 0 | 0 | 20 | 0 | 764 | 20 | 15280 | 664.72 | 20 | 13294.4 | 764 | 99.28 | 15280 | 1985.6
2820 | STP PUMP ROOM BBM,PATALI,DPC,INTERNAL & EXTERNAL PLASTER | 0 | Started | Labour | (L)BBM WORK-9'' (Above Top Sheet, Depth-9'') | RFT | 106 | 35 | 3710 | 0 | 0 | 0 | 0 | 35 | 0 | 106 | 35 | 3710 | 91.94 | 35 | 3217.9 | 106 | 14.06 | 3710 | 492.1
2821 | STP PUMP ROOM BBM,PATALI,DPC,INTERNAL & EXTERNAL PLASTER | 0 | Started | Labour | (L)BBM WORK-9'' (B/w top sheet, Depth-24'') | RFT | 182 | 75 | 13650 | 0 | 0 | 0 | 0 | 75 | 0 | 182 | 75 | 13650 | 158.29 | 75 | 11871.75 | 182 | 23.71 | 13650 | 1778.25
2822 | STP PUMP ROOM BBM,PATALI,DPC,INTERNAL & EXTERNAL PLASTER | 0 | Started | Labour | (L)DPC-15OMM (Depth) | RFT | 161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161 | 18 | 2898 | 140.33 | 18 | 2525.94 | 161 | 20.67 | 0 | -2525.94
2823 | STP PUMP ROOM BBM,PATALI,DPC,INTERNAL & EXTERNAL PLASTER | 0 | Started | Labour | (L)PATALI-100MM (Depth) | RFT | 226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226 | 15 | 3390 | 196.09 | 15 | 2941.35 | 226 | 29.91 | 0 | -2941.35
2824 | STP PUMP ROOM BBM,PATALI,DPC,INTERNAL & EXTERNAL PLASTER | 0 | Started | Labour | (L)single coat plaster | SQFT | 5227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5227 | 22 | 114994 | 1836.75 | 22 | 40408.5 | 5227 | 3390.25 | 0 | -40408.5
2825 | STP TANK ABOVE PARAPET WALL DPC,PATALI,BBM & PLASTER | 0 | Started | Labour | (L)BBM WORK-125MM (UPTO PATALI) | SQFT | 809 | 20 | 16180 | 0 | 0 | 0 | 0 | 20 | 0 | 809 | 20 | 16180 | 703.32 | 20 | 14066.4 | 809 | 105.68 | 16180 | 2113.6
2826 | STP TANK ABOVE PARAPET WALL DPC,PATALI,BBM & PLASTER | 0 | Started | Labour | (L)PATALI-100MM (Depth) | RFT | 493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 493 | 15 | 7395 | 428.63 | 15 | 6429.45 | 493 | 64.37 | 0 | -6429.45
2827 | STP TANK ABOVE PARAPET WALL DPC,PATALI,BBM & PLASTER | 0 | Started | Labour | (L)single coat plaster | SQFT | 2528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2528 | 22 | 55616 | 2198.34 | 22 | 48363.48 | 2528 | 329.66 | 0 | -48363.48
2828 | STP SISE COMPOUND WALL EXTENSION BBM & PLASTER | 0 | Tentative | Labour | (L)BBM WORK-125MM (UPTO BEAM BOTT.) | SQFT | 143 | 22 | 3146 | 0 | 0 | 0 | 0 | 22 | 0 | 143 | 22 | 3146 | 0 | 0 | 0 | 143 | 143 | 3146 | 3146
2829 | STP SISE COMPOUND WALL EXTENSION BBM & PLASTER | 0 | Tentative | Labour | (L)single coat plaster | SQFT | 313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 313 | 22 | 6886 | 0 | 0 | 0 | 313 | 313 | 0 | 0
2830 | STP PUMP ROOM M.S FABRICATION & CEMENT SHEET FIXING WORK | 0 | Started | Labour | (L)FABRICATION & CEMENT SHED WORK (M+L) | SQFT | 1090 | 96 | 104640 | 0 | 0 | 0 | 0 | 96 | 0 | 1090 | 96 | 104640 | 1089.165 | 96 | 104559.84 | 1090 | 0.835 | 104640 | 80.16
2831 | STP TANK MANHOLE COVER | 0 | Started | Material | (M)FRP CHAMBER COVER WITH FRAME-24"X 36" (HEAVY DUTY) | SET | 4 | 5900 | 23600 | 4 | 5900 | 23600 | 0 | 5900 | 0 | 4 | 9971 | 39884 | 0 | 0 | 0 | 4 | 4 | 23600 | 23600
2832 | STP TANK MANHOLE COVER | 0 | Started | Material | (M)FRP CHAMBER COVER WITH FRAME-24"X 36" (LIGHT) | SET | 6 | 4130 | 24780 | 6 | 4130 | 24780 | 0 | 4130 | 0 | 6 | 5605 | 33630 | 0 | 0 | 0 | 6 | 6 | 24780 | 24780
2833 | STP INTERNAL WP WORK | 0 | Started | Material | (M)Artificial Sand | BRASS | 22 | 5880 | 129360 | 22 | 5880 | 129360 | 0 | 5880 | 0 | 22 | 6300 | 138600 | 0 | 0 | 0 | 22 | 22 | 129360 | 129360
2834 | STP INTERNAL WP WORK | 0 | Started | Material | (M)CEMENT PPC 50KG | BAG | 262 | 320 | 83840 | 262 | 320 | 83840 | 0 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 262 | 262 | 83840 | 83840
2835 | STP INTERNAL WP WORK | 0 | Started | Material | (M)Water Proofing Chemical LW+ | LTR | 150 | 177 | 26550 | 150 | 177 | 26550 | 0 | 177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 150 | 26550 | 26550
2836 | STP INTERNAL WP WORK | 0 | Started | Material | (M)Waterproofing Dr. FIXIT Pidifin 2k- 15 kg | SET | 52 | 2784.8 | 144809.6 | 52 | 2784.8 | 144809.6 | 0 | 2784.8 | 0 | 52 | 1705.1 | 88665.2 | 0 | 0 | 0 | 52 | 52 | 144809.6 | 144809.6
2837 | STP INTERNAL WP WORK | 0 | Started | Labour | (L)Waterproofing (Lab) | SQFT | 7630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7630 | 18 | 137340 | 7612.88 | 18 | 137031.84 | 7630 | 17.12 | 0 | -137031.84
2838 | SERVICES DEVL.STP ELECTRICAL LINE HT CABLE LAYING-LABOUR | 0 | Started | Labour | (L)Chamber 2 x 3 ft Electrical | NOS | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1900 | 5700 | 3 | 1900 | 5700 | 3 | 0 | 0 | -5700
2839 | SERVICES DEVL.STP ELECTRICAL LINE HT CABLE LAYING-LABOUR | 0 | Started | Labour | (L)RCC line 12-inch Electrical Line | RFT | 149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149 | 50 | 7450 | 149 | 50 | 7450 | 149 | 0 | 0 | -7450
2840 | SERVICES DEVL.STP SEPTIC TANK DRAINAGE LINE & CHAMBER-LABOUR | 0 | Started | Labour | (L)Chamber 2 x 3 ft Drainage | NOS | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2100 | 4200 | 2 | 2100 | 4200 | 2 | 0 | 0 | -4200
2841 | SERVICES DEVL.STP SEPTIC TANK DRAINAGE LINE & CHAMBER-LABOUR | 0 | Started | Labour | (L)PVC Line 8 inch | RFT | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 8 | 184 | 0 | 0 | 0 | 23 | 23 | 0 | 0
2842 | SERVICES DEVL.STP SEPTIC TANK DRAINAGE LINE & CHAMBER-LABOUR | 0 | Started | Labour | (L)RCC line 12-inch Drainage Line | RFT | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 55 | 770 | 13 | 55 | 715 | 14 | 1 | 0 | -715
2843 | SERVICES DEVL.STP SEPTIC TANK DRAINAGE LINE & CHAMBER-LABOUR | 0 | Started | Labour | (L)RCC line 6-inch Drainage Line | RFT | 59.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59.04 | 28 | 1653.12 | 59.04 | 28 | 1653.12 | 59.04 | 0 | 0 | -1653.12
2844 | SERVICES DEVL.STP SEPTIC TANK DRAINAGE LINE & CHAMBER-LABOUR | 0 | Started | Labour | (L)Round Chamber Extension above 5' | NOS | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3400 | 10200 | 2 | 3400 | 6800 | 3 | 1 | 0 | -6800
2845 | SERVICES DEVL.STP SEPTIC TANK DRAINAGE LINE & CHAMBER-LABOUR | 0 | Started | Labour | (L)Round Chamber Extension above 5' (H=8'0'') | NOS | 1 | 4720 | 4720 | 0 | 0 | 0 | 0 | 4720 | 0 | 1 | 4000 | 4000 | 1 | 4000 | 4000 | 1 | 0 | 4720 | 720
2846 | AMENITY EQUIPMENT INDENT-09/CLUB HOUSE/GYM-EQUIPMENT | 10 | Started | Material | (M)BENCH WITH STAND | NOS | 1 | 26000 | 26000 | 1 | 26000 | 26000 | 0 | 26000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 26000 | 26000
2847 | AMENITY EQUIPMENT INDENT-09/CLUB HOUSE/GYM-EQUIPMENT | 10 | Started | Material | (M)Commercial Ellipitical | NOS | 1 | 69500 | 69500 | 1 | 69500 | 69500 | 0 | 69500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 69500 | 69500
2848 | AMENITY EQUIPMENT INDENT-09/CLUB HOUSE/GYM-EQUIPMENT | 10 | Started | Material | (M)Commercial Treadmill | NOS | 2 | 102000 | 204000 | 2 | 102000 | 204000 | 0 | 102000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 204000 | 204000
2849 | AMENITY EQUIPMENT INDENT-09/CLUB HOUSE/GYM-EQUIPMENT | 10 | Started | Material | (M)Dummbell Rack | NOS | 1 | 10800 | 10800 | 1 | 10800 | 10800 | 0 | 10800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 10800 | 10800
2850 | AMENITY EQUIPMENT INDENT-09/CLUB HOUSE/GYM-EQUIPMENT | 10 | Started | Material | (M)FID Bench | NOS | 2 | 26500 | 53000 | 2 | 26500 | 53000 | 0 | 26500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 53000 | 53000
2851 | AMENITY EQUIPMENT INDENT-09/CLUB HOUSE/GYM-EQUIPMENT | 10 | Started | Material | (M)Gym Ball | NOS | 1 | 880 | 880 | 1 | 880 | 880 | 0 | 880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 880 | 880
2852 | AMENITY EQUIPMENT INDENT-09/CLUB HOUSE/GYM-EQUIPMENT | 10 | Started | Material | (M)Hex Rubber Dummbell | NOS | 120 | 150 | 18000 | 120 | 150 | 18000 | 12 | 150 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 120 | 16200 | 18000
2853 | AMENITY EQUIPMENT INDENT-09/CLUB HOUSE/GYM-EQUIPMENT | 10 | Started | Material | (M)Multi Gym 4 Station | NOS | 1 | 149600 | 149600 | 1 | 149600 | 149600 | 0 | 149600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 149600 | 149600
2854 | AMENITY EQUIPMENT INDENT-09/CLUB HOUSE/GYM-EQUIPMENT | 10 | Started | Material | (M)OLYMPIC PLATES | NOS | 105 | 150 | 15750 | 105 | 150 | 15750 | 11 | 150 | 1650 | 0 | 0 | 0 | 0 | 0 | 0 | 94 | 105 | 14100 | 15750
2855 | AMENITY EQUIPMENT INDENT-09/CLUB HOUSE/GYM-EQUIPMENT | 10 | Started | Material | (M)PLATE RACK | NOS | 1 | 9180 | 9180 | 1 | 9180 | 9180 | 0 | 9180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 9180 | 9180
2856 | AMENITY EQUIPMENT INDENT-09/CLUB HOUSE/GYM-EQUIPMENT | 10 | Started | Material | (M)RODS | NOS | 11 | 990 | 10890 | 11 | 990 | 10890 | 1 | 990 | 990 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 11 | 9900 | 10890
2857 | AMENITY EQUIPMENT INDENT-09/CLUB HOUSE/GYM-EQUIPMENT | 10 | Started | Material | (M)Smith Machine With Half Rack | NOS | 1 | 97500 | 97500 | 1 | 97500 | 97500 | 0 | 97500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 97500 | 97500
2858 | AMENITY EQUIPMENT INDENT-09/CLUB HOUSE/GYM-EQUIPMENT | 10 | Started | Material | (M)Upright Bike | NOS | 1 | 23500 | 23500 | 1 | 23500 | 23500 | 0 | 23500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 23500 | 23500
2859 | AMENITY EQUIPMENT INDENT-14/CLUB HOUSE/INDOOR GAMES EQP. | 10 | Started | Material | (M)Carrum Board Stand | NOS | 2 | 1250 | 2500 | 2 | 1250 | 2500 | 0 | 1250 | 0 | 2 | 2124 | 4248 | 0 | 0 | 0 | 2 | 2 | 2500 | 2500
2860 | AMENITY EQUIPMENT INDENT-14/CLUB HOUSE/INDOOR GAMES EQP. | 10 | Started | Material | (M)Champion Carrum Board | NOS | 2 | 3500 | 7000 | 2 | 3500 | 7000 | 0 | 3500 | 0 | 2 | 2124 | 4248 | 0 | 0 | 0 | 2 | 2 | 7000 | 7000
2861 | AMENITY EQUIPMENT INDENT-14/CLUB HOUSE/INDOOR GAMES EQP. | 10 | Started | Material | (M)Chess Stand | NOS | 1 | 1250 | 1250 | 1 | 1250 | 1250 | 0 | 1250 | 0 | 1 | 2124 | 2124 | 0 | 0 | 0 | 1 | 1 | 1250 | 1250
2862 | AMENITY EQUIPMENT INDENT-14/CLUB HOUSE/INDOOR GAMES EQP. | 10 | Started | Material | (M)Foos ball table with Accessories | SET | 1 | 24999 | 24999 | 1 | 24999 | 24999 | 0 | 24999 | 0 | 1 | 39530 | 39530 | 0 | 0 | 0 | 1 | 1 | 24999 | 24999
2863 | AMENITY EQUIPMENT INDENT-14/CLUB HOUSE/INDOOR GAMES EQP. | 10 | Started | Material | (M)Suzuki TT Table | NOS | 1 | 25000 | 25000 | 1 | 25000 | 25000 | 0 | 25000 | 0 | 1 | 29500 | 29500 | 0 | 0 | 0 | 1 | 1 | 25000 | 25000
2864 | AMENITY EQUIPMENT INDENT-14/CLUB HOUSE/INDOOR GAMES EQP. | 10 | Started | Material | (M)TT Ball Set | SET | 2 | 250 | 500 | 2 | 250 | 500 | 0 | 250 | 0 | 2 | 295 | 590 | 0 | 0 | 0 | 2 | 2 | 500 | 500
2865 | AMENITY EQUIPMENT INDENT-14/CLUB HOUSE/INDOOR GAMES EQP. | 10 | Started | Material | (M)TT Bat | NOS | 4 | 500 | 2000 | 4 | 500 | 2000 | 0 | 500 | 0 | 4 | 767 | 3068 | 0 | 0 | 0 | 4 | 4 | 2000 | 2000
2866 | AMENITY EQUIPMENT INDENT-14/CLUB HOUSE/INDOOR GAMES EQP. | 10 | Started | Material | (M)Woodern Carrum Coins | SET | 2 | 450 | 900 | 2 | 450 | 900 | 0 | 450 | 0 | 2 | 531 | 1062 | 0 | 0 | 0 | 2 | 2 | 900 | 900
2867 | AMENITY EQUIPMENT INDENT-14/CLUB HOUSE/INDOOR GAMES EQP. | 10 | Started | Material | (M)Woodern Chess Board with Coins | SET | 1 | 1850 | 1850 | 1 | 1850 | 1850 | 0 | 1850 | 0 | 1 | 2065 | 2065 | 0 | 0 | 0 | 1 | 1 | 1850 | 1850
2868 | AMENITY EQUIPMENT INDENT-12/EXERCISE EQUIPMENT-OUT DOOR | 10 | Started | Material | (M)4 SHOULDER WHEELS | NOS | 1 | 34810 | 34810 | 1 | 34810 | 34810 | 0 | 34810 | 0 | 1 | 19470 | 19470 | 0 | 0 | 0 | 1 | 1 | 34810 | 34810
2869 | AMENITY EQUIPMENT INDENT-12/EXERCISE EQUIPMENT-OUT DOOR | 10 | Started | Material | (M)CHEST PRESS | NOS | 1 | 47082 | 47082 | 1 | 47082 | 47082 | 0 | 47082 | 0 | 1 | 19470 | 19470 | 0 | 0 | 0 | 1 | 1 | 47082 | 47082
2870 | AMENITY EQUIPMENT INDENT-12/EXERCISE EQUIPMENT-OUT DOOR | 10 | Started | Material | (M)FIX BENCHES FRP-5 FT | NOS | 6 | 5900 | 35400 | 6 | 5900 | 35400 | 1 | 5900 | 5900 | 6 | 7788 | 46728 | 0 | 0 | 0 | 5 | 6 | 29500 | 35400
2871 | AMENITY EQUIPMENT INDENT-12/EXERCISE EQUIPMENT-OUT DOOR | 10 | Started | Material | (M)LEG PRESS | NOS | 1 | 31624 | 31624 | 1 | 31624 | 31624 | 0 | 31624 | 0 | 1 | 21417 | 21417 | 0 | 0 | 0 | 1 | 1 | 31624 | 31624
2872 | AMENITY EQUIPMENT INDENT-12/EXERCISE EQUIPMENT-OUT DOOR | 10 | Started | Material | (M)SHOULDER PRESS | NOS | 1 | 47082 | 47082 | 1 | 47082 | 47082 | 0 | 47082 | 0 | 1 | 19470 | 19470 | 0 | 0 | 0 | 1 | 1 | 47082 | 47082
2873 | AMENITY EQUIPMENT INDENT-12/EXERCISE EQUIPMENT-OUT DOOR | 10 | Started | Material | (M)SINGLE AIR WALKER | NOS | 2 | 67732 | 135464 | 2 | 67732 | 135464 | 0 | 67732 | 0 | 1 | 18496.5 | 18496.5 | 0 | 0 | 0 | 2 | 2 | 135464 | 135464
2874 | AMENITY EQUIPMENT INDENT-12/EXERCISE EQUIPMENT-OUT DOOR | 10 | Started | Material | (M)TRIPPLE STANDING TWISTER | NOS | 1 | 39530 | 39530 | 1 | 39530 | 39530 | 0 | 39530 | 0 | 1 | 19470 | 19470 | 0 | 0 | 0 | 1 | 1 | 39530 | 39530
2875 | AMENITY EQUIPMENT INDENT-11/CHILDREN PLAY COURT-EQUIPMENT | 10 | Started | Material | (M)Horse Rider 1-Seater-2'6''x1'0''x2'6'' | NOS | 1 | 23010 | 23010 | 1 | 23010 | 23010 | 0 | 23010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 23010 | 23010
2876 | AMENITY EQUIPMENT INDENT-11/CHILDREN PLAY COURT-EQUIPMENT | 10 | Started | Material | (M)MGR 4-Seater-4'x4'x4' | NOS | 1 | 32450 | 32450 | 1 | 32450 | 32450 | 0 | 32450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 32450 | 32450
2877 | AMENITY EQUIPMENT INDENT-11/CHILDREN PLAY COURT-EQUIPMENT | 10 | Started | Material | (M)Multi Play System-35'x13'x25' | NOS | 1 | 596195 | 596195 | 1 | 596195 | 596195 | 0 | 596195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 596195 | 596195
2878 | AMENITY EQUIPMENT INDENT-11/CHILDREN PLAY COURT-EQUIPMENT | 10 | Started | Material | (M)Net Climber-6'x5'x7' | NOS | 1 | 45076 | 45076 | 1 | 45076 | 45076 | 0 | 45076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 45076 | 45076
2879 | AMENITY EQUIPMENT INDENT-11/CHILDREN PLAY COURT-EQUIPMENT | 10 | Started | Material | (M)Orbit Climber-9'6''x5'6''x9' | NOS | 1 | 46610 | 46610 | 1 | 46610 | 46610 | 0 | 46610 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 46610 | 46610
2880 | AMENITY EQUIPMENT INDENT-11/CHILDREN PLAY COURT-EQUIPMENT | 10 | Started | Material | (M)See Saw 4-Seater-10'x6'x3' | NOS | 1 | 28910 | 28910 | 1 | 28910 | 28910 | 0 | 28910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 28910 | 28910
2881 | AMENITY EQUIPMENT INDENT-11/CHILDREN PLAY COURT-EQUIPMENT | 10 | Started | Material | (M)Swing 2-Seater-10'x3'x8' | NOS | 1 | 27730 | 27730 | 1 | 27730 | 27730 | 0 | 27730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 27730 | 27730
2882 | DEVELOPEMENT ELECTRICAL PANEL,FEEDER PILLAR & RMU | 10 | Started | Material | (M)11_Club House Meter Panel-5 (Locn-DTC) | SET | 1 | 41300 | 41300 | 1 | 41300 | 41300 | 0 | 41300 | 0 | 1 | 43868.86 | 43868.86 | 0 | 0 | 0 | 1 | 1 | 41300 | 41300
2883 | DEVELOPEMENT ELECTRICAL PANEL,FEEDER PILLAR & RMU | 10 | Started | Material | (M)16_Common Utility C/O Panel-1 (Locn-DTC) | SET | 1 | 295000 | 295000 | 1 | 295000 | 295000 | 0 | 295000 | 0 | 1 | 270487.86 | 270487.86 | 0 | 0 | 0 | 1 | 1 | 295000 | 295000
2884 | DEVELOPEMENT ELECTRICAL PANEL,FEEDER PILLAR & RMU | 10 | Started | Material | (M)17_Common Utility C/O Panel-2 (Locn-DTC) | SET | 1 | 106200 | 106200 | 1 | 106200 | 106200 | 0 | 106200 | 0 | 1 | 72275 | 72275 | 0 | 0 | 0 | 1 | 1 | 106200 | 106200
2885 | DEVELOPEMENT ELECTRICAL PANEL,FEEDER PILLAR & RMU | 10 | Started | Material | (M)20_Club House C/O Panel-4 (Locn-DTC) | SET | 1 | 88500 | 88500 | 1 | 88500 | 88500 | 0 | 88500 | 0 | 1 | 73101 | 73101 | 0 | 0 | 0 | 1 | 1 | 88500 | 88500
2886 | DEVELOPEMENT ELECTRICAL PANEL,FEEDER PILLAR & RMU | 10 | Started | Material | (M)22Kv SF6 Moto. SCADA Comp. RMU (2+3) | SET | 1 | 708000 | 708000 | 1 | 708000 | 708000 | 0 | 708000 | 0 | 1 | 1463200 | 1463200 | 0 | 0 | 0 | 1 | 1 | 708000 | 708000
2887 | DEVELOPEMENT ELECTRICAL PANEL,FEEDER PILLAR & RMU | 10 | Started | Material | (M)22KV. 630A. 21KA/3Sec 2 way outdoor RMU (1+1) | SET | 1 | 1416000 | 1416000 | 1 | 1416000 | 1416000 | 0 | 1416000 | 0 | 1 | 772900 | 772900 | 0 | 0 | 0 | 1 | 1 | 1416000 | 1416000
2888 | DEVELOPEMENT ELECTRICAL PANEL,FEEDER PILLAR & RMU | 10 | Started | Material | (M)24_APFC Panel-1, 45KVAR (Locn-Panel Room) | SET | 1 | 165200 | 165200 | 1 | 165200 | 165200 | 0 | 165200 | 0 | 1 | 116251.24 | 116251.24 | 0 | 0 | 0 | 1 | 1 | 165200 | 165200
2889 | DEVELOPEMENT ELECTRICAL PANEL,FEEDER PILLAR & RMU | 10 | Started | Material | (M)25_UGWT PUMP PANEL (Locn-UGT PUMP ROOM) | SET | 1 | 49560 | 49560 | 1 | 49560 | 49560 | 0 | 49560 | 0 | 1 | 44688.96 | 44688.96 | 0 | 0 | 0 | 1 | 1 | 49560 | 49560
2890 | DEVELOPEMENT ELECTRICAL PANEL,FEEDER PILLAR & RMU | 10 | Started | Material | (M)26_DG Distribution Panel-1 (Trans. Room) | SET | 1 | 236000 | 236000 | 1 | 236000 | 236000 | 0 | 236000 | 0 | 1 | 222330.88 | 222330.88 | 0 | 0 | 0 | 1 | 1 | 236000 | 236000
2891 | DEVELOPEMENT ELECTRICAL PANEL,FEEDER PILLAR & RMU | 10 | Started | Material | (M)3-Phase 630 KVA Distribution Transformer | SET | 2 | 1221300 | 2442600 | 2 | 1221300 | 2442600 | 0 | 1221300 | 0 | 2 | 1062000 | 2124000 | 0 | 0 | 0 | 2 | 2 | 2442600 | 2442600
2892 | DEVELOPEMENT ELECTRICAL PANEL,FEEDER PILLAR & RMU | 10 | Started | Material | (M)8_Common CT Meter Panel-1 (Locn-DTC) | SET | 1 | 76700 | 76700 | 1 | 76700 | 76700 | 0 | 76700 | 0 | 1 | 78677.68 | 78677.68 | 0 | 0 | 0 | 1 | 1 | 76700 | 76700
2893 | DEVELOPEMENT ELECTRICAL PANEL,FEEDER PILLAR & RMU | 10 | Started | Material | (M)9_Common CT Meter Panel-2 (Locn-DTC) | SET | 1 | 33040 | 33040 | 1 | 33040 | 33040 | 0 | 33040 | 0 | 1 | 39950.08 | 39950.08 | 0 | 0 | 0 | 1 | 1 | 33040 | 33040
2894 | DEVELOPEMENT ELECTRICAL PANEL,FEEDER PILLAR & RMU | 10 | Started | Material | (M)LT 8 Way ACB Feeder Pillar with HRC fuse link | SET | 2 | 21240 | 42480 | 2 | 21240 | 42480 | 0 | 21240 | 0 | 2 | 104996.4 | 209992.8 | 0 | 0 | 0 | 2 | 2 | 42480 | 42480
2895 | DEVELOPEMENT ELECTRICAL PANEL,FEEDER PILLAR & RMU | 10 | Started | Material | (M)Metering Panel-1 (Common CT Meter panel-1) | NOS | 1 | 9243.19 | 9243.19 | 1 | 9243.19 | 9243.19 | 0 | 9243.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 9243.19 | 9243.19
2896 | DEVELOPEMENT ELECTRICAL PANEL,FEEDER PILLAR & RMU | 10 | Started | Material | (M)Metering Panel-2 (Common CT Meter panel-2) | NOS | 1 | 7844.86 | 7844.86 | 1 | 7844.86 | 7844.86 | 0 | 7844.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 7844.86 | 7844.86
2897 | DEVELOPEMENT ELECTRICAL PANEL,FEEDER PILLAR & RMU | 10 | Started | Material | (M)Metering Panel-3 (Club House Meter panel-5) | NOS | 1 | 7844.86 | 7844.86 | 1 | 7844.86 | 7844.86 | 0 | 7844.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 7844.86 | 7844.86
2898 | Transformer Room Rcc work Material | 0 | Started | Material | (M)MS Binding Wire 18G | KG | 150 | 50 | 7500 | 150 | 50 | 7500 | 0 | 50 | 0 | 150 | 76.7 | 11505 | 0 | 0 | 0 | 150 | 150 | 7500 | 7500
2899 | Transformer Room Rcc work Material | 0 | Started | Material | (M)PERMA BOND SBR 25 LTR BUCKET | BUCKET | 1 | 4491.75 | 4491.75 | 1 | 4491.75 | 4491.75 | 0 | 4491.75 | 0 | 1 | 5654 | 5654 | 0 | 0 | 0 | 1 | 1 | 4491.75 | 4491.75
2900 | Transformer Room Rcc work Material | 0 | Started | Material | (M)RMC M-15 | CUM | 30 | 3500 | 105000 | 30 | 3500 | 105000 | 0 | 3500 | 0 | 30 | 5000 | 150000.003 | 0 | 0 | 0 | 30 | 30 | 105000 | 105000
2901 | Transformer Room Rcc work Material | 0 | Started | Material | (M)RMC M-25 | CUM | 55 | 4600 | 253000 | 55 | 4600 | 253000 | 0 | 4600 | 0 | 41 | 5165.85 | 211799.9995 | 0 | 0 | 0 | 55 | 55 | 253000 | 253000
2902 | Transformer Room Rcc work Material | 0 | Started | Material | (M)T.M.T.Bar 10mm (Fe 500, 0.617 KGS/Rm) | KG | 2000 | 59 | 118000 | 2000 | 59 | 118000 | 0 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2000 | 118000 | 118000
2903 | Transformer Room Rcc work Material | 0 | Started | Material | (M)T.M.T.Bar 12mm (Fe 500, 0.888 KGS/Rm) | KG | 2300 | 59 | 135700 | 2300 | 59 | 135700 | 0 | 59 | 0 | 0 | 0 | 0 | 597.31 | 60.06 | 35872.77 | 2300 | 1702.69 | 135700 | 99827.23
2904 | Transformer Room Rcc work Material | 0 | Started | Material | (M)T.M.T.Bar 16mm (Fe 500, 1.58 KGS/Rm) | KG | 1000 | 59 | 59000 | 1000 | 59 | 59000 | 0 | 59 | 0 | 1000 | 57.23 | 57230 | 0 | 0 | 0 | 1000 | 1000 | 59000 | 59000
2905 | Transformer Room Rcc work Material | 0 | Started | Material | (M)T.M.T.Bar 20mm (Fe 500, 2.47 KGS/Rm) | KG | 600 | 59 | 35400 | 600 | 59 | 35400 | 0 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 600 | 35400 | 35400
2906 | Transformer Room Rcc work Material | 0 | Started | Material | (M)T.M.T.Bar 8mm (Fe 500, 0.395 KGS/Rm) | KG | 4000 | 59 | 236000 | 4000 | 59 | 236000 | 0 | 59 | 0 | 0 | 0 | 0 | 805.8 | 61.77 | 49777.13 | 4000 | 3194.2 | 236000 | 186222.87
2907 | Transformer Liassioning Charge-After Sanction | 0 | Started | Labour | (L)Transformer Liassioning Charge | NOS | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250000 | 1 | 250000 | 250000 | 1 | 250000 | 250000 | 0 | 0 | -250000
2908 | Transformer Liassioning Charge-After WCR Release & Inspectio | 0 | Started | Labour | (L)Transformer Liassioning Charge | NOS | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 1 | 100000 | 100000 | 1 | 100000 | 100000 | 0 | 0 | -100000
2909 | Transformer Liassioning Charge-After Charging Permission | 0 | Started | Labour | (L)Transformer Liassioning Charge | NOS | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 1 | 100000 | 100000 | 1 | 100000 | 100000 | 0 | 0 | -100000
2910 | Transformer Liassioning Charge-After Meter Sanction | 0 | Started | Labour | (L)Transformer Liassioning Charge | NOS | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100000 | 1 | 100000 | 100000 | 1 | 100000 | 100000 | 0 | 0 | -100000
2911 | TRAN.ROOM TRENCH PCC,BBM & PLASTER WORK-MATERIAL | 0 | Started | Material | (M)Artificial Sand | BRASS | 6 | 5880 | 35280 | 6 | 5880 | 35280 | 0 | 5880 | 0 | 6 | 6300 | 37800 | 0 | 0 | 0 | 6 | 6 | 35280 | 35280
2912 | TRAN.ROOM TRENCH PCC,BBM & PLASTER WORK-MATERIAL | 0 | Started | Material | (M)CEMENT PPC 50KG | BAG | 113 | 320 | 36160 | 113 | 320 | 36160 | 0 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113 | 113 | 36160 | 36160
2913 | TRAN.ROOM TRENCH PCC,BBM & PLASTER WORK-MATERIAL | 0 | Started | Material | (M)Crush Sand | BRASS | 6 | 3675 | 22050 | 5 | 3675 | 18375 | 0 | 3675 | 0 | 5 | 3675 | 18375 | 0 | 0 | 0 | 6 | 6 | 22050 | 22050
2914 | TRAN.ROOM TRENCH PCC,BBM & PLASTER WORK-MATERIAL | 0 | Started | Material | (M)Flyash Bricks 6" | NOS | 16500 | 8.96 | 147840 | 16500 | 8.96 | 147840 | 0 | 8.96 | 0 | 16500 | 9.24 | 152460 | 0 | 0 | 0 | 16500 | 16500 | 147840 | 147840
2915 | TRAN.ROOM TRENCH PCC,BBM & PLASTER WORK-MATERIAL | 0 | Started | Material | (M)Metal No.III 20MM | BRASS | 3 | 3045 | 9135 | 3 | 3045 | 9135 | 0 | 3045 | 0 | 2 | 3360 | 6720 | 0 | 0 | 0 | 3 | 3 | 9135 | 9135
2916 | TRAN.ROOM TRENCH PCC,BBM & PLASTER WORK-MATERIAL | 0 | Started | Labour | (L)BBM 6" thick | BRASS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2917 | TRENCH SIDE PLASTER WORK-labour | 0 | Started | Labour | (L)9" Brickwork Labour | SQFT | 1402.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1402.77 | 21 | 29458.17 | 834.31 | 21 | 17520.51 | 1402.77 | 568.46 | 0 | -17520.51
2918 | TRENCH SIDE PLASTER WORK-labour | 0 | Started | Labour | (L)PCC Work (labour) | SQFT | 708.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 708.49 | 10 | 7084.9 | 708.49 | 10 | 7084.9 | 708.49 | 0 | 0 | -7084.9
2919 | TRENCH SIDE PLASTER WORK-labour | 0 | Started | Labour | (L)single coat plaster | SQFT | 945.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 945.93 | 16 | 15134.88 | 945.93 | 16 | 15134.88 | 945.93 | 0 | 0 | -15134.88
2920 | TRENCH SIDE PLASTER WORK-labour | 0 | Started | Labour | (L)Tar Plaster (Labour) | SQFT | 510.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 510.28 | 5 | 2551.4 | 510.28 | 5 | 2551.4 | 510.28 | 0 | 0 | -2551.4
2921 | SEPTIC TANK BBM & PLASTER-LABOUR | 0 | Started | Labour | (L)9" Brickwork Labour | SQFT | 153.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 153.17 | 21 | 3216.57 | 153.17 | 21 | 3216.57 | 153.17 | 0 | 0 | -3216.57
2922 | SEPTIC TANK BBM & PLASTER-LABOUR | 0 | Started | Labour | (L)single coat plaster | SQFT | 306.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 306.34 | 16 | 4901.44 | 306.34 | 16 | 4901.44 | 306.34 | 0 | 0 | -4901.44
2923 | TRANSFORMER ROOM BBM & PLASTER WORK-MAT & LAB | 0 | Started | Material | (M)AAC Block-125MM | CUM | 14 | 4200 | 58800 | 14 | 4200 | 58800 | 0 | 4200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 14 | 58800 | 58800
2924 | TRANSFORMER ROOM BBM & PLASTER WORK-MAT & LAB | 0 | Started | Material | (M)Artificial Sand | BRASS | 6 | 5880 | 35280 | 6 | 5880 | 35280 | 0 | 5880 | 0 | 6 | 6300 | 37800 | 0 | 0 | 0 | 6 | 6 | 35280 | 35280
2925 | TRANSFORMER ROOM BBM & PLASTER WORK-MAT & LAB | 0 | Started | Material | (M)BLOCK ADHESIEVE | 40 KG/BAG | 14 | 400 | 5600 | 14 | 400 | 5600 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 14 | 5600 | 5600
2926 | TRANSFORMER ROOM BBM & PLASTER WORK-MAT & LAB | 0 | Started | Material | (M)CEMENT PPC 50KG | BAG | 115 | 320 | 36800 | 115 | 320 | 36800 | 0 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115 | 115 | 36800 | 36800
2927 | TRANSFORMER ROOM BBM & PLASTER WORK-MAT & LAB | 0 | Started | Labour | (L)BBM ABOVE SLAB-125MM (D=200MM) | RFT | 156 | 23.6 | 3681.6 | 0 | 0 | 0 | 0 | 23.6 | 0 | 156 | 20 | 3120 | 141.47 | 20 | 2829.4 | 156 | 14.53 | 3681.6 | 852.2
2928 | TRANSFORMER ROOM BBM & PLASTER WORK-MAT & LAB | 0 | Started | Labour | (L)BBM B/W TOP BOTTOM CHHAJA-125MM (D=400MM) | RFT | 58 | 41.3 | 2395.4 | 0 | 0 | 0 | 0 | 41.3 | 0 | 58 | 35 | 2030 | 52.96 | 35 | 1853.6 | 58 | 5.04 | 2395.4 | 541.8
2929 | TRANSFORMER ROOM BBM & PLASTER WORK-MAT & LAB | 0 | Started | Labour | (L)BBM WORK-125MM (UPTO BEAM BOTT.) | SQFT | 390 | 22 | 8580 | 0 | 0 | 0 | 0 | 22 | 0 | 390 | 22 | 8580 | 354.54 | 22 | 7799.88 | 390 | 35.46 | 8580 | 780.12
2930 | TRANSFORMER ROOM BBM & PLASTER WORK-MAT & LAB | 0 | Started | Labour | (L)BBM WORK-125MM (UPTO PATALI) | SQFT | 532 | 20 | 10640 | 0 | 0 | 0 | 0 | 20 | 0 | 532 | 20 | 10640 | 483.94 | 20 | 9678.8 | 532 | 48.06 | 10640 | 961.2
2931 | TRANSFORMER ROOM BBM & PLASTER WORK-MAT & LAB | 0 | Started | Labour | (L)BBM WORK-200MM THK | SQFT | 29 | 29.5 | 855.5 | 0 | 0 | 0 | 0 | 29.5 | 0 | 29 | 25 | 725 | 26.37 | 25 | 659.25 | 29 | 2.63 | 855.5 | 196.25
2932 | TRANSFORMER ROOM BBM & PLASTER WORK-MAT & LAB | 0 | Started | Labour | (L)PATALI-100MM (Depth) | RFT | 311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 311 | 15 | 4665 | 282.61 | 15 | 4239.15 | 311 | 28.39 | 0 | -4239.15
2933 | TRANSFORMER ROOM BBM & PLASTER WORK-MAT & LAB | 0 | Started | Labour | (L)Single Coat Plaster (Labour) | SQFT | 5129 | 22 | 112838 | 0 | 0 | 0 | 0 | 22 | 0 | 5129 | 22 | 112838 | 1219.1 | 22 | 26820.2 | 5129 | 3909.9 | 112838 | 86017.8
2934 | TRANSFORMER ROOM TRENCH BOTTOM PLASTER WORK | 0 | Started | Material | (M)Artificial Sand | BRASS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2935 | TRANSFORMER ROOM TRENCH BOTTOM PLASTER WORK | 0 | Started | Material | (M)CEMENT PPC 50KG | BAG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2936 | TRANSFORMER ROOM TRENCH BOTTOM PLASTER WORK | 0 | Started | Material | (M)Perma Plasto-O-Proof | BUCKET | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2937 | TRANSFORMER ROOM TRENCH BOTTOM PLASTER WORK | 0 | Started | Labour | (L)Single Coat plaster (Ghotai plaster) | SQFT | 411 | 18 | 7398 | 0 | 0 | 0 | 0 | 18 | 0 | 411 | 18 | 7398 | 410.46 | 18 | 7388.28 | 411 | 0.54 | 7398 | 9.72
2938 | TRANSFORMER ROOM FOUNDATION PCC PLASTER WORK | 0 | Started | Material | (M)Artificial Sand | BRASS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2939 | TRANSFORMER ROOM FOUNDATION PCC PLASTER WORK | 0 | Started | Material | (M)CEMENT PPC 50KG | BAG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2940 | TRANSFORMER ROOM FOUNDATION PCC PLASTER WORK | 0 | Started | Material | (M)Perma Plasto-O-Proof | BUCKET | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2941 | TRANSFORMER ROOM FOUNDATION PCC PLASTER WORK | 0 | Started | Labour | (L)Single Coat plaster (Ghotai plaster) | SQFT | 601 | 18 | 10818 | 0 | 0 | 0 | 0 | 18 | 0 | 601 | 18 | 10818 | 600.77 | 18 | 10813.86 | 601 | 0.23 | 10818 | 4.14
2942 | TRANSFORMER ROOM RCC-PLINTH BEAM: FOOTING, COL. UPTO PLINTH | 0 | Started | Labour | (L)RCC WORK-LABOUR | SQFT | 249.3811 | 197.06 | 49143.04 | 0 | 0 | 0 | 0 | 197.06 | 0 | 249.3811 | 173 | 43142.9303 | 249.3811 | 173 | 43142.93 | 249.3811 | 0 | 49143.04 | 6000.1096
2943 | TRANSFORMER ROOM RCC- PLINTH BEAM CMPLETION | 0 | Started | Labour | (L)RCC WORK-LABOUR | SQFT | 174.5668 | 197.06 | 34400.13 | 0 | 0 | 0 | 0 | 197.06 | 0 | 174.5668 | 173 | 30200.0564 | 174.5668 | 173 | 30200.06 | 174.5668 | 0 | 34400.134 | 4200.0736
2944 | TRANSFORMER ROOM RCC-PLINTH BEAM: SOLING & PCC | 0 | Started | Labour | (L)RCC WORK-LABOUR | SQFT | 74.8143 | 197.06 | 14742.91 | 0 | 0 | 0 | 0 | 197.06 | 0 | 74.8143 | 173 | 12942.8739 | 74.8143 | 173 | 12942.87 | 74.8143 | 0 | 14742.906 | 1800.036
2945 | TRANSFORMER ROOM RCC-1ST SLAB: COLUMN UP TO SLAB | 0 | Started | Labour | (L)RCC WORK-LABOUR | SQFT | 336.6645 | 197.06 | 66343.11 | 0 | 0 | 0 | 0 | 197.06 | 0 | 336.6645 | 173 | 58242.9585 | 336.6645 | 173 | 58242.96 | 336.6645 | 0 | 66343.106 | 8100.1464
2946 | TRANSFORMER ROOM RCC-1ST SLAB: SHUTT. REINF. & CAST. OF SLAB | 0 | Started | Labour | (L)RCC WORK-LABOUR | SQFT | 673.329 | 197.06 | 132686.21 | 0 | 0 | 0 | 0 | 197.06 | 0 | 673.329 | 173 | 116485.917 | 673.329 | 173 | 116485.92 | 673.329 | 0 | 132686.213 | 16200.2927
2947 | TRANSFORMER ROOM RCC-1ST SLAB: HACKING, DESHUTTERING. | 0 | Started | Labour | (L)RCC WORK-LABOUR | SQFT | 112.2215 | 197.06 | 22114.37 | 0 | 0 | 0 | 0 | 197.06 | 0 | 112.2215 | 173 | 19414.3195 | 112.2215 | 173 | 19414.32 | 112.2215 | 0 | 22114.369 | 2700.0488
2948 | TRANSFORMER ROOM RCC-MISC. & CLEANING WORK. | 0 | Started | Labour | (L)RCC WORK-LABOUR | SQFT | 41.5635 | 197.06 | 8190.5 | 0 | 0 | 0 | 0 | 197.06 | 0 | 41.5635 | 173 | 7190.4855 | 41.5635 | 173 | 7190.49 | 41.5635 | 0 | 8190.503 | 1000.0133
2949 | TRANSFORMER ROOM & STP ROLLING SHUTTER | 0 | Started | Material | (M)Red Oxide (20 LTR/BUCKET) | LITRE | 20 | 177 | 3540 | 20 | 177 | 3540 | 0 | 177 | 0 | 20 | 259.6 | 5192 | 0 | 0 | 0 | 20 | 20 | 3540 | 3540
2950 | TRANSFORMER ROOM & STP ROLLING SHUTTER | 0 | Started | Labour | (L)GI TOP COVER FOR SHUTTER | RFT | 45 | 160 | 7200 | 0 | 0 | 0 | 0 | 160 | 0 | 45 | 160 | 7200 | 44.15 | 160 | 7064 | 45 | 0.85 | 7200 | 136
2951 | TRANSFORMER ROOM & STP ROLLING SHUTTER | 0 | Started | Labour | (L)MS GEAR SET FOR SHUTTER WITH MS HANDLE | NOS | 4 | 7500 | 30000 | 0 | 0 | 0 | 0 | 7500 | 0 | 4 | 7500 | 30000 | 4 | 7500 | 30000 | 4 | 0 | 30000 | 0
2952 | TRANSFORMER ROOM & STP ROLLING SHUTTER | 0 | Started | Labour | (L)MS GRID PATTTI MAKING CHARGES | SQ.FT. | 98 | 50 | 4900 | 0 | 0 | 0 | 0 | 50 | 0 | 98 | 50 | 4900 | 95.38 | 50 | 4769 | 98 | 2.62 | 4900 | 131
2953 | TRANSFORMER ROOM & STP ROLLING SHUTTER | 0 | Started | Labour | (L)MS ROLLING SHUTTER (20 Guage) | SQ.FT. | 499 | 155 | 77345 | 0 | 0 | 0 | 0 | 155 | 0 | 499 | 155 | 77345 | 480.28 | 155 | 74443.4 | 499 | 18.72 | 77345 | 2901.6
2954 | TRANSFORMER ROOM & STP ROLLING SHUTTER | 0 | Started | Labour | (L)MS SQ TUBE 40 X 60 | NOS | 2 | 1000 | 2000 | 0 | 0 | 0 | 0 | 1000 | 0 | 2 | 1000 | 2000 | 1 | 1000 | 1000 | 2 | 1 | 2000 | 1000
2955 | TRANSFORMER ROOM SLAB TOP BRICK BAT WP WORK | 0 | Tentative | Material | (M)Artificial Sand | BRASS | 3 | 5880 | 17640 | 3 | 5880 | 17640 | 0 | 5880 | 0 | 3 | 6300 | 18900 | 0 | 0 | 0 | 3 | 3 | 17640 | 17640
2956 | TRANSFORMER ROOM SLAB TOP BRICK BAT WP WORK | 0 | Tentative | Material | (M)CEMENT PPC 50KG | BAG | 48 | 320 | 15360 | 48 | 320 | 15360 | 0 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 48 | 15360 | 15360
2957 | TRANSFORMER ROOM SLAB TOP BRICK BAT WP WORK | 0 | Tentative | Material | (M)Pidifin - 2k - 15kg | PACKET | 11 | 1465 | 16115 | 0 | 0 | 0 | 0 | 1465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 11 | 16115 | 16115
2958 | TRANSFORMER ROOM SLAB TOP BRICK BAT WP WORK | 0 | Tentative | Material | (M)Red Bricks 4" | NOS | 4730 | 8.5 | 40205 | 4730 | 8.5 | 40205 | 0 | 8.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4730 | 4730 | 40205 | 40205
2959 | TRANSFORMER ROOM SLAB TOP BRICK BAT WP WORK | 0 | Tentative | Labour | (L)Waterproofing (Lab) | SQFT | 1182.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1182.5 | 21 | 24832.5 | 0 | 0 | 0 | 1182.5 | 1182.5 | 0 | 0
2960 | TRANSFORMER ROOM FABRICATION WORK | 0 | Started | Labour | (L)M.S.Grill (Mat.+Lab.) | SQFT | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 100 | 1600 | 16 | 100 | 1600 | 16 | 0 | 0 | -1600
2961 | TRANSFORMER ROOM FABRICATION WORK | 0 | Started | Labour | (L)Perforated Sheet With Frame (Mat+Lab) | SQFT | 133 | 153.4 | 20402.2 | 0 | 0 | 0 | 0 | 153.4 | 0 | 133 | 130 | 17290 | 132.43 | 130 | 17215.9 | 133 | 0.57 | 20402.2 | 3186.3
2962 | TRANSFORMER ROOM FABRICATION WORK | 0 | Started | Labour | (L)SAFETY DOOR | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 8000 | 8000 | 1 | 8000 | 8000 | 1 | 0 | 0 | -8000
2963 | TRANSFORMER ROOM FABRICATION WORK | 0 | Started | Labour | (L)TRENCH JALI FABRICATION (Mat+Lab) | SQFT | 592 | 153.4 | 90812.8 | 0 | 0 | 0 | 0 | 153.4 | 0 | 592 | 130 | 76960 | 349.48 | 130 | 45432.4 | 592 | 242.52 | 90812.8 | 45380.4
2964 | STP PUMP ROOM FABRICATION WORK | 0 | Started | Labour | (L)M.S.Grill (Mat.+Lab.) | SQFT | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 100 | 3800 | 37.5635 | 100 | 3756.35 | 38 | 0.4365 | 0 | -3756.35
2965 | STP PUMP ROOM FABRICATION WORK | 0 | Started | Labour | (L)Perforated Sheet With Frame (Mat+Lab) | SQFT | 182 | 153.4 | 27918.8 | 0 | 0 | 0 | 0 | 153.4 | 0 | 182 | 125.3 | 22804.6 | 154.52 | 125.3 | 19361.36 | 182 | 27.48 | 27918.8 | 8557.44
2966 | STP PUMP ROOM FABRICATION WORK | 0 | Started | Labour | (L)SAFETY DOOR | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 8000 | 8000 | 1 | 8000 | 8000 | 1 | 0 | 0 | -8000
2967 | STP & TRANSFORMER ROOM EARTHING WORK (M+L) | 0 | Started | Labour | (L)Copper Earthing 80mm dia, 3mtr long (BFC Bag 50kg/pipe) | NOS | 6 | 2400 | 14400 | 0 | 0 | 0 | 0 | 2400 | 0 | 6 | 2832 | 16992 | 6 | 2832 | 16992 | 6 | 0 | 14400 | -2592
2968 | STP & TRANSFORMER ROOM EARTHING WORK (M+L) | 0 | Started | Labour | (L)COPPER EARTHING ROD-17MM X 1MTR | NOS | 11 | 885 | 9735 | 0 | 0 | 0 | 0 | 885 | 0 | 11 | 885 | 9735 | 11 | 885 | 9735 | 11 | 0 | 9735 | 0
2969 | STP & TRANSFORMER ROOM EARTHING WORK (M+L) | 0 | Started | Labour | (L)Earthing Borehole & Installation 10ft Depth | NOS | 21 | 1888 | 39648 | 0 | 0 | 0 | 0 | 1888 | 0 | 21 | 1888 | 39648 | 19 | 1888 | 35872 | 21 | 2 | 39648 | 3776
2970 | STP & TRANSFORMER ROOM EARTHING WORK (M+L) | 0 | Started | Labour | (L)GI Earthing 80mm dia, 3mtr long (BFC Bag 50kg/pipe) | NOS | 15 | 1500 | 22500 | 0 | 0 | 0 | 0 | 1500 | 0 | 15 | 1770 | 26550 | 13.6667 | 1770 | 24190.05 | 15 | 1.3333 | 22500 | -1690.05
2971 | MATERIAL TRANPORTATION CHARGE- EXTRA | 0 | Tentative | Labour | (L)MATERIAL TRANSPORT EXTRA | NOS | 1 | 1000 | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1000 | 1000
2972 | DEVELOPEMENT-24 AVENUE LT ROOM HT CABLES | 0 | Tentative | Material | (M)120 sq.mm x 3.5 core Aluminium Armoured XLPE Cable | RMT | 277 | 708 | 196116 | 277 | 708 | 196116 | 0 | 708 | 0 | 277 | 625.4 | 173235.8 | 0 | 0 | 0 | 277 | 277 | 196116 | 196116
2973 | DEVELOPEMENT-24 AVENUE LT ROOM HT CABLES | 0 | Tentative | Material | (M)150 sq.mm x 3.5 core Aluminium Armoured XLPE Cable | RMT | 399 | 708 | 282492 | 399 | 708 | 282492 | 0 | 708 | 0 | 399 | 719.8 | 287200.2 | 0 | 0 | 0 | 399 | 399 | 282492 | 282492
2974 | DEVELOPEMENT-24 AVENUE LT ROOM HT CABLES | 0 | Tentative | Material | (M)240 sq.mm x 3.5 core Aluminium Armoured XLPE Cable | RMT | 95 | 826 | 78470 | 95 | 826 | 78470 | 0 | 826 | 0 | 95 | 1156.4 | 109858 | 0 | 0 | 0 | 95 | 95 | 78470 | 78470
2975 | DEVELOPEMENT-24 AVENUE LT ROOM HT CABLES | 0 | Tentative | Material | (M)25 sq.mm x 3.5 core Aluminium Armoured XLPE Cable | RMT | 35 | 177 | 6195 | 35 | 177 | 6195 | 0 | 177 | 0 | 35 | 179.36 | 6277.6 | 0 | 0 | 0 | 35 | 35 | 6195 | 6195
2976 | DEVELOPEMENT-24 AVENUE LT ROOM HT CABLES | 0 | Tentative | Material | (M)300 sq.mm x 3.5 core 3R Aluminium Armoured XLPE Cable | RMT | 86 | 1368.8 | 117716.8 | 86 | 1368.8 | 117716.8 | 0 | 1368.8 | 0 | 86 | 1404.2 | 120761.2 | 0 | 0 | 0 | 86 | 86 | 117716.8 | 117716.8
2977 | DEVELOPEMENT-24 AVENUE LT ROOM HT CABLES | 0 | Tentative | Material | (M)35 sq.mm x 3.5 core Aluminium Armoured XLPE Cable | RMT | 287 | 112.1 | 32172.7 | 232 | 112.1 | 26007.2 | 0 | 112.1 | 0 | 232 | 218.3 | 50645.6 | 0 | 0 | 0 | 287 | 287 | 32172.7 | 32172.7
2978 | DEVELOPEMENT-24 AVENUE LT ROOM HT CABLES | 0 | Tentative | Material | (M)50 sq.mm x 3.5 core Aluminium Armoured XLPE Cable | RMT | 28 | 165.2 | 4625.6 | 28 | 165.2 | 4625.6 | 0 | 165.2 | 0 | 28 | 295 | 8260 | 0 | 0 | 0 | 28 | 28 | 4625.6 | 4625.6
2979 | DEVELOPEMENT-24 AVENUE LT ROOM HT CABLES | 0 | Tentative | Material | (M)6 sq.mm x 4 core Copper Armoured Cable | RMT | 12 | 59 | 708 | 12 | 59 | 708 | 0 | 59 | 0 | 12 | 413 | 4956 | 0 | 0 | 0 | 12 | 12 | 708 | 708
2980 | DEVELOPEMENT-24 AVENUE LT ROOM HT CABLES | 0 | Tentative | Material | (M)70 sq.mm x 3.5 core Aluminium Armoured XLPE Cable | RMT | 56 | 354 | 19824 | 56 | 354 | 19824 | 0 | 354 | 0 | 56 | 389.4 | 21806.4 | 0 | 0 | 0 | 56 | 56 | 19824 | 19824
2981 | DEVELOPEMENT-24 AVENUE LT ROOM HT CABLES | 0 | Tentative | Material | (M)95 sq.mm x 3 core HT 22KV Aluminium Armoured XLPE Cable | RMT | 175 | 472 | 82600 | 175 | 472 | 82600 | 0 | 472 | 0 | 175 | 1303.9 | 228182.5 | 0 | 0 | 0 | 175 | 175 | 82600 | 82600
2982 | DG SET 160KVA BACK UP & SENSE CABLE | 0 | Tentative | Material | (M)120 sq.mm x 3.5 core Aluminium Armoured XLPE Cable | RMT | 12 | 708 | 8496 | 12 | 708 | 8496 | 0 | 708 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 8496 | 8496
2983 | DG SET 160KVA BACK UP & SENSE CABLE | 0 | Tentative | Material | (M)16 sq.mm x 4 core Aluminium Armoured XLPE Cable | RMT | 197 | 129.8 | 25570.6 | 197 | 129.8 | 25570.6 | 0 | 129.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 197 | 197 | 25570.6 | 25570.6
2984 | DG SET 160KVA BACK UP & SENSE CABLE | 0 | Tentative | Material | (M)185 sq.mm x 3.5 core Aluminium Armoured XLPE Cable | RMT | 62 | 590 | 36580 | 62 | 590 | 36580 | 0 | 590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62 | 62 | 36580 | 36580
2985 | DG SET 160KVA BACK UP & SENSE CABLE | 0 | Tentative | Material | (M)2.5 sq.mm x 4 core Copper Armoured Cable | RMT | 77 | 185.26 | 14265.02 | 77 | 185.26 | 14265.02 | 0 | 185.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77 | 77 | 14265.02 | 14265.02
2986 | DG SET 160KVA BACK UP & SENSE CABLE | 0 | Tentative | Material | (M)25 sq.mm x 3.5 core Aluminium Armoured XLPE Cable | RMT | 109 | 177 | 19293 | 45 | 177 | 7965 | 0 | 177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 109 | 19293 | 19293
2987 | DEVELOPEMENT - LT ROOM TRANSFORMER CABLE JOINTING MATERIAL | 0 | Tentative | Material | (M)0033 Flange Type Gland | NOS | 8 | 550 | 4400 | 8 | 550 | 4400 | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 4400 | 4400
2988 | DEVELOPEMENT - LT ROOM TRANSFORMER CABLE JOINTING MATERIAL | 0 | Tentative | Material | (M)150 Sqmm Alluminium Lugs | NOS | 14 | 32 | 448 | 14 | 32 | 448 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 14 | 448 | 448
2989 | DEVELOPEMENT - LT ROOM TRANSFORMER CABLE JOINTING MATERIAL | 0 | Tentative | Material | (M)300 sq.mm x 3.5 core 22kv Aluminium Arm. XLPE Round Cable | RMT | 30 | 1357 | 40710 | 30 | 1357 | 40710 | 0 | 1357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 40710 | 40710
2990 | DEVELOPEMENT - LT ROOM TRANSFORMER CABLE JOINTING MATERIAL | 0 | Tentative | Material | (M)300 sq.mm x 3.5 core 3R Aluminium Armoured XLPE Cable | RMT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2991 | DEVELOPEMENT - LT ROOM TRANSFORMER CABLE JOINTING MATERIAL | 0 | Tentative | Material | (M)300 Sqmm Alluminium Lugs | NOS | 42 | 55 | 2310 | 42 | 55 | 2310 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 42 | 2310 | 2310
2992 | DEVELOPEMENT - LT ROOM TRANSFORMER CABLE JOINTING MATERIAL | 0 | Tentative | Material | (M)63mm Double Compressor Gland | NOS | 6 | 1770 | 10620 | 6 | 1770 | 10620 | 0 | 1770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 10620 | 10620
2993 | DEVELOPEMENT - LT ROOM TRANSFORMER CABLE JOINTING MATERIAL | 0 | Tentative | Material | (M)COPPER PATTI 50MM x 5MM | RMT | 35 | 177 | 6195 | 35 | 177 | 6195 | 0 | 177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 35 | 6195 | 6195
2994 | DEVELOPEMENT - LT ROOM TRANSFORMER CABLE JOINTING MATERIAL | 0 | Tentative | Material | (M)ELE. SLEEVES 50MM X 5MM (50M/BUNDLE) | BUNDLE | 4 | 59 | 236 | 4 | 59 | 236 | 0 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 236 | 236
2995 | DEVELOPEMENT - LT ROOM TRANSFORMER CABLE JOINTING MATERIAL | 0 | Tentative | Material | (M)GI PATTI 50MM x 5MM | RMT | 120 | 88.5 | 10620 | 120 | 88.5 | 10620 | 0 | 88.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 120 | 10620 | 10620
2996 | DEVELOPEMENT - LT ROOM TRANSFORMER CABLE JOINTING MATERIAL | 0 | Tentative | Material | (M)INDOOR HT JOINT KIT-95 SQ.MM 3 CORE | NOS | 2 | 2.36 | 4.72 | 2 | 2.36 | 4.72 | 0 | 2.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 4.72 | 4.72
2997 | DEVELOPEMENT - LT ROOM TRANSFORMER CABLE JOINTING MATERIAL | 0 | Tentative | Material | (M)Insulation Tape | NOS | 20 | 11.8 | 236 | 20 | 11.8 | 236 | 0 | 11.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 236 | 236
2998 | DEVELOPEMENT - LT ROOM TRANSFORMER CABLE JOINTING MATERIAL | 0 | Tentative | Material | (M)NUT-BOLT 30 X 8 | NOS | 400 | 1.18 | 472 | 400 | 1.18 | 472 | 0 | 1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 400 | 472 | 472
2999 | DEVELOPEMENT - LT ROOM TRANSFORMER CABLE JOINTING MATERIAL | 0 | Tentative | Material | (M)TOUCHPROOF JOINT KIT | NOS | 2 | 2360 | 4720 | 2 | 2360 | 4720 | 0 | 2360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 4720 | 4720
3000 | CCTV SITE INDENT-832/24 AVENUE SITE/CCTV | 0 | Started | Material | (M)CCTV Cat-6 Cable | RMT | 380 | 53.1 | 20178 | 380 | 53.1 | 20178 | 0 | 53.1 | 0 | 380 | 69.1 | 26258 | 0 | 0 | 0 | 380 | 380 | 20178 | 20178
3001 | CCTV SITE INDENT-832/24 AVENUE SITE/CCTV | 0 | Started | Material | (M)Connector CCTV | NOS | 20 | 53.1 | 1062 | 20 | 53.1 | 1062 | 0 | 53.1 | 0 | 20 | 60.7 | 1214 | 0 | 0 | 0 | 20 | 20 | 1062 | 1062
3002 | CCTV SITE INDENT-832/24 AVENUE SITE/CCTV | 0 | Started | Material | (M)HDD Recording Storage-1TB CCTV | NOS | 1 | 3776 | 3776 | 1 | 3776 | 3776 | 0 | 3776 | 0 | 1 | 4316.56 | 4316.56 | 0 | 0 | 0 | 1 | 1 | 3776 | 3776
3003 | CCTV SITE INDENT-832/24 AVENUE SITE/CCTV | 0 | Started | Material | (M)Hikvision 08 Channel Network Video Recorder | NOS | 1 | 10030 | 10030 | 1 | 10030 | 10030 | 0 | 10030 | 0 | 1 | 11465.87 | 11465.87 | 0 | 0 | 0 | 1 | 1 | 10030 | 10030
3004 | CCTV SITE INDENT-832/24 AVENUE SITE/CCTV | 0 | Started | Material | (M)Hikvision IP Camera 2MP Bullet | NOS | 8 | 3717 | 29736 | 8 | 3717 | 29736 | 0 | 3717 | 0 | 8 | 4097.89 | 32783.1 | 0 | 0 | 0 | 8 | 8 | 29736 | 29736
3005 | CCTV SITE INDENT-832/24 AVENUE SITE/CCTV | 0 | Started | Material | (M)Monitor for CCTV Camera | NOS | 1 | 4130 | 4130 | 1 | 4130 | 4130 | 0 | 4130 | 0 | 1 | 4721.24 | 4721.24 | 0 | 0 | 0 | 1 | 1 | 4130 | 4130
3006 | CCTV SITE INDENT-832/24 AVENUE SITE/CCTV | 0 | Started | Material | (M)POE LAN SWITCH 4 PORT | NOS | 2 | 4956 | 9912 | 2 | 4956 | 9912 | 0 | 4956 | 0 | 2 | 4784.12 | 9568.24 | 0 | 0 | 0 | 2 | 2 | 9912 | 9912
3007 | CCTV SITE INDENT-832/24 AVENUE SITE/CCTV | 0 | Started | Material | (M)PVC BOX 5x5 | NOS | 3 | 59 | 177 | 3 | 59 | 177 | 0 | 59 | 0 | 3 | 67.44 | 202.32 | 0 | 0 | 0 | 3 | 3 | 177 | 177
3008 | CCTV SITE INDENT-832/24 AVENUE SITE/CCTV | 0 | Started | Material | (M)Wall Mount for Monitor | NOS | 1 | 1121 | 1121 | 1 | 1121 | 1121 | 0 | 1121 | 0 | 1 | 1281.48 | 1281.48 | 0 | 0 | 0 | 1 | 1 | 1121 | 1121
3009 | CLUB HOUSE CCTV CAMERA-MATERIAL & INSTALLATION WORK | 0 | Tentative | Material | (M)CCTV Cat-6 Cable | RMT | 180 | 53.1 | 9558 | 180 | 53.1 | 9558 | 0 | 53.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 180 | 9558 | 9558
3010 | CLUB HOUSE CCTV CAMERA-MATERIAL & INSTALLATION WORK | 0 | Tentative | Material | (M)CCTV DVR Rack/NVR/Server/Network Rack | NOS | 1 | 3540 | 3540 | 1 | 3540 | 3540 | 0 | 3540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3540 | 3540
3011 | CLUB HOUSE CCTV CAMERA-MATERIAL & INSTALLATION WORK | 0 | Tentative | Material | (M)HDD Recording Storage-2TB CCTV | NOS | 1 | 7198 | 7198 | 1 | 7198 | 7198 | 0 | 7198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 7198 | 7198
3012 | CLUB HOUSE CCTV CAMERA-MATERIAL & INSTALLATION WORK | 0 | Tentative | Material | (M)Hikvision 16 Channel Network Video Recorder | NOS | 1 | 13570 | 13570 | 1 | 13570 | 13570 | 0 | 13570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 13570 | 13570
3013 | CLUB HOUSE CCTV CAMERA-MATERIAL & INSTALLATION WORK | 0 | Tentative | Material | (M)Hikvision IP Camera 2MP Bullet | NOS | 4 | 3717 | 14868 | 4 | 3717 | 14868 | 0 | 3717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 14868 | 14868
3014 | CLUB HOUSE CCTV CAMERA-MATERIAL & INSTALLATION WORK | 0 | Tentative | Material | (M)Hikvision IP Camera 2MP Dome | NOS | 4 | 3599 | 14396 | 4 | 3599 | 14396 | 0 | 3599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 14396 | 14396
3015 | CLUB HOUSE CCTV CAMERA-MATERIAL & INSTALLATION WORK | 0 | Tentative | Material | (M)Monitor for CCTV Camera | NOS | 1 | 4130 | 4130 | 1 | 4130 | 4130 | 0 | 4130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 4130 | 4130
3016 | CLUB HOUSE CCTV CAMERA-MATERIAL & INSTALLATION WORK | 0 | Tentative | Material | (M)POE LAN SWITCH 8 PORT | NOS | 1 | 4602 | 4602 | 1 | 4602 | 4602 | 0 | 4602 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 4602 | 4602
3017 | DEVELOPEMENT-LANDSCAPING AREA TRIMIX | 0 | Started | Material | (M)Black Plastic for Trimix | KG | 134 | 106.2 | 14230.8 | 134 | 106.2 | 14230.8 | 0 | 106.2 | 0 | 134 | 86.14 | 11542.76 | 0 | 0 | 0 | 134 | 134 | 14230.8 | 14230.8
3018 | DEVELOPEMENT-LANDSCAPING AREA TRIMIX | 0 | Started | Material | (M)MS Binding Wire 18G | KG | 30 | 50 | 1500 | 30 | 50 | 1500 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 1500 | 1500
3019 | DEVELOPEMENT-LANDSCAPING AREA TRIMIX | 0 | Started | Material | (M)RCC Chamber Cover with Frame 600mm X 600mm MD (Drain Hole) | SET | 2 | 1416 | 2832 | 2 | 1416 | 2832 | 0 | 1416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2832 | 2832
3020 | DEVELOPEMENT-LANDSCAPING AREA TRIMIX | 0 | Started | Material | (M)RMC M-20 | CUM | 80 | 3800 | 304000 | 80 | 3800 | 304000 | 0 | 3800 | 0 | 80 | 4900 | 392000.016 | 0 | 0 | 0 | 80 | 80 | 304000 | 304000
3021 | DEVELOPEMENT-LANDSCAPING AREA TRIMIX | 0 | Started | Material | (M)RMC M-25 | CUM | 80 | 4600 | 368000 | 0 | 0 | 0 | 0 | 4600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 80 | 368000 | 368000
3022 | DEVELOPEMENT-LANDSCAPING AREA TRIMIX | 0 | Started | Material | (M)T.M.T.Bar 8mm (Fe 500, 0.395 KGS/Rm) | KG | 2000 | 59 | 118000 | 2000 | 59 | 118000 | 0 | 59 | 0 | 0 | 0 | 0 | 1208.7 | 61.77 | 74665.63 | 2000 | 791.3 | 118000 | 43334.37
3023 | DEVELOPEMENT-LANDSCAPING AREA TRIMIX | 0 | Started | Labour | (L)DIFFERENCE AMOUNT (RAWADI) | BRASS | 15 | 525 | 7875 | 0 | 0 | 0 | 0 | 525 | 0 | 15 | 525 | 7875 | 15 | 525 | 7875 | 15 | 0 | 7875 | 0
3024 | DEVELOPEMENT-LANDSCAPING AREA TRIMIX | 0 | Started | Labour | (L)Trimix Concrete (Lab) | SQFT | 5400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4641 | 7 | 32487 | 4401.71 | 7 | 30811.97 | 5400 | 998.29 | 0 | -30811.97
3025 | DEVELOPEMENT-LANDSCAPING AREA TRIMIX | 0 | Started | Labour | (L)Trimix Steel Binding (Lab) | SQFT | 5400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4641 | 2 | 9282 | 4641 | 2 | 9282 | 5400 | 759 | 0 | -9282
3026 | DEVELOPEMENT-LANDSCAPING AREA TRIMIX | 0 | Started | Labour | (L)WBM 2-LAYER (M+L) | SQFT | 5400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4641 | 43 | 199563 | 4640.59 | 43 | 199545.37 | 5400 | 759.41 | 0 | -199545.37
3027 | TRANS.ROOM, STP SIDE & CLUB HOUSE PATHWAY MURUM FILLING | 0 | Started | Material | (M)Murum | BRASS | 82.5 | 1050 | 86625 | 82.5 | 1050 | 86625 | 0 | 1050 | 0 | 82.5 | 840 | 69300 | 0 | 0 | 0 | 82.5 | 82.5 | 86625 | 86625
3028 | LANSCAPING AREA PATHWAY PAVER BLOCK & KERB STONE | 0 | Started | Material | (M)CEMENT PPC 50KG | BAG | 20 | 320 | 6400 | 20 | 320 | 6400 | 0 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 6400 | 6400
3029 | LANSCAPING AREA PATHWAY PAVER BLOCK & KERB STONE | 0 | Started | Material | (M)KERB STONE (350 X 200 X125) 1MTR | NOS | 58 | 501.5 | 29087 | 58 | 501.5 | 29087 | 0 | 501.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 58 | 29087 | 29087
3030 | LANSCAPING AREA PATHWAY PAVER BLOCK & KERB STONE | 0 | Started | Material | (M)Metal No.I 6mm (Grit) | BRASS | 13 | 3000 | 39000 | 13 | 3000 | 39000 | 0 | 3000 | 0 | 13 | 3675 | 47775 | 0 | 0 | 0 | 13 | 13 | 39000 | 39000
3031 | LANSCAPING AREA PATHWAY PAVER BLOCK & KERB STONE | 0 | Started | Material | (M)Paver Blocks 60 mm 12" x 18" White | SQFT | 1336 | 59 | 78824 | 1336 | 59 | 78824 | 0 | 59 | 0 | 1336 | 64.76 | 86519.36 | 0 | 0 | 0 | 1336 | 1336 | 78824 | 78824
3032 | LANSCAPING AREA PATHWAY PAVER BLOCK & KERB STONE | 0 | Started | Material | (M)Paver Blocks 60 mm 6" x 6" Black | SQFT | 82 | 59 | 4838 | 82 | 59 | 4838 | 0 | 59 | 0 | 82 | 53.65 | 4399.3 | 0 | 0 | 0 | 82 | 82 | 4838 | 4838
3033 | LANSCAPING AREA PATHWAY PAVER BLOCK & KERB STONE | 0 | Started | Material | (M)Paver Blocks 60 mm 6" x 6" Gray | SQFT | 82 | 177 | 14514 | 82 | 177 | 14514 | 0 | 177 | 0 | 82 | 53.65 | 4399.3 | 0 | 0 | 0 | 82 | 82 | 14514 | 14514
3034 | LANSCAPING AREA PATHWAY PAVER BLOCK & KERB STONE | 0 | Started | Labour | (L)Paver Flooring at Ground | SQFT | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400 | 11 | 26400 | 2356.95 | 11 | 25926.45 | 2400 | 43.05 | 0 | -25926.45
3035 | LANSCAPING AREA-ENTRY PLAZA BASE PCC & TILING WORK | 0 | Started | Material | (M)CEMENT PPC 50KG | BAG | 40 | 320 | 12800 | 40 | 320 | 12800 | 0 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 12800 | 12800
3036 | LANSCAPING AREA-ENTRY PLAZA BASE PCC & TILING WORK | 0 | Started | Material | (M)Crush Sand | BRASS | 1 | 3675 | 3675 | 1 | 3675 | 3675 | 0 | 3675 | 0 | 1 | 3675 | 3675 | 0 | 0 | 0 | 1 | 1 | 3675 | 3675
3037 | LANSCAPING AREA-ENTRY PLAZA BASE PCC & TILING WORK | 0 | Started | Material | (M)MAPLEWOOD MARONE TILE-200 X 1200,Thk-9mm | BOX | 58 | 708 | 41064 | 58 | 708 | 41064 | 0 | 708 | 0 | 58 | 640.46 | 37146.6742 | 0 | 0 | 0 | 58 | 58 | 41064 | 41064
3038 | LANSCAPING AREA-ENTRY PLAZA BASE PCC & TILING WORK | 0 | Started | Material | (M)Metal No.I 6mm (Grit) | BRASS | 3 | 3000 | 9000 | 3 | 3000 | 9000 | 0 | 3000 | 0 | 3 | 3675 | 11025 | 0 | 0 | 0 | 3 | 3 | 9000 | 9000
3039 | LANSCAPING AREA-ENTRY PLAZA BASE PCC & TILING WORK | 0 | Started | Material | (M)Metal No.III 20MM | BRASS | 1 | 3045 | 3045 | 1 | 3045 | 3045 | 0 | 3045 | 0 | 1 | 3360 | 3360 | 0 | 0 | 0 | 1 | 1 | 3045 | 3045
3040 | LANDSCAPING AREA-EPDM RUBBER FLOORING | 0 | Tentative | Material | (M)EPDM FLOORING-25MM THK | SQFT | 2314 | 265.5 | 614367 | 2314 | 265.5 | 614367 | 0 | 265.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2314 | 2314 | 614367 | 614367
3041 | LANDSCAPING AREA-EPDM RUBBER FLOORING | 0 | Tentative | Material | (M)Multisports Turf-15mm | SQFT | 2476 | 121.54 | 300933.04 | 2476 | 121.54 | 300933.04 | 0 | 121.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2476 | 2476 | 300933.04 | 300933.04
3042 | LANDSCAPING AREA KERB STONE,PCC,BBM & PLASTER WORK | 0 | Started | Labour | (L)6" Brickwork Labour | SQFT | 465 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 465 | 17 | 7905 | 465 | 17 | 7905 | 465 | 0 | 0 | -7905
3043 | LANDSCAPING AREA KERB STONE,PCC,BBM & PLASTER WORK | 0 | Started | Labour | (L)9" Brickwork Labour | SQFT | 468 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 468 | 21 | 9828 | 467.53 | 21 | 9818.13 | 468 | 0.47 | 0 | -9818.13
3044 | LANDSCAPING AREA KERB STONE,PCC,BBM & PLASTER WORK | 0 | Started | Labour | (L)CHHAT PLASTER | SQFT | 302 | 5 | 1510 | 0 | 0 | 0 | 0 | 5 | 0 | 302 | 5 | 1510 | 300.524 | 5 | 1502.62 | 302 | 1.476 | 1510 | 7.38
3045 | LANDSCAPING AREA KERB STONE,PCC,BBM & PLASTER WORK | 0 | Started | Labour | (L)Curb stone fixing | RFT | 235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 235 | 42 | 9870 | 234.19 | 42 | 9835.98 | 235 | 0.81 | 0 | -9835.98
3046 | LANDSCAPING AREA KERB STONE,PCC,BBM & PLASTER WORK | 0 | Started | Labour | (L)DPC-15OMM (Depth) | RFT | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368 | 12 | 4416 | 368 | 12 | 4416 | 368 | 0 | 0 | -4416
3047 | LANDSCAPING AREA KERB STONE,PCC,BBM & PLASTER WORK | 0 | Started | Labour | (L)PCC Work (labour) | SQFT | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 10 | 6000 | 589.18 | 10 | 5891.8 | 600 | 10.82 | 0 | -5891.8
3048 | LANDSCAPING AREA KERB STONE,PCC,BBM & PLASTER WORK | 0 | Started | Labour | (L)single coat plaster | SQFT | 1490 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1490 | 18 | 26820 | 1489 | 18 | 26802 | 1490 | 1 | 0 | -26802
3049 | CLUB HOUSE COURTYARD FLOWER BED PLANTATION | 0 | Tentative | Material | (M)AGLAONEMA PLANT | NOS | 8 | 236 | 1888 | 8 | 236 | 1888 | 0 | 236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 1888 | 1888
3050 | CLUB HOUSE COURTYARD FLOWER BED PLANTATION | 0 | Tentative | Material | (M)ARTIFICIAL LAWN | SQFT | 176 | 88.5 | 15576 | 176 | 88.5 | 15576 | 0 | 88.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176 | 176 | 15576 | 15576
3051 | CLUB HOUSE COURTYARD FLOWER BED PLANTATION | 0 | Tentative | Material | (M)SONCHAFA PLANT | NOS | 1 | 251.34 | 251.34 | 1 | 251.34 | 251.34 | 0 | 251.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 251.34 | 251.34
3052 | INDOOR GAMES CORNER SIDE FLOWER BED PLANTATION | 0 | Tentative | Material | (M)PANDANUS PLANT | NOS | 80 | 23.6 | 1888 | 80 | 23.6 | 1888 | 0 | 23.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 80 | 1888 | 1888
3053 | SEATING AREA (CHILDREN PLAY AREA SIDE) PLANTATION | 0 | Tentative | Material | (M)IXORA PLANT - RED | NOS | 30 | 118 | 3540 | 30 | 118 | 3540 | 0 | 118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 3540 | 3540
3054 | SEATING AREA (CHILDREN PLAY AREA SIDE) PLANTATION | 0 | Tentative | Material | (M)IXORA PLANT - YELLOW | NOS | 30 | 118 | 3540 | 30 | 118 | 3540 | 0 | 118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 3540 | 3540
3055 | TANISH COMP. WALL & PLOTTING SIDE PLANTATION | 0 | Tentative | Material | (M)TABEBUIA ROSEA PLANT | NOS | 32 | 35.4 | 1132.8 | 32 | 35.4 | 1132.8 | 0 | 35.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 32 | 1132.8 | 1132.8
3056 | CLUB HOUSE FRONT SIDE PLANTATION | 0 | Tentative | Material | (M)TAIWAN LAWN (ON SQ.FT.) | SQFT | 950 | 15.34 | 14573 | 950 | 15.34 | 14573 | 0 | 15.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 950 | 950 | 14573 | 14573
3057 | PLOTTIND SIDE & PATHWAY NEAR LAWN PLANTATION | 0 | Tentative | Material | (M)TAIWAN LAWN (ON SQ.FT.) | SQFT | 950 | 15.34 | 14573 | 950 | 15.34 | 14573 | 0 | 15.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 950 | 950 | 14573 | 14573
3058 | ROW HOUSE-16 FRONT SIDE TAIWAN LAWN-(MAT + LAB) | 0 | Started | Labour | (L)LABOUR TRANSPORT | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 800 | 800 | 1 | 800 | 800 | 1 | 0 | 0 | -800
3059 | ROW HOUSE-16 FRONT SIDE TAIWAN LAWN-(MAT + LAB) | 0 | Started | Labour | (L)Taiwan Lawn Plantation (M+L) | SQFT | 130 | 20 | 2600 | 0 | 0 | 0 | 0 | 20 | 0 | 130 | 20 | 2600 | 130 | 20 | 2600 | 130 | 0 | 2600 | 0
3060 | DEVELOPEMENT-12M ROAD SIDE PAVER BLOCK REWORK | 0 | Started | Material | (M)CEMENT PPC 50KG | BAG | 18 | 320 | 5760 | 18 | 320 | 5760 | 0 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 5760 | 5760
3061 | DEVELOPEMENT-12M ROAD SIDE PAVER BLOCK REWORK | 0 | Started | Material | (M)Crush Sand | BRASS | 5 | 3675 | 18375 | 5 | 3675 | 18375 | 0 | 3675 | 0 | 3 | 4265 | 12795 | 0 | 0 | 0 | 5 | 5 | 18375 | 18375
3062 | DEVELOPEMENT-12M ROAD SIDE PAVER BLOCK REWORK | 0 | Started | Material | (M)Metal No.I 6mm (Grit) | BRASS | 5.5 | 3000 | 16500 | 5.5 | 3000 | 16500 | 0 | 3000 | 0 | 3 | 4265 | 12795 | 0 | 0 | 0 | 5.5 | 5.5 | 16500 | 16500
3063 | DEVELOPEMENT-12M ROAD SIDE PAVER BLOCK REWORK | 0 | Started | Material | (M)Paver Blocks 60 mm 8" x 8" Black | SQFT | 150 | 56.64 | 8496 | 150 | 56.64 | 8496 | 0 | 56.64 | 0 | 150 | 56.85 | 8527.5 | 0 | 0 | 0 | 150 | 150 | 8496 | 8496
3064 | DEVELOPEMENT-12M ROAD SIDE PAVER BLOCK REWORK | 0 | Started | Material | (M)Paver Blocks 60 mm 8" x 8" Gray | SQFT | 150 | 56.64 | 8496 | 150 | 56.64 | 8496 | 0 | 56.64 | 0 | 150 | 56.85 | 8527.5 | 0 | 0 | 0 | 150 | 150 | 8496 | 8496
3065 | DEVELOPEMENT-12M ROAD SIDE PAVER BLOCK REWORK | 0 | Started | Material | (M)Paver Blocks 60 mm 8" x 8" Orange | SQFT | 150 | 56.64 | 8496 | 150 | 56.64 | 8496 | 0 | 56.64 | 0 | 150 | 59.43 | 8914.5 | 0 | 0 | 0 | 150 | 150 | 8496 | 8496
3066 | DEVELOPEMENT-12M ROAD SIDE PAVER BLOCK REWORK | 0 | Started | Material | (M)Paver Blocks 60 mm Gray (Set of Five) | SQFT | 1945 | 59 | 114755 | 1945 | 59 | 114755 | 0 | 59 | 0 | 250 | 59.43 | 14857.5 | 0 | 0 | 0 | 1945 | 1945 | 114755 | 114755
3067 | B & C WING ELECTRICAL SERVICES LINE PIPING-DEVELOPMENT WORK | 0 | Tentative | Material | (M)RCC Chamber Cover with Frame 1200mm X 1200mm HD | SET | 4 | 5900 | 23600 | 4 | 5900 | 23600 | 0 | 5900 | 0 | 4 | 16205.15 | 64820.604 | 0 | 0 | 0 | 4 | 4 | 23600 | 23600
3068 | B & C WING ELECTRICAL SERVICES LINE PIPING-DEVELOPMENT WORK | 0 | Tentative | Material | (M)RCC Chamber Cover with Frame 900mm X 600mm HD | SET | 8 | 1829 | 14632 | 5 | 1829 | 9145 | 0 | 1829 | 0 | 5 | 3198.18 | 15990.88 | 0 | 0 | 0 | 8 | 8 | 14632 | 14632
3069 | B & C WING ELECTRICAL SERVICES LINE PIPING-DEVELOPMENT WORK | 0 | Tentative | Material | (M)RCC Chamber Cover with Frame 900mm X 600mm MD | SET | 4 | 1770 | 7080 | 4 | 1770 | 7080 | 0 | 1770 | 0 | 4 | 2339.55 | 9358.2 | 0 | 0 | 0 | 4 | 4 | 7080 | 7080
3070 | B & C WING ELECTRICAL SERVICES LINE PIPING-DEVELOPMENT WORK | 0 | Tentative | Material | (M)RCC PIPE 150mm NP-2 with pre-socketed collar | NOS | 109 | 649 | 70741 | 109 | 649 | 70741 | 0 | 649 | 0 | 109 | 519.2 | 56592.8 | 0 | 0 | 0 | 109 | 109 | 70741 | 70741
3071 | B & C WING ELECTRICAL SERVICES LINE PIPING-DEVELOPMENT WORK | 0 | Tentative | Material | (M)RCC PIPE 200mm NP-2 with pre-socketed collar | NOS | 52 | 885 | 46020 | 52 | 885 | 46020 | 0 | 885 | 0 | 52 | 637.2 | 33134.4 | 0 | 0 | 0 | 52 | 52 | 46020 | 46020
3072 | B & C WING ELECTRICAL SERVICES LINE PIPING-DEVELOPMENT WORK | 0 | Tentative | Material | (M)RCC PIPE 300mm NP-3 with pre-socketed collar | NOS | 133 | 1239 | 164787 | 133 | 1239 | 164787 | 0 | 1239 | 0 | 133 | 1392.4 | 185189.2 | 0 | 0 | 0 | 133 | 133 | 164787 | 164787
3073 | TRANSFORMER ROOM ELEC.HT LINE & SEPTIC TANK SERVICES | 0 | Tentative | Material | (M)RCC Chamber Cover with Frame 900mm X 600mm HD | SET | 3 | 1829 | 5487 | 3 | 1829 | 5487 | 0 | 1829 | 0 | 3 | 3198.18 | 9594.54 | 0 | 0 | 0 | 3 | 3 | 5487 | 5487
3074 | TRANSFORMER ROOM ELEC.HT LINE & SEPTIC TANK SERVICES | 0 | Tentative | Material | (M)RCC PIPE 200mm NP-2 with pre-socketed collar | NOS | 9 | 885 | 7965 | 9 | 885 | 7965 | 0 | 885 | 0 | 9 | 637.2 | 5734.8 | 0 | 0 | 0 | 9 | 9 | 7965 | 7965
3075 | TRANSFORMER ROOM ELEC.HT LINE & SEPTIC TANK SERVICES | 0 | Tentative | Material | (M)RCC PIPE 300mm NP-3 with pre-socketed collar | NOS | 26 | 1239 | 32214 | 26 | 1239 | 32214 | 0 | 1239 | 0 | 26 | 1392.4 | 36202.4 | 0 | 0 | 0 | 26 | 26 | 32214 | 32214
3076 | TRANSFORMER ROOM ELEC.HT LINE & SEPTIC TANK SERVICES | 0 | Tentative | Material | (M)RCC Round Cover with Frame 24" HD | SET | 1 | 1416 | 1416 | 1 | 1416 | 1416 | 0 | 1416 | 0 | 1 | 2143.29 | 2143.29 | 0 | 0 | 0 | 1 | 1 | 1416 | 1416
3077 | ELECTRICAL SERVICES LINE A & CWING TEMPORARY ELE.SUPPLY LINE | 0 | Tentative | Material | (M)1.5 Sqmm 3 Core Polycab Copper Flexible Cable | RMT | 100 | 41.3 | 4130 | 100 | 41.3 | 4130 | 0 | 41.3 | 0 | 100 | 64.65 | 6465.48 | 0 | 0 | 0 | 100 | 100 | 4130 | 4130
3078 | ELECTRICAL SERVICES LINE A & CWING TEMPORARY ELE.SUPPLY LINE | 0 | Tentative | Material | (M)16 sq.mm x 3.5 core Aluminium Armoured Cable | RMT | 60 | 118 | 7080 | 60 | 118 | 7080 | 0 | 118 | 0 | 60 | 179.61 | 10776.6 | 0 | 0 | 0 | 60 | 60 | 7080 | 7080
3079 | ELECTRICAL SERVICES LINE A & CWING TEMPORARY ELE.SUPPLY LINE | 0 | Tentative | Material | (M)25 sq.mm x 3.5 core Aluminium Armoured XLPE Cable | RMT | 60 | 177 | 10620 | 60 | 177 | 10620 | 0 | 177 | 0 | 60 | 210.54 | 12632.4 | 0 | 0 | 0 | 60 | 60 | 10620 | 10620
3080 | ELECTRICAL SERVICES LINE A & CWING TEMPORARY ELE.SUPPLY LINE | 0 | Tentative | Material | (M)35 sq.mm x 4 core Aluminium Armoured Cable | RMT | 120 | 240.72 | 28886.4 | 120 | 240.72 | 28886.4 | 0 | 240.72 | 0 | 120 | 303.32 | 36398.4 | 0 | 0 | 0 | 120 | 120 | 28886.4 | 28886.4
3081 | ELECTRICAL SERVICES LINE A & CWING TEMPORARY ELE.SUPPLY LINE | 0 | Tentative | Material | (M)63 Amp 4 Pole MCB Schneider with Box | NOS | 2 | 1866.76 | 3733.52 | 2 | 1866.76 | 3733.52 | 0 | 1866.76 | 0 | 2 | 2091.09 | 4182.18 | 0 | 0 | 0 | 2 | 2 | 3733.52 | 3733.52
3082 | ELECTRICAL SERVICES LINE A & CWING TEMPORARY ELE.SUPPLY LINE | 0 | Tentative | Material | (M)Aluminium Cable Lugs 25 sq mm | NOS | 60 | 14.16 | 849.6 | 60 | 14.16 | 849.6 | 0 | 14.16 | 0 | 60 | 8.33 | 499.8 | 0 | 0 | 0 | 60 | 60 | 849.6 | 849.6
3083 | ELECTRICAL SERVICES LINE A & CWING TEMPORARY ELE.SUPPLY LINE | 0 | Tentative | Material | (M)Aluminium Cable Lugs 35 sq mm | NOS | 12 | 17.7 | 212.4 | 12 | 17.7 | 212.4 | 0 | 17.7 | 0 | 12 | 9.52 | 114.24 | 0 | 0 | 0 | 12 | 12 | 212.4 | 212.4
3084 | ELECTRICAL SERVICES LINE A & CWING TEMPORARY ELE.SUPPLY LINE | 0 | Tentative | Material | (M)BusBar Alluminium Enclosure 100 Amp | NOS | 1 | 59 | 59 | 1 | 59 | 59 | 0 | 59 | 0 | 1 | 2747.68 | 2747.68 | 0 | 0 | 0 | 1 | 1 | 59 | 59
3085 | ELECTRICAL SERVICES LINE A & CWING TEMPORARY ELE.SUPPLY LINE | 0 | Tentative | Material | (M)Cable GLands 35 sq mm | NOS | 2 | 35.4 | 70.8 | 2 | 35.4 | 70.8 | 0 | 35.4 | 0 | 2 | 130.84 | 261.68 | 0 | 0 | 0 | 2 | 2 | 70.8 | 70.8
3086 | B BLDG DEVELOPMENT DRAINAGE LINE & CHAMBER | 0 | Started | Labour | (L)RCC line 12-inch Drainage Line | RFT | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 55 | 715 | 13 | 55 | 715 | 13 | 0 | 0 | -715
3087 | B BLDG DEVELOPMENT DRAINAGE LINE & CHAMBER | 0 | Started | Labour | (L)Round Chamber Extension above 5' | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3400 | 3400 | 1 | 3400 | 3400 | 1 | 0 | 0 | -3400
3088 | B BLDG DEVELOPMENT ELECTRIC LINE & CHAMBER | 0 | Started | Labour | (L)Chamber 2 x 3 ft Electrical | NOS | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 1900 | 11400 | 6 | 1900 | 11400 | 6 | 0 | 0 | -11400
3089 | B BLDG DEVELOPMENT ELECTRIC LINE & CHAMBER | 0 | Started | Labour | (L)Chamber 4 X 4 ft Electrical | NOS | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2800 | 5600 | 2 | 2800 | 5600 | 2 | 0 | 0 | -5600
3090 | B BLDG DEVELOPMENT ELECTRIC LINE & CHAMBER | 0 | Started | Labour | (L)RCC line 12-inch Electrical Line | RFT | 623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 623 | 50 | 31150 | 623 | 50 | 31150 | 623 | 0 | 0 | -31150
3091 | B BLDG DEVELOPMENT ELECTRIC LINE & CHAMBER | 0 | Started | Labour | (L)RCC line 6-inch Electrical Line | RFT | 311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 311 | 24 | 7464 | 311 | 24 | 7464 | 311 | 0 | 0 | -7464
3092 | B BLDG DEVELOPMENT STORM WATER LINE & CHAMBER | 0 | Started | Labour | (L)Chamber 2 x 3 ft Strom | NOS | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2100 | 12600 | 6 | 2100 | 12600 | 6 | 0 | 0 | -12600
3093 | B BLDG DEVELOPMENT STORM WATER LINE & CHAMBER | 0 | Started | Labour | (L)RCC line 12-inch Strom Water Line | RFT | 296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 296 | 55 | 16280 | 296 | 55 | 16280 | 296 | 0 | 0 | -16280
3094 | B BLDG DEVELOPMENT STORM WATER LINE & CHAMBER | 0 | Started | Labour | (L)Round Chamber Extension above 5' | NOS | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3400 | 10200 | 3 | 3400 | 10200 | 3 | 0 | 0 | -10200
3095 | SITE TOILET FOUNDATION & ORRISA PAN FIXING WORK | 0 | Started | Labour | (L)ORISSA PAN FIXING | NOS | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1000 | 3000 | 3 | 1000 | 3000 | 3 | 0 | 0 | -3000
3096 | SITE TOILET FOUNDATION & ORRISA PAN FIXING WORK | 0 | Started | Labour | (L)TOILET FOUNDATION BBM WORK | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2500 | 2500 | 1 | 2500 | 2500 | 1 | 0 | 0 | -2500
3097 | STP SIDE DRAINAGE LINE DEVELOPEMENT WORK | 0 | Started | Labour | (L)Chamber 2 x 3 ft Drainage | NOS | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2100 | 4200 | 0 | 0 | 0 | 2 | 2 | 0 | 0
3098 | STP SIDE DRAINAGE LINE DEVELOPEMENT WORK | 0 | Started | Labour | (L)RCC line 6-inch Drainage Line | RFT | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 28 | 728 | 0 | 0 | 0 | 26 | 26 | 0 | 0
3099 | STP SIDE DRAINAGE LINE DEVELOPEMENT WORK | 0 | Started | Labour | (L)Round Chamber Extension above 5' | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3400 | 3400 | 0 | 0 | 0 | 1 | 1 | 0 | 0
3100 | STP SIDE ELECTRICAL LINE DEVELOPEMENT WORK | 0 | Started | Labour | (L)Chamber 2 x 3 ft Electrical | NOS | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1900 | 5700 | 0 | 0 | 0 | 3 | 3 | 0 | 0
3101 | STP SIDE ELECTRICAL LINE DEVELOPEMENT WORK | 0 | Started | Labour | (L)RCC line 12-inch Electrical Line | RFT | 149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 149 | 50 | 7450 | 0 | 0 | 0 | 149 | 149 | 0 | 0
3102 | CLUB HOUSE SIDE DRAINAGE LINE DEVELOPEMENT WORK | 0 | Started | Material | (M)FRP Round Cover with Frame 24" HD | SET | 1 | 12980 | 12980 | 1 | 12980 | 12980 | 0 | 12980 | 0 | 1 | 7068.2 | 7068.2 | 0 | 0 | 0 | 1 | 1 | 12980 | 12980
3103 | CLUB HOUSE SIDE DRAINAGE LINE DEVELOPEMENT WORK | 0 | Started | Labour | (L)Chamber 1'' x 1'' Electrical Bolard Chamber | NOS | 5 | 590 | 2950 | 0 | 0 | 0 | 0 | 590 | 0 | 5 | 500 | 2500 | 5 | 500 | 2500 | 5 | 0 | 2950 | 450
3104 | CLUB HOUSE SIDE DRAINAGE LINE DEVELOPEMENT WORK | 0 | Started | Labour | (L)Chamber 1'' x 1.5'' Electrical | NOS | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 1200 | 6000 | 5 | 1200 | 6000 | 5 | 0 | 0 | -6000
3105 | CLUB HOUSE SIDE DRAINAGE LINE DEVELOPEMENT WORK | 0 | Started | Labour | (L)Chamber 2 x 3 ft Drainage | NOS | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2100 | 6300 | 3 | 2100 | 6300 | 3 | 0 | 0 | -6300
3106 | CLUB HOUSE SIDE DRAINAGE LINE DEVELOPEMENT WORK | 0 | Started | Labour | (L)Gully Trap Chamber 1' x 1' (Lab) | NOS | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 500 | 2000 | 4 | 500 | 2000 | 4 | 0 | 0 | -2000
3107 | CLUB HOUSE SIDE DRAINAGE LINE DEVELOPEMENT WORK | 0 | Started | Labour | (L)RCC line 6-inch Drainage Line | RFT | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58 | 28 | 1624 | 58 | 28 | 1624 | 58 | 0 | 0 | -1624
3108 | C BLDG SIDE DRAINAGE LINE DEVELOPEMENT WORK | 0 | Started | Labour | (L)Round Chamber Extension above 5' | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3400 | 3400 | 0 | 0 | 0 | 1 | 1 | 0 | 0
3109 | 24 AVENUE PUMPING SYSTEM- STP, UGWT & BASEMENT | 0 | Tentative | Material | (M)Basement Sump Dewatering P/F & Its all Req.Accessories | SET | 2 | 41300 | 82600 | 2 | 41300 | 82600 | 0 | 41300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 82600 | 82600
3110 | 24 AVENUE PUMPING SYSTEM- STP, UGWT & BASEMENT | 0 | Tentative | Material | (M)Domestic Water for C-Wing P/F & Its all Req.Accessories | SET | 2 | 35400 | 70800 | 2 | 35400 | 70800 | 0 | 35400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 70800 | 70800
3111 | 24 AVENUE PUMPING SYSTEM- STP, UGWT & BASEMENT | 0 | Tentative | Material | (M)Domestic Water P/F & Its all Req.Accessories | SET | 3 | 41300 | 123900 | 3 | 41300 | 123900 | 0 | 41300 | 0 | 3 | 91683.98 | 275051.9499 | 0 | 0 | 0 | 3 | 3 | 123900 | 123900
3112 | 24 AVENUE PUMPING SYSTEM- STP, UGWT & BASEMENT | 0 | Tentative | Material | (M)Drinking Water P/F & Its all Req.Accessories | SET | 2 | 41300 | 82600 | 2 | 41300 | 82600 | 0 | 41300 | 0 | 2 | 73115.82 | 146231.64 | 0 | 0 | 0 | 2 | 2 | 82600 | 82600
3113 | 24 AVENUE PUMPING SYSTEM- STP, UGWT & BASEMENT | 0 | Tentative | Material | (M)Flushing Water P/F & Its all Req.Accessories | SET | 2 | 47200 | 94400 | 2 | 47200 | 94400 | 0 | 47200 | 0 | 2 | 77700.64 | 155401.28 | 0 | 0 | 0 | 2 | 2 | 94400 | 94400
3114 | 24 AVENUE PUMPING SYSTEM- STP, UGWT & BASEMENT | 0 | Tentative | Material | (M)Pump Room Sump Dewatering P/F & Its all Req.Accessories | SET | 2 | 23600 | 47200 | 2 | 23600 | 47200 | 0 | 23600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 47200 | 47200
3115 | MACHINERY FOR SOCITY SERVICES-24 AVENUE | 0 | Tentative | Material | (M)DIESEL GENERATOR (DG)-160kVA | SET | 1 | 1003000 | 1003000 | 1 | 1003000 | 1003000 | 0 | 1003000 | 0 | 1 | 1567040 | 1567040 | 0 | 0 | 0 | 1 | 1 | 1003000 | 1003000
3116 | MACHINERY FOR SOCITY SERVICES-24 AVENUE | 0 | Tentative | Material | (M)DIESEL GENERATOR (DG)-40kVA | SET | 1 | 413000 | 413000 | 1 | 413000 | 413000 | 0 | 413000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 413000 | 413000
3117 | MACHINERY FOR SOCITY SERVICES-24 AVENUE | 0 | Tentative | Material | (M)Organic Waste Composite Machine-608Kg/Day | NOS | 1 | 826000 | 826000 | 1 | 826000 | 826000 | 0 | 826000 | 0 | 1 | 901600 | 901600 | 0 | 0 | 0 | 1 | 1 | 826000 | 826000
3118 | PLOTTING DEVELOPEMENT WORK (ELECTRICAL WORK) | 0 | Started | Labour | (L)Dismentling of Bolard light (Removing) | NOS | 20 | 150 | 3000 | 0 | 0 | 0 | 0 | 150 | 0 | 20 | 150 | 3000 | 20 | 150 | 3000 | 20 | 0 | 3000 | 0
3119 | PLOTTING DEVELOPEMENT WORK (ELECTRICAL WORK) | 0 | Started | Labour | (L)Installation of 2200 mm stright light and pole | NOS | 19 | 750 | 14250 | 0 | 0 | 0 | 0 | 750 | 0 | 19 | 750 | 14250 | 19 | 750 | 14250 | 19 | 0 | 14250 | 0
3120 | PLOTTING DEVELOPEMENT WORK (ELECTRICAL WORK) | 0 | Started | Labour | (L)Installation of 2400 mm stright light and pole | NOS | 26 | 750 | 19500 | 0 | 0 | 0 | 0 | 750 | 0 | 26 | 750 | 19500 | 26 | 750 | 19500 | 26 | 0 | 19500 | 0
3121 | PLOTTING DEVELOPEMENT WORK (ELECTRICAL WORK) | 0 | Started | Labour | (L)Installation of Bolard light | NOS | 20 | 350 | 7000 | 0 | 0 | 0 | 0 | 350 | 0 | 20 | 350 | 7000 | 20 | 350 | 7000 | 20 | 0 | 7000 | 0
3122 | PLOTTING DEVELOPEMENT WORK (ELECTRICAL WORK) | 0 | Started | Labour | (L)Installation of Bolard light (Refixing) | NOS | 20 | 350 | 7000 | 0 | 0 | 0 | 0 | 350 | 0 | 20 | 350 | 7000 | 20 | 350 | 7000 | 20 | 0 | 7000 | 0
3123 | PLOTTING DEVELOPEMENT WORK (ELECTRICAL WORK) | 0 | Started | Labour | (L)Laying of 4 sq.mm X4 c copper armad cable | Mtr. | 383 | 25 | 9575 | 0 | 0 | 0 | 0 | 25 | 0 | 383 | 25 | 9575 | 383 | 25 | 9575 | 383 | 0 | 9575 | 0
3124 | PLOTTING DEVELOPEMENT WORK (ELECTRICAL WORK) | 0 | Started | Labour | (L)Laying of 4 sq.mmx4 C copper armad cable with 2.5" PVC pipe | Mtr. | 80 | 25 | 2000 | 0 | 0 | 0 | 0 | 25 | 0 | 80 | 25 | 2000 | 80 | 25 | 2000 | 80 | 0 | 2000 | 0
3125 | PLOTTING DEVELOPEMENT WORK (ELECTRICAL WORK) | 0 | Started | Labour | (L)Laying of 6 sq.mm X4 c copper armad cable | Mtr. | 59 | 25 | 1475 | 0 | 0 | 0 | 0 | 25 | 0 | 59 | 25 | 1475 | 59 | 25 | 1475 | 59 | 0 | 1475 | 0
3126 | PLOTTING DEVELOPEMENT WORK (ELECTRICAL WORK) | 0 | Started | Labour | (L)Termiation of 6 sq.mm X4 c copper armad cable | NOS | 10 | 70 | 700 | 0 | 0 | 0 | 0 | 70 | 0 | 10 | 70 | 700 | 10 | 70 | 700 | 10 | 0 | 700 | 0
3127 | PLOTTING DEVELOPEMENT WORK (ELECTRICAL WORK) | 0 | Started | Labour | (L)Termination of 1.0 sq.mm X 2c copper flexible | NOS | 20 | 40 | 800 | 0 | 0 | 0 | 0 | 40 | 0 | 20 | 40 | 800 | 20 | 40 | 800 | 20 | 0 | 800 | 0
3128 | PLOTTING DEVELOPEMENT WORK (ELECTRICAL WORK) | 0 | Started | Labour | (L)Termination of 4 sq.mm X 4 c copper armad cable | NOS | 87 | 40 | 3480 | 0 | 0 | 0 | 0 | 40 | 0 | 87 | 40 | 3480 | 87 | 40 | 3480 | 87 | 0 | 3480 | 0
3129 | SITE-FEEDER PILAAR SHIFTING & LAB.CAMP LT SPAN,CABLE LAYING | 0 | Started | Labour | (L)Laying of 4C x 16Sqmm LT Cable | RMT | 25 | 110 | 2750 | 0 | 0 | 0 | 0 | 110 | 0 | 25 | 110 | 2750 | 25 | 110 | 2750 | 25 | 0 | 2750 | 0
3130 | SITE-FEEDER PILAAR SHIFTING & LAB.CAMP LT SPAN,CABLE LAYING | 0 | Started | Labour | (L)Laying of 4C x 25Sqmm LT Cable | RMT | 85 | 110 | 9350 | 0 | 0 | 0 | 0 | 110 | 0 | 85 | 110 | 9350 | 85 | 110 | 9350 | 85 | 0 | 9350 | 0
3131 | SITE-FEEDER PILAAR SHIFTING & LAB.CAMP LT SPAN,CABLE LAYING | 0 | Started | Labour | (L)LT SPAN SHIFTING | NOS | 1 | 5000 | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | 1 | 5000 | 5000 | 1 | 5000 | 5000 | 1 | 0 | 5000 | 0
3132 | SITE-FEEDER PILAAR SHIFTING & LAB.CAMP LT SPAN,CABLE LAYING | 0 | Started | Labour | (L)SHIFTING OF 4 WAY FEEDER PILLAR | NOS | 1 | 10000 | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | 1 | 10000 | 10000 | 1 | 10000 | 10000 | 1 | 0 | 10000 | 0
3133 | SINGLE HYDRANT VALVE | 0 | Tentative | Labour | (L)Fire Courtyard System-Installation Charge | NOS | 13 | 1.18 | 15.34 | 0 | 0 | 0 | 0 | 1.18 | 0 | 13 | 200 | 2600 | 0 | 0 | 0 | 13 | 13 | 15.34 | 15.34
3134 | SINGLE HYDRANT VALVE | 0 | Tentative | Labour | (L)Fire Courtyard System-Supply Charge | NOS | 13 | 1.18 | 15.34 | 0 | 0 | 0 | 0 | 1.18 | 0 | 13 | 4248 | 55224 | 0 | 0 | 0 | 13 | 13 | 15.34 | 15.34
3135 | SINGLE DOOR HOSE BOX | 0 | Tentative | Labour | (L)Fire Courtyard System-Installation Charge | NOS | 13 | 1.18 | 15.34 | 0 | 0 | 0 | 0 | 1.18 | 0 | 13 | 200 | 2600 | 0 | 0 | 0 | 13 | 13 | 15.34 | 15.34
3136 | SINGLE DOOR HOSE BOX | 0 | Tentative | Labour | (L)Fire Courtyard System-Supply Charge | NOS | 13 | 1.18 | 15.34 | 0 | 0 | 0 | 0 | 1.18 | 0 | 13 | 1109.2 | 14419.6 | 0 | 0 | 0 | 13 | 13 | 15.34 | 15.34
3137 | HOSE PIPE | 0 | Tentative | Labour | (L)Fire Courtyard System-Installation Charge | NOS | 13 | 1.18 | 15.34 | 0 | 0 | 0 | 0 | 1.18 | 0 | 13 | 100 | 1300 | 0 | 0 | 0 | 13 | 13 | 15.34 | 15.34
3138 | HOSE PIPE | 0 | Tentative | Labour | (L)Fire Courtyard System-Supply Charge | NOS | 13 | 1.18 | 15.34 | 0 | 0 | 0 | 0 | 1.18 | 0 | 13 | 3584 | 46592 | 0 | 0 | 0 | 13 | 13 | 15.34 | 15.34
3139 | BRANCH PIPE | 0 | Tentative | Labour | (L)Fire Courtyard System-Installation Charge | NOS | 13 | 1.18 | 15.34 | 0 | 0 | 0 | 0 | 1.18 | 0 | 13 | 100 | 1300 | 0 | 0 | 0 | 13 | 13 | 15.34 | 15.34
3140 | BRANCH PIPE | 0 | Tentative | Labour | (L)Fire Courtyard System-Supply Charge | NOS | 13 | 1.18 | 15.34 | 0 | 0 | 0 | 0 | 1.18 | 0 | 13 | 1545.8 | 20095.4 | 0 | 0 | 0 | 13 | 13 | 15.34 | 15.34
3141 | GI PIPE FOR COURTYARD SYSTEMS-15Omm Dia (HYDRANT LINE) | 0 | Tentative | Labour | (L)Fire Courtyard System-Installation Charge (GI Pipes) | RMT | 518 | 1.18 | 611.24 | 0 | 0 | 0 | 0 | 1.18 | 0 | 518 | 660 | 341880 | 0 | 0 | 0 | 518 | 518 | 611.24 | 611.24
3142 | GI PIPE FOR COURTYARD SYSTEMS-15Omm Dia (HYDRANT LINE) | 0 | Tentative | Labour | (L)Fire Courtyard System-Supply Charge (GI Pipes) | RMT | 518 | 1.18 | 611.24 | 0 | 0 | 0 | 0 | 1.18 | 0 | 518 | 2358.82 | 1221868.76 | 0 | 0 | 0 | 518 | 518 | 611.24 | 611.24
3143 | GI PIPE FOR COURTYARD SYSTEMS-8Omm Dia (Post) | 0 | Tentative | Labour | (L)Fire Courtyard System-Installation Charge (GI Pipes) | RMT | 42 | 1.18 | 49.56 | 0 | 0 | 0 | 0 | 1.18 | 0 | 42 | 330 | 13860 | 0 | 0 | 0 | 42 | 42 | 49.56 | 49.56
3144 | GI PIPE FOR COURTYARD SYSTEMS-8Omm Dia (Post) | 0 | Tentative | Labour | (L)Fire Courtyard System-Supply Charge (GI Pipes) | RMT | 42 | 1.18 | 49.56 | 0 | 0 | 0 | 0 | 1.18 | 0 | 42 | 1131.62 | 47528.04 | 0 | 0 | 0 | 42 | 42 | 49.56 | 49.56
3145 | FOUR WAY | 0 | Tentative | Labour | (L)Fire Courtyard System-Installation Charge | NOS | 4 | 1.18 | 4.72 | 0 | 0 | 0 | 0 | 1.18 | 0 | 4 | 350 | 1400 | 0 | 0 | 0 | 4 | 4 | 4.72 | 4.72
3146 | FOUR WAY | 0 | Tentative | Labour | (L)Fire Courtyard System-Supply Charge | NOS | 4 | 1.18 | 4.72 | 0 | 0 | 0 | 0 | 1.18 | 0 | 4 | 7316 | 29264 | 0 | 0 | 0 | 4 | 4 | 4.72 | 4.72
3147 | Butterfly valves-150mm Dia | 0 | Tentative | Labour | (L)Fire Courtyard System-Installation Charge | NOS | 4 | 1.18 | 4.72 | 0 | 0 | 0 | 0 | 1.18 | 0 | 4 | 510 | 2040 | 0 | 0 | 0 | 4 | 4 | 4.72 | 4.72
3148 | Butterfly valves-150mm Dia | 0 | Tentative | Labour | (L)Fire Courtyard System-Supply Charge | NOS | 4 | 1.18 | 4.72 | 0 | 0 | 0 | 0 | 1.18 | 0 | 4 | 3826.74 | 15306.96 | 0 | 0 | 0 | 4 | 4 | 4.72 | 4.72
3149 | STRUCTURAL STEEL C-CHANNEL [100MM X 50MM] | 0 | Tentative | Labour | (L)Fire Courtyard System-Installation Charge (Str.Steel) | RMT | 114 | 1.18 | 134.52 | 0 | 0 | 0 | 0 | 1.18 | 0 | 114 | 280 | 31920 | 0 | 0 | 0 | 114 | 114 | 134.52 | 134.52
3150 | STRUCTURAL STEEL C-CHANNEL [100MM X 50MM] | 0 | Tentative | Labour | (L)Fire Courtyard System-Supply Charge (Str.Steel) | RMT | 114 | 1.18 | 134.52 | 0 | 0 | 0 | 0 | 1.18 | 0 | 114 | 1038.4 | 118377.6 | 0 | 0 | 0 | 114 | 114 | 134.52 | 134.52
3151 | Corrosion Protection Tape of 4mm thick-150mm | 0 | Tentative | Labour | (L)Fire Courtyard System-Installation Charge (4mm thk.Tape) | RMT | 518 | 1 | 518 | 0 | 0 | 0 | 0 | 1 | 0 | 40 | 150 | 6000 | 0 | 0 | 0 | 518 | 518 | 518 | 518
3152 | Corrosion Protection Tape of 4mm thick-150mm | 0 | Tentative | Labour | (L)Fire Courtyard System-Supply Charge (4mm thk.Tape) | RMT | 518 | 1.18 | 611.24 | 0 | 0 | 0 | 0 | 1.18 | 0 | 40 | 295 | 11800 | 0 | 0 | 0 | 518 | 518 | 611.24 | 611.24
3153 | Main Hydrant Pump of 2280 LPM & 90Head M | 0 | Tentative | Labour | (L)Fire Pump Room-Installation Charge | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 29500 | 29500 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
3154 | Main Hydrant Pump of 2280 LPM & 90Head M | 0 | Tentative | Labour | (L)Fire Pump Room-Supply Charge | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 211220 | 211220 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
3155 | Stand By Pump of 2280LPM & 90Head M | 0 | Tentative | Labour | (L)Fire Pump Room-Installation Charge | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 29500 | 29500 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
3156 | Stand By Pump of 2280LPM & 90Head M | 0 | Tentative | Labour | (L)Fire Pump Room-Supply Charge | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 211220 | 211220 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
3157 | Sprinkler Pump of 2280LPM & 90Head M | 0 | Tentative | Labour | (L)Fire Pump Room-Installation Charge | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 25000 | 25000 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
3158 | Sprinkler Pump of 2280LPM & 90Head M | 0 | Tentative | Labour | (L)Fire Pump Room-Supply Charge | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 229120 | 229120 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
3159 | Jockey Pump of 180 LPM & 90 Head M | 0 | Tentative | Labour | (L)Fire Pump Room-Installation Charge | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 16520 | 16520 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
3160 | Jockey Pump of 180 LPM & 90 Head M | 0 | Tentative | Labour | (L)Fire Pump Room-Supply Charge | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 92040 | 92040 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
3161 | CONTROL PANEL- FABRICATED | 0 | Tentative | Labour | (L)Fire Pump Room-Installation Charge | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 3000 | 3000 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
3162 | CONTROL PANEL- FABRICATED | 0 | Tentative | Labour | (L)Fire Pump Room-Supply Charge | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 136880 | 136880 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
3163 | 35 Sqmm X 3 core AL Armoured Cable - For Main Pump | 0 | Tentative | Labour | (L)Fire Pump Room - Installation Charge | RMT | 90 | 1.18 | 106.2 | 0 | 0 | 0 | 0 | 1.18 | 0 | 90 | 96 | 8640 | 0 | 0 | 0 | 90 | 90 | 106.2 | 106.2
3164 | 35 Sqmm X 3 core AL Armoured Cable - For Main Pump | 0 | Tentative | Labour | (L)Fire Pump Room - Supply Charge | RMT | 90 | 1.18 | 106.2 | 0 | 0 | 0 | 0 | 1.18 | 0 | 90 | 379.96 | 34196.4 | 0 | 0 | 0 | 90 | 90 | 106.2 | 106.2
3165 | 6 Sqmm X 3 core AL Armoured Cable - For JKY Pump | 0 | Tentative | Labour | (L)Fire Pump Room - Installation Charge | RMT | 15 | 1.18 | 17.7 | 0 | 0 | 0 | 0 | 1.18 | 0 | 15 | 41 | 615 | 0 | 0 | 0 | 15 | 15 | 17.7 | 17.7
3166 | 6 Sqmm X 3 core AL Armoured Cable - For JKY Pump | 0 | Tentative | Labour | (L)Fire Pump Room - Supply Charge | RMT | 15 | 1.18 | 17.7 | 0 | 0 | 0 | 0 | 1.18 | 0 | 15 | 161.66 | 2424.9 | 0 | 0 | 0 | 15 | 15 | 17.7 | 17.7
3167 | 1 Sqmm X 2 core Cu Flexible Cable - For Pressure Switch | 0 | Tentative | Labour | (L)Fire Pump Room - Installation Charge | RMT | 80 | 1.18 | 94.4 | 0 | 0 | 0 | 0 | 1.18 | 0 | 80 | 28 | 2240 | 0 | 0 | 0 | 80 | 80 | 94.4 | 94.4
3168 | 1 Sqmm X 2 core Cu Flexible Cable - For Pressure Switch | 0 | Tentative | Labour | (L)Fire Pump Room - Supply Charge | RMT | 80 | 1.18 | 94.4 | 0 | 0 | 0 | 0 | 1.18 | 0 | 80 | 107.38 | 8590.4 | 0 | 0 | 0 | 80 | 80 | 94.4 | 94.4
3169 | CABLE TRAY-100 X 50 FOR MAIN PUMP [VERTICAL SIDE] | 0 | Tentative | Labour | (L)Fire Pump Room - Installation Charge | RMT | 7.5 | 1.18 | 8.85 | 0 | 0 | 0 | 0 | 1.18 | 0 | 7.5 | 144 | 1080 | 0 | 0 | 0 | 7.5 | 7.5 | 8.85 | 8.85
3170 | CABLE TRAY-100 X 50 FOR MAIN PUMP [VERTICAL SIDE] | 0 | Tentative | Labour | (L)Fire Pump Room - Supply Charge | RMT | 7.5 | 1.18 | 8.85 | 0 | 0 | 0 | 0 | 1.18 | 0 | 7.5 | 700.92 | 5256.9 | 0 | 0 | 0 | 7.5 | 7.5 | 8.85 | 8.85
3171 | CABLE TRAY-50 X 50 FOR JKY PUMP [VERTICAL SIDE] | 0 | Tentative | Labour | (L)Fire Pump Room - Installation Charge | RMT | 2.5 | 1.18 | 2.95 | 0 | 0 | 0 | 0 | 1.18 | 0 | 2.5 | 107 | 267.5 | 0 | 0 | 0 | 2.5 | 2.5 | 2.95 | 2.95
3172 | CABLE TRAY-50 X 50 FOR JKY PUMP [VERTICAL SIDE] | 0 | Tentative | Labour | (L)Fire Pump Room - Supply Charge | RMT | 2.5 | 1.18 | 2.95 | 0 | 0 | 0 | 0 | 1.18 | 0 | 2.5 | 417.72 | 1044.3 | 0 | 0 | 0 | 2.5 | 2.5 | 2.95 | 2.95
3173 | CABLE TRAY-200 X 50 FOR ALL PUMP [HORIZONTAL SIDE] | 0 | Tentative | Labour | (L)Fire Pump Room - Installation Charge | RMT | 7.5 | 1.18 | 8.85 | 0 | 0 | 0 | 0 | 1.18 | 0 | 7.5 | 180 | 1350 | 0 | 0 | 0 | 7.5 | 7.5 | 8.85 | 8.85
3174 | CABLE TRAY-200 X 50 FOR ALL PUMP [HORIZONTAL SIDE] | 0 | Tentative | Labour | (L)Fire Pump Room - Supply Charge | RMT | 7.5 | 1.18 | 8.85 | 0 | 0 | 0 | 0 | 1.18 | 0 | 7.5 | 708 | 5310 | 0 | 0 | 0 | 7.5 | 7.5 | 8.85 | 8.85
3175 | GI Pipe for Pump Room - 200 mm Dia | 0 | Tentative | Labour | (L)Fire Pump Room - Installation Charge | RMT | 12 | 1.18 | 14.16 | 0 | 0 | 0 | 0 | 1.18 | 0 | 12 | 880 | 10560 | 0 | 0 | 0 | 12 | 12 | 14.16 | 14.16
3176 | GI Pipe for Pump Room - 200 mm Dia | 0 | Tentative | Labour | (L)Fire Pump Room - Supply Charge | RMT | 12 | 1.18 | 14.16 | 0 | 0 | 0 | 0 | 1.18 | 0 | 12 | 4021.44 | 48257.28 | 0 | 0 | 0 | 12 | 12 | 14.16 | 14.16
3177 | GI Pipe for Pump Room - 150 mm Dia | 0 | Tentative | Labour | (L)Fire Pump Room - Installation Charge | RMT | 24 | 1.18 | 28.32 | 0 | 0 | 0 | 0 | 1.18 | 0 | 24 | 660 | 15840 | 0 | 0 | 0 | 24 | 24 | 28.32 | 28.32
3178 | GI Pipe for Pump Room - 150 mm Dia | 0 | Tentative | Labour | (L)Fire Pump Room - Supply Charge | RMT | 24 | 1.18 | 28.32 | 0 | 0 | 0 | 0 | 1.18 | 0 | 24 | 2358.82 | 56611.68 | 0 | 0 | 0 | 24 | 24 | 28.32 | 28.32
3179 | GI Pipe for Pump Room - 100 mm Dia | 0 | Tentative | Labour | (L)Fire Pump Room - Installation Charge | RMT | 6 | 1.18 | 7.08 | 0 | 0 | 0 | 0 | 1.18 | 0 | 6 | 440 | 2640 | 0 | 0 | 0 | 6 | 6 | 7.08 | 7.08
3180 | GI Pipe for Pump Room - 100 mm Dia | 0 | Tentative | Labour | (L)Fire Pump Room - Supply Charge | RMT | 6 | 1.18 | 7.08 | 0 | 0 | 0 | 0 | 1.18 | 0 | 6 | 1611.88 | 9671.28 | 0 | 0 | 0 | 6 | 6 | 7.08 | 7.08
3181 | GI Pipe for Pump Room - 80 mm Dia | 0 | Tentative | Labour | (L)Fire Pump Room - Installation Charge | RMT | 6 | 1.18 | 7.08 | 0 | 0 | 0 | 0 | 1.18 | 0 | 6 | 330 | 1980 | 0 | 0 | 0 | 6 | 6 | 7.08 | 7.08
3182 | GI Pipe for Pump Room - 80 mm Dia | 0 | Tentative | Labour | (L)Fire Pump Room - Supply Charge | RMT | 6 | 1.18 | 7.08 | 0 | 0 | 0 | 0 | 1.18 | 0 | 6 | 1131.62 | 6789.72 | 0 | 0 | 0 | 6 | 6 | 7.08 | 7.08
3183 | NRV Valve-200 mm Dia Wafer Type | 0 | Tentative | Labour | (L)Fire Pump Room-Installation Charge | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 640 | 640 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
3184 | NRV Valve-200 mm Dia Wafer Type | 0 | Tentative | Labour | (L)Fire Pump Room-Supply Charge | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 5874.04 | 5874.04 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
3185 | NRV Valve-150 mm Dia Ball Type | 0 | Tentative | Labour | (L)Fire Pump Room-Installation Charge | NOS | 3 | 1.18 | 3.54 | 0 | 0 | 0 | 0 | 1.18 | 0 | 3 | 480 | 1440 | 0 | 0 | 0 | 3 | 3 | 3.54 | 3.54
3186 | NRV Valve-150 mm Dia Ball Type | 0 | Tentative | Labour | (L)Fire Pump Room-Supply Charge | NOS | 3 | 1.18 | 3.54 | 0 | 0 | 0 | 0 | 1.18 | 0 | 3 | 22119.1 | 66357.3 | 0 | 0 | 0 | 3 | 3 | 3.54 | 3.54
3187 | NRV Valve-100 mm Dia Ball Type | 0 | Tentative | Labour | (L)Fire Pump Room-Installation Charge | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 320 | 320 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
3188 | NRV Valve-100 mm Dia Ball Type | 0 | Tentative | Labour | (L)Fire Pump Room-Supply Charge | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 9296.04 | 9296.04 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
3189 | Flexible Bellows-150 mm Dia | 0 | Tentative | Labour | (L)Fire Pump Room-Installation Charge | NOS | 3 | 1.18 | 3.54 | 0 | 0 | 0 | 0 | 1.18 | 0 | 3 | 480 | 1440 | 0 | 0 | 0 | 3 | 3 | 3.54 | 3.54
3190 | Flexible Bellows-150 mm Dia | 0 | Tentative | Labour | (L)Fire Pump Room-Supply Charge | NOS | 3 | 1.18 | 3.54 | 0 | 0 | 0 | 0 | 1.18 | 0 | 3 | 10530.32 | 31590.96 | 0 | 0 | 0 | 3 | 3 | 3.54 | 3.54
3191 | Flexible Bellows-100 mm Dia | 0 | Tentative | Labour | (L)Fire Pump Room-Installation Charge | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 320 | 320 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
3192 | Flexible Bellows-100 mm Dia | 0 | Tentative | Labour | (L)Fire Pump Room-Supply Charge | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 8304.84 | 8304.84 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
3193 | SLUICE Valve (PN:16)-200mm Dia | 0 | Tentative | Labour | (L)Fire Pump Room-Installation Charge | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 640 | 640 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
3194 | SLUICE Valve (PN:16)-200mm Dia | 0 | Tentative | Labour | (L)Fire Pump Room-Supply Charge | NOS | 1 | 1.18 | 1.18 | 0 | 0 | 0 | 0 | 1.18 | 0 | 1 | 28261 | 28261 | 0 | 0 | 0 | 1 | 1 | 1.18 | 1.18
3195 | SLUICE Valve (PN:16)-150mm Dia | 0 | Tentative | Labour | (L)Fire Pump Room-Installation Charge | NOS | 10 | 1.18 | 11.8 | 0 | 0 | 0 | 0 | 1.18 | 0 | 10 | 480 | 4800 | 0 | 0 | 0 | 10 | 10 | 11.8 | 11.8
3196 | SLUICE Valve (PN:16)-150mm Dia | 0 | Tentative | Labour | (L)Fire Pump Room-Supply Charge | NOS | 10 | 1.18 | 11.8 | 0 | 0 | 0 | 0 | 1.18 | 0 | 10 | 16157.74 | 161577.4 | 0 | 0 | 0 | 10 | 10 | 11.8 | 11.8
3197 | SLUICE Valve (PN:16)-100mm Dia | 0 | Tentative | Labour | (L)Fire Pump Room-Installation Charge | NOS | 2 | 1.18 | 2.36 | 0 | 0 | 0 | 0 | 1.18 | 0 | 2 | 320 | 640 | 0 | 0 | 0 | 2 | 2 | 2.36 | 2.36
3198 | SLUICE Valve (PN:16)-100mm Dia | 0 | Tentative | Labour | (L)Fire Pump Room-Supply Charge | NOS | 2 | 1.18 | 2.36 | 0 | 0 | 0 | 0 | 1.18 | 0 | 2 | 10683.72 | 21367.44 | 0 | 0 | 0 | 2 | 2 | 2.36 | 2.36
3199 | SLUICE Valve (PN:16)-80mm Dia BF Valve | 0 | Tentative | Labour | (L)Fire Pump Room-Installation Charge | NOS | 2 | 1.18 | 2.36 | 0 | 0 | 0 | 0 | 1.18 | 0 | 2 | 240 | 480 | 0 | 0 | 0 | 2 | 2 | 2.36 | 2.36
3200 | SLUICE Valve (PN:16)-80mm Dia BF Valve | 0 | Tentative | Labour | (L)Fire Pump Room-Supply Charge | NOS | 2 | 1.18 | 2.36 | 0 | 0 | 0 | 0 | 1.18 | 0 | 2 | 2395.4 | 4790.8 | 0 | 0 | 0 | 2 | 2 | 2.36 | 2.36
3201 | Glycerin-Filled Pressure Gauges | 0 | Tentative | Labour | (L)Fire Pump Room-Installation Charge | NOS | 2 | 1.18 | 2.36 | 0 | 0 | 0 | 0 | 1.18 | 0 | 2 | 150 | 300 | 0 | 0 | 0 | 2 | 2 | 2.36 | 2.36
3202 | Glycerin-Filled Pressure Gauges | 0 | Tentative | Labour | (L)Fire Pump Room-Supply Charge | NOS | 2 | 1.18 | 2.36 | 0 | 0 | 0 | 0 | 1.18 | 0 | 2 | 1696.84 | 3393.68 | 0 | 0 | 0 | 2 | 2 | 2.36 | 2.36
3203 | Pressure Switch of capacity 14 kg./Sq.cm | 0 | Tentative | Labour | (L)Fire Pump Room-Installation Charge | NOS | 4 | 1.18 | 4.72 | 0 | 0 | 0 | 0 | 1.18 | 0 | 4 | 150 | 600 | 0 | 0 | 0 | 4 | 4 | 4.72 | 4.72
3204 | Pressure Switch of capacity 14 kg./Sq.cm | 0 | Tentative | Labour | (L)Fire Pump Room-Supply Charge | NOS | 4 | 1.18 | 4.72 | 0 | 0 | 0 | 0 | 1.18 | 0 | 4 | 1416 | 5664 | 0 | 0 | 0 | 4 | 4 | 4.72 | 4.72
3205 | Y - STAINER 150MM DIA | 0 | Tentative | Labour | (L)Fire Pump Room-Installation Charge | NOS | 2 | 1.18 | 2.36 | 0 | 0 | 0 | 0 | 1.18 | 0 | 2 | 480 | 960 | 0 | 0 | 0 | 2 | 2 | 2.36 | 2.36
3206 | Y - STAINER 150MM DIA | 0 | Tentative | Labour | (L)Fire Pump Room-Supply Charge | NOS | 2 | 1.18 | 2.36 | 0 | 0 | 0 | 0 | 1.18 | 0 | 2 | 12106.8 | 24213.6 | 0 | 0 | 0 | 2 | 2 | 2.36 | 2.36
3207 | AIR VESSEL TANK-450 X 1200MM | 0 | Tentative | Labour | (L)Fire Pump Room-Installation Charge | NOS | 2 | 1.18 | 2.36 | 0 | 0 | 0 | 0 | 1.18 | 0 | 2 | 2000 | 4000 | 0 | 0 | 0 | 2 | 2 | 2.36 | 2.36
3208 | AIR VESSEL TANK-450 X 1200MM | 0 | Tentative | Labour | (L)Fire Pump Room-Supply Charge | NOS | 2 | 1.18 | 2.36 | 0 | 0 | 0 | 0 | 1.18 | 0 | 2 | 24780 | 49560 | 0 | 0 | 0 | 2 | 2 | 2.36 | 2.36
3209 | STRUCTURAL STEEL [150MM X 75 MM] | 0 | Tentative | Labour | (L)Fire Pump Room - Installation Charge | RMT | 36 | 1.18 | 42.48 | 0 | 0 | 0 | 0 | 1.18 | 0 | 36 | 270 | 9720 | 0 | 0 | 0 | 36 | 36 | 42.48 | 42.48
3210 | STRUCTURAL STEEL [150MM X 75 MM] | 0 | Tentative | Labour | (L)Fire Pump Room - Supply Charge | RMT | 36 | 1.18 | 42.48 | 0 | 0 | 0 | 0 | 1.18 | 0 | 36 | 1722.8 | 62020.8 | 0 | 0 | 0 | 36 | 36 | 42.48 | 42.48
3211 | GI PIPE FOR SPRINKLER SYSTEMS-100MM DIA | 0 | Tentative | Labour | (L)Fire Sprinkler Systems - Installation Charge | RMT | 66 | 1.18 | 77.88 | 0 | 0 | 0 | 0 | 1.18 | 0 | 66 | 495.6 | 32709.6 | 0 | 0 | 0 | 66 | 66 | 77.88 | 77.88
3212 | GI PIPE FOR SPRINKLER SYSTEMS-100MM DIA | 0 | Tentative | Labour | (L)Fire Sprinkler Systems - Supply Charge | RMT | 66 | 1.18 | 77.88 | 0 | 0 | 0 | 0 | 1.18 | 0 | 66 | 1611.88 | 106384.08 | 0 | 0 | 0 | 66 | 66 | 77.88 | 77.88
3213 | GI PIPE FOR SPRINKLER SYSTEMS-80MM DIA | 0 | Tentative | Labour | (L)Fire Sprinkler Systems - Installation Charge | RMT | 18 | 1.18 | 21.24 | 0 | 0 | 0 | 0 | 1.18 | 0 | 18 | 371.7 | 6690.6 | 0 | 0 | 0 | 18 | 18 | 21.24 | 21.24
3214 | GI PIPE FOR SPRINKLER SYSTEMS-80MM DIA | 0 | Tentative | Labour | (L)Fire Sprinkler Systems - Supply Charge | RMT | 18 | 1.18 | 21.24 | 0 | 0 | 0 | 0 | 1.18 | 0 | 18 | 1131.62 | 20369.16 | 0 | 0 | 0 | 18 | 18 | 21.24 | 21.24
3215 | GI PIPE FOR SPRINKLER SYSTEMS-65MM DIA | 0 | Tentative | Labour | (L)Fire Sprinkler Systems - Installation Charge | RMT | 60 | 1.18 | 70.8 | 0 | 0 | 0 | 0 | 1.18 | 0 | 60 | 310.34 | 18620.4 | 0 | 0 | 0 | 60 | 60 | 70.8 | 70.8
3216 | GI PIPE FOR SPRINKLER SYSTEMS-65MM DIA | 0 | Tentative | Labour | (L)Fire Sprinkler Systems - Supply Charge | RMT | 60 | 1.18 | 70.8 | 0 | 0 | 0 | 0 | 1.18 | 0 | 60 | 915.68 | 54940.8 | 0 | 0 | 0 | 60 | 60 | 70.8 | 70.8
3217 | GI PIPE FOR SPRINKLER SYSTEMS-50MM DIA | 0 | Tentative | Labour | (L)Fire Sprinkler Systems - Installation Charge | RMT | 60 | 1.18 | 70.8 | 0 | 0 | 0 | 0 | 1.18 | 0 | 60 | 247.8 | 14868 | 0 | 0 | 0 | 60 | 60 | 70.8 | 70.8
3218 | GI PIPE FOR SPRINKLER SYSTEMS-50MM DIA | 0 | Tentative | Labour | (L)Fire Sprinkler Systems - Supply Charge | RMT | 60 | 1.18 | 70.8 | 0 | 0 | 0 | 0 | 1.18 | 0 | 60 | 722.16 | 43329.6 | 0 | 0 | 0 | 60 | 60 | 70.8 | 70.8
3219 | GI PIPE FOR SPRINKLER SYSTEMS-40MM DIA | 0 | Tentative | Labour | (L)Fire Sprinkler Systems - Installation Charge | RMT | 60 | 1.18 | 70.8 | 0 | 0 | 0 | 0 | 1.18 | 0 | 60 | 186.44 | 11186.4 | 0 | 0 | 0 | 60 | 60 | 70.8 | 70.8
3220 | GI PIPE FOR SPRINKLER SYSTEMS-40MM DIA | 0 | Tentative | Labour | (L)Fire Sprinkler Systems - Supply Charge | RMT | 60 | 1.18 | 70.8 | 0 | 0 | 0 | 0 | 1.18 | 0 | 60 | 533.36 | 32001.6 | 0 | 0 | 0 | 60 | 60 | 70.8 | 70.8
3221 | GI PIPE FOR SPRINKLER SYSTEMS-32MM DIA | 0 | Tentative | Labour | (L)Fire Sprinkler Systems - Installation Charge | RMT | 78 | 1.18 | 92.04 | 0 | 0 | 0 | 0 | 1.18 | 0 | 78 | 154.58 | 12057.24 | 0 | 0 | 0 | 78 | 78 | 92.04 | 92.04
3222 | GI PIPE FOR SPRINKLER SYSTEMS-32MM DIA | 0 | Tentative | Labour | (L)Fire Sprinkler Systems - Supply Charge | RMT | 78 | 1.18 | 92.04 | 0 | 0 | 0 | 0 | 1.18 | 0 | 78 | 464.92 | 36263.76 | 0 | 0 | 0 | 78 | 78 | 92.04 | 92.04
3223 | GI PIPE FOR SPRINKLER SYSTEMS-25MM DIA | 0 | Tentative | Labour | (L)Fire Sprinkler Systems - Installation Charge | RMT | 642 | 1.18 | 757.56 | 0 | 0 | 0 | 0 | 1.18 | 0 | 642 | 123.9 | 79543.8 | 0 | 0 | 0 | 642 | 642 | 757.56 | 757.56
3224 | GI PIPE FOR SPRINKLER SYSTEMS-25MM DIA | 0 | Tentative | Labour | (L)Fire Sprinkler Systems - Supply Charge | RMT | 642 | 1.18 | 757.56 | 0 | 0 | 0 | 0 | 1.18 | 0 | 642 | 365.8 | 234843.6 | 0 | 0 | 0 | 642 | 642 | 757.56 | 757.56
3225 | Sprinkler quartzoid - UPRIGHT SPRINKLER 68' | 0 | Tentative | Labour | (L)Fire Sprinkler Systems-Installation Charge | NOS | 117 | 1.18 | 138.06 | 0 | 0 | 0 | 0 | 1.18 | 0 | 117 | 94.4 | 11044.8 | 0 | 0 | 0 | 117 | 117 | 138.06 | 138.06
3226 | Sprinkler quartzoid - UPRIGHT SPRINKLER 68' | 0 | Tentative | Labour | (L)Fire Sprinkler Systems-Supply Charge | NOS | 117 | 1.18 | 138.06 | 0 | 0 | 0 | 0 | 1.18 | 0 | 117 | 230.1 | 26921.7 | 0 | 0 | 0 | 117 | 117 | 138.06 | 138.06
3227 | Sprinkler quartzoid - PENDENT SPRINKLER 68' | 0 | Tentative | Labour | (L)Fire Sprinkler Systems-Installation Charge | NOS | 60 | 1.18 | 70.8 | 0 | 0 | 0 | 0 | 1.18 | 0 | 60 | 94.4 | 5664 | 0 | 0 | 0 | 60 | 60 | 70.8 | 70.8
3228 | Sprinkler quartzoid - PENDENT SPRINKLER 68' | 0 | Tentative | Labour | (L)Fire Sprinkler Systems-Supply Charge | NOS | 60 | 1.18 | 70.8 | 0 | 0 | 0 | 0 | 1.18 | 0 | 60 | 230.1 | 13806 | 0 | 0 | 0 | 60 | 60 | 70.8 | 70.8
3229 | Sprinkler quartzoid - SIDEWALL SPRINKLER 68' | 0 | Tentative | Labour | (L)Fire Sprinkler Systems-Installation Charge | NOS | 74 | 1.18 | 87.32 | 0 | 0 | 0 | 0 | 1.18 | 0 | 74 | 129.8 | 9605.2 | 0 | 0 | 0 | 74 | 74 | 87.32 | 87.32
3230 | Sprinkler quartzoid - SIDEWALL SPRINKLER 68' | 0 | Tentative | Labour | (L)Fire Sprinkler Systems-Supply Charge | NOS | 74 | 1.18 | 87.32 | 0 | 0 | 0 | 0 | 1.18 | 0 | 74 | 260.78 | 19297.72 | 0 | 0 | 0 | 74 | 74 | 87.32 | 87.32
3231 | Butterfly Valves-100 mm Dia | 0 | Tentative | Labour | (L)Fire Sprinkler Systems-Installation Charge | NOS | 4 | 1.18 | 4.72 | 0 | 0 | 0 | 0 | 1.18 | 0 | 4 | 377.6 | 1510.4 | 0 | 0 | 0 | 4 | 4 | 4.72 | 4.72
3232 | Butterfly Valves-100 mm Dia | 0 | Tentative | Labour | (L)Fire Sprinkler Systems-Supply Charge | NOS | 4 | 1.18 | 4.72 | 0 | 0 | 0 | 0 | 1.18 | 0 | 4 | 2476.82 | 9907.28 | 0 | 0 | 0 | 4 | 4 | 4.72 | 4.72
3233 | Butterfly Valves-50 mm Dia | 0 | Tentative | Labour | (L)Fire Sprinkler Systems-Installation Charge | NOS | 4 | 1.18 | 4.72 | 0 | 0 | 0 | 0 | 1.18 | 0 | 4 | 188.8 | 755.2 | 0 | 0 | 0 | 4 | 4 | 4.72 | 4.72
3234 | Butterfly Valves-50 mm Dia | 0 | Tentative | Labour | (L)Fire Sprinkler Systems-Supply Charge | NOS | 4 | 1.18 | 4.72 | 0 | 0 | 0 | 0 | 1.18 | 0 | 4 | 1642.56 | 6570.24 | 0 | 0 | 0 | 4 | 4 | 4.72 | 4.72
3235 | 1A]. Advance With PO, Amt-10% | 0 | Tentative | Labour | (L)Mechanical Puzzle Parking System (M+L) | NOS | 8.4 | 188800 | 1585920 | 0 | 0 | 0 | 0 | 188800 | 0 | 8.4 | 188800 | 1585920 | 0 | 0 | 0 | 8.4 | 8.4 | 1585920 | 1585920
3236 | 2A]. Against drawing for sr. no-1(B Bldg back side), Amt-25. | 0 | Tentative | Labour | (L)Mechanical Puzzle Parking System (M+L) | NOS | 21.5 | 188800 | 4059200 | 0 | 0 | 0 | 0 | 188800 | 0 | 21.5 | 188800 | 4059200 | 0 | 0 | 0 | 21.5 | 21.5 | 4059200 | 4059200
3237 | 2B]. Against drawing for sr. no-2 (Abv.Podium) Amt-24.4% | 0 | Tentative | Labour | (L)Mechanical Puzzle Parking System (M+L) | NOS | 20.5 | 188800 | 3870400 | 0 | 0 | 0 | 0 | 188800 | 0 | 20.5 | 188800 | 3870400 | 0 | 0 | 0 | 20.5 | 20.5 | 3870400 | 3870400
3238 | 3A]. Agnst Material Dispatch for sr. no-1 (B Bldg back side | 0 | Tentative | Labour | (L)Mechanical Puzzle Parking System (M+L) | NOS | 15.05 | 188800 | 2841440 | 0 | 0 | 0 | 0 | 188800 | 0 | 15.05 | 188800 | 2841440 | 0 | 0 | 0 | 15.05 | 15.05 | 2841440 | 2841440
3239 | 3B]. Agnst Material Dispatch for sr. no-2 (Abv.Podium) Amt | 0 | Tentative | Labour | (L)Mechanical Puzzle Parking System (M+L) | NOS | 14.35 | 188800 | 2709280 | 0 | 0 | 0 | 0 | 188800 | 0 | 14.35 | 188800 | 2709280 | 0 | 0 | 0 | 14.35 | 14.35 | 2709280 | 2709280
3240 | 4A]. After Handover for Sr. no-1 (B Bldg back side) Amt-2.6% | 0 | Tentative | Labour | (L)Mechanical Puzzle Parking System (M+L) | NOS | 2.15 | 188800 | 405920 | 0 | 0 | 0 | 0 | 188800 | 0 | 2.15 | 188800 | 405920 | 0 | 0 | 0 | 2.15 | 2.15 | 405920 | 405920
3241 | 4B]. After Handover for Sr. no-2 (Abv.Podium) Amt-2.4% | 0 | Tentative | Labour | (L)Mechanical Puzzle Parking System (M+L) | NOS | 2.05 | 188800 | 387040 | 0 | 0 | 0 | 0 | 188800 | 0 | 2.05 | 188800 | 387040 | 0 | 0 | 0 | 2.05 | 2.05 | 387040 | 387040
3242 | INDENT-908/STP-TRACTOR BREAKER | 10 | Started | Material | (M)TRACTOR BREAKER | DAY | 3 | 4500 | 13500 | 0 | 0 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 13500 | 13500
3243 | INDENT-974/STP PART-2 AREA SOFT MURUM EXCAVATION WORK-BUCKET | 10 | Started | Material | (M)POCLAIN - BUCKET | HOURS | 15 | 2000 | 30000 | 0 | 0 | 0 | 2 | 2000 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 15 | 26000 | 30000
3244 | INDENT-974/STP PART-2 AREA HARD ROCK BREAKING WORK-BREAKER | 10 | Started | Material | (M)POCLAIN - BREAKER | HOURS | 4 | 2200 | 8800 | 0 | 0 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 8800 | 8800
3245 | INDENT-15/STP BLOCK EXCAVATION WORK-JCB | 10 | Started | Material | (M)JCB (BUCKET & LOADER) | HOURS | 42 | 900 | 37800 | 0 | 0 | 0 | 4 | 900 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 42 | 34200 | 37800
3246 | INDENT-15/STP EXCAVTED SOIL SHIFTING-TRACTOR TROLLEY | 10 | Started | Material | (M)TRACTOR TROLLEY | DAY | 11 | 4500 | 49500 | 0 | 0 | 0 | 1 | 4500 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 11 | 45000 | 49500
3247 | INDENT-16/STP TRACTOR TROLLEY | 10 | Started | Material | (M)TRACTOR TROLLEY | DAY | 3 | 4500 | 13500 | 0 | 0 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 13500 | 13500
3248 | INDENT-33/STP TRACTOR TROLLEY | 10 | Started | Material | (M)TRACTOR TROLLEY | DAY | 2 | 4500 | 9000 | 0 | 0 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 9000 | 9000
3249 | INDENT-908/UGWT-TRACTOR BREAKER | 10 | Started | Material | (M)TRACTOR BREAKER | DAY | 3 | 4500 | 13500 | 0 | 0 | 0 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 13500 | 13500
3250 | INDENT-922/UGWT-TRACTOR BREAKER | 10 | Started | Material | (M)TRACTOR BREAKER | DAY | 10 | 4500 | 45000 | 0 | 0 | 0 | 1 | 4500 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 10 | 40500 | 45000
3251 | INDENT-958/UGWT-MINI POCLAIN-BREAKER | 10 | Started | Material | (M)Mini Exavator (Poclain)-Breaker | HOURS | 14 | 1400 | 19600 | 0 | 0 | 0 | 1 | 1400 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 14 | 18200 | 19600
3252 | INDENT-958/UGWT MINI POCLAIN-BUCKET | 10 | Started | Material | (M)Mini Exavator (Poclain)-Bucket | HOURS | 8.5 | 1200 | 10200 | 0 | 0 | 0 | 1 | 1200 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 7.5 | 8.5 | 9000 | 10200
3253 | INDENT-972/UGWT MINI POCLAIN-BREAKER | 10 | Started | Material | (M)Mini Exavator (Poclain)-Breaker | HOURS | 2 | 1400 | 2800 | 0 | 0 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2800 | 2800
3254 | INDENT-972/UGWT MINI POCLAIN-BUCKET | 10 | Started | Material | (M)Mini Exavator (Poclain)-Bucket | HOURS | 5.5 | 1200 | 6600 | 0 | 0 | 0 | 1 | 1200 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5 | 5.5 | 5400 | 6600
3255 | INDENT-982/UGWT POCLAIN-BUCKET | 10 | Started | Material | (M)POCLAIN - BUCKET | HOURS | 1.5 | 2000 | 3000 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 1.5 | 3000 | 3000
3256 | UGWT,STP & AMENITY BUILDING DEWATERING WORK | 0 | Tentative | Material | (M)Diesel | LITRE | 550 | 106.2 | 58410 | 550 | 106.2 | 58410 | 0 | 106.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550 | 550 | 58410 | 58410
3257 | UGWT,STP & AMENITY BUILDING DEWATERING WORK | 0 | Tentative | Material | (M)Petrol | LITRE | 451 | 106 | 47806 | 451 | 106 | 47806 | 0 | 106 | 0 | 100 | 103.83 | 10383 | 0 | 0 | 0 | 451 | 451 | 47806 | 47806
3258 | INDENT-958/NEW LABOUR CAMP-EXC.FOR SEPTIC TANK | 10 | Started | Material | (M)JCB (BUCKET & LOADER) | HOURS | 8 | 900 | 7200 | 0 | 0 | 0 | 1 | 900 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 8 | 6300 | 7200
3259 | INDENT-972/NEW LABOUR CAMP WATER TANKER-10000 LTR | 10 | Started | Material | (M)Construction Water (Tanker-10,000 Lts.) | TRIP | 3 | 800 | 2400 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 2400 | 2400
3260 | INDENT-987/NEW LABOUR CAMP WATER TANKER-10000 LTR | 10 | Started | Material | (M)Construction Water (Tanker-10,000 Lts.) | TRIP | 9 | 800 | 7200 | 0 | 0 | 0 | 1 | 800 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 9 | 6400 | 7200
3261 | INDENT-16/NEW LABOUR CAMP WATER TANKER-10000 LTR | 10 | Started | Material | (M)Construction Water (Tanker-10,000 Lts.) | TRIP | 6 | 800 | 4800 | 0 | 0 | 0 | 1 | 800 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 6 | 4000 | 4800
3262 | INDENT-28/NEW LABOUR CAMP WATER TANKER-10000 LTR | 10 | Started | Material | (M)Construction Water (Tanker-10,000 Lts.) | TRIP | 2 | 800 | 1600 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 1600 | 1600
3263 | INDENT-33/NEW LABOUR CAMP WATER TANKER-10000 LTR | 10 | Started | Material | (M)Construction Water (Tanker-10,000 Lts.) | TRIP | 2 | 800 | 1600 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 1600 | 1600
3264 | INDENT-63/LABOUR CAMP WATER SUPPLY LINE | 0 | Started | Material | (M)PVC Agri Elbow 90 mm - 3" | NOS | 6 | 118 | 708 | 6 | 118 | 708 | 0 | 118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 708 | 708
3265 | INDENT-63/LABOUR CAMP WATER SUPPLY LINE | 0 | Started | Material | (M)PVC Agri Pipes R/F 20ft long (6KGS/Class 3) 90 mm - 3" | NOS | 12 | 590 | 7080 | 12 | 590 | 7080 | 0 | 590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 7080 | 7080
3266 | INDENT-972/CLUB HOUSE MINI POCLAIN-BUCKET | 10 | Started | Material | (M)Mini Exavator (Poclain)-Bucket | HOURS | 12 | 1200 | 14400 | 0 | 0 | 0 | 1 | 1200 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 12 | 13200 | 14400
3267 | INDENT-974/CLUB HOUSE MINI ROLLER-COMPACTOR | 10 | Started | Material | (M)Mini Roller-Compactor | DAY | 1 | 3500 | 3500 | 0 | 0 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3500 | 3500
3268 | INDENT-33/SERVICES LINE CLUB HOUSE & C WING-JCB | 10 | Started | Material | (M)JCB (BUCKET & LOADER) | HOURS | 12 | 900 | 10800 | 0 | 0 | 0 | 1 | 900 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 12 | 9900 | 10800
3269 | INDENT-972/B WING & C WING MACHINERY BOBCAT | 10 | Started | Material | (M)BOBCAT | HOURS | 4 | 900 | 3600 | 0 | 0 | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 3600 | 3600
3270 | INDENT-974/WATER TANKER FOR-SITE & LABOUR CAMP USE-10000 LTR | 10 | Started | Material | (M)Construction Water (Tanker-10,000 Lts.) | TRIP | 9 | 800 | 7200 | 0 | 0 | 0 | 1 | 800 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 9 | 6400 | 7200
3271 | INDENT-982/B WING & C WING MACHINERY WATER TANKER-10000 LTR | 10 | Started | Material | (M)Construction Water (Tanker-10,000 Lts.) | TRIP | 7 | 800 | 5600 | 0 | 0 | 0 | 1 | 800 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 7 | 4800 | 5600
3272 | INDENT-982/B WING,C WING & SITE WORK-JCB | 10 | Started | Material | (M)JCB (BUCKET & LOADER) | HOURS | 11.5 | 900 | 10350 | 0 | 0 | 0 | 1 | 900 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 10.5 | 11.5 | 9450 | 10350
3273 | INDENT-982/MISCELLANEOUS WORK BOBCAT | 10 | Started | Material | (M)BOBCAT | HOURS | 4 | 900 | 3600 | 0 | 0 | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 3600 | 3600
3274 | INDENT-987/MISCELLANEOUS WORK JCB | 10 | Started | Material | (M)JCB (BUCKET & LOADER) | HOURS | 17.75 | 900 | 15975 | 0 | 0 | 0 | 2 | 900 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 15.75 | 17.75 | 14175 | 15975
3275 | INDENT-15/C WING CURING & SLAB CASTING WORK WATER TANKER-100 | 10 | Started | Material | (M)Construction Water (Tanker-10,000 Lts.) | TRIP | 1 | 800 | 800 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 800 | 800
3276 | INDENT-16/CLUB HOUSE MAT.SHFTING & SITE WORK. | 10 | Started | Material | (M)JCB (BUCKET & LOADER) | HOURS | 18 | 900 | 16200 | 0 | 0 | 0 | 2 | 900 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 18 | 14400 | 16200
3277 | INDENT-28/B & C WING MATERIAL SHIFTING-BOBCAT | 10 | Started | Material | (M)BOBCAT | HOURS | 9.5 | 900 | 8550 | 0 | 0 | 0 | 1 | 900 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 8.5 | 9.5 | 7650 | 8550
3278 | INDENT-28/C WING SLAB CASTING & CURRING WORK WATER TANKER-10 | 10 | Started | Material | (M)Construction Water (Tanker-10,000 Lts.) | TRIP | 4 | 800 | 3200 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 3200 | 3200
3279 | INDENT-33/C WING & CLUB HOUSE/WATER TANKER-10000 LTR | 10 | Started | Material | (M)Construction Water (Tanker-10,000 Lts.) | TRIP | 2 | 800 | 1600 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 1600 | 1600
3280 | INDENT-908/TRACTOR BREAKER/STP & UGWT | 0 | Started | Labour | (L)Tractor breaker | DAY | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 4500 | 27000 | 5 | 4500 | 22500 | 6 | 1 | 0 | -22500
3281 | INDET-922/TRACTOR BREAKER FOR STP & UGWT | 0 | Started | Labour | (L)Tractor breaker | DAY | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 4000 | 40000 | 4 | 4000 | 16000 | 10 | 6 | 0 | -16000
3282 | MACHINERY JCB | 0 | Started | Labour | (L)JCB BUCKET | HOURS | 131.75 | 1062 | 139918.5 | 0 | 0 | 0 | 0 | 1062 | 0 | 131.75 | 850 | 111987.5 | 0 | 0 | 0 | 131.75 | 131.75 | 139918.5 | 139918.5
3283 | MACHINERY POCLAIN-BUCKET | 0 | Started | Labour | (L)POCLAIN BUCKET | HOURS | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5 | 1900 | 6650 | 0 | 0 | 0 | 3.5 | 3.5 | 0 | 0
3284 | MACHINERY POCLAIN-BUCKET | 0 | Started | Labour | (L)POCLAIN TRAVELING TRANSPORT | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 7000 | 7000 | 0 | 0 | 0 | 1 | 1 | 0 | 0
3285 | MACHINERY BOBCAT | 0 | Started | Labour | (L)BOBCAT on Hours | HOURS | 32 | 1062 | 33984 | 0 | 0 | 0 | 0 | 1062 | 0 | 32 | 850 | 27200 | 0 | 0 | 0 | 32 | 32 | 33984 | 33984
3286 | MACHINERY TRACTOR TROLLEY | 0 | Started | Labour | (L)TRACTOR ON RENT | DAY | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 2562.5 | 61500 | 1 | 3000 | 3000 | 24 | 23 | 0 | -3000
3287 | MACHINERY MINI ROLLER-COMPACTOR | 0 | Started | Labour | (L)Fare Charges Transportation - | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 500 | 500 | 1 | 500 | 500 | 1 | 0 | 0 | -500
3288 | MACHINERY MINI ROLLER-COMPACTOR | 0 | Started | Labour | (L)MINI ROLLER COMPACTOR | DAY | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 3916.67 | 23500 | 6 | 3916.67 | 23500 | 6 | 0 | 0 | -23500
3289 | MACHINERY MINI POCLAIN-BREAKER | 0 | Started | Labour | (L)MINI POCLAIN BREAKER | HOURS | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 1400 | 22400 | 16 | 1400 | 22400 | 16 | 0 | 0 | -22400
3290 | MACHINERY MINI POCLAIN-BUCKET | 0 | Started | Labour | (L)Fare Charges Transportation - | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1500 | 1500 | 1 | 1500 | 1500 | 1 | 0 | 0 | -1500
3291 | MACHINERY MINI POCLAIN-BUCKET | 0 | Started | Labour | (L)MINI POCLAIN BUCKET | HOURS | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 1200 | 31200 | 26 | 1200 | 31200 | 26 | 0 | 0 | -31200
3292 | MACHINERY CRANE | 0 | Started | Labour | (L)Farana Crane - 15 Ton | HOURS | 40.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40.5 | 1000 | 40500 | 40.5 | 1000 | 40500 | 40.5 | 0 | 0 | -40500
3293 | MACHINERY DOUBLE DRUM VIBRO ROLLER | 0 | Started | Labour | (L)DOUBLE DRUM VIBRO ROLLER | DAY | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 8000 | 8000 | 1 | 8000 | 8000 | 1 | 0 | 0 | -8000
3294 | 1.5 HP MOTOR WINDING & REPARING WORK (M+L) | 0 | Started | Labour | (L)DEWATERING PUMP REPAIRING WORK | NOS | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4775 | 9550 | 2 | 4775 | 9550 | 2 | 0 | 0 | -9550
3295 | 1 HP MOTOR WINDING & REPARING WORK (M+L) | 0 | Started | Labour | (L)DEWATERING PUMP REPAIRING WORK | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 10300 | 10300 | 1 | 10300 | 10300 | 1 | 0 | 0 | -10300
3296 | 7.5 HP MOTOR WINDING & REPARING WORK (M+L) | 0 | Started | Labour | (L)DEWATERING PUMP REPAIRING WORK | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 8000 | 8000 | 1 | 8000 | 8000 | 1 | 0 | 0 | -8000
3297 | MACHINERY WORK FOR MONTH AUG-2024 | 0 | Started | Labour | (L)BOBCAT on Hours | HOURS | 77 | 1062 | 81774 | 0 | 0 | 0 | 0 | 1062 | 0 | 77 | 1003 | 77231 | 77 | 1003 | 77231 | 77 | 0 | 81774 | 4543
3298 | MACHINERY WORK FOR MONTH AUG-2024 | 0 | Started | Labour | (L)JCB BREAKER | HOURS | 1 | 1652 | 1652 | 0 | 0 | 0 | 0 | 1652 | 0 | 1 | 1652 | 1652 | 1 | 1652 | 1652 | 1 | 0 | 1652 | 0
3299 | MACHINERY WORK FOR MONTH AUG-2024 | 0 | Started | Labour | (L)JCB BUCKET | HOURS | 118 | 1062 | 125316 | 0 | 0 | 0 | 0 | 1062 | 0 | 118 | 1003 | 118354 | 118 | 1003 | 118354 | 118 | 0 | 125316 | 6962
3300 | MACHINERY WORK FOR MONTH AUG-2024 | 0 | Started | Labour | (L)MINI POCLAIN BUCKET | HOURS | 6.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.5 | 1003 | 6519.5 | 6.5 | 1003 | 6519.5 | 6.5 | 0 | 0 | -6519.5
3301 | MACHINERY WORK FOR MONTH AUG-2024 | 0 | Started | Labour | (L)TRACTOR ON RENT | DAY | 11.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.5 | 2950 | 33925 | 11.5 | 2950 | 33925 | 11.5 | 0 | 0 | -33925
3302 | MACHINERY WORK FOR MONTH JULY-2024 | 0 | Started | Labour | (L)BOBCAT on Hours | HOURS | 3.5 | 1062 | 3717 | 0 | 0 | 0 | 0 | 1062 | 0 | 3.5 | 1003 | 3510.5 | 0 | 0 | 0 | 3.5 | 3.5 | 3717 | 3717
3303 | MACHINERY WORK FOR MONTH JULY-2024 | 0 | Started | Labour | (L)JCB BUCKET | HOURS | 44.25 | 1062 | 46993.5 | 0 | 0 | 0 | 0 | 1062 | 0 | 44.25 | 1003 | 44382.76 | 0 | 0 | 0 | 44.25 | 44.25 | 46993.5 | 46993.5
3304 | MACHINERY WORK FOR MONTH JULY-2024 | 0 | Started | Labour | (L)MINI POCLAIN BUCKET | HOURS | 14.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.5 | 944 | 13688 | 14.5 | 944 | 13688 | 14.5 | 0 | 0 | -13688
3305 | MACHINERY WORK FOR MONTH JULY-2024 | 0 | Started | Labour | (L)TRACTOR ON RENT | DAY | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2950 | 11800 | 0 | 0 | 0 | 4 | 4 | 0 | 0
3306 | MACHINERY WORK FOR MONTH SEPTEMBER-2024 | 0 | Started | Labour | (L)BOBCAT on Hours | HOURS | 18 | 1062 | 19116 | 0 | 0 | 0 | 0 | 1062 | 0 | 18 | 1003 | 18054 | 18 | 1003 | 18054 | 18 | 0 | 19116 | 1062
3307 | MACHINERY WORK FOR MONTH SEPTEMBER-2024 | 0 | Started | Labour | (L)JCB BUCKET | HOURS | 75 | 1062 | 79650 | 0 | 0 | 0 | 0 | 1062 | 0 | 75 | 1003 | 75225 | 75 | 1003 | 75225 | 75 | 0 | 79650 | 4425
3308 | MACHINERY WORK FOR MONTH SEPTEMBER-2024 | 0 | Started | Labour | (L)MINI POCLAIN BUCKET | HOURS | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 944 | 51920 | 55 | 944 | 51920 | 55 | 0 | 0 | -51920
3309 | MACHINERY WORK FOR MONTH SEPTEMBER-2024 | 0 | Started | Labour | (L)TRACTOR ON RENT | DAY | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 2950 | 4425 | 1.5 | 2950 | 4425 | 1.5 | 0 | 0 | -4425
3310 | MACHINERY WORK FOR MONTH OCTOBER-2024 | 0 | Started | Labour | (L)BOBCAT on Hours | HOURS | 28 | 1062 | 29736 | 0 | 0 | 0 | 0 | 1062 | 0 | 28 | 1003 | 28084 | 28 | 1003 | 28084 | 28 | 0 | 29736 | 1652
3311 | MACHINERY WORK FOR MONTH OCTOBER-2024 | 0 | Started | Labour | (L)JCB BUCKET | HOURS | 83.91 | 1062 | 89112.42 | 0 | 0 | 0 | 0 | 1062 | 0 | 83.91 | 1003 | 84161.74 | 83.91 | 1003 | 84161.74 | 83.91 | 0 | 89112.42 | 4950.68
3312 | MACHINERY WORK FOR MONTH OCTOBER-2024 | 0 | Started | Labour | (L)TRACTOR ON RENT | DAY | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2950 | 14750 | 5 | 2950 | 14750 | 5 | 0 | 0 | -14750
3313 | MACHINERY WORK FOR MONTH NOVEMBER-2024 | 0 | Started | Labour | (L)BOBCAT on Hours | HOURS | 36 | 1062 | 38232 | 0 | 0 | 0 | 0 | 1062 | 0 | 36 | 1003 | 36108 | 36 | 1003 | 36108 | 36 | 0 | 38232 | 2124
3314 | MACHINERY WORK FOR MONTH NOVEMBER-2024 | 0 | Started | Labour | (L)JCB BUCKET | HOURS | 83.5 | 1062 | 88677 | 0 | 0 | 0 | 0 | 1062 | 0 | 83.5 | 1003 | 83750.5 | 83.5 | 1003 | 83750.5 | 83.5 | 0 | 88677 | 4926.5
3315 | MACHINERY WORK FOR MONTH NOVEMBER-2024 | 0 | Started | Labour | (L)TRACTOR ON RENT | DAY | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2950 | 11800 | 4 | 2950 | 11800 | 4 | 0 | 0 | -11800
3316 | MACHINERY WORK FOR MONTH DECEMBER-2024 | 0 | Started | Labour | (L)BOBCAT on Hours | HOURS | 57 | 1062 | 60534 | 0 | 0 | 0 | 0 | 1062 | 0 | 57 | 1003 | 57171 | 57 | 1003 | 57171 | 57 | 0 | 60534 | 3363
3317 | MACHINERY WORK FOR MONTH DECEMBER-2024 | 0 | Started | Labour | (L)JCB BUCKET | HOURS | 97.08 | 1062 | 103098.96 | 0 | 0 | 0 | 0 | 1062 | 0 | 97.08 | 1003 | 97371.24 | 97.08 | 1003 | 97371.26 | 97.08 | 0 | 103098.96 | 5727.7
3318 | MACHINERY WORK FOR MONTH DECEMBER-2024 | 0 | Started | Labour | (L)MINI POCLAIN BUCKET | HOURS | 8 | 1200 | 9600 | 0 | 0 | 0 | 0 | 1200 | 0 | 8 | 1003 | 8024 | 8 | 1003 | 8024 | 8 | 0 | 9600 | 1576
3319 | MACHINERY WORK FOR MONTH DECEMBER-2024 | 0 | Started | Labour | (L)TRACTOR ON RENT | DAY | 5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.5 | 2950 | 16225 | 5.5 | 2950 | 16225 | 5.5 | 0 | 0 | -16225
3320 | MACHINERY-TRANSFORMER BELOW PCC COMPACTION WORK. | 0 | Started | Labour | (L)DOUBLE DRUM VIBRO ROLLER | DAY | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 8000 | 8000 | 1 | 8000 | 8000 | 1 | 0 | 0 | -8000
3321 | MACHINERY-TRANSFORMER BELOW PCC COMPACTION WORK. | 0 | Started | Labour | (L)MINI ROLLER COMPACTOR | DAY | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 4000 | 20000 | 5 | 4000 | 20000 | 5 | 0 | 0 | -20000
3322 | CLUB HOUSE BACK SIDE & TRANSFORMER TRENCH COMPACTING WORK | 0 | Started | Labour | (L)Fare Charges Transportation - | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 500 | 500 | 1 | 500 | 500 | 1 | 0 | 0 | -500
3323 | CLUB HOUSE BACK SIDE & TRANSFORMER TRENCH COMPACTING WORK | 0 | Started | Labour | (L)MINI ROLLER COMPACTOR | DAY | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3500 | 7000 | 2 | 3500 | 7000 | 2 | 0 | 0 | -7000
3324 | B BLDG PARKING DRAINAGE LINE EXCAVATION | 0 | Started | Labour | (L)Fare Charges Transportation - | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1500 | 1500 | 0 | 0 | 0 | 1 | 1 | 0 | 0
3325 | B BLDG PARKING DRAINAGE LINE EXCAVATION | 0 | Started | Labour | (L)MINI POCLAIN BUCKET | HOURS | 24.5 | 1200 | 29400 | 0 | 0 | 0 | 0 | 1200 | 0 | 24.5 | 1200 | 29400 | 23.5 | 1200 | 28200 | 24.5 | 1 | 29400 | 1200
3326 | TRACTOR LOADING,UNLOADING,DUMPING & MATERIAL SHIFTING | 0 | Started | Labour | (L)TRACTOR LOCAL TRIP- LOADING & UNLOADING | TRIP | 17 | 1400 | 23800 | 0 | 0 | 0 | 0 | 1400 | 0 | 17 | 1400 | 23800 | 17 | 1400 | 23800 | 17 | 0 | 23800 | 0
3327 | TRACTOR LOADING,UNLOADING,DUMPING & MATERIAL SHIFTING | 0 | Started | Labour | (L)TRACTOR LOCAL TRIP-LOADING & DUMPING | TRIP | 13 | 700 | 9100 | 0 | 0 | 0 | 0 | 700 | 0 | 13 | 700 | 9100 | 13 | 700 | 9100 | 13 | 0 | 9100 | 0
3328 | TRACTOR LOADING,UNLOADING,DUMPING & MATERIAL SHIFTING | 0 | Started | Labour | (L)TRACTOR ON RENT | DAY | 15 | 3000 | 45000 | 0 | 0 | 0 | 0 | 3000 | 0 | 15 | 3000 | 45000 | 15 | 3000 | 45000 | 15 | 0 | 45000 | 0
3329 | DEPARTMENT WORK-LABOUR CURING WORK & OTHER MISS.WORK | 0 | Started | Labour | (L)FC | NOS | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 0 | 0
3330 | DEPARTMENT WORK-LABOUR CURING WORK & OTHER MISS.WORK | 0 | Started | Labour | (L)MC | NOS | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 0 | 0
3331 | INDENT-929/STP & UGWT SAFETY NET-LABOUR | 0 | Started | Labour | (L)Safety Net Labour | NOS | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 800 | 9600 | 12 | 800 | 9600 | 12 | 0 | 0 | -9600
3332 | INDENT-936/CLUB HOUSE/PATHWAY & SEATING-LABOUR | 0 | Started | Labour | (L)6" Brickwork Labour | SQFT | 46.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46.89 | 17 | 797.13 | 46.89 | 17 | 797.13 | 46.89 | 0 | 0 | -797.13
3333 | INDENT-936/CLUB HOUSE/PATHWAY & SEATING-LABOUR | 0 | Started | Labour | (L)9" Brickwork Labour | SQFT | 681.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 681.5 | 21 | 14311.5 | 602.49 | 21 | 12652.29 | 681.5 | 79.01 | 0 | -12652.29
3334 | INDENT-936/CLUB HOUSE/PATHWAY & SEATING-LABOUR | 0 | Started | Labour | (L)single coat plaster | SQFT | 316.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 316.47 | 18 | 5696.46 | 235.74 | 18 | 4243.32 | 316.47 | 80.73 | 0 | -4243.32
3335 | INDENT-936/CLUB HOUSE/PATHWAY & SEATING-LABOUR | 0 | Started | Labour | (L)Tar Plaster (Labour) | SQFT | 381.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 381.2 | 14 | 5336.8 | 78.36 | 14 | 1097.04 | 381.2 | 302.84 | 0 | -1097.04
3336 | INDENT-968/B BLDG/FLAT SKIRTING-DPS CHE.COATING | 0 | Started | Labour | (L)2.5 BHK-DPS Chemical Coating-Labour | Per Flat | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 1200 | 28800 | 24 | 1200 | 28800 | 24 | 0 | 0 | -28800 | Building
3337 | INDENT-968/B BLDG/FLAT SKIRTING-DPS CHE.COATING | 0 | Started | Labour | (L)2BHK-DPS Chemical Coating-Labour | Per Flat | 97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 1200 | 102000 | 85 | 1200 | 102000 | 97 | 12 | 0 | -102000 | Building
3338 | INDENT-968/B BLDG/FLAT SKIRTING-DPS CHE.COATING | 0 | Started | Labour | (L)4BHK-DPS Chemical Coating-Labour | Per Flat | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 1400 | 15400 | 11 | 1400 | 15400 | 11 | 0 | 0 | -15400 | Building
3339 | INDENT-482/CLUB HOUSE/BBM & PLASTER (INT.& EXT.) | 0 | Started | Labour | (L)AAC BLOCK WORK-125MM | SQFT | 4491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4491 | 20 | 89820 | 1087.91 | 20 | 21758.2 | 4491 | 3403.09 | 0 | -21758.2
3340 | INDENT-482/CLUB HOUSE/BBM & PLASTER (INT.& EXT.) | 0 | Started | Labour | (L)Double Coat Plaster (Labour) | SQFT | 3753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3753 | 28 | 105084 | 26.96 | 28 | 754.88 | 3753 | 3726.04 | 0 | -754.88
3341 | INDENT-482/CLUB HOUSE/BBM & PLASTER (INT.& EXT.) | 0 | Started | Labour | (L)DPC-15OMM (Depth) | RFT | 603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 603 | 18 | 10854 | 451.75 | 18 | 8131.5 | 603 | 151.25 | 0 | -8131.5
3342 | INDENT-482/CLUB HOUSE/BBM & PLASTER (INT.& EXT.) | 0 | Started | Labour | (L)PATALI-100MM (Depth) | RFT | 555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 555 | 12 | 6660 | 413.96 | 12 | 4967.52 | 555 | 141.04 | 0 | -4967.52
3343 | INDENT-482/CLUB HOUSE/BBM & PLASTER (INT.& EXT.) | 0 | Started | Labour | (L)Sanla Plaster (Lab) | SQFT | 965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 965 | 14 | 13510 | 369.45 | 14 | 5172.3 | 965 | 595.55 | 0 | -5172.3
3344 | INDENT-482/CLUB HOUSE/BBM & PLASTER (INT.& EXT.) | 0 | Started | Labour | (L)Tar Plaster (Labour) | SQFT | 6727 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6727 | 14 | 94178 | 1131.44 | 14 | 15840.16 | 6727 | 5595.56 | 0 | -15840.16
3345 | INDENT-671/CLUB HOUSE/MS PERGOLA LABOUR-ERRECTION | 0 | Started | Labour | (L)MS BEAM (ISMB-200mm) | KG | 5250.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5250.5 | 28 | 147014 | 0 | 0 | 0 | 5250.5 | 5250.5 | 0 | 0
3346 | INDENT-671/CLUB HOUSE/MS PERGOLA LABOUR-ERRECTION | 0 | Started | Labour | (L)MS CHANEL (75mm X 40mm) | KG | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 28 | 2016 | 0 | 0 | 0 | 72 | 72 | 0 | 0
3347 | INDENT-671/CLUB HOUSE/MS PERGOLA LABOUR-ERRECTION | 0 | Started | Labour | (L)MS CHANNEL (ISMC-100mm X 50mm) | KG | 2690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2690 | 28 | 75320 | 2506.45 | 28 | 70180.6 | 2690 | 183.55 | 0 | -70180.6
3348 | INDENT-671/CLUB HOUSE/MS PERGOLA LABOUR-ERRECTION | 0 | Started | Labour | (L)MS FLAT PATTI -150mm X 100mm X 10mm | KG | 139.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 139.5 | 28 | 3906 | 69.75 | 28 | 1953 | 139.5 | 69.75 | 0 | -1953
3349 | INDENT-671/CLUB HOUSE/MS PERGOLA LABOUR-ERRECTION | 0 | Started | Labour | (L)MS PLATE (250mm x 150mm x 12mm) | KG | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 28 | 924 | 0 | 0 | 0 | 33 | 33 | 0 | 0
3350 | INDENT-671/CLUB HOUSE/MS PERGOLA LABOUR-ERRECTION | 0 | Started | Labour | (L)MS SQ.TUBE (50mm X 50mm) | KG | 2440.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2440.5 | 28 | 68334 | 2395.29 | 28 | 67068.12 | 2440.5 | 45.21 | 0 | -67068.12
3351 | INDENT-671/CLUB HOUSE/MS PERGOLA LABOUR-ERRECTION | 0 | Started | Labour | (L)MS SQ.TUBE (SHS-72mm X 72mm) | KG | 624.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 624.5 | 28 | 17486 | 0 | 0 | 0 | 624.5 | 624.5 | 0 | 0
3352 | Indent-944/Lift Material Godown Work | 0 | Started | Labour | (L)Patra (Tin sheet) Fixing | SQFT | 920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 920 | 10 | 9200 | 920 | 10 | 9200 | 920 | 0 | 0 | -9200 | STUB COLUMN
3353 | DEP.LABOUR FOR CURING & OTHER SITE MISC.WORK (MAR-24 TO 25) | 0 | Started | Labour | (L)FC | NOS | 1095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1095 | 372.74 | 408150 | 99 | 350 | 34650 | 1095 | 996 | 0 | -34650
3354 | DEP.LABOUR FOR CURING & OTHER SITE MISC.WORK (MAR-24 TO 25) | 0 | Started | Labour | (L)FC-LABOUR | NOS | 365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 365 | 375 | 136875 | 198 | 375 | 74250 | 365 | 167 | 0 | -74250
3355 | DEP.LABOUR FOR CURING & OTHER SITE MISC.WORK (MAR-24 TO 25) | 0 | Started | Labour | (L)MC | NOS | 1460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1460 | 471.32 | 688131.9425 | 419.2223 | 462.2 | 193762.54 | 1460 | 1040.7777 | 0 | -193762.54
3356 | DEP.LABOUR FOR CURING & OTHER SITE MISC.WORK (MAR-24 TO 25) | 0 | Started | Labour | (L)MC-LABOUR | NOS | 365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 365 | 475 | 173375 | 365 | 475 | 173375 | 365 | 0 | 0 | -173375
3357 | UGWT COMMERCIAL TANK BLACK SOIL REMOVING & CLEANING WORK | 0 | Started | Labour | (L)MC-LABOUR | NOS | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 575 | 8050 | 14 | 575 | 8050 | 14 | 0 | 0 | -8050
3358 | 24 AVENUE SITE SECURITY (MAR-24 TO MAR-25) | 0 | Started | Labour | (L)FC (Developement & House Keeping) | NOS | 122 | 400 | 48800 | 0 | 0 | 0 | 0 | 400 | 0 | 122 | 400 | 48800 | 43.5 | 400 | 17400 | 122 | 78.5 | 48800 | 31400
3359 | 24 AVENUE SITE SECURITY (MAR-24 TO MAR-25) | 0 | Started | Labour | (L)MC (Garden Watering & House Keeping) | NOS | 360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360 | 483.33 | 174000 | 180 | 466.67 | 84000 | 360 | 180 | 0 | -84000
3360 | 24 AVENUE SITE SECURITY (MAR-24 TO MAR-25) | 0 | Started | Labour | (L)SECURITY-DAY | NOS | 1080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720 | 433.33 | 312000.48 | 663.1136 | 433.33 | 287349.67 | 1080 | 416.8864 | 0 | -287349.67
3361 | 24 AVENUE SITE SECURITY (MAR-24 TO MAR-25) | 0 | Started | Labour | (L)SECURITY-NIGHT | NOS | 1080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720 | 433.33 | 312000.48 | 663.1136 | 433.33 | 287349.67 | 1080 | 416.8864 | 0 | -287349.67
3362 | 24 AVENUE LABOUR CAMP SECURITY (MAR-24 TO MAR-25) | 0 | Started | Labour | (L)SECURITY-DAY | NOS | 1080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360 | 433.33 | 156000.24 | 239.0333 | 433.33 | 103581.26 | 1080 | 840.9667 | 0 | -103581.26
3363 | 24 AVENUE LABOUR CAMP SECURITY (MAR-24 TO MAR-25) | 0 | Started | Labour | (L)SECURITY-NIGHT | NOS | 1080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360 | 433.33 | 156000.24 | 239.0333 | 433.33 | 103581.26 | 1080 | 840.9667 | 0 | -103581.26
3364 | GARDEN MAINTANANCE FOR JUNE MONTH | 0 | Started | Labour | (L)MC (Garden Watering & House Keeping) | NOS | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 500 | 10500 | 21 | 500 | 10500 | 21 | 0 | 0 | -10500
3365 | Labour Camp Toilet Cleaning-(April-24 to March-25) | 0 | Started | Labour | (L)Toilet Cleaning (Sweeper services) | Month. | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 12 | 0 | 0
3366 | Labour Camp Toilet Cleaning-(April-24 to March-25) | 0 | Started | Labour | (L)Toilet Cleaning (Sweeper-Services) | NOS | 144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 500 | 72000 | 56 | 500 | 28000 | 144 | 88 | 0 | -28000
3367 | DRINKING WATER BOTTLE (SITE & SALES OFFICE) | 0 | Started | Labour | (L)WATER BOTTLE (20 LTR JAR) | BOTTLE | 720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 720 | 40 | 28800 | 275 | 40 | 11000 | 720 | 445 | 0 | -11000
3368 | LABOUR CAMP PEST CONTROL-MONTHLY BASIS | 0 | Started | Labour | (L)Mosquito Management Services | NOS | 48 | 1062 | 50976 | 0 | 0 | 0 | 0 | 1062 | 0 | 48 | 1062 | 50976 | 22 | 1062 | 23364 | 48 | 26 | 50976 | 27612
3369 | MISCELLANEOUS WATER TANKER-10000 LTR | 0 | Started | Labour | (L)Construction Water-10000 Ltr/Tanker | TRIP | 330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 330 | 853.33 | 281600 | 291 | 860.48 | 250400 | 330 | 39 | 0 | -250400
3370 | 24-AVENUE PETTY CASH | 0 | Started | Labour | (L)PETTY CASH | Per Month | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 21029.67 | 63089 | 0.7094 | 25000 | 17735 | 3 | 2.2906 | 0 | -17735
3371 | MATERIAL UNLOADING-CHARGES | 0 | Started | Labour | (L)AAC BLOCK UNLOADING CHARGES- TONNE | TON | 463.837 | 200 | 92767.4 | 0 | 0 | 0 | 0 | 200 | 0 | 463.837 | 200 | 92767.4 | 463.837 | 200 | 92767.4 | 463.837 | 0 | 92767.4 | 0
3372 | MATERIAL UNLOADING-CHARGES | 0 | Started | Labour | (L)CHEMICAL UNLOADING WORK | TON | 33.4 | 200 | 6680 | 0 | 0 | 0 | 0 | 200 | 0 | 33.4 | 200 | 6680 | 33.4 | 200 | 6680 | 33.4 | 0 | 6680 | 0
3373 | MATERIAL UNLOADING-CHARGES | 0 | Started | Labour | (L)TILE UNLOADING WORK | TON | 44.685 | 250 | 11171.25 | 0 | 0 | 0 | 0 | 250 | 0 | 44.685 | 250 | 11171.25 | 44.685 | 250 | 11171.25 | 44.685 | 0 | 11171.25 | 0
3374 | BLOCK UNLOADING-CHARGES BLOCK UNLOADING(Rate/tonne-250) | 0 | Started | Labour | (L)AAC BLOCK UNLOADING CHARGES- TONNE | TON | 46.886 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46.886 | 250 | 11721.5 | 46.886 | 250 | 11721.5 | 46.886 | 0 | 0 | -11721.5
3375 | MATERIAL UNLOADING CHARGES FOR SITE 24 AVENUE | 0 | Tentative | Labour | (L)AAC BLOCK UNLOADING CHARGES- TONNE | TON | 305.58 | 200 | 61116 | 0 | 0 | 0 | 0 | 200 | 0 | 305.58 | 236 | 72116.88 | 0 | 0 | 0 | 305.58 | 305.58 | 61116 | 61116
3376 | MATERIAL UNLOADING CHARGES FOR SITE 24 AVENUE | 0 | Tentative | Labour | (L)CHEMICAL UNLOADING WORK | TON | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 240.72 | 2407.2 | 0 | 0 | 0 | 10 | 10 | 0 | 0
3377 | MATERIAL UNLOADING CHARGES FOR SITE 24 AVENUE | 0 | Tentative | Labour | (L)DOORS UNLOADING WORK | NOS | 257 | 20.06 | 5155.42 | 0 | 0 | 0 | 0 | 20.06 | 0 | 257 | 20.06 | 5155.42 | 0 | 0 | 0 | 257 | 257 | 5155.42 | 5155.42
3378 | MATERIAL UNLOADING CHARGES FOR SITE 24 AVENUE | 0 | Tentative | Labour | (L)GRANITE UNLOADING WORK | SQFT | 680 | 3.54 | 2407.2 | 0 | 0 | 0 | 0 | 3.54 | 0 | 680 | 3.54 | 2407.2 | 0 | 0 | 0 | 680 | 680 | 2407.2 | 2407.2
3379 | MATERIAL UNLOADING CHARGES FOR SITE 24 AVENUE | 0 | Tentative | Labour | (L)KADDAPA UNLOADING WORK | TON | 22.75 | 342.2 | 7785.05 | 0 | 0 | 0 | 0 | 342.2 | 0 | 22.75 | 342.2 | 7785.06 | 0 | 0 | 0 | 22.75 | 22.75 | 7785.05 | 7785.05
3380 | MATERIAL UNLOADING CHARGES FOR SITE 24 AVENUE | 0 | Tentative | Labour | (L)SHAHABAD UNLOADING WORK | TON | 50.03 | 295 | 14758.85 | 0 | 0 | 0 | 0 | 295 | 0 | 50.03 | 295 | 14758.86 | 0 | 0 | 0 | 50.03 | 50.03 | 14758.85 | 14758.85
3381 | MATERIAL UNLOADING CHARGES FOR SITE 24 AVENUE | 0 | Tentative | Labour | (L)TILE UNLOADING WORK | TON | 147.41 | 370 | 54541.7 | 0 | 0 | 0 | 0 | 370 | 0 | 147.41 | 304.1 | 44827.02 | 0 | 0 | 0 | 147.41 | 147.41 | 54541.7 | 54541.7
3382 | MATERIAL UNLOADING CHARGES FOR SITE 24 AVENUE | 0 | Tentative | Labour | (L)WB UNLOADING WORK | NOS | 262 | 23.6 | 6183.2 | 0 | 0 | 0 | 0 | 23.6 | 0 | 262 | 23.6 | 6183.2 | 0 | 0 | 0 | 262 | 262 | 6183.2 | 6183.2
3383 | CONSTRUCTION WATER SUPPLY | 0 | Started | Labour | (L)WATER SUPPLY FOR CURING WORK | Per Month | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 15000 | 180000 | 5 | 15000 | 75000 | 12 | 7 | 0 | -75000
3384 | OTHER MISC.WORK | 0 | Started | Labour | (L)BOCW REG. & REN. CHARGE | NOS | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 5500 | 66000 | 12 | 5500 | 66000 | 12 | 0 | 0 | -66000
3385 | OTHER MISC.WORK | 0 | Started | Labour | (L)CORE CUTTING (B WING/INDENT-919) | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 16830 | 16830 | 1 | 16830 | 16830 | 1 | 0 | 0 | -16830
3386 | OTHER MISC.WORK | 0 | Started | Labour | (L)CORE CUTTING (C WING/INDENT-920) | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 810 | 810 | 1 | 810 | 810 | 1 | 0 | 0 | -810
3387 | OTHER MISC.WORK | 0 | Started | Labour | (L)DOOR STEP SCHOOL (APRIL-2024) | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5000 | 5000 | 1 | 5000 | 5000 | 1 | 0 | 0 | -5000
3388 | OTHER MISC.WORK | 0 | Started | Labour | (L)KHAYATEE STARTER | NOS | 1 | 4720 | 4720 | 0 | 0 | 0 | 0 | 4720 | 0 | 1 | 4720 | 4720 | 1 | 4720 | 4720 | 1 | 0 | 4720 | 0
3389 | OTHER MISC.WORK | 0 | Started | Labour | (L)LABOUR CAMP SEPTIC TANK WORK | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5500 | 5500 | 1 | 5500 | 5500 | 1 | 0 | 0 | -5500
3390 | OTHER MISC.WORK | 0 | Started | Labour | (L)LAWN CUTTING & CLEANING CHARGE | NOS | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 650 | 3900 | 6 | 650 | 3900 | 6 | 0 | 0 | -3900
3391 | OTHER MISC.WORK | 0 | Started | Labour | (L)OSIYAN PLUMBING MAINTANANCE WORK | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 6000 | 6000 | 1 | 6000 | 6000 | 1 | 0 | 0 | -6000
3392 | OTHER MISC.WORK | 0 | Started | Labour | (L)STEEL BINDIBG WORK | SQFT | 1049 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1049 | 3 | 3147 | 306 | 3 | 918 | 1049 | 743 | 0 | -918
3393 | OTHER MISC.WORK | 0 | Started | Labour | (L)STEEL SHIFTING WORK | NOS | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 600 | 4800 | 8 | 600 | 4800 | 8 | 0 | 0 | -4800
3394 | CLUB HOUSE WORK | 0 | Started | Labour | (L)CLUB HOUSE OPEN COURTYARD IPS WP | SQFT | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 15 | 2400 | 151 | 15 | 2265 | 160 | 9 | 0 | -2265
3395 | CLUB HOUSE WORK | 0 | Started | Labour | (L)CLUB HOUSE PATHWAY PCC WORK | SQFT | 1050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1050 | 10 | 10500 | 306 | 10 | 3060 | 1050 | 744 | 0 | -3060
3396 | CLUB HOUSE WORK | 0 | Started | Labour | (L)CLUB HOUSE SKIRTING-DPS | RFT | 285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 285 | 5 | 1425 | 285 | 5 | 1425 | 285 | 0 | 0 | -1425
3397 | CLUB HOUSE WORK | 0 | Started | Labour | (L)PCC BREAKING & COL.TOP CONC. | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1700 | 1700 | 1 | 1700 | 1700 | 1 | 0 | 0 | -1700
3398 | UGWT EXCAVATED & BREAKING LOOSE MURUM/SOIL REMOVING WORK | 0 | Started | Labour | (L)FC-LABOUR | NOS | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 350 | 5600 | 16 | 350 | 5600 | 16 | 0 | 0 | -5600
3399 | UGWT EXCAVATED & BREAKING LOOSE MURUM/SOIL REMOVING WORK | 0 | Started | Labour | (L)MC-LABOUR | NOS | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 450 | 6300 | 14 | 450 | 6300 | 14 | 0 | 0 | -6300
3400 | TRANSFORMER ROOM UPTO PLINTH MURUM FILLING | 0 | Started | Labour | (L)Murum Filling (Lab) | CFT | 1781.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1746.02 | 2.6 | 4539.652 | 1746.02 | 2.6 | 4539.65 | 1781.92 | 35.9 | 0 | -4539.65
3401 | ROW HOUSE-16,17 COMP.WALL BBM WORK | 0 | Started | Labour | (L)REPARING WORK (BBM & PLASTER) | NOS | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
3402 | ROW HOUSE-16 EXTERNAL PLASTER TOUCHUP WORK | 0 | Started | Labour | (L)REPARING WORK (BBM & PLASTER) | NOS | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 8000 | 8000 | 1 | 8000 | 8000 | 1 | 0 | 1 | -7999
3403 | C WING LGF PLASTER REPAIRING WORK | 0 | Started | Labour | (L)REPARING WORK (BBM & PLASTER) | NOS | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1700 | 1700 | 1 | 1700 | 1700 | 1 | 0 | 1 | -1699
3404 | C WING COLUMN CHHAT PLASTER FOR GYPSUM WORK | 0 | Started | Labour | (L)REPARING WORK (BBM & PLASTER) | NOS | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 3400 | 3400 | 1 | 3400 | 3400 | 1 | 0 | 1 | -3399
3405 | B BLDG PASSENGER LIFT DOOR WALL PLASTER | 0 | Started | Labour | (L)REPARING WORK (BBM & PLASTER) | NOS | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 2000 | 2000 | 1 | 2000 | 2000 | 1 | 0 | 1 | -1999
3406 | C BLDG LGF SHOP CLEANING WORK | 0 | Started | Labour | (L)REPARING WORK (BBM & PLASTER) | NOS | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 2250 | 2250 | 1 | 2250 | 2250 | 1 | 0 | 1 | -2249
3407 | C BLDG FLOOR CLEANING WORK | 0 | Started | Labour | (L)MISC.CLEANING WORK | NOS | 8 | 875 | 7000 | 0 | 0 | 0 | 0 | 875 | 0 | 8 | 875 | 7000 | 8 | 875 | 7000 | 8 | 0 | 7000 | 0
3408 | 24 AVENUE LOGO MAINTANANCE WORK | 0 | Started | Labour | (L)22 WATT TUBE LIGHT REPLACE | NOS | 7 | 188.8 | 1321.6 | 0 | 0 | 0 | 0 | 188.8 | 0 | 7 | 188.8 | 1321.6 | 7 | 188.8 | 1321.6 | 7 | 0 | 1321.6 | 0
3409 | 24 AVENUE LOGO MAINTANANCE WORK | 0 | Started | Labour | (L)ACP BOARD REPAIR & MAINTANANCE WORK | NOS | 1 | 590 | 590 | 0 | 0 | 0 | 0 | 590 | 0 | 1 | 590 | 590 | 1 | 590 | 590 | 1 | 0 | 590 | 0
3410 | 24 AVENUE LOGO MAINTANANCE WORK | 0 | Started | Labour | (L)LED ADAPTER 400WT | NOS | 1 | 1416 | 1416 | 0 | 0 | 0 | 0 | 1416 | 0 | 1 | 1416 | 1416 | 1 | 1416 | 1416 | 1 | 0 | 1416 | 0
3411 | CONCRETE MIX DESIGN | 0 | Started | Labour | (L)Conven. Mix Design M25 (With Admixture) | NOS | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 7080 | 7080 | 0 | 0 | 0 | 1 | 1 | 0 | 0
3412 | CONCRETE MIX DESIGN | 0 | Started | Labour | (L)Conven. Mix Design M25 (Without Admix.) | NOS | 1 | 7080 | 7080 | 0 | 0 | 0 | 0 | 7080 | 0 | 1 | 7080 | 7080 | 1 | 7080 | 7080 | 1 | 0 | 7080 | 0
3413 | CONCRETE MIX DESIGN | 0 | Started | Labour | (L)Conven. Mix Design M30 (Without Admix.) | NOS | 1 | 7080 | 7080 | 0 | 0 | 0 | 0 | 7080 | 0 | 1 | 7080 | 7080 | 0 | 0 | 0 | 1 | 1 | 7080 | 7080
3414 | CONCRETE MIX DESIGN | 0 | Started | Labour | (L)Testing Of Material For Mix Design | NOS | 1 | 4425 | 4425 | 0 | 0 | 0 | 0 | 4425 | 0 | 1 | 4425 | 4425 | 0 | 0 | 0 | 1 | 1 | 4425 | 4425
3415 | 24 AVENUE SITE SAFETY MATERIAL | 0 | Started | Material | (M)FIRST AID BOX as Per BOCW | BOX | 1 | 8496 | 8496 | 1 | 8496 | 8496 | 0 | 8496 | 0 | 1 | 8496 | 8496 | 0 | 0 | 0 | 1 | 1 | 8496 | 8496
3416 | 24 AVENUE SITE SAFETY MATERIAL | 0 | Started | Material | (M)Safety Belt Double lanyard with shocker | SET | 15 | 1652 | 24780 | 15 | 1652 | 24780 | 0 | 1652 | 0 | 5 | 1624 | 8120 | 0 | 0 | 0 | 15 | 15 | 24780 | 24780
3417 | INDENT-79/A,B & C WING ELECTRICAL SUPPLY LINE | 0 | Started | Material | (M)INDUSTRIAL PIN TOP | NOS | 36 | 141.6 | 5097.6 | 36 | 141.6 | 5097.6 | 0 | 141.6 | 0 | 36 | 96.76 | 3483.36 | 0 | 0 | 0 | 36 | 36 | 5097.6 | 5097.6
3418 | INDENT-79/A,B & C WING ELECTRICAL SUPPLY LINE | 0 | Started | Material | (M)POWER SUPPLY PANEL WITH INDUSRIAL SOCKET & RCCB | NOS | 21 | 6041.6 | 126873.6 | 21 | 6041.6 | 126873.6 | 0 | 6041.6 | 0 | 21 | 6041.6 | 126873.6 | 0 | 0 | 0 | 21 | 21 | 126873.6 | 126873.6
3419 | OSIYAN G.F TOILET & SALES OFFICE CP FITTING (MAINTANANCE WOR | 0 | Started | Material | (M)Angle Cock | NOS | 1 | 1239 | 1239 | 1 | 1239 | 1239 | 0 | 1239 | 0 | 1 | 259.6 | 259.6 | 0 | 0 | 0 | 1 | 1 | 1239 | 1239
3420 | OSIYAN G.F TOILET & SALES OFFICE CP FITTING (MAINTANANCE WOR | 0 | Started | Material | (M)CP Health Faucet | NOS | 2 | 631.4 | 1262.8 | 2 | 631.4 | 1262.8 | 0 | 631.4 | 0 | 2 | 566.4 | 1132.8 | 0 | 0 | 0 | 2 | 2 | 1262.8 | 1262.8
3421 | OSIYAN G.F TOILET & SALES OFFICE CP FITTING (MAINTANANCE WOR | 0 | Started | Material | (M)CP Pillar Cock (DLX-CHR-508KN) | NOS | 1 | 1025 | 1025 | 1 | 1025 | 1025 | 0 | 1025 | 0 | 1 | 531 | 531 | 0 | 0 | 0 | 1 | 1 | 1025 | 1025
3422 | OSIYAN G.F TOILET & SALES OFFICE CP FITTING (MAINTANANCE WOR | 0 | Started | Material | (M)Inlet Pipe - 1/2'' (Long-24") | NOS | 1 | 283.2 | 283.2 | 1 | 283.2 | 283.2 | 0 | 283.2 | 0 | 1 | 94.4 | 94.4 | 0 | 0 | 0 | 1 | 1 | 283.2 | 283.2
3423 | OSIYAN G.F TOILET & SALES OFFICE CP FITTING (MAINTANANCE WOR | 0 | Started | Material | (M)PVC Waste / Fiexible Pipe | NOS | 2 | 141.6 | 283.2 | 2 | 141.6 | 283.2 | 0 | 141.6 | 0 | 2 | 47.2 | 94.4 | 0 | 0 | 0 | 2 | 2 | 283.2 | 283.2
3424 | OSIYAN G.F TOILET & SALES OFFICE CP FITTING (MAINTANANCE WOR | 0 | Started | Material | (M)Teflon Tape | NOS | 2 | 19.48 | 38.96 | 2 | 19.48 | 38.96 | 0 | 19.48 | 0 | 2 | 23.6 | 47.2 | 0 | 0 | 0 | 2 | 2 | 38.96 | 38.96
3425 | INDENT-131/MISC.WORK & SAFETY WORK MATERIAL | 0 | Started | Material | (M)Caution Barricade Tape 250mtr | BUNDLE | 20 | 354 | 7080 | 20 | 354 | 7080 | 0 | 354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 7080 | 7080
3426 | INDENT-131/MISC.WORK & SAFETY WORK MATERIAL | 0 | Started | Material | (M)Insulation Tape | NOS | 30 | 11.8 | 354 | 30 | 11.8 | 354 | 0 | 11.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 354 | 354
3427 | INDENT-131/MISC.WORK & SAFETY WORK MATERIAL | 0 | Started | Material | (M)MYK Arment Armgrout Hf (Bar Reba.chem.) | KG | 5 | 354 | 1770 | 5 | 354 | 1770 | 0 | 354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 1770 | 1770
3428 | INDENT-131/MISC.WORK & SAFETY WORK MATERIAL | 0 | Started | Material | (M)Waterproof Tape (Cable Jointing) | NOS | 20 | 23.6 | 472 | 20 | 23.6 | 472 | 0 | 23.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 472 | 472
3429 | OTHER MATERIAL-24 AVENUE SITE SAFETY MATERIAL | 0 | Started | Material | (M)12MM SAFETY ROPE (PP ROPE) | KG | 15 | 500 | 7500 | 15 | 500 | 7500 | 0 | 500 | 0 | 1 | 212.4 | 212.4 | 0 | 0 | 0 | 15 | 15 | 7500 | 7500
3430 | OTHER MATERIAL-24 AVENUE SITE SAFETY MATERIAL | 0 | Started | Material | (M)5 kg Ceiling Mounted Fire Extinguisher | NOS | 2 | 5900 | 11800 | 0 | 0 | 0 | 0 | 5900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 11800 | 11800
3431 | OTHER MATERIAL-24 AVENUE SITE SAFETY MATERIAL | 0 | Started | Material | (M)8 Number Safety Shoes | NOS | 1 | 932.2 | 932.2 | 1 | 932.2 | 932.2 | 0 | 932.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 932.2 | 932.2
3432 | OTHER MATERIAL-24 AVENUE SITE SAFETY MATERIAL | 0 | Started | Material | (M)ABC Powder Type Fire Extinguisher-6Kg | NOS | 10 | 1888 | 18880 | 10 | 1888 | 18880 | 0 | 1888 | 0 | 1 | 1711 | 1711 | 0 | 0 | 0 | 10 | 10 | 18880 | 18880
3433 | OTHER MATERIAL-24 AVENUE SITE SAFETY MATERIAL | 0 | Started | Material | (M)CO2 Type Fire Extinguiser-4.5 KG | NOS | 5 | 4720 | 23600 | 5 | 4720 | 23600 | 0 | 4720 | 0 | 1 | 4366 | 4366 | 0 | 0 | 0 | 5 | 5 | 23600 | 23600
3434 | OTHER MATERIAL-24 AVENUE SITE SAFETY MATERIAL | 0 | Started | Material | (M)CONSTRUCTION NOSE MASK - HEAVY QUALITY | NOS | 1 | 50 | 50 | 1 | 50 | 50 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 50 | 50
3435 | OTHER MATERIAL-24 AVENUE SITE SAFETY MATERIAL | 0 | Started | Material | (M)Cotton Hand Gloves | NOS | 5 | 30 | 150 | 5 | 30 | 150 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 150 | 150
3436 | OTHER MATERIAL-24 AVENUE SITE SAFETY MATERIAL | 0 | Started | Material | (M)EAR PLUG (BOTH EAR) | NOS | 10 | 118 | 1180 | 10 | 118 | 1180 | 0 | 118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 1180 | 1180
3437 | OTHER MATERIAL-24 AVENUE SITE SAFETY MATERIAL | 0 | Started | Material | (M)Fall Arrester Fall Protection 16 MM - | NOS | 1 | 1180 | 1180 | 1 | 1180 | 1180 | 0 | 1180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1180 | 1180
3438 | OTHER MATERIAL-24 AVENUE SITE SAFETY MATERIAL | 0 | Started | Material | (M)FIRE BUCKET WITH STAND | NOS | 2 | 1000 | 2000 | 2 | 1000 | 2000 | 0 | 1000 | 0 | 2 | 224.2 | 448.4 | 0 | 0 | 0 | 2 | 2 | 2000 | 2000
3439 | OTHER MATERIAL-24 AVENUE SITE SAFETY MATERIAL | 0 | Started | Material | (M)Gumboot | NOS | 1 | 200 | 200 | 1 | 200 | 200 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 200 | 200
3440 | OTHER MATERIAL-24 AVENUE SITE SAFETY MATERIAL | 0 | Started | Material | (M)HANDGROVES -LEATHER( ELECTRICAL) | Pair | 2 | 200 | 400 | 2 | 200 | 400 | 0 | 200 | 0 | 2 | 367.5 | 735 | 0 | 0 | 0 | 2 | 2 | 400 | 400
3441 | OTHER MATERIAL-24 AVENUE SITE SAFETY MATERIAL | 0 | Started | Material | (M)MEGAPHONE SIREN-RED COLOUR | NOS | 1 | 1416 | 1416 | 1 | 1416 | 1416 | 0 | 1416 | 0 | 1 | 1534 | 1534 | 0 | 0 | 0 | 1 | 1 | 1416 | 1416
3442 | OTHER MATERIAL-24 AVENUE SITE SAFETY MATERIAL | 0 | Started | Material | (M)MULTI POINT PLUG SOCKET (INDUSTRIAL) | NOS | 1 | 118 | 118 | 1 | 118 | 118 | 0 | 118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 118 | 118
3443 | OTHER MATERIAL-24 AVENUE SITE SAFETY MATERIAL | 0 | Started | Material | (M)POLYAMIDE ROPE FOR FALL ARRESTER | RMT | 60 | 30 | 1800 | 60 | 30 | 1800 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 60 | 1800 | 1800
3444 | OTHER MATERIAL-24 AVENUE SITE SAFETY MATERIAL | 0 | Started | Material | (M)REFLECTIVE JACKET- GREEN | NOS | 1 | 200 | 200 | 1 | 200 | 200 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 200 | 200
3445 | OTHER MATERIAL-24 AVENUE SITE SAFETY MATERIAL | 0 | Started | Material | (M)REFLECTIVE JACKET- ORANGE | NOS | 1 | 200 | 200 | 1 | 200 | 200 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 200 | 200
3446 | OTHER MATERIAL-24 AVENUE SITE SAFETY MATERIAL | 0 | Started | Material | (M)RUBBER MAT - 1mtr X 1mtr | NOS | 6 | 1180 | 7080 | 6 | 1180 | 7080 | 0 | 1180 | 0 | 6 | 767 | 4602 | 0 | 0 | 0 | 6 | 6 | 7080 | 7080
3447 | OTHER MATERIAL-24 AVENUE SITE SAFETY MATERIAL | 0 | Started | Material | (M)Safety Goggles (Clear) | NOS | 2 | 100 | 200 | 2 | 100 | 200 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 200 | 200
3448 | OTHER MATERIAL-24 AVENUE SITE SAFETY MATERIAL | 0 | Started | Material | (M)Safety Goggles (Welding) | NOS | 2 | 100 | 200 | 2 | 100 | 200 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 200 | 200
3449 | OTHER MATERIAL-24 AVENUE SITE SAFETY MATERIAL | 0 | Started | Material | (M)SAFETY HELMATE- BLUE | NOS | 1 | 80 | 80 | 1 | 80 | 80 | 0 | 80 | 0 | 1 | 218.4 | 218.4 | 0 | 0 | 0 | 1 | 1 | 80 | 80
3450 | OTHER MATERIAL-24 AVENUE SITE SAFETY MATERIAL | 0 | Started | Material | (M)SAFETY HELMATE- GREEN | NOS | 1 | 80 | 80 | 1 | 80 | 80 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 80 | 80
3451 | OTHER MATERIAL-24 AVENUE SITE SAFETY MATERIAL | 0 | Started | Material | (M)SAFETY HELMATE- GREY /BLACK | NOS | 1 | 80 | 80 | 1 | 80 | 80 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 80 | 80
3452 | OTHER MATERIAL-24 AVENUE SITE SAFETY MATERIAL | 0 | Started | Material | (M)SAFETY HELMATE- PURPLE | NOS | 1 | 80 | 80 | 1 | 80 | 80 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 80 | 80
3453 | OTHER MATERIAL-24 AVENUE SITE SAFETY MATERIAL | 0 | Started | Material | (M)SAFETY HELMATE- RED | NOS | 1 | 100 | 100 | 1 | 100 | 100 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 100 | 100
3454 | OTHER MATERIAL-24 AVENUE SITE SAFETY MATERIAL | 0 | Started | Material | (M)SAFETY HELMATE-ORANGE COLOUR | NOS | 4 | 413 | 1652 | 4 | 413 | 1652 | 0 | 413 | 0 | 4 | 168 | 672 | 0 | 0 | 0 | 4 | 4 | 1652 | 1652
3455 | OTHER MATERIAL-24 AVENUE SITE SAFETY MATERIAL | 0 | Started | Material | (M)SAFETY HELMATE-WHITE COLOUR | NOS | 2 | 413 | 826 | 2 | 413 | 826 | 0 | 413 | 0 | 2 | 126 | 252 | 0 | 0 | 0 | 2 | 2 | 826 | 826
3456 | OTHER MATERIAL-24 AVENUE SITE SAFETY MATERIAL | 0 | Started | Material | (M)SAFETY HELMATE-YELLOW COLOUR | NOS | 5 | 212.4 | 1062 | 5 | 212.4 | 1062 | 0 | 212.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 1062 | 1062
3457 | OTHER MATERIAL-24 AVENUE SITE SAFETY MATERIAL | 0 | Started | Material | (M)Safety Mannequin Male with all safety Accessories | NOS | 1 | 8000 | 8000 | 1 | 8000 | 8000 | 0 | 8000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 8000 | 8000
3458 | OTHER MATERIAL-24 AVENUE SITE SAFETY MATERIAL | 0 | Started | Material | (M)SHOULDER PADS FOR STEEL SHIFTING | NOS | 5 | 50 | 250 | 5 | 50 | 250 | 0 | 50 | 0 | 5 | 126 | 630 | 0 | 0 | 0 | 5 | 5 | 250 | 250
3459 | OTHER MATERIAL-24 AVENUE SITE SAFETY MATERIAL | 0 | Started | Material | (M)SINGLE FOLDING MS STRETCHER | NOS | 1 | 1888 | 1888 | 1 | 1888 | 1888 | 0 | 1888 | 0 | 1 | 2513.4 | 2513.4 | 0 | 0 | 0 | 1 | 1 | 1888 | 1888
3460 | OTHER MATERIAL-24 AVENUE SITE SAFETY MATERIAL | 0 | Started | Material | (M)WELDING - APRON - BEST QUALITY | NOS | 1 | 880 | 880 | 0 | 0 | 0 | 0 | 880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 880 | 880
3461 | OTHER MATERIAL-24 AVENUE SITE SAFETY MATERIAL | 0 | Started | Material | (M)WELDING BLANKET | NOS | 2 | 1000 | 2000 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2000 | 2000
3462 | OTHER MATERIAL-24 AVENUE SITE SAFETY MATERIAL | 0 | Started | Material | (M)WELDING FACE SHIELD | NOS | 1 | 500 | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 500 | 500
3463 | SAFETY SHOES & JACKET FOR ENGG. STAFF-24 AVENUE | 0 | Started | Material | (M)10 Number Safety Shoes | NOS | 1 | 973.5 | 973.5 | 1 | 973.5 | 973.5 | 0 | 973.5 | 0 | 1 | 973.5 | 973.5 | 0 | 0 | 0 | 1 | 1 | 973.5 | 973.5
3464 | SAFETY SHOES & JACKET FOR ENGG. STAFF-24 AVENUE | 0 | Started | Material | (M)7 Number Safety Shoes | NOS | 1 | 932.2 | 932.2 | 1 | 932.2 | 932.2 | 0 | 932.2 | 0 | 1 | 932.2 | 932.2 | 0 | 0 | 0 | 1 | 1 | 932.2 | 932.2
3465 | SAFETY SHOES & JACKET FOR ENGG. STAFF-24 AVENUE | 0 | Started | Material | (M)8 Number Safety Shoes | NOS | 2 | 932.2 | 1864.4 | 2 | 932.2 | 1864.4 | 0 | 932.2 | 0 | 2 | 932.2 | 1864.4 | 0 | 0 | 0 | 2 | 2 | 1864.4 | 1864.4
3466 | SAFETY SHOES & JACKET FOR ENGG. STAFF-24 AVENUE | 0 | Started | Material | (M)9 Number Safety Shoes | NOS | 2 | 944 | 1888 | 2 | 944 | 1888 | 0 | 944 | 0 | 2 | 944 | 1888 | 0 | 0 | 0 | 2 | 2 | 1888 | 1888
3467 | SAFETY SHOES & JACKET FOR ENGG. STAFF-24 AVENUE | 0 | Started | Material | (M)Safety Jacket | NOS | 12 | 177 | 2124 | 12 | 177 | 2124 | 0 | 177 | 0 | 12 | 177 | 2124 | 0 | 0 | 0 | 12 | 12 | 2124 | 2124
3468 | DESTINATION 24 AVENUE SITE - SAFETY SIGNAGE BOARD | 0 | Started | Labour | (L)A4-ECO WITH 5MM FOAM SHEET | NOS | 2 | 80 | 160 | 0 | 0 | 0 | 0 | 80 | 0 | 2 | 80 | 160 | 2 | 80 | 160 | 2 | 0 | 160 | 0
3469 | DESTINATION 24 AVENUE SITE - SAFETY SIGNAGE BOARD | 0 | Started | Labour | (L)FLEX BOARD FOR SAFETY-2'0'' X 3'0'' | NOS | 48 | 130 | 6240 | 0 | 0 | 0 | 0 | 130 | 0 | 48 | 130 | 6240 | 48 | 130 | 6240 | 48 | 0 | 6240 | 0
3470 | DESTINATION 24 AVENUE SITE - SAFETY SIGNAGE BOARD | 0 | Started | Labour | (L)FLEX BOARD SAFETY PARK-6'0'' X 8'0'' | NOS | 1 | 576 | 576 | 0 | 0 | 0 | 0 | 576 | 0 | 1 | 576 | 576 | 1 | 576 | 576 | 1 | 0 | 576 | 0
3471 | DESTINATION 24 AVENUE - SALES OFFICE CHAIRS | 0 | Tentative | Material | (M)Honda Revolving Chair | NOS | 17 | 3776 | 64192 | 17 | 3776 | 64192 | 0 | 3776 | 0 | 17 | 3776 | 64192 | 0 | 0 | 0 | 17 | 17 | 64192 | 64192
3472 | FIVE STAR AAC BLOCK LABORATORY TEST | 0 | Started | Labour | (L)Compressive Test | NOS | 12 | 289.1 | 3469.2 | 0 | 0 | 0 | 0 | 289.1 | 0 | 12 | 289.1 | 3469.2 | 0 | 0 | 0 | 12 | 12 | 3469.2 | 3469.2
3473 | FIVE STAR AAC BLOCK LABORATORY TEST | 0 | Started | Labour | (L)Density Test | NOS | 3 | 289.1 | 867.3 | 0 | 0 | 0 | 0 | 289.1 | 0 | 3 | 289.1 | 867.3 | 0 | 0 | 0 | 3 | 3 | 867.3 | 867.3
3474 | FIVE STAR AAC BLOCK LABORATORY TEST | 0 | Started | Labour | (L)Sample Preparation Charge | NOS | 1 | 1180 | 1180 | 0 | 0 | 0 | 0 | 1180 | 0 | 1 | 1180 | 1180 | 0 | 0 | 0 | 1 | 1 | 1180 | 1180
3475 | A,B,C & DEVELOPEMENT CURING WORK (PIPE) | 0 | Started | Material | (M)Curing Pipe 3/4" 30mtr Nylon Braided | NOS | 5 | 1947 | 9735 | 5 | 1947 | 9735 | 0 | 1947 | 0 | 5 | 944 | 4720 | 0 | 0 | 0 | 5 | 5 | 9735 | 9735
3476 | DEVELOPEMENT-STP & UGWT TANK DEWATERING WORK | 0 | Started | Material | (M)CONNECTOR SOCEKT 2'' (HOSE PIPE) | NOS | 3 | 50 | 150 | 3 | 50 | 150 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 150 | 150
3477 | DEVELOPEMENT-STP & UGWT TANK DEWATERING WORK | 0 | Started | Material | (M)COTTON HOSE PIPE 2'' x 30 mtr | BUNDLE | 1 | 3500 | 3500 | 1 | 3500 | 3500 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3500 | 3500
3478 | DEVELOPEMENT-STP & UGWT TANK DEWATERING WORK | 0 | Started | Material | (M)COTTON HOSE PIPE 3'' x 30 MTR | BUNDLE | 4 | 4720 | 18880 | 4 | 4720 | 18880 | 0 | 4720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 18880 | 18880
3479 | BORE WELL (B-BLDG BACK SIDE) DEVELOPEMENT | 0 | Tentative | Material | (M)Flexible Cable 2.5 sq.mm x 3 core (FLAT CABLE) | RMT | 92 | 118 | 10856 | 92 | 118 | 10856 | 0 | 118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 92 | 10856 | 10856
3480 | BORE WELL (B-BLDG BACK SIDE) DEVELOPEMENT | 0 | Tentative | Material | (M)HDPE Pipes (PE-100/ PN-10) OD-50 mm - 1 1/2" | RMT | 92 | 123.9 | 11398.8 | 92 | 123.9 | 11398.8 | 0 | 123.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 92 | 11398.8 | 11398.8
3481 | BORE WELL (B-BLDG BACK SIDE) DEVELOPEMENT | 0 | Tentative | Material | (M)SINGLE PHASE STARTER 2HP (AUTOMATIC) | NOS | 1 | 2360 | 2360 | 1 | 2360 | 2360 | 0 | 2360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2360 | 2360
3482 | DEVELOPEMENT & C BLDG - HALOGEN FOR SITE USE-AT NIGHT WORK | 0 | Tentative | Material | (M)Aluminium Flexible Cable 2.5 sq.mm x 2 core | RMT | 300 | 47.2 | 14160 | 300 | 47.2 | 14160 | 0 | 47.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 300 | 14160 | 14160
3483 | DEVELOPEMENT & C BLDG - HALOGEN FOR SITE USE-AT NIGHT WORK | 0 | Tentative | Material | (M)LED Halogen light - 150Watt | NOS | 7 | 2950 | 20650 | 7 | 2950 | 20650 | 0 | 2950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 20650 | 20650
3484 | A BLDG EXTERNAL PLASTER (B WING COVERING PURPOSE) | 0 | Tentative | Material | (M)Green Shed Net (ROLL SIZE-1.5M X 50M) | SQFT | 10500 | 4.13 | 43365 | 10500 | 4.13 | 43365 | 0 | 4.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10500 | 10500 | 43365 | 43365
3485 | OSIYAN MAIN GATE FABRICATION WORK-ADVANCED_60% | 0 | Started | Labour | (L)FABRICATION WORK (MATERIAL + LABOUR) | NOS | 1 | 130887.6 | 130887.6 | 0 | 0 | 0 | 0 | 130887.6 | 0 | 1 | 130887.6 | 130887.6 | 1 | 130887.6 | 130887.6 | 1 | 0 | 130887.6 | 0
3486 | OSIYAN MAIN GATE FABRICATION WORK-AFTER COMP.OF WORK_40% | 0 | Tentative | Labour | (L)FABRICATION WORK (MATERIAL + LABOUR) | NOS | 1 | 130887.6 | 130887.6 | 0 | 0 | 0 | 0 | 130887.6 | 0 | 1 | 87258.4 | 87258.4 | 0 | 0 | 0 | 1 | 1 | 130887.6 | 130887.6
3487 | Project Management Consultant Service Fee (Dest. 24 Avenue) | 0 | Started | Labour | (L)24 Avenue Ploting | NOS | 1 | 944000 | 944000 | 0 | 0 | 0 | 0 | 944000 | 0 | 1 | 944000 | 944000 | 0 | 0 | 0 | 1 | 1 | 944000 | 944000
3488 | Project Management Consultant Service Fee (Dest. 24 Avenue) | 0 | Started | Labour | (L)Consultancy Charges | Per Month | 36 | 204754.78 | 7371172.08 | 0 | 0 | 0 | 0 | 204754.78 | 0 | 36 | 204754.78 | 7371172.08 | 1 | 204754.78 | 204754.78 | 36 | 35 | 7371172.08 | 7166417.3
3489 | Project Management Consultant Ser.Fee A-Bldg | 0 | Started | Labour | (L)Consultancy Charges | Per Month | 18 | 204754.78 | 3685586.04 | 0 | 0 | 0 | 0 | 204754.78 | 0 | 18 | 83008 | 1494144 | 1 | 83008 | 83008 | 18 | 17 | 3685586.04 | 3602578.04
3490 | Project Management Consultant Ser.Fee -A Bldg | 0 | Started | Labour | (L)Consultancy Charges | Per Month | 6 | 204754.78 | 1228528.68 | 0 | 0 | 0 | 0 | 204754.78 | 0 | 6 | 124512 | 747072 | 0 | 0 | 0 | 6 | 6 | 1228528.68 | 1228528.68
3491 | CQRA HEALTH SAFETY & ENVIRONMENT (HSE) WORK | 0 | Started | Labour | (L)SITE SAFETY MONITORING | Month. | 12 | 115640 | 1387680 | 0 | 0 | 0 | 0 | 115640 | 0 | 12 | 115640 | 1387680 | 6 | 115640 | 693840 | 12 | 6 | 1387680 | 693840
3492 | CQRA QUALITY ASSURANCE/QUALITY CONTROL (QA/QC) WORK | 0 | Started | Labour | (L)CONSTRUCTION QUALITY MONITORING | Month. | 12 | 82600 | 991200 | 0 | 0 | 0 | 0 | 82600 | 0 | 12 | 165200 | 1982400 | 6 | 165200 | 991200 | 12 | 6 | 991200 | 0
3493 | A BLDG: RCC CONSULTANCY FEE | 0 | Tentative | Labour | (L)STAGE-1, ADVANCE-10% | SQFT | 7172.8 | 5.9 | 42319.52 | 0 | 0 | 0 | 0 | 5.9 | 0 | 7172.8 | 5.9 | 42319.52 | 0 | 0 | 0 | 7172.8 | 7172.8 | 42319.52 | 42319.52
3494 | A BLDG: RCC CONSULTANCY FEE | 0 | Tentative | Labour | (L)STAGE-2, FINAL OF FRAMING-30% | SQFT | 21518.4 | 5.9 | 126958.56 | 0 | 0 | 0 | 0 | 5.9 | 0 | 21518.4 | 5.9 | 126958.56 | 0 | 0 | 0 | 21518.4 | 21518.4 | 126958.56 | 126958.56
3495 | A BLDG: RCC CONSULTANCY FEE | 0 | Tentative | Labour | (L)STAGE-3, COMP. OF DESIGN DRAWING-30% | SQFT | 21518.4 | 5.9 | 126958.56 | 0 | 0 | 0 | 0 | 5.9 | 0 | 21518.4 | 5.9 | 126958.56 | 0 | 0 | 0 | 21518.4 | 21518.4 | 126958.56 | 126958.56
3496 | A BLDG: RCC CONSULTANCY FEE | 0 | Tentative | Labour | (L)STAGE-4, AGAINST PRO RATA OF WORK-25% | SQFT | 17932 | 5.9 | 105798.8 | 0 | 0 | 0 | 0 | 5.9 | 0 | 17932 | 5.9 | 105798.8 | 0 | 0 | 0 | 17932 | 17932 | 105798.8 | 105798.8
3497 | A BLDG: RCC CONSULTANCY FEE | 0 | Tentative | Labour | (L)STAGE-5, AGAINST COMP. OF STRUCTUR-5% | SQFT | 3586.4 | 5.9 | 21159.76 | 0 | 0 | 0 | 0 | 5.9 | 0 | 3586.4 | 5.9 | 21159.76 | 0 | 0 | 0 | 3586.4 | 3586.4 | 21159.76 | 21159.76
3498 | B BLDG: RCC CONSULTANCY FEE | 0 | Tentative | Labour | (L)STAGE-1, ADVANCE-10% | SQFT | 12119.2 | 5.9 | 71503.28 | 0 | 0 | 0 | 0 | 5.9 | 0 | 12119.2 | 5.9 | 71503.28 | 0 | 0 | 0 | 12119.2 | 12119.2 | 71503.28 | 71503.28
3499 | B BLDG: RCC CONSULTANCY FEE | 0 | Tentative | Labour | (L)STAGE-2, FINAL OF FRAMING-30% | SQFT | 36357.6 | 5.9 | 214509.84 | 0 | 0 | 0 | 0 | 5.9 | 0 | 36357.6 | 5.9 | 214509.84 | 0 | 0 | 0 | 36357.6 | 36357.6 | 214509.84 | 214509.84
3500 | B BLDG: RCC CONSULTANCY FEE | 0 | Tentative | Labour | (L)STAGE-3, COMP. OF DESIGN DRAWING-30% | SQFT | 36357.6 | 5.9 | 214509.84 | 0 | 0 | 0 | 0 | 5.9 | 0 | 36357.6 | 5.9 | 214509.84 | 0 | 0 | 0 | 36357.6 | 36357.6 | 214509.84 | 214509.84
3501 | B BLDG: RCC CONSULTANCY FEE | 0 | Tentative | Labour | (L)STAGE-4, AGAINST PRO RATA OF WORK-25% | SQFT | 30298 | 5.9 | 178758.2 | 0 | 0 | 0 | 0 | 5.9 | 0 | 30298 | 5.9 | 178758.2 | 0 | 0 | 0 | 30298 | 30298 | 178758.2 | 178758.2
3502 | B BLDG: RCC CONSULTANCY FEE | 0 | Tentative | Labour | (L)STAGE-5, AGAINST COMP. OF STRUCTUR-5% | SQFT | 6059.6 | 5.9 | 35751.64 | 0 | 0 | 0 | 0 | 5.9 | 0 | 6059.6 | 5.9 | 35751.64 | 0 | 0 | 0 | 6059.6 | 6059.6 | 35751.64 | 35751.64
3503 | C BLDG: RCC CONSULTANCY FEE | 0 | Tentative | Labour | (L)STAGE-1, ADVANCE-10% | SQFT | 8024.6 | 5.9 | 47345.14 | 0 | 0 | 0 | 0 | 5.9 | 0 | 8024.6 | 5.9 | 47345.14 | 0 | 0 | 0 | 8024.6 | 8024.6 | 47345.14 | 47345.14
3504 | C BLDG: RCC CONSULTANCY FEE | 0 | Tentative | Labour | (L)STAGE-2, FINAL OF FRAMING-30% | SQFT | 24073.8 | 5.9 | 142035.42 | 0 | 0 | 0 | 0 | 5.9 | 0 | 24073.8 | 5.9 | 142035.42 | 0 | 0 | 0 | 24073.8 | 24073.8 | 142035.42 | 142035.42
3505 | C BLDG: RCC CONSULTANCY FEE | 0 | Tentative | Labour | (L)STAGE-3, COMP. OF DESIGN DRAWING-30% | SQFT | 24073.8 | 5.9 | 142035.42 | 0 | 0 | 0 | 0 | 5.9 | 0 | 24073.8 | 5.9 | 142035.42 | 0 | 0 | 0 | 24073.8 | 24073.8 | 142035.42 | 142035.42
3506 | C BLDG: RCC CONSULTANCY FEE | 0 | Tentative | Labour | (L)STAGE-4, AGAINST PRO RATA OF WORK-25% | SQFT | 20061.5 | 5.9 | 118362.85 | 0 | 0 | 0 | 0 | 5.9 | 0 | 20061.5 | 5.9 | 118362.86 | 0 | 0 | 0 | 20061.5 | 20061.5 | 118362.85 | 118362.85
3507 | C BLDG: RCC CONSULTANCY FEE | 0 | Tentative | Labour | (L)STAGE-5, AGAINST COMP. OF STRUCTUR-5% | SQFT | 4012.3 | 5.9 | 23672.57 | 0 | 0 | 0 | 0 | 5.9 | 0 | 4012.3 | 5.9 | 23672.58 | 0 | 0 | 0 | 4012.3 | 4012.3 | 23672.57 | 23672.57
3508 | D BLDG: RCC CONSULTANCY FEE | 0 | Tentative | Labour | (L)STAGE-1, ADVANCE-10% | SQFT | 6530.8 | 5.9 | 38531.72 | 0 | 0 | 0 | 0 | 5.9 | 0 | 6530.8 | 5.9 | 38531.72 | 0 | 0 | 0 | 6530.8 | 6530.8 | 38531.72 | 38531.72
3509 | D BLDG: RCC CONSULTANCY FEE | 0 | Tentative | Labour | (L)STAGE-2, FINAL OF FRAMING-30% | SQFT | 19592.4 | 5.9 | 115595.16 | 0 | 0 | 0 | 0 | 5.9 | 0 | 19592.4 | 5.9 | 115595.16 | 0 | 0 | 0 | 19592.4 | 19592.4 | 115595.16 | 115595.16
3510 | D BLDG: RCC CONSULTANCY FEE | 0 | Tentative | Labour | (L)STAGE-3, COMP. OF DESIGN DRAWING-30% | SQFT | 19592.4 | 5.9 | 115595.16 | 0 | 0 | 0 | 0 | 5.9 | 0 | 19592.4 | 5.9 | 115595.16 | 0 | 0 | 0 | 19592.4 | 19592.4 | 115595.16 | 115595.16
3511 | D BLDG: RCC CONSULTANCY FEE | 0 | Tentative | Labour | (L)STAGE-4, AGAINST PRO RATA OF WORK-25% | SQFT | 16327 | 5.9 | 96329.3 | 0 | 0 | 0 | 0 | 5.9 | 0 | 16327 | 5.9 | 96329.3 | 0 | 0 | 0 | 16327 | 16327 | 96329.3 | 96329.3
3512 | D BLDG: RCC CONSULTANCY FEE | 0 | Tentative | Labour | (L)STAGE-5, AGAINST COMP. OF STRUCTUR-5% | SQFT | 3265.4 | 5.9 | 19265.86 | 0 | 0 | 0 | 0 | 5.9 | 0 | 3265.4 | 5.9 | 19265.86 | 0 | 0 | 0 | 3265.4 | 3265.4 | 19265.86 | 19265.86
3513 | E BLDG: RCC CONSULTANCY FEE | 0 | Tentative | Labour | (L)STAGE-1, ADVANCE-10% | SQFT | 4955.6 | 5.9 | 29238.04 | 0 | 0 | 0 | 0 | 5.9 | 0 | 4955.6 | 5.9 | 29238.04 | 0 | 0 | 0 | 4955.6 | 4955.6 | 29238.04 | 29238.04
3514 | E BLDG: RCC CONSULTANCY FEE | 0 | Tentative | Labour | (L)STAGE-2, FINAL OF FRAMING-30% | SQFT | 14866.8 | 5.9 | 87714.12 | 0 | 0 | 0 | 0 | 5.9 | 0 | 14866.8 | 5.9 | 87714.12 | 0 | 0 | 0 | 14866.8 | 14866.8 | 87714.12 | 87714.12
3515 | E BLDG: RCC CONSULTANCY FEE | 0 | Tentative | Labour | (L)STAGE-3, COMP. OF DESIGN DRAWING-30% | SQFT | 14866.8 | 5.9 | 87714.12 | 0 | 0 | 0 | 0 | 5.9 | 0 | 14866.8 | 5.9 | 87714.12 | 0 | 0 | 0 | 14866.8 | 14866.8 | 87714.12 | 87714.12
3516 | E BLDG: RCC CONSULTANCY FEE | 0 | Tentative | Labour | (L)STAGE-4, AGAINST PRO RATA OF WORK-25% | SQFT | 12389 | 5.9 | 73095.1 | 0 | 0 | 0 | 0 | 5.9 | 0 | 12389 | 5.9 | 73095.1 | 0 | 0 | 0 | 12389 | 12389 | 73095.1 | 73095.1
3517 | E BLDG: RCC CONSULTANCY FEE | 0 | Tentative | Labour | (L)STAGE-5, AGAINST COMP. OF STRUCTUR-5% | SQFT | 2477.8 | 5.9 | 14619.02 | 0 | 0 | 0 | 0 | 5.9 | 0 | 2477.8 | 5.9 | 14619.02 | 0 | 0 | 0 | 2477.8 | 2477.8 | 14619.02 | 14619.02
3518 | CLUB HOUSE: RCC CONSULTANCY FEE | 0 | Tentative | Labour | (L)STAGE-1, ADVANCE-10% | SQFT | 587 | 5.9 | 3463.3 | 0 | 0 | 0 | 0 | 5.9 | 0 | 587 | 5.9 | 3463.3 | 0 | 0 | 0 | 587 | 587 | 3463.3 | 3463.3
3519 | CLUB HOUSE: RCC CONSULTANCY FEE | 0 | Tentative | Labour | (L)STAGE-2, FINAL OF FRAMING-30% | SQFT | 1761 | 5.9 | 10389.9 | 0 | 0 | 0 | 0 | 5.9 | 0 | 1761 | 5.9 | 10389.9 | 0 | 0 | 0 | 1761 | 1761 | 10389.9 | 10389.9
3520 | CLUB HOUSE: RCC CONSULTANCY FEE | 0 | Tentative | Labour | (L)STAGE-3, COMP. OF DESIGN DRAWING-30% | SQFT | 1761 | 5.9 | 10389.9 | 0 | 0 | 0 | 0 | 5.9 | 0 | 1761 | 5.9 | 10389.9 | 0 | 0 | 0 | 1761 | 1761 | 10389.9 | 10389.9
3521 | CLUB HOUSE: RCC CONSULTANCY FEE | 0 | Tentative | Labour | (L)STAGE-4, AGAINST PRO RATA OF WORK-25% | SQFT | 1467.5 | 5.9 | 8658.25 | 0 | 0 | 0 | 0 | 5.9 | 0 | 1467.5 | 5.9 | 8658.26 | 0 | 0 | 0 | 1467.5 | 1467.5 | 8658.25 | 8658.25
3522 | CLUB HOUSE: RCC CONSULTANCY FEE | 0 | Tentative | Labour | (L)STAGE-5, AGAINST COMP. OF STRUCTUR-5% | SQFT | 293.5 | 5.9 | 1731.65 | 0 | 0 | 0 | 0 | 5.9 | 0 | 293.5 | 5.9 | 1731.66 | 0 | 0 | 0 | 293.5 | 293.5 | 1731.65 | 1731.65
3523 | PODIUM: RCC CONSULTANCY FEE | 0 | Started | Labour | (L)STAGE-1, ADVANCE-10% | SQFT | 3078.1 | 5.9 | 18160.79 | 0 | 0 | 0 | 0 | 5.9 | 0 | 3078.1 | 5.9 | 18160.8 | 3078.1 | 5.9 | 18160.8 | 3078.1 | 0 | 18160.79 | -0.01
3524 | PODIUM: RCC CONSULTANCY FEE | 0 | Started | Labour | (L)STAGE-2, FINAL OF FRAMING-30% | SQFT | 9234.3 | 5.9 | 54482.37 | 0 | 0 | 0 | 0 | 5.9 | 0 | 9234.3 | 5.9 | 54482.38 | 9234.3 | 5.9 | 54482.38 | 9234.3 | 0 | 54482.37 | -0.01
3525 | PODIUM: RCC CONSULTANCY FEE | 0 | Started | Labour | (L)STAGE-3, COMP. OF DESIGN DRAWING-30% | SQFT | 9234.3 | 5.9 | 54482.37 | 0 | 0 | 0 | 0 | 5.9 | 0 | 9234.3 | 5.9 | 54482.38 | 9234.3 | 5.9 | 54482.38 | 9234.3 | 0 | 54482.37 | -0.01
3526 | PODIUM: RCC CONSULTANCY FEE | 0 | Started | Labour | (L)STAGE-4, AGAINST PRO RATA OF WORK-25% | SQFT | 7695.25 | 5.9 | 45401.98 | 0 | 0 | 0 | 0 | 5.9 | 0 | 7695.25 | 5.9 | 45401.97 | 0 | 0 | 0 | 7695.25 | 7695.25 | 45401.975 | 45401.975
3527 | PODIUM: RCC CONSULTANCY FEE | 0 | Started | Labour | (L)STAGE-5, AGAINST COMP. OF STRUCTUR-5% | SQFT | 1539.05 | 5.9 | 9080.4 | 0 | 0 | 0 | 0 | 5.9 | 0 | 1539.05 | 5.9 | 9080.39 | 0 | 0 | 0 | 1539.05 | 1539.05 | 9080.395 | 9080.395
3528 | Advance-1 (as per work order Advance@10%) | 0 | Tentative | Labour | (L)Architects Fee | SQFT | 33871.162 | 17.7 | 599519.57 | 0 | 0 | 0 | 0 | 17.7 | 0 | 33871.162 | 17.7 | 599519.57 | 0 | 0 | 0 | 33871.162 | 33871.162 | 599519.567 | 599519.5674
3529 | Advance-2 (as per work order Advance@20%) | 0 | Tentative | Labour | (L)Architects Fee | SQFT | 67742.324 | 17.7 | 1199039.13 | 0 | 0 | 0 | 0 | 17.7 | 0 | 67742.324 | 17.7 | 1199039.14 | 0 | 0 | 0 | 67742.324 | 67742.324 | 1199039.135 | 1199039.1348
3530 | Stage-1 (June-22, July-22 & Aug-22) | 0 | Tentative | Labour | (L)Architects Fee | SQFT | 23709.8134 | 17.7 | 419663.7 | 0 | 0 | 0 | 0 | 17.7 | 0 | 23709.8134 | 17.7 | 419663.701 | 0 | 0 | 0 | 23709.8134 | 23709.8134 | 419663.697 | 419663.6972
3531 | Stage-2 (Sep-22) | 0 | Tentative | Labour | (L)Architects Fee | SQFT | 7903.2707 | 17.7 | 139887.89 | 0 | 0 | 0 | 0 | 17.7 | 0 | 7903.2707 | 17.7 | 139887.9005 | 0 | 0 | 0 | 7903.2707 | 7903.2707 | 139887.891 | 139887.8914
3532 | Stage-3 (Oct-22) | 0 | Tentative | Labour | (L)Architects Fee | SQFT | 7903.2707 | 17.7 | 139887.89 | 0 | 0 | 0 | 0 | 17.7 | 0 | 7903.2707 | 17.7 | 139887.9005 | 0 | 0 | 0 | 7903.2707 | 7903.2707 | 139887.891 | 139887.8914
3533 | Stage-4 (Nov-22) | 0 | Tentative | Labour | (L)Architects Fee | SQFT | 7903.2707 | 17.7 | 139887.89 | 0 | 0 | 0 | 0 | 17.7 | 0 | 7903.2707 | 17.7 | 139887.9005 | 0 | 0 | 0 | 7903.2707 | 7903.2707 | 139887.891 | 139887.8914
3534 | Stage-5 (Dec-22) | 0 | Tentative | Labour | (L)Architects Fee | SQFT | 7903.2707 | 17.7 | 139887.89 | 0 | 0 | 0 | 0 | 17.7 | 0 | 7903.2707 | 17.7 | 139887.9005 | 0 | 0 | 0 | 7903.2707 | 7903.2707 | 139887.891 | 139887.8914
3535 | Stage-6 (Jan-23) | 0 | Tentative | Labour | (L)Architects Fee | SQFT | 7903.2707 | 17.7 | 139887.89 | 0 | 0 | 0 | 0 | 17.7 | 0 | 7903.2707 | 17.7 | 139887.9005 | 0 | 0 | 0 | 7903.2707 | 7903.2707 | 139887.891 | 139887.8914
3536 | Stage-7 (Feb-23) | 0 | Tentative | Labour | (L)Architects Fee | SQFT | 7903.2707 | 17.7 | 139887.89 | 0 | 0 | 0 | 0 | 17.7 | 0 | 7903.2707 | 17.7 | 139887.9005 | 0 | 0 | 0 | 7903.2707 | 7903.2707 | 139887.891 | 139887.8914
3537 | Stage-8 (Mar-23) | 0 | Tentative | Labour | (L)Architects Fee | SQFT | 7903.2707 | 17.7 | 139887.89 | 0 | 0 | 0 | 0 | 17.7 | 0 | 7903.2707 | 17.7 | 139887.9005 | 0 | 0 | 0 | 7903.2707 | 7903.2707 | 139887.891 | 139887.8914
3538 | Stage-9 (April-23) | 0 | Tentative | Labour | (L)Architects Fee | SQFT | 7903.2707 | 17.7 | 139887.89 | 0 | 0 | 0 | 0 | 17.7 | 0 | 7903.2707 | 17.7 | 139887.9005 | 0 | 0 | 0 | 7903.2707 | 7903.2707 | 139887.891 | 139887.8914
3539 | Stage-10 (May-23) | 0 | Tentative | Labour | (L)Architects Fee | SQFT | 7903.2707 | 17.7 | 139887.89 | 0 | 0 | 0 | 0 | 17.7 | 0 | 7903.2707 | 17.7 | 139887.9005 | 0 | 0 | 0 | 7903.2707 | 7903.2707 | 139887.891 | 139887.8914
3540 | Stage-11 (June-23) | 0 | Tentative | Labour | (L)Architects Fee | SQFT | 7903.2707 | 17.7 | 139887.89 | 0 | 0 | 0 | 0 | 17.7 | 0 | 7903.2707 | 17.7 | 139887.9005 | 0 | 0 | 0 | 7903.2707 | 7903.2707 | 139887.891 | 139887.8914
3541 | Stage-12 (July-23) | 0 | Tentative | Labour | (L)Architects Fee | SQFT | 7903.2707 | 17.7 | 139887.89 | 0 | 0 | 0 | 0 | 17.7 | 0 | 7903.2707 | 17.7 | 139887.9005 | 0 | 0 | 0 | 7903.2707 | 7903.2707 | 139887.891 | 139887.8914
3542 | Stage-13 (Aug-23) | 0 | Tentative | Labour | (L)Architects Fee | SQFT | 7903.2707 | 17.7 | 139887.89 | 0 | 0 | 0 | 0 | 17.7 | 0 | 7903.2707 | 17.7 | 139887.9005 | 0 | 0 | 0 | 7903.2707 | 7903.2707 | 139887.891 | 139887.8914
3543 | Stage-14 (Sep-23) | 0 | Tentative | Labour | (L)Architects Fee | SQFT | 7903.2707 | 17.7 | 139887.89 | 0 | 0 | 0 | 0 | 17.7 | 0 | 7903.2707 | 17.7 | 139887.9005 | 0 | 0 | 0 | 7903.2707 | 7903.2707 | 139887.891 | 139887.8914
3544 | Stage-15 (Oct-23) | 0 | Tentative | Labour | (L)Architects Fee | SQFT | 7903.2707 | 17.7 | 139887.89 | 0 | 0 | 0 | 0 | 17.7 | 0 | 7903.2707 | 17.7 | 139887.9005 | 0 | 0 | 0 | 7903.2707 | 7903.2707 | 139887.891 | 139887.8914
3545 | Stage-16 (Nov-23) | 0 | Tentative | Labour | (L)Architects Fee | SQFT | 7903.2707 | 17.7 | 139887.89 | 0 | 0 | 0 | 0 | 17.7 | 0 | 7903.2707 | 17.7 | 139887.9005 | 0 | 0 | 0 | 7903.2707 | 7903.2707 | 139887.891 | 139887.8914
3546 | Stage-17 (Dec-23) | 0 | Tentative | Labour | (L)Architects Fee | SQFT | 7903.2707 | 17.7 | 139887.89 | 0 | 0 | 0 | 0 | 17.7 | 0 | 7903.2707 | 17.7 | 139887.9005 | 0 | 0 | 0 | 7903.2707 | 7903.2707 | 139887.891 | 139887.8914
3547 | Stage-18 (Jan-24) | 0 | Tentative | Labour | (L)Architects Fee | SQFT | 7903.2707 | 17.7 | 139887.89 | 0 | 0 | 0 | 0 | 17.7 | 0 | 7903.2707 | 17.7 | 139887.9005 | 0 | 0 | 0 | 7903.2707 | 7903.2707 | 139887.891 | 139887.8914
3548 | Stage-19 (Feb-24) | 0 | Tentative | Labour | (L)Architects Fee | SQFT | 7903.2707 | 17.7 | 139887.89 | 0 | 0 | 0 | 0 | 17.7 | 0 | 7903.2707 | 17.7 | 139887.9005 | 0 | 0 | 0 | 7903.2707 | 7903.2707 | 139887.891 | 139887.8914
3549 | Stage-20 (Mar-24) | 0 | Tentative | Labour | (L)Architects Fee | SQFT | 7903.2707 | 17.7 | 139887.89 | 0 | 0 | 0 | 0 | 17.7 | 0 | 7903.2707 | 17.7 | 139887.9005 | 0 | 0 | 0 | 7903.2707 | 7903.2707 | 139887.891 | 139887.8914
3550 | Stage-21 (Apr-24) | 0 | Started | Labour | (L)Architects Fee | SQFT | 7903.2707 | 17.7 | 139887.89 | 0 | 0 | 0 | 0 | 17.7 | 0 | 7903.2707 | 17.7 | 139887.9005 | 7903.2707 | 17.7 | 139887.9 | 7903.2707 | 0 | 139887.891 | -0.0086
3551 | Stage-22 (May-24) | 0 | Started | Labour | (L)Architects Fee | SQFT | 7903.2707 | 17.7 | 139887.89 | 0 | 0 | 0 | 0 | 17.7 | 0 | 7903.2707 | 17.7 | 139887.9005 | 7903.2707 | 17.7 | 139887.9 | 7903.2707 | 0 | 139887.891 | -0.0086
3552 | Stage-23 (Jun-24) | 0 | Tentative | Labour | (L)Architects Fee | SQFT | 7903.2707 | 17.7 | 139887.89 | 0 | 0 | 0 | 0 | 17.7 | 0 | 7903.2707 | 17.7 | 139887.9005 | 0 | 0 | 0 | 7903.2707 | 7903.2707 | 139887.891 | 139887.8914
3553 | Stage-24 (July-24) | 0 | Started | Labour | (L)Architects Fee | SQFT | 7903.2707 | 17.7 | 139887.89 | 0 | 0 | 0 | 0 | 17.7 | 0 | 7903.2707 | 17.7 | 139887.9005 | 7903.2707 | 17.7 | 139887.9 | 7903.2707 | 0 | 139887.891 | -0.0086
3554 | Stage-25 (Aug-24) | 0 | Tentative | Labour | (L)Architects Fee | SQFT | 7903.2707 | 17.7 | 139887.89 | 0 | 0 | 0 | 0 | 17.7 | 0 | 7903.2707 | 17.7 | 139887.9005 | 0 | 0 | 0 | 7903.2707 | 7903.2707 | 139887.891 | 139887.8914
3555 | Stage-26 (Sep-24) | 0 | Tentative | Labour | (L)Architects Fee | SQFT | 7903.2707 | 17.7 | 139887.89 | 0 | 0 | 0 | 0 | 17.7 | 0 | 7903.2707 | 17.7 | 139887.9005 | 0 | 0 | 0 | 7903.2707 | 7903.2707 | 139887.891 | 139887.8914
3556 | Stage-27 (Oct-24) | 0 | Tentative | Labour | (L)Architects Fee | SQFT | 7903.2707 | 17.7 | 139887.89 | 0 | 0 | 0 | 0 | 17.7 | 0 | 7903.2707 | 17.7 | 139887.9005 | 0 | 0 | 0 | 7903.2707 | 7903.2707 | 139887.891 | 139887.8914
3557 | Stage-28 (Nov-24) | 0 | Tentative | Labour | (L)Architects Fee | SQFT | 7903.2707 | 17.7 | 139887.89 | 0 | 0 | 0 | 0 | 17.7 | 0 | 7903.2707 | 17.7 | 139887.9005 | 0 | 0 | 0 | 7903.2707 | 7903.2707 | 139887.891 | 139887.8914
3558 | A BLDG MEP SERVICES CONSULTANCY FEE | 0 | Started | Labour | (L)STAGE-1, ADVANCE-10% | SQFT | 6591.7 | 5.9 | 38891.03 | 0 | 0 | 0 | 0 | 5.9 | 0 | 6591.7 | 3.3 | 21778.98 | 0 | 0 | 0 | 6591.7 | 6591.7 | 38891.03 | 38891.03
3559 | A BLDG MEP SERVICES CONSULTANCY FEE | 0 | Started | Labour | (L)STAGE-2, AGAINST PRELIMINARY DWG-15% | SQFT | 9887.55 | 3.3 | 32628.92 | 0 | 0 | 0 | 0 | 3.3 | 0 | 9887.55 | 3.3 | 32668.46 | 9887.55 | 3.3 | 32668.46 | 9887.55 | 0 | 32628.915 | -39.545
3560 | A BLDG MEP SERVICES CONSULTANCY FEE | 0 | Started | Labour | (L)STAGE-3, AFTER APPROVAL OF DWG-15% | SQFT | 9887.55 | 3.3 | 32628.92 | 0 | 0 | 0 | 0 | 3.3 | 0 | 9887.55 | 3.3 | 32668.46 | 9887.55 | 3.3 | 32668.46 | 9887.55 | 0 | 32628.915 | -39.545
3561 | A BLDG MEP SERVICES CONSULTANCY FEE | 0 | Started | Labour | (L)STAGE-4, AGAINST GFC DWG-30% | SQFT | 19775.1 | 3.3 | 65257.83 | 0 | 0 | 0 | 0 | 3.3 | 0 | 19775.1 | 3.3 | 65336.94 | 0 | 0 | 0 | 19775.1 | 19775.1 | 65257.83 | 65257.83
3562 | A BLDG MEP SERVICES CONSULTANCY FEE | 0 | Started | Labour | (L)STAGE-5, AGA. PRORATA ON SITE PROG.-15% | SQFT | 9887.55 | 3.3 | 32628.92 | 0 | 0 | 0 | 0 | 3.3 | 0 | 9887.55 | 3.3 | 32668.46 | 0 | 0 | 0 | 9887.55 | 9887.55 | 32628.915 | 32628.915
3563 | A BLDG MEP SERVICES CONSULTANCY FEE | 0 | Started | Labour | (L)STAGE-6 AFTER COMP. OF EXT. SERVICES-15% | SQFT | 9887.55 | 3.3 | 32628.92 | 0 | 0 | 0 | 0 | 3.3 | 0 | 9887.55 | 3.3 | 32668.46 | 0 | 0 | 0 | 9887.55 | 9887.55 | 32628.915 | 32628.915
3564 | B BLDG MEP SERVICES CONSULTANCY FEE | 0 | Started | Labour | (L)STAGE-1, ADVANCE-10% | SQFT | 11856.3 | 5.9 | 69952.17 | 0 | 0 | 0 | 0 | 5.9 | 0 | 11856.3 | 3.3 | 39173.22 | 0 | 0 | 0 | 11856.3 | 11856.3 | 69952.17 | 69952.17
3565 | B BLDG MEP SERVICES CONSULTANCY FEE | 0 | Started | Labour | (L)STAGE-2, AGAINST PRELIMINARY DWG-15% | SQFT | 17784.45 | 3.3 | 58688.69 | 0 | 0 | 0 | 0 | 3.3 | 0 | 17784.45 | 3.3 | 58759.82 | 0 | 0 | 0 | 17784.45 | 17784.45 | 58688.685 | 58688.685
3566 | B BLDG MEP SERVICES CONSULTANCY FEE | 0 | Started | Labour | (L)STAGE-3, AFTER APPROVAL OF DWG-15% | SQFT | 17784.45 | 3.3 | 58688.69 | 0 | 0 | 0 | 0 | 3.3 | 0 | 17784.45 | 3.3 | 58759.82 | 0 | 0 | 0 | 17784.45 | 17784.45 | 58688.685 | 58688.685
3567 | B BLDG MEP SERVICES CONSULTANCY FEE | 0 | Started | Labour | (L)STAGE-4, AGAINST GFC DWG-30% | SQFT | 35568.9 | 3.3 | 117377.37 | 0 | 0 | 0 | 0 | 3.3 | 0 | 35568.9 | 3.3 | 117519.64 | 0 | 0 | 0 | 35568.9 | 35568.9 | 117377.37 | 117377.37
3568 | B BLDG MEP SERVICES CONSULTANCY FEE | 0 | Started | Labour | (L)STAGE-5, AGA. PRORATA ON SITE PROG.-15% | SQFT | 17784.45 | 3.3 | 58688.69 | 0 | 0 | 0 | 0 | 3.3 | 0 | 17784.45 | 3.3 | 58759.82 | 0 | 0 | 0 | 17784.45 | 17784.45 | 58688.685 | 58688.685
3569 | B BLDG MEP SERVICES CONSULTANCY FEE | 0 | Started | Labour | (L)STAGE-6 AFTER COMP. OF EXT. SERVICES-15% | SQFT | 17784.45 | 3.3 | 58688.69 | 0 | 0 | 0 | 0 | 3.3 | 0 | 17784.45 | 3.3 | 58759.82 | 0 | 0 | 0 | 17784.45 | 17784.45 | 58688.685 | 58688.685
3570 | C BLDG MEP SERVICES CONSULTANCY FEE | 0 | Started | Labour | (L)STAGE-1, ADVANCE-10% | SQFT | 7334.6 | 5.9 | 43274.14 | 0 | 0 | 0 | 0 | 5.9 | 0 | 7334.6 | 3.3 | 24233.52 | 0 | 0 | 0 | 7334.6 | 7334.6 | 43274.14 | 43274.14
3571 | C BLDG MEP SERVICES CONSULTANCY FEE | 0 | Started | Labour | (L)STAGE-2, AGAINST PRELIMINARY DWG-15% | SQFT | 11001.9 | 3.3 | 36306.27 | 0 | 0 | 0 | 0 | 3.3 | 0 | 11001.9 | 3.3 | 36350.28 | 0 | 0 | 0 | 11001.9 | 11001.9 | 36306.27 | 36306.27
3572 | C BLDG MEP SERVICES CONSULTANCY FEE | 0 | Started | Labour | (L)STAGE-3, AFTER APPROVAL OF DWG-15% | SQFT | 11001.9 | 3.3 | 36306.27 | 0 | 0 | 0 | 0 | 3.3 | 0 | 11001.9 | 3.3 | 36350.28 | 0 | 0 | 0 | 11001.9 | 11001.9 | 36306.27 | 36306.27
3573 | C BLDG MEP SERVICES CONSULTANCY FEE | 0 | Started | Labour | (L)STAGE-4, AGAINST GFC DWG-30% | SQFT | 22003.8 | 3.3 | 72612.54 | 0 | 0 | 0 | 0 | 3.3 | 0 | 22003.8 | 3.3 | 72700.56 | 0 | 0 | 0 | 22003.8 | 22003.8 | 72612.54 | 72612.54
3574 | C BLDG MEP SERVICES CONSULTANCY FEE | 0 | Started | Labour | (L)STAGE-5, AGA. PRORATA ON SITE PROG.-15% | SQFT | 11001.9 | 3.3 | 36306.27 | 0 | 0 | 0 | 0 | 3.3 | 0 | 11001.9 | 3.3 | 36350.28 | 0 | 0 | 0 | 11001.9 | 11001.9 | 36306.27 | 36306.27
3575 | C BLDG MEP SERVICES CONSULTANCY FEE | 0 | Started | Labour | (L)STAGE-6 AFTER COMP. OF EXT. SERVICES-15% | SQFT | 11001.9 | 3.3 | 36306.27 | 0 | 0 | 0 | 0 | 3.3 | 0 | 11001.9 | 3.3 | 36350.28 | 0 | 0 | 0 | 11001.9 | 11001.9 | 36306.27 | 36306.27
3576 | D BLDG MEP SERVICES CONSULTANCY FEE | 0 | Started | Labour | (L)STAGE-1, ADVANCE-10% | SQFT | 6578.4 | 5.9 | 38812.56 | 0 | 0 | 0 | 0 | 5.9 | 0 | 6578.4 | 3.3 | 21735.04 | 0 | 0 | 0 | 6578.4 | 6578.4 | 38812.56 | 38812.56
3577 | D BLDG MEP SERVICES CONSULTANCY FEE | 0 | Started | Labour | (L)STAGE-2, AGAINST PRELIMINARY DWG-15% | SQFT | 9867.6 | 3.3 | 32563.08 | 0 | 0 | 0 | 0 | 3.3 | 0 | 9867.6 | 3.3 | 32602.56 | 0 | 0 | 0 | 9867.6 | 9867.6 | 32563.08 | 32563.08
3578 | D BLDG MEP SERVICES CONSULTANCY FEE | 0 | Started | Labour | (L)STAGE-3, AFTER APPROVAL OF DWG-15% | SQFT | 9867.6 | 3.3 | 32563.08 | 0 | 0 | 0 | 0 | 3.3 | 0 | 9867.6 | 3.3 | 32602.56 | 0 | 0 | 0 | 9867.6 | 9867.6 | 32563.08 | 32563.08
3579 | D BLDG MEP SERVICES CONSULTANCY FEE | 0 | Started | Labour | (L)STAGE-4, AGAINST GFC DWG-30% | SQFT | 19735.2 | 3.3 | 65126.16 | 0 | 0 | 0 | 0 | 3.3 | 0 | 19735.2 | 3.3 | 65205.1 | 0 | 0 | 0 | 19735.2 | 19735.2 | 65126.16 | 65126.16
3580 | D BLDG MEP SERVICES CONSULTANCY FEE | 0 | Started | Labour | (L)STAGE-5, AGA. PRORATA ON SITE PROG.-15% | SQFT | 9867.6 | 3.3 | 32563.08 | 0 | 0 | 0 | 0 | 3.3 | 0 | 9867.6 | 3.3 | 32602.56 | 0 | 0 | 0 | 9867.6 | 9867.6 | 32563.08 | 32563.08
3581 | D BLDG MEP SERVICES CONSULTANCY FEE | 0 | Started | Labour | (L)STAGE-6 AFTER COMP. OF EXT. SERVICES-15% | SQFT | 9867.6 | 3.3 | 32563.08 | 0 | 0 | 0 | 0 | 3.3 | 0 | 9867.6 | 3.3 | 32602.56 | 0 | 0 | 0 | 9867.6 | 9867.6 | 32563.08 | 32563.08
3582 | E (AMENITY) BLDG MEP SERVICES CONSULTANCY FEE | 0 | Started | Labour | (L)STAGE-1, ADVANCE-10% | SQFT | 11226.6786 | 5.9 | 66237.4 | 0 | 0 | 0 | 0 | 5.9 | 0 | 11226.6786 | 3.3 | 37092.9401 | 8928.9286 | 3.3 | 29501.18 | 11226.6786 | 2297.75 | 66237.404 | 36736.2237
3583 | E (AMENITY) BLDG MEP SERVICES CONSULTANCY FEE | 0 | Started | Labour | (L)STAGE-2, AGAINST PRELIMINARY DWG-15% | SQFT | 16840.0179 | 3.3 | 55572.06 | 0 | 0 | 0 | 0 | 3.3 | 0 | 16840.0179 | 3.3 | 55639.4101 | 16840.0179 | 3.3 | 55639.41 | 16840.0179 | 0 | 55572.059 | -67.3509
3584 | E (AMENITY) BLDG MEP SERVICES CONSULTANCY FEE | 0 | Started | Labour | (L)STAGE-3, AFTER APPROVAL OF DWG-15% | SQFT | 16840.0179 | 3.3 | 55572.06 | 0 | 0 | 0 | 0 | 3.3 | 0 | 16840.0179 | 3.3 | 55639.4101 | 16840.0179 | 3.3 | 55639.41 | 16840.0179 | 0 | 55572.059 | -67.3509
3585 | E (AMENITY) BLDG MEP SERVICES CONSULTANCY FEE | 0 | Started | Labour | (L)STAGE-4, AGAINST GFC DWG-30% | SQFT | 33680.0358 | 3.3 | 111144.12 | 0 | 0 | 0 | 0 | 3.3 | 0 | 33680.0358 | 3.3 | 111278.8402 | 0 | 0 | 0 | 33680.0358 | 33680.0358 | 111144.118 | 111144.1181
3586 | E (AMENITY) BLDG MEP SERVICES CONSULTANCY FEE | 0 | Started | Labour | (L)STAGE-5, AGA. PRORATA ON SITE PROG.-15% | SQFT | 16840.0179 | 3.3 | 55572.06 | 0 | 0 | 0 | 0 | 3.3 | 0 | 16840.0179 | 3.3 | 55639.4101 | 0 | 0 | 0 | 16840.0179 | 16840.0179 | 55572.059 | 55572.0591
3587 | E (AMENITY) BLDG MEP SERVICES CONSULTANCY FEE | 0 | Started | Labour | (L)STAGE-6 AFTER COMP. OF EXT. SERVICES-15% | SQFT | 16840.0179 | 3.3 | 55572.06 | 0 | 0 | 0 | 0 | 3.3 | 0 | 16840.0179 | 3.3 | 55639.4101 | 0 | 0 | 0 | 16840.0179 | 16840.0179 | 55572.059 | 55572.0591
3588 | PLOTTING,DEVEL.,CLUB HOUSE,ROW HOUSE MEP SERV. CONSUL. FEE | 0 | Started | Labour | (L)STAGE-1, ADVANCE-10% | SQFT | 9809.2 | 5.9 | 57874.28 | 0 | 0 | 0 | 0 | 5.9 | 0 | 9809.2 | 3.3 | 32409.6 | 0 | 0 | 0 | 9809.2 | 9809.2 | 57874.28 | 57874.28
3589 | PLOTTING,DEVEL.,CLUB HOUSE,ROW HOUSE MEP SERV. CONSUL. FEE | 0 | Started | Labour | (L)STAGE-2, AGAINST PRELIMINARY DWG-15% | SQFT | 14713.8 | 3.3 | 48555.54 | 0 | 0 | 0 | 0 | 3.3 | 0 | 14713.8 | 3.3 | 48614.4 | 0 | 0 | 0 | 14713.8 | 14713.8 | 48555.54 | 48555.54
3590 | PLOTTING,DEVEL.,CLUB HOUSE,ROW HOUSE MEP SERV. CONSUL. FEE | 0 | Started | Labour | (L)STAGE-3, AFTER APPROVAL OF DWG-15% | SQFT | 14713.8 | 3.3 | 48555.54 | 0 | 0 | 0 | 0 | 3.3 | 0 | 14713.8 | 3.3 | 48614.4 | 0 | 0 | 0 | 14713.8 | 14713.8 | 48555.54 | 48555.54
3591 | PLOTTING,DEVEL.,CLUB HOUSE,ROW HOUSE MEP SERV. CONSUL. FEE | 0 | Started | Labour | (L)STAGE-4, AGAINST GFC DWG-30% | SQFT | 29427.6 | 3.3 | 97111.08 | 0 | 0 | 0 | 0 | 3.3 | 0 | 29427.6 | 3.3 | 97228.8 | 29427.6 | 3.3 | 97228.8 | 29427.6 | 0 | 97111.08 | -117.72
3592 | PLOTTING,DEVEL.,CLUB HOUSE,ROW HOUSE MEP SERV. CONSUL. FEE | 0 | Started | Labour | (L)STAGE-5, AGA. PRORATA ON SITE PROG.-15% | SQFT | 14713.8 | 3.3 | 48555.54 | 0 | 0 | 0 | 0 | 3.3 | 0 | 14713.8 | 3.3 | 48614.4 | 0 | 0 | 0 | 14713.8 | 14713.8 | 48555.54 | 48555.54
3593 | PLOTTING,DEVEL.,CLUB HOUSE,ROW HOUSE MEP SERV. CONSUL. FEE | 0 | Started | Labour | (L)STAGE-6 AFTER COMP. OF EXT. SERVICES-15% | SQFT | 14713.8 | 3.3 | 48555.54 | 0 | 0 | 0 | 0 | 3.3 | 0 | 14713.8 | 3.3 | 48614.4 | 0 | 0 | 0 | 14713.8 | 14713.8 | 48555.54 | 48555.54
3594 | VETTING/PROOF CHECKING & CERT. STR. DWG FOR AMENITY BUILDING | 0 | Started | Labour | (L)1ST STAGE- ADVANCE. 40% | NOS | 1 | 141600 | 141600 | 0 | 0 | 0 | 0 | 141600 | 0 | 1 | 141600 | 141600 | 0 | 0 | 0 | 1 | 1 | 141600 | 141600
3595 | VETTING/PROOF CHECKING & CERT. STR. DWG FOR AMENITY BUILDING | 0 | Started | Labour | (L)2 ND STAGE-AFTER ISSUING LETTER/CERTIFICATE. 60% | NOS | 1 | 212400 | 212400 | 0 | 0 | 0 | 0 | 212400 | 0 | 1 | 212400 | 212400 | 1 | 212400 | 212400 | 1 | 0 | 212400 | 0
3596 | Amenity bldg. Drawings set prints for vetting and courier Ch | 0 | Started | Labour | (L)Drawings Set Prints and Courier Charges | NOS | 1 | 13900 | 13900 | 0 | 0 | 0 | 0 | 13900 | 0 | 1 | 13900 | 13900 | 1 | 13900 | 13900 | 1 | 0 | 13900 | 0
3597 | ARCHITECTURAL CONSULTANCY, DESIGN CHARGES FOR AMENITY BLDG. | 0 | Tentative | Labour | (L)1ST STAGE ADVANCE-10% | NOS | 1 | 70800 | 70800 | 0 | 0 | 0 | 0 | 70800 | 0 | 1 | 70800 | 70800 | 0 | 0 | 0 | 1 | 1 | 70800 | 70800
3598 | ARCHITECTURAL CONSULTANCY, DESIGN CHARGES FOR AMENITY BLDG. | 0 | Tentative | Labour | (L)2ND STAGE AGAINST PRELIMINARY DWG-15% | NOS | 1 | 106200 | 106200 | 0 | 0 | 0 | 0 | 106200 | 0 | 1 | 106200 | 106200 | 0 | 0 | 0 | 1 | 1 | 106200 | 106200
3599 | ARCHITECTURAL CONSULTANCY, DESIGN CHARGES FOR AMENITY BLDG. | 0 | Tentative | Labour | (L)3RD STAGE AGAINST ISSUE OF GFC-35% | NOS | 1 | 247800 | 247800 | 0 | 0 | 0 | 0 | 247800 | 0 | 1 | 247800 | 247800 | 0 | 0 | 0 | 1 | 1 | 247800 | 247800
3600 | ARCHITECTURAL CONSULTANCY, DESIGN CHARGES FOR AMENITY BLDG. | 0 | Tentative | Labour | (L)4TH STAGE AGAINST PRORATA ON SITE PROGRESS-30% | NOS | 1 | 212400 | 212400 | 0 | 0 | 0 | 0 | 212400 | 0 | 1 | 212400 | 212400 | 0 | 0 | 0 | 1 | 1 | 212400 | 212400
3601 | ARCHITECTURAL CONSULTANCY, DESIGN CHARGES FOR AMENITY BLDG. | 0 | Tentative | Labour | (L)5TH STAGE AFTER COMPLETION OF WORK-10% | NOS | 1 | 70800 | 70800 | 0 | 0 | 0 | 0 | 70800 | 0 | 1 | 70800 | 70800 | 0 | 0 | 0 | 1 | 1 | 70800 | 70800
3602 | Tensile roofing work in Amenity building | 0 | Tentative | Labour | (L)ADVANCE WITH PO FOR DESIGN-10% | SQFT | 538.2 | 684.4 | 368344.08 | 0 | 0 | 0 | 0 | 684.4 | 0 | 538.2 | 684.4 | 368344.08 | 0 | 0 | 0 | 538.2 | 538.2 | 368344.08 | 368344.08
3603 | Tensile roofing work in Amenity building | 0 | Tentative | Labour | (L)ADVANCE FOR MAT. PURCHASE-45% | SQFT | 2421.9 | 684.4 | 1657548.36 | 0 | 0 | 0 | 0 | 684.4 | 0 | 2421.9 | 684.4 | 1657548.36 | 0 | 0 | 0 | 2421.9 | 2421.9 | 1657548.36 | 1657548.36
3604 | Tensile roofing work in Amenity building | 0 | Tentative | Labour | (L)AFTER 3 MONTHS OF COMPL.-5% | SQFT | 269.1 | 684.4 | 184172.04 | 0 | 0 | 0 | 0 | 684.4 | 0 | 269.1 | 684.4 | 184172.04 | 0 | 0 | 0 | 269.1 | 269.1 | 184172.04 | 184172.04
3605 | Tensile roofing work in Amenity building | 0 | Tentative | Labour | (L)AGAINST MAT. DELIVERY-30% | SQFT | 1614.6 | 684.4 | 1105032.24 | 0 | 0 | 0 | 0 | 684.4 | 0 | 1614.6 | 684.4 | 1105032.24 | 0 | 0 | 0 | 1614.6 | 1614.6 | 1105032.24 | 1105032.24
3606 | Tensile roofing work in Amenity building | 0 | Tentative | Labour | (L)AGAINST WORK COMPLETION-10% | SQFT | 538.2 | 684.4 | 368344.08 | 0 | 0 | 0 | 0 | 684.4 | 0 | 538.2 | 684.4 | 368344.08 | 0 | 0 | 0 | 538.2 | 538.2 | 368344.08 | 368344.08
3607 | ROW HOUSE ARCHITECTURAL DESIGN WITH DWG-FEE | 0 | Started | Labour | (L)Architects Fee | SQFT | 2340 | 17.7 | 41418 | 0 | 0 | 0 | 0 | 17.7 | 0 | 2340 | 252.14 | 589999.968 | 0 | 0 | 0 | 2340 | 2340 | 41418 | 41418
3608 | CLUB HOUSE ARCHITECTURAL DESIGN WITH DWG-FEE | 0 | Started | Labour | (L)Architects Fee | SQFT | 4090 | 17.7 | 72393 | 0 | 0 | 0 | 0 | 17.7 | 0 | 4090 | 57.7 | 236000.222 | 0 | 0 | 0 | 4090 | 4090 | 72393 | 72393
3609 | PODIUM RCC WORK-RAFT PCC,FOOTING,COLUMN UP TO PLINTH | 0 | Started | Material | (M)CEMENT OPC 43 | BAG | 670 | 378.88 | 253849.6 | 670 | 378.88 | 253849.6 | 0 | 378.88 | 0 | 300 | 365 | 109500 | 0 | 0 | 0 | 670 | 670 | 253849.6 | 253849.6
3610 | PODIUM RCC WORK-RAFT PCC,FOOTING,COLUMN UP TO PLINTH | 0 | Started | Material | (M)Crush Sand | BRASS | 20.534 | 3675 | 75462.45 | 20.534 | 3675 | 75462.45 | 0 | 3675 | 0 | 20.534 | 3675 | 75462.4599 | 0 | 0 | 0 | 20.534 | 20.534 | 75462.45 | 75462.45
3611 | PODIUM RCC WORK-RAFT PCC,FOOTING,COLUMN UP TO PLINTH | 0 | Started | Material | (M)Metal No.III 20MM | BRASS | 25.3 | 3045 | 77038.5 | 25.3 | 3045 | 77038.5 | 0 | 3045 | 0 | 25.3 | 3360 | 85008 | 0 | 0 | 0 | 25.3 | 25.3 | 77038.5 | 77038.5
3612 | PODIUM RCC WORK-RAFT PCC,FOOTING,COLUMN UP TO PLINTH | 0 | Started | Material | (M)METAL-60MM | BRASS | 3 | 3200 | 9600 | 3 | 3200 | 9600 | 0 | 3200 | 0 | 3 | 3150 | 9450 | 0 | 0 | 0 | 3 | 3 | 9600 | 9600
3613 | PODIUM RCC WORK-RAFT PCC,FOOTING,COLUMN UP TO PLINTH | 0 | Started | Material | (M)MS Binding Wire 18G | KG | 360 | 50 | 18000 | 360 | 50 | 18000 | 0 | 50 | 0 | 360 | 80.24 | 28886.4 | 0 | 0 | 0 | 360 | 360 | 18000 | 18000
3614 | PODIUM RCC WORK-RAFT PCC,FOOTING,COLUMN UP TO PLINTH | 0 | Started | Material | (M)PERMA BOND SBR | LITRE | 25 | 291.08 | 7277 | 25 | 291.08 | 7277 | 0 | 291.08 | 0 | 25 | 212 | 5300 | 0 | 0 | 0 | 25 | 25 | 7277 | 7277
3615 | PODIUM RCC WORK-RAFT PCC,FOOTING,COLUMN UP TO PLINTH | 0 | Started | Material | (M)RMC M-15 | CUM | 124 | 3500 | 434000 | 124 | 3500 | 434000 | 0 | 3500 | 0 | 124 | 4700 | 582800.0036 | 0 | 0 | 0 | 124 | 124 | 434000 | 434000
3616 | PODIUM RCC WORK-RAFT PCC,FOOTING,COLUMN UP TO PLINTH | 0 | Started | Material | (M)RMC M-25 | CUM | 300 | 4600 | 1380000 | 300 | 4600 | 1380000 | 0 | 4600 | 0 | 225.5 | 5211.42 | 1175174.9902 | 0 | 0 | 0 | 300 | 300 | 1380000 | 1380000
3617 | PODIUM RCC WORK-RAFT PCC,FOOTING,COLUMN UP TO PLINTH | 0 | Started | Material | (M)T.M.T.Bar 10mm (Fe 500, 0.617 KGS/Rm) | KG | 4158 | 59 | 245322 | 4158 | 59 | 245322 | 0 | 59 | 0 | 4158 | 57.19 | 237779.388 | 0 | 0 | 0 | 4158 | 4158 | 245322 | 245322
3618 | PODIUM RCC WORK-RAFT PCC,FOOTING,COLUMN UP TO PLINTH | 0 | Started | Material | (M)T.M.T.Bar 12mm (Fe 500, 0.888 KGS/Rm) | KG | 1969 | 59 | 116171 | 1969 | 59 | 116171 | 0 | 59 | 0 | 1969 | 56.58 | 111398.144 | 0 | 0 | 0 | 1969 | 1969 | 116171 | 116171
3619 | PODIUM RCC WORK-RAFT PCC,FOOTING,COLUMN UP TO PLINTH | 0 | Started | Material | (M)T.M.T.Bar 16mm (Fe 500, 1.58 KGS/Rm) | KG | 516 | 59 | 30444 | 516 | 59 | 30444 | 0 | 59 | 0 | 516 | 56.58 | 29193.216 | 0 | 0 | 0 | 516 | 516 | 30444 | 30444
3620 | PODIUM RCC WORK-RAFT PCC,FOOTING,COLUMN UP TO PLINTH | 0 | Started | Material | (M)T.M.T.Bar 20mm (Fe 500, 2.47 KGS/Rm) | KG | 7397 | 59 | 436423 | 7397 | 59 | 436423 | 0 | 59 | 0 | 7397 | 57.19 | 423004.842 | 0 | 0 | 0 | 7397 | 7397 | 436423 | 436423
3621 | PODIUM RCC WORK-RAFT PCC,FOOTING,COLUMN UP TO PLINTH | 0 | Started | Material | (M)T.M.T.Bar 25mm (Fe 500, 3.85 KGS/Rm) | KG | 3780 | 59 | 223020 | 3780 | 59 | 223020 | 0 | 59 | 0 | 3780 | 57.19 | 216163.08 | 0 | 0 | 0 | 3780 | 3780 | 223020 | 223020
3622 | PODIUM RCC WORK-RAFT PCC,FOOTING,COLUMN UP TO PLINTH | 0 | Started | Material | (M)T.M.T.Bar 8mm (Fe 500, 0.395 KGS/Rm) | KG | 13230 | 59 | 780570 | 13230 | 59 | 780570 | 0 | 59 | 0 | 13230 | 58.4 | 772579.08 | 0 | 0 | 0 | 13230 | 13230 | 780570 | 780570
3623 | PODIUM TRENCH DEWATERING - LGF | 0 | Tentative | Material | (M)PVC PERFORATED PIPE 6'' X 6MTR (B-TYPE) 4KG/SQCM | NOS | 18 | 2407.2 | 43329.6 | 18 | 2407.2 | 43329.6 | 0 | 2407.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 18 | 43329.6 | 43329.6
3624 | PODIUM RAFT BOX TYPE SHAHABAD WATERPROOFING WORK-MAT | 0 | Tentative | Material | (M)Artificial Sand | BRASS | 14 | 5880 | 82320 | 14 | 5880 | 82320 | 0 | 5880 | 0 | 14 | 6300 | 88200 | 0 | 0 | 0 | 14 | 14 | 82320 | 82320
3625 | PODIUM RAFT BOX TYPE SHAHABAD WATERPROOFING WORK-MAT | 0 | Tentative | Material | (M)CEMENT PPC 50KG | BAG | 550 | 320 | 176000 | 550 | 320 | 176000 | 0 | 320 | 0 | 500 | 320 | 160000 | 0 | 0 | 0 | 550 | 550 | 176000 | 176000
3626 | PODIUM RAFT BOX TYPE SHAHABAD WATERPROOFING WORK-MAT | 0 | Tentative | Material | (M)Dr.Fixit LW+ 50Ltr Drum | DRUM | 1 | 3800 | 3800 | 1 | 3800 | 3800 | 0 | 3800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3800 | 3800
3627 | PODIUM RAFT BOX TYPE SHAHABAD WATERPROOFING WORK-MAT | 0 | Tentative | Material | (M)Shahabad Tile 2'x1'6" | SQFT | 9166 | 20.2 | 185153.2 | 9166 | 20.2 | 185153.2 | 0 | 20.2 | 0 | 9166 | 17.85 | 163613.1 | 0 | 0 | 0 | 9166 | 9166 | 185153.2 | 185153.2
3628 | PODIUM-RAFT BASE SHAHABAD WATERPROOFING WORK-LABOUR | 0 | Started | Labour | (L)Waterproofing (Lab) | SQFT | 8845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8845 | 8845 | 0 | 0
3629 | PODIUM-RETAINING WALL EXTERNAL SIDE SHAHABAD WP WORK-LABOUR | 0 | Started | Labour | (L)Waterproofing (Lab) | SQFT | 3018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3018 | 3018 | 0 | 0
3630 | PODIUM RAFT BASE WP WORK-100% COMP. | 0 | Started | Labour | (L)Rough Shahabad Waterproofing Work | NOS | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 148873.69 | 148873.69 | 1 | 148873.69 | 148873.69 | 1 | 0 | 1 | -148872.69
3631 | PODIUM RCC PARDI OUTER SIDE WP WORK-50% COMP. | 0 | Started | Labour | (L)Rough Shahabad Waterproofing Work | NOS | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 28279.21 | 28279.21 | 1 | 28279.21 | 28279.21 | 1 | 0 | 1 | -28278.21
3632 | PODIUM RCC PARDI OUTER SIDE WP WORK-BAL 50% COMP. | 0 | Started | Labour | (L)Rough Shahabad Waterproofing Work | NOS | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 28279.21 | 28279.21 | 1 | 28279.21 | 28279.21 | 1 | 0 | 1 | -28278.21
3633 | PODIUM - RETENTION ATER COMPLETION OF WORK | 0 | Tentative | Labour | (L)Rough Shahabad Waterproofing Work | NOS | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 22825.79 | 22825.79 | 0 | 0 | 0 | 1 | 1 | 1 | 1
3634 | PODIUM WP WORK (EXTRA AREA) | 0 | Tentative | Labour | (L)Rough Shahabad Waterproofing Work | NOS | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 3808.65 | 3808.65 | 0 | 0 | 0 | 1 | 1 | 1 | 1
3635 | PODIUM PARDI BOX TYPE SHAHABAD WATERPROOFING WORK-MAT | 0 | Tentative | Material | (M)Artificial Sand | BRASS | 6 | 5880 | 35280 | 6 | 5880 | 35280 | 0 | 5880 | 0 | 6 | 6300 | 37800 | 0 | 0 | 0 | 6 | 6 | 35280 | 35280
3636 | PODIUM PARDI BOX TYPE SHAHABAD WATERPROOFING WORK-MAT | 0 | Tentative | Material | (M)CEMENT PPC 50KG | BAG | 200 | 320 | 64000 | 200 | 320 | 64000 | 0 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 64000 | 64000
3637 | PODIUM PARDI BOX TYPE SHAHABAD WATERPROOFING WORK-MAT | 0 | Tentative | Material | (M)Shahabad Tile 2'x1'6" | SQFT | 3303 | 20.2 | 66720.6 | 3303 | 20.2 | 66720.6 | 0 | 20.2 | 0 | 3303 | 17.85 | 58958.55 | 0 | 0 | 0 | 3303 | 3303 | 66720.6 | 66720.6
3638 | PODIUM PARDI BOX TYPE SHAHABAD WATERPROOFING WORK-MAT | 0 | Tentative | Material | (M)Water Proofing Chemical LW+ | LTR | 20 | 177 | 3540 | 20 | 177 | 3540 | 0 | 177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 3540 | 3540
3639 | PODIUM FOOTING WBM (BLOCK METTALING) WORK-BEFORE PCC | 0 | Started | Labour | (L)BLOCK METALLING (Mat+Lab) | SQFT | 8013 | 42 | 336546 | 0 | 0 | 0 | 0 | 42 | 0 | 8013 | 49.36 | 395514 | 8013 | 42 | 336546 | 8013 | 0 | 336546 | 0
3640 | PODIUM BLOCK EXCAVATION WORK-SOFT MURUM | 0 | Started | Labour | (L)Labour for Block Excavation | CUM | 3095.61 | 78.76 | 243810.24 | 0 | 0 | 0 | 0 | 78.76 | 0 | 3095.61 | 177 | 547922.98 | 3095.61 | 177 | 547922.98 | 3095.61 | 0 | 243810.244 | -304112.7364