## Work_Completion_Browse638744627
Work Completion Browse
Project : DESTINATION OSTIA
From Date : 06/01/2000 To date: 06/01/2000
Page 1 of 1
Total Records: 409 Records 1 to 409
Labour | Labour_Cat1 | Labour_Cat2 | Contractor | WO_No | Wo_Date | Task | Qty | Rate | OtherAmount | Amount | Tax | WC_Date | Pay_Schedule | PS_Percent | Remark | RA_Bill_No | RABill_Date | Approve_Amount | Approve_Date | Balanced | Executed_By
Fabrication (M+L) | N/C | N/C | S.S. ENTERPRISES | 1 | 2024-04-26 | MAIN SHOP CORNER MS FINS FIXING WORK FOR VISAWA | 135.62 | 350 | 0 | 47467 | 0 | 2024-05-17 11:49 | 100% COMPLETION | 100 |  | 4 | 2024-05-17 | 47467 | 2024-07-10 16:22 | 0 | S.S. ENTERPRISES
CRANE 12 MT | N/C | N/C | SAIRANG CRANE & SHIFTING SERVICES | 10 | 2024-07-12 | MACHINARY CRANE ON RENTAL BASIS | 5.5 | 700 | 0 | 3850 | 0 | 2024-07-20 18:04 | 100% COMPLETION | 100 |  | 67 | 2024-07-20 | 3850 | 2024-07-22 18:32 | 0 | SAIRANG CRANE & SHIFTING SERVICES
CRANE 12 MT | N/C | N/C | SAIRANG CRANE & SHIFTING SERVICES | 10 | 2024-07-12 | MACHINARY CRANE ON RENTAL BASIS | 8.5 | 700 | 0 | 5950 | 0 | 2025-01-20 15:47 | 100% COMPLETION | 100 | Against Bill No 349 | 995 | 2025-01-20 | 5950 | 2025-01-22 13:50 | 0 | SAIRANG CRANE & SHIFTING SERVICES
CRANE 12 MT | N/C | N/C | SAIRANG CRANE & SHIFTING SERVICES | 10 | 2024-07-12 | MACHINARY CRANE ON RENTAL BASIS | 9.5 | 700 | 0 | 6650 | 0 | 2024-08-06 18:26 | 100% COMPLETION | 100 | Bill Against Challan no 2821 and 2824 | 102 | 2024-08-06 | 6650 | 2024-08-07 18:44 | 0 | SAIRANG CRANE & SHIFTING SERVICES
CRANE 12 MT | N/C | N/C | SAIRANG CRANE & SHIFTING SERVICES | 10 | 2024-07-12 | MACHINARY CRANE ON RENTAL BASIS | 8 | 700 | 0 | 5600 | 0 | 2024-12-21 17:57 | 100% COMPLETION | 100 | Against Challan No 3062 | 750 | 2024-12-21 | 16100 | 2024-12-26 12:27 | -10500 | SAIRANG CRANE & SHIFTING SERVICES
CRANE 15 MT | N/C | N/C | SAIRANG CRANE & SHIFTING SERVICES | 10 | 2024-07-12 | MACHINARY CRANE ON RENTAL BASIS | 10.5 | 1000 | 0 | 10500 | 0 | 2024-12-21 17:57 | 100% COMPLETION | 100 | Against Ch no 3063, 3101 | 750 | 2024-12-21 | 16100 | 2024-12-26 12:27 | -5600 | SAIRANG CRANE & SHIFTING SERVICES
MC-LABOUR | N/C | N/C | DAYASHANKAR AHIRWAR | 100 | 2025-02-05 | DEPT LABOUR FOR MATERIAL SHIFTING,CLEANING & OTHER SITE MISC | 112 | 550 | 0 | 61600 | 0 | 2025-02-05 15:25 | 100% COMPLETION | 100 | DEPT LABOUR FOR MATERIAL SHIFTING,CLEANING & OTHER SITE MISC-1JAN 25 TO 31 JAN 2025 | 1096 | 2025-02-05 | 61600 | 1900-01-01 | 0 | DAYASHANKAR AHIRWAR
Furniture Dismantle Work (Partition) | N/C | N/C | Audumbar D Kangane | 101 | 2025-02-05 | OSTIA SALES OFFICE WOODEN PARTITION REMOVING & DISMENTLING W | 961 | 10.5 | 0 | 10090.5 | 0 | 2025-02-05 15:23 | 100% COMPLETION | 100 | OSTIA SALES OFFICE WOODEN PARTITION REMOVING & DISMENTLING WORK | 1095 | 2025-02-05 | 10090.5 | 1900-01-01 | 0 | Audumbar D Kangane
Internal Concealed Work | N/C | N/C | SOMNATH KALYAN TAPKIR | 11 | 2024-07-16 | F1 Bldg Toilet & Bathroom-LG, UG & MEZZ.FLOOR | 100 | 1 | 0 | 100 | 0 | 2024-07-20 18:39 | 100% COMPLETION | 100 |  | 69 | 2024-07-20 | 102572.93 | 2024-07-22 18:31 | -102472.93 | SOMNATH KALYAN TAPKIR
Internal Concealed Work | N/C | N/C | SOMNATH KALYAN TAPKIR | 11 | 2024-07-16 | F1 Bldg Pressure Testing & Levelling LG,UG & 1st Floor | 100 | 1 | 0 | 100 | 0 | 2024-07-20 18:39 | 100% COMPLETION | 100 |  | 69 | 2024-07-20 | 102572.93 | 2024-07-22 18:31 | -102472.93 | SOMNATH KALYAN TAPKIR
Internal Concealed Work | N/C | N/C | SOMNATH KALYAN TAPKIR | 11 | 2024-07-16 | F1 Bldg P-Trap, N-Trap & Outlet LG,UG & 1st Floor | 100 | 1 | 0 | 100 | 0 | 2024-07-20 18:39 | 100% COMPLETION | 100 |  | 69 | 2024-07-20 | 102572.93 | 2024-07-22 18:31 | -102472.93 | SOMNATH KALYAN TAPKIR
Internal Concealed Work | N/C | N/C | SOMNATH KALYAN TAPKIR | 11 | 2024-07-16 | F1 Bldg Toilet & Bathroom-LG, UG & MEZZ.FLOOR | 55573.8 | 1 | 0 | 55573.8 | 0 | 2024-07-20 18:45 | 100% COMPLETION | 100 |  | 69 | 2024-07-20 | 102572.93 | 2024-07-22 18:31 | -46999.13 | SOMNATH KALYAN TAPKIR
Internal Concealed Work | N/C | N/C | SOMNATH KALYAN TAPKIR | 11 | 2024-07-16 | F1 Bldg Pressure Testing & Levelling LG,UG & 1st Floor | 22593.13 | 1 | 0 | 22593.13 | 0 | 2024-07-20 18:45 | 100% COMPLETION | 100 |  | 69 | 2024-07-20 | 102572.93 | 2024-07-22 18:31 | -79979.8 | SOMNATH KALYAN TAPKIR
Internal Concealed Work | N/C | N/C | SOMNATH KALYAN TAPKIR | 11 | 2024-07-16 | F1 Bldg P-Trap, N-Trap & Outlet LG,UG & 1st Floor | 24106 | 1 | 0 | 24106 | 0 | 2024-07-20 18:45 | 100% COMPLETION | 100 |  | 69 | 2024-07-20 | 102572.93 | 2024-07-22 18:31 | -78466.93 | SOMNATH KALYAN TAPKIR
External Plumbing Work | N/C | N/C | SOMNATH KALYAN TAPKIR | 11 | 2024-07-16 | F1 Bldg Duct SH:01-04 C.Toilet UPVC-100% COMP. | 8653.65 | 1 | 0 | 8653.65 | 0 | 2025-01-03 10:49 | 100% COMPLETION | 100 | F1 Bldg Duct SH:01-04 C.Toilet UPVC-100% | 826 | 2025-01-03 | 53495.28 | 2025-01-06 14:46 | -44841.63 | SOMNATH KALYAN TAPKIR
External Plumbing Work | N/C | N/C | SOMNATH KALYAN TAPKIR | 11 | 2024-07-16 | F1 Bldg Duct SH:05-09 C.Toilet UPVC-100% COMP. | 8653.65 | 1 | 0 | 8653.65 | 0 | 2025-01-03 10:49 | 100% COMPLETION | 100 | F1 Bldg Duct SH:05-09 C.Toilet UPVC-100% | 826 | 2025-01-03 | 53495.28 | 2025-01-06 14:46 | -44841.63 | SOMNATH KALYAN TAPKIR
External Plumbing Work | N/C | N/C | SOMNATH KALYAN TAPKIR | 11 | 2024-07-16 | F1 Bldg Duct SH:10-15 C.Toilet UPVC-100% COMP. | 8653.65 | 1 | 0 | 8653.65 | 0 | 2025-01-03 10:49 | 100% COMPLETION | 100 | F1 Bldg Duct SH:10-15 C.Toilet UPVC-100% | 826 | 2025-01-03 | 53495.28 | 2025-01-06 14:46 | -44841.63 | SOMNATH KALYAN TAPKIR
External Plumbing Work | N/C | N/C | SOMNATH KALYAN TAPKIR | 11 | 2024-07-16 | F1 Bldg Duct SH:16-18 C.Toilet UPVC-100% COMP. | 8653.65 | 1 | 0 | 8653.65 | 0 | 2025-01-03 10:49 | 100% COMPLETION | 100 | F1 Bldg Duct SH:16-18 C.Toilet UPVC-100% | 826 | 2025-01-03 | 53495.28 | 2025-01-06 14:46 | -44841.63 | SOMNATH KALYAN TAPKIR
External Plumbing Work | N/C | N/C | SOMNATH KALYAN TAPKIR | 11 | 2024-07-16 | F1 Bldg Duct SH:10-15 Terrace Line-100% COMP. | 9440.34 | 1 | 0 | 9440.34 | 0 | 2025-01-03 10:52 | 100% COMPLETION | 100 | F1 Bldg Duct SH:10-15 Terrace Line-100% COMP. | 826 | 2025-01-03 | 53495.28 | 2025-01-06 14:46 | -44054.94 | SOMNATH KALYAN TAPKIR
External Plumbing Work | N/C | N/C | SOMNATH KALYAN TAPKIR | 11 | 2024-07-16 | F1 Bldg Duct SH:16-18 Terrace Line-100% COMP. | 9440.34 | 1 | 0 | 9440.34 | 0 | 2025-01-03 10:52 | 100% COMPLETION | 100 | F1 Bldg Duct SH:16-18 Terrace Line-100% COMP. | 826 | 2025-01-03 | 53495.28 | 2025-01-06 14:46 | -44054.94 | SOMNATH KALYAN TAPKIR
Internal Concealed Work | N/C | N/C | SOMNATH KALYAN TAPKIR | 11 | 2024-07-16 | F1 Bldg Toilet & Bathroom-1ST, 2ND& 3RD FLOOR | 41755 | 1 | 0 | 41755 | 0 | 2024-08-16 11:11 | 100% COMPLETION | 100 | F1 Building Internal Concealed Plumbing for 1st and 2nd Floor. | 153 | 2024-08-16 | 52647 | 2024-09-04 16:31 | -10892 | SOMNATH KALYAN TAPKIR
Internal Concealed Work | N/C | N/C | SOMNATH KALYAN TAPKIR | 11 | 2024-07-16 | F1 Bldg Flush Valve Fixing-LG,UG,1ST,2ND,3RD FLOOR | 10892 | 1 | 0 | 10892 | 0 | 2024-08-16 11:11 | 100% COMPLETION | 100 | Fi Building Internal Toilet Flush Valve Fixing Work for LG, Ug Floor | 153 | 2024-08-16 | 52647 | 2024-09-04 16:31 | -41755 | SOMNATH KALYAN TAPKIR
Internal Concealed Work | N/C | N/C | SOMNATH KALYAN TAPKIR | 11 | 2024-07-16 | F1 Bldg Toilet & Bathroom-1ST, 2ND& 3RD FLOOR | 41755 | 1 | 0 | 41755 | 0 | 2024-10-14 18:56 | 100% COMPLETION | 100 | BIll NO 3/ FOR 3rd FLOOR | 444 | 2024-10-14 | 101362.13 | 2024-12-20 14:15 | -59607.13 | SOMNATH KALYAN TAPKIR
Internal Concealed Work | N/C | N/C | SOMNATH KALYAN TAPKIR | 11 | 2024-07-16 | F1 Bldg Pressure Testing & Levelling 2nd & 3rd Floor | 22693.13 | 1 | 0 | 22693.13 | 0 | 2024-10-14 18:56 | 100% COMPLETION | 100 | BIll NO 3/ FOR2ND AND 3rd FLOOR | 444 | 2024-10-14 | 101362.13 | 2024-12-20 14:15 | -78669 | SOMNATH KALYAN TAPKIR
Internal Concealed Work | N/C | N/C | SOMNATH KALYAN TAPKIR | 11 | 2024-07-16 | F1 Bldg P-Trap, N-Trap & Outlet 2nd & 3rd Floor | 24206 | 1 | 0 | 24206 | 0 | 2024-10-14 18:56 | 100% COMPLETION | 100 | BIll NO 3/ FOR2ND AND 3rd FLOOR | 444 | 2024-10-14 | 101362.13 | 2024-12-20 14:15 | -77156.13 | SOMNATH KALYAN TAPKIR
Internal Concealed Work | N/C | N/C | SOMNATH KALYAN TAPKIR | 11 | 2024-07-16 | F1 Bldg Flush Valve Fixing-LG,UG,1ST,2ND,3RD FLOOR | 12708 | 1 | 0 | 12708 | 0 | 2024-10-14 18:56 | 100% COMPLETION | 100 | BIll NO 3/ FOR 1st & 2ND FLOOR | 444 | 2024-10-14 | 101362.13 | 2024-12-20 14:15 | -88654.13 | SOMNATH KALYAN TAPKIR
External Plumbing Work | N/C | N/C | SOMNATH KALYAN TAPKIR | 11 | 2024-07-16 | F1 Bldg Duct SH:01-04 C.Toilet PVC-100% COMP. | 18880 | 1 | 0 | 18880 | 0 | 2024-12-21 10:41 | 100% COMPLETION | 100 | F1 Bldg Duct SH:01-04 C.Toilet PVC-100% COMP | 736 | 2024-12-21 | 107108 | 2024-12-26 12:51 | -88228 | SOMNATH KALYAN TAPKIR
External Plumbing Work | N/C | N/C | SOMNATH KALYAN TAPKIR | 11 | 2024-07-16 | F1 Bldg Duct SH:05-09 C.Toilet PVC-100% COMP. | 18880 | 1 | 0 | 18880 | 0 | 2024-12-21 10:41 | 100% COMPLETION | 100 | F1 Bldg Duct SH:05-09 C.Toilet PVC-100% COMP. | 736 | 2024-12-21 | 107108 | 2024-12-26 12:51 | -88228 | SOMNATH KALYAN TAPKIR
External Plumbing Work | N/C | N/C | SOMNATH KALYAN TAPKIR | 11 | 2024-07-16 | F1 Bldg Duct SH:10-15 C.Toilet PVC-100% COMP. | 18880 | 1 | 0 | 18880 | 0 | 2024-12-21 10:41 | 100% COMPLETION | 100 | F1 Bldg Duct SH:10-15 C.Toilet PVC-100% COMP | 736 | 2024-12-21 | 107108 | 2024-12-26 12:51 | -88228 | SOMNATH KALYAN TAPKIR
External Plumbing Work | N/C | N/C | SOMNATH KALYAN TAPKIR | 11 | 2024-07-16 | F1 Bldg Duct SH:16-18 C.Toilet PVC-100% COMP. | 18880 | 1 | 0 | 18880 | 0 | 2024-12-21 10:41 | 100% COMPLETION | 100 | F1 Bldg Duct SH:16-18 C.Toilet PVC-100% COMP | 736 | 2024-12-21 | 107108 | 2024-12-26 12:51 | -88228 | SOMNATH KALYAN TAPKIR
External Plumbing Work | N/C | N/C | SOMNATH KALYAN TAPKIR | 11 | 2024-07-16 | F1 Bldg Duct SH:01-04 Terrace Line-100% COMP. | 9440 | 1 | 0 | 9440 | 0 | 2024-12-21 10:41 | 100% COMPLETION | 100 | F1 Bldg Duct SH:01-04 Terrace Line-100% COMP | 736 | 2024-12-21 | 107108 | 2024-12-26 12:51 | -97668 | SOMNATH KALYAN TAPKIR
External Plumbing Work | N/C | N/C | SOMNATH KALYAN TAPKIR | 11 | 2024-07-16 | F1 Bldg Duct SH:05-09 Terrace Line-100% COMP. | 9440 | 1 | 0 | 9440 | 0 | 2024-12-21 10:41 | 100% COMPLETION | 100 | F1 Bldg Duct SH:05-09 Terrace Line-100% COMP | 736 | 2024-12-21 | 107108 | 2024-12-26 12:51 | -97668 | SOMNATH KALYAN TAPKIR
Internal Concealed Work | N/C | N/C | SOMNATH KALYAN TAPKIR | 11 | 2024-07-16 | F1 Bldg Flush Valve Fixing-LG,UG,1ST,2ND,3RD FLOOR | 12708 | 1 | 0 | 12708 | 0 | 2024-12-21 10:41 | 100% COMPLETION | 100 | F1 Bldg Flush Valve Fixing-3RD FLOOR | 736 | 2024-12-21 | 107108 | 2024-12-26 12:51 | -94400 | SOMNATH KALYAN TAPKIR
External Plumbing Work | N/C | N/C | SOMNATH KALYAN TAPKIR | 12 | 2024-07-18 | G1 Bldg, Duct SH:01-04 Toilet PVC -100% Comp. | 5962.32 | 1 | 0 | 5962.32 | 0 | 2025-01-03 11:03 | 100% COMPLETION | 100 | G1 Bldg, Duct SH:01-04 Toilet PVC -100% | 827 | 2025-01-03 | 36117.9 | 2025-01-06 14:47 | -30155.58 | SOMNATH KALYAN TAPKIR
External Plumbing Work | N/C | N/C | SOMNATH KALYAN TAPKIR | 12 | 2024-07-18 | G1 Bldg, Duct SH:05-09 Toilet PVC -100% Comp. | 5962.32 | 1 | 0 | 5962.32 | 0 | 2025-01-03 11:03 | 100% COMPLETION | 100 | G1 Bldg, Duct SH:05-09 Toilet PVC -100% | 827 | 2025-01-03 | 36117.9 | 2025-01-06 14:47 | -30155.58 | SOMNATH KALYAN TAPKIR
External Plumbing Work | N/C | N/C | SOMNATH KALYAN TAPKIR | 12 | 2024-07-18 | G1 Bldg, Duct SH:01-04 Toilet UPVC -100% Comp. | 2683.04 | 1 | 0 | 2683.04 | 0 | 2025-01-03 11:03 | 100% COMPLETION | 100 | G1 Bldg, Duct SH:01-04 Toilet UPVC -100% | 827 | 2025-01-03 | 36117.9 | 2025-01-06 14:47 | -33434.86 | SOMNATH KALYAN TAPKIR
External Plumbing Work | N/C | N/C | SOMNATH KALYAN TAPKIR | 12 | 2024-07-18 | G1 Bldg, Duct SH:05-09 Toilet UPVC -100% Comp. | 2683.04 | 1 | 0 | 2683.04 | 0 | 2025-01-03 11:03 | 100% COMPLETION | 100 | G1 Bldg, Duct SH:05-09 Toilet UPVC -100% | 827 | 2025-01-03 | 36117.9 | 2025-01-06 14:47 | -33434.86 | SOMNATH KALYAN TAPKIR
External Plumbing Work | N/C | N/C | SOMNATH KALYAN TAPKIR | 12 | 2024-07-18 | G1 Bldg, Duct SH:01-04 Terr. line -100% Comp. | 4769.86 | 1 | 0 | 4769.86 | 0 | 2025-01-03 11:03 | 100% COMPLETION | 100 | G1 Bldg, Duct SH:01-04 Terr. line -100% | 827 | 2025-01-03 | 36117.9 | 2025-01-06 14:47 | -31348.04 | SOMNATH KALYAN TAPKIR
External Plumbing Work | N/C | N/C | SOMNATH KALYAN TAPKIR | 12 | 2024-07-18 | G1 Bldg, Duct SH:05-09 Terr. line -100% Comp. | 4769.86 | 1 | 0 | 4769.86 | 0 | 2025-01-03 11:03 | 100% COMPLETION | 100 | G1 Bldg, Duct SH:05-09 Terr. line -100% | 827 | 2025-01-03 | 36117.9 | 2025-01-06 14:47 | -31348.04 | SOMNATH KALYAN TAPKIR
External Plumbing Work | N/C | N/C | SOMNATH KALYAN TAPKIR | 12 | 2024-07-18 | G1 Bldg, Duct Front Pass. line -100% Comp. | 2981.16 | 1 | 0 | 2981.16 | 0 | 2025-01-03 11:03 | 100% COMPLETION | 100 | G1 Bldg, Duct Front Pass. line -100% | 827 | 2025-01-03 | 36117.9 | 2025-01-06 14:47 | -33136.74 | SOMNATH KALYAN TAPKIR
External Plumbing Work | N/C | N/C | SOMNATH KALYAN TAPKIR | 12 | 2024-07-18 | G1 Bldg, "Looping" Top Terr-100% Comp. | 6306.3 | 1 | 0 | 6306.3 | 0 | 2025-01-03 11:03 | 100% COMPLETION | 100 | G1 Bldg, "Looping" Top Terr-100% Comp. | 827 | 2025-01-03 | 36117.9 | 2025-01-06 14:47 | -29811.6 | SOMNATH KALYAN TAPKIR
SHUTTERING, R/F & CASTING OF SLAB | N/C | N/C | SWEETY ENTERPRISES | 14 | 2024-07-18 | F1 Bldg RCC- 7TH SLAB SHUTTERING,REINF.,CASTING | 4602.6503 | 163 | 0 | 750231.9989 | 135041.76 | 2024-07-20 18:51 | 100% COMPLETION | 100 |  | 70 | 2024-07-20 | 750232 | 2024-07-22 18:50 | -0.0011 | SWEETY ENTERPRISES
SHUTTERING, R/F & CASTING OF SLAB | N/C | N/C | Shri Swami Samarth Construction & Developers | 15 | 2024-07-19 | G1 RCC- 7TH SLAB SHUTTERING,REINF.,CASTING | 2402.1494 | 162 | 0 | 389148.2028 | 70046.68 | 2024-07-20 17:25 | 100% COMPLETION | 100 |  | 65 | 2024-07-20 | 389148.2 | 2024-07-20 18:08 | 0.0028 | Shri Swami Samarth Construction & Developers
SHUTTERING, R/F & CASTING OF SLAB | N/C | N/C | Shri Swami Samarth Construction & Developers | 15 | 2024-07-19 | G1 RCC- OHWT, ST.CASE TOP SLAB SHUTTERING,REINF.,CASTING | 377.4848 | 162 | 0 | 61152.5376 | 11007.46 | 2024-09-20 15:33 | 100% COMPLETION | 100 | Against Bill no 64 | 310 | 2024-09-20 | 72857.04 | 2024-12-20 14:15 | -11704.5024 | Shri Swami Samarth Construction & Developers
ST-CASE PARDI,LINTEL & LOFT | N/C | N/C | Shri Swami Samarth Construction & Developers | 15 | 2024-07-19 | G1 RCC- ST. PARDI & MISC. WORK COMPLETION | 72.25 | 162 | 0 | 11704.5 | 2106.82 | 2024-09-20 15:49 | 100% COMPLETION | 100 | Against Bill no 64 | 310 | 2024-09-20 | 72857.04 | 2024-12-20 14:15 | -61152.54 | Shri Swami Samarth Construction & Developers
Hacking & Deshuttering | N/C | N/C | Shri Swami Samarth Construction & Developers | 15 | 2024-07-19 | G1 RCC- 5TH SLAB DESHUTTERING,HACKING | 162.5515 | 162 | 0 | 26333.343 | 4740 | 2024-09-05 15:23 | 100% COMPLETION | 100 | F1, G1 Building | 230 | 2024-09-05 | 223637.32 | 2024-12-20 14:15 | -197303.977 | Shri Swami Samarth Construction & Developers
Hacking & Deshuttering | N/C | N/C | Shri Swami Samarth Construction & Developers | 15 | 2024-07-19 | G1 RCC- 6TH SLAB DESHUTTERING,HACKING | 168.5719 | 162 | 0 | 27308.6478 | 4915.56 | 2024-09-05 15:23 | 100% COMPLETION | 100 | F1, G1 Building | 230 | 2024-09-05 | 223637.32 | 2024-12-20 14:15 | -196328.6722 | Shri Swami Samarth Construction & Developers
SHUTTERING, R/F & CASTING OF SLAB | N/C | N/C | Shri Swami Samarth Construction & Developers | 15 | 2024-07-19 | G1 RCC- OHWT, ST.CASE TOP SLAB SHUTTERING,REINF.,CASTING | 880.7839 | 162 | 0 | 142686.9918 | 25683.66 | 2024-09-05 15:23 | 100% COMPLETION | 100 | G1 Building | 230 | 2024-09-05 | 223637.32 | 2024-12-20 14:15 | -80950.3282 | Shri Swami Samarth Construction & Developers
ST-CASE PARDI,LINTEL & LOFT | N/C | N/C | Shri Swami Samarth Construction & Developers | 15 | 2024-07-19 | G1 RCC- ST. PARDI & MISC. WORK COMPLETION | 168.57 | 162 | 0 | 27308.34 | 4915.5 | 2024-09-05 15:23 | 100% COMPLETION | 100 | G1 Building | 230 | 2024-09-05 | 223637.32 | 2024-12-20 14:15 | -196328.98 | Shri Swami Samarth Construction & Developers
Hacking & Deshuttering | N/C | N/C | Shri Swami Samarth Construction & Developers | 15 | 2024-07-19 | G1 RCC- 7TH SLAB DESHUTTERING,HACKING | 126.4289 | 162 | 0 | 20481.4818 | 3686.66 | 2024-10-15 14:51 | 100% COMPLETION | 100 | AGAINST BILL NO 67 | 453 | 2024-10-15 | 52240.8 | 2024-12-20 14:16 | -31759.3182 | Shri Swami Samarth Construction & Developers
Hacking & Deshuttering | N/C | N/C | Shri Swami Samarth Construction & Developers | 15 | 2024-07-19 | G1 RCC- OHWT, ST.CASE TOP SLAB DESHUTTERING,HACKING | 66.2247 | 162 | 0 | 10728.4014 | 1931.12 | 2024-10-15 14:51 | 100% COMPLETION | 100 | AGAINST BILL NO 67 | 453 | 2024-10-15 | 52240.8 | 2024-12-20 14:16 | -41512.3986 | Shri Swami Samarth Construction & Developers
RCC CLEANING WORK | N/C | N/C | Shri Swami Samarth Construction & Developers | 15 | 2024-07-19 | G1 RCC- CLEANING UPTO 4TH SLAB & REMAINING.CLEANING | 129.8205 | 162 | 0 | 21030.921 | 3785.56 | 2024-10-15 | 100% COMPLETION | 100 |  | 453 | 2024-10-15 | 52240.8 | 2024-12-20 14:16 | -31209.879 | Shri Swami Samarth Construction & Developers
EXTERNAL PLASTER WORK | N/C | N/C | SURAJ CONSTRUCTION | 16 | 2024-07-19 | G1 Bldg- EXT. PLASTER EAST SIDE PORTION-50% | 64466 | 1 | 0 | 64466 | 11603.88 | 2024-09-05 18:04 | 100% COMPLETION | 100 | G1 External Plaster | 233 | 2024-09-05 | 64466 | 2024-12-24 10:50 | 0 | SURAJ CONSTRUCTION
EXTERNAL PLASTER WORK | N/C | N/C | SURAJ CONSTRUCTION | 16 | 2024-07-19 | G1 Bldg- EXT. PLASTER EAST SIDE BALANCE-50% | 64466 | 1 | 0 | 64466 | 11603.88 | 2024-09-05 18:04 | 100% COMPLETION | 100 | G1 External Plaster | 234 | 2024-09-05 | 64466 | 2024-12-24 10:50 | 0 | SURAJ CONSTRUCTION
BBM WORK | N/C | N/C | SUNITA TANAJI KACHARE | 17 | 2024-07-19 | G1 Bldg- BBM WORK - THIRD FLOOR | 38197 | 1 | 0 | 38197 | 0 | 2024-08-20 15:34 | 100% COMPLETION | 100 | G1 Building | 164 | 2024-08-20 | 93755 | 2024-09-04 16:29 | -55558 | SUNITA TANAJI KACHARE
INTERNAL PLASTER- | N/C | N/C | SUNITA TANAJI KACHARE | 17 | 2024-07-19 | G1 Bldg- INT. PLASTER SECOND FLOOR | 15701 | 1 | 0 | 15701 | 0 | 2024-08-20 15:34 | 100% COMPLETION | 100 | G1 Building | 164 | 2024-08-20 | 93755 | 2024-09-04 16:29 | -78054 | SUNITA TANAJI KACHARE
INTERNAL PLASTER- | N/C | N/C | SUNITA TANAJI KACHARE | 17 | 2024-07-19 | G1 Bldg- INT. PLASTER THIRD FLOOR | 15701 | 1 | 0 | 15701 | 0 | 2024-08-20 15:34 | 100% COMPLETION | 100 | G1 Building | 164 | 2024-08-20 | 93755 | 2024-09-04 16:29 | -78054 | SUNITA TANAJI KACHARE
INTERNAL PLASTER- | N/C | N/C | SUNITA TANAJI KACHARE | 17 | 2024-07-19 | G1 Bldg- INT. PLASTER PASSAGE 1ST,2ND & 3RD FLOOR | 24156 | 1 | 0 | 24156 | 0 | 2024-08-20 15:34 | 100% COMPLETION | 100 | G1 Building | 164 | 2024-08-20 | 93755 | 2024-09-04 16:29 | -69599 | SUNITA TANAJI KACHARE
BBM WORK | N/C | N/C | SUNITA TANAJI KACHARE | 17 | 2024-07-19 | G1 Bldg- BBM WORK - TOP TERRACE FLOOR | 10417 | 1 | 0 | 10417 | 0 | 2024-09-05 17:58 | 100% COMPLETION | 100 | Top Terrace BBM Work At G1 Building | 232 | 2024-09-05 | 42650 | 2024-12-20 14:17 | -32233 | SUNITA TANAJI KACHARE
EXTERNAL PLASTER WORK | N/C | N/C | SUNITA TANAJI KACHARE | 17 | 2024-07-19 | G1 Bldg- EXT. PLASTER PARAPET | 32233 | 1 | 0 | 32233 | 0 | 2024-09-05 17:58 | 100% COMPLETION | 100 | External Plaster G1 Building | 232 | 2024-09-05 | 42650 | 2024-12-20 14:17 | -10417 | SUNITA TANAJI KACHARE
EXTERNAL PLASTER WORK | N/C | N/C | SUNITA TANAJI KACHARE | 17 | 2024-07-19 | G1 Bldg- EXT. PLASTER LIFT SCAFF. & PLASTER | 32233 | 1 | 0 | 32233 | 0 | 2025-01-03 10:19 | 100% COMPLETION | 100 | G1 Bldg- EXT. PLASTER LIFT SCAFF. & PLASTER-DONE | 823 | 2025-01-03 | 32233 | 2025-01-06 14:44 | 0 | SUNITA TANAJI KACHARE
BBM WORK | N/C | N/C | SUNITA TANAJI KACHARE | 17 | 2024-07-19 | G1 Bldg- BBM WORK - LIFT BBM | 9549 | 1 | 0 | 9549 | 0 | 2024-10-15 11:56 | 100% COMPLETION | 100 | Against Bill no 7 | 452 | 2024-10-15 | 41782 | 2024-12-20 14:17 | -32233 | SUNITA TANAJI KACHARE
EXTERNAL PLASTER WORK | N/C | N/C | SUNITA TANAJI KACHARE | 17 | 2024-07-19 | G1 Bldg- EXT. PLASTER OHWT | 32233 | 1 | 0 | 32233 | 0 | 2024-10-15 11:56 | 100% COMPLETION | 100 | Against Bill no 7 | 452 | 2024-10-15 | 41782 | 2024-12-20 14:17 | -9549 | SUNITA TANAJI KACHARE
EXTERNAL PLASTER WORK | N/C | N/C | SURAJ CONSTRUCTION | 18 | 2024-07-19 | F1 Bldg Part- EXT. PLASTER EAST SIDE-50% | 50151 | 1 | 0 | 50151 | 9027.18 | 2024-10-15 11:02 | 100% COMPLETION | 100 | Against Bill no 39/ 04-10-2024 | 450 | 2024-10-15 | 50151 | 2024-12-24 10:44 | 0 | SURAJ CONSTRUCTION
EXTERNAL PLASTER WORK | N/C | N/C | SURAJ CONSTRUCTION | 18 | 2024-07-19 | F1 Bldg Part- EXT. PLASTER EAST SIDE BAL.PLASTER | 50151 | 1 | 0 | 50151 | 9027.18 | 2024-10-15 11:04 | 100% COMPLETION | 100 | Against Bill no 42 | 451 | 2024-10-15 | 50151 | 2024-12-24 10:44 | 0 | SURAJ CONSTRUCTION
EXTERNAL PLASTER WORK | N/C | N/C | SUNITA TANAJI KACHARE | 19 | 2024-07-19 | F1 Bldg Part- EXT. PLASTER WEST SIDE-50% | 69654 | 1 | 0 | 69654 | 0 | 2024-08-05 15:37 | 100% COMPLETION | 100 | Work Completed | 95 | 2024-08-05 | 78877 | 2024-08-06 15:18 | -9223 | SUNITA TANAJI KACHARE
INTERNAL PLASTER- | N/C | N/C | SUNITA TANAJI KACHARE | 19 | 2024-07-19 | F1 Bldg Part- INT.PLASTER SECOND FLOOR | 9223 | 1 | 0 | 9223 | 0 | 2024-08-05 15:37 | 100% COMPLETION | 100 | Work Completed | 95 | 2024-08-05 | 78877 | 2024-08-06 15:18 | -69654 | SUNITA TANAJI KACHARE
Brickbat Waterproofing Labour only per Toilet | N/C | N/C | SHREE SWAMI SAMARTHA CONSTRUCTION | 2 | 2024-05-16 | Lower Ground Shop Toilet Waterproofing Brickbat Water Proofi | 4.0002 | 1499.9 | 0 | 1055.9824 | 0 | 2024-05-16 16:17 | Chemical Coat | 17.6 | Complete | 3 | 2024-05-16 | 5174.32 | 2024-07-26 19:08 | -4118.3376 | SHREE SWAMI SAMARTHA CONSTRUCTION
Brickbat Waterproofing Labour only per Toilet | N/C | N/C | SHREE SWAMI SAMARTHA CONSTRUCTION | 2 | 2024-05-16 | Lower Ground Shop Toilet Waterproofing Brickbat Water Proofi | 4.0002 | 1499.9 | 0 | 1319.978 | 0 | 2024-05-16 16:17 | Base Coat | 22 | Complete | 3 | 2024-05-16 | 5174.32 | 2024-07-26 19:08 | -3854.342 | SHREE SWAMI SAMARTHA CONSTRUCTION
Brickbat Waterproofing Labour only per Toilet | N/C | N/C | SHREE SWAMI SAMARTHA CONSTRUCTION | 2 | 2024-05-16 | Lower Ground Shop Toilet Waterproofing Brickbat Water Proofi | 4.0002 | 1499.9 | 0 | 1319.978 | 0 | 2024-05-16 16:17 | Brick Bat | 22 | Complete | 3 | 2024-05-16 | 5174.32 | 2024-07-26 19:08 | -3854.342 | SHREE SWAMI SAMARTHA CONSTRUCTION
Brickbat Waterproofing Labour only per Toilet | N/C | N/C | SHREE SWAMI SAMARTHA CONSTRUCTION | 2 | 2024-05-16 | Lower Ground Shop Toilet Waterproofing Brickbat Water Proofi | 4.0002 | 1499.9 | 0 | 1478.3754 | 0 | 2024-05-16 16:17 | Finishing | 24.64 | Complete | 3 | 2024-05-16 | 5174.32 | 2024-07-26 19:08 | -3695.9446 | SHREE SWAMI SAMARTHA CONSTRUCTION
EXTERNAL PLASTER WORK | N/C | N/C | Shree Gopal Ruplal Pawar | 20 | 2024-07-19 | F1 Bldg Part- EXT. PLASTER EAST SIDE | 74078 | 1 | 0 | 74078 | 13334.04 | 2024-09-05 13:08 | 100% COMPLETION | 100 | East Face External Plaster at F1 Building | 229 | 2024-09-05 | 140749 | 2024-12-24 10:33 | -66671 | Shree Gopal Ruplal Pawar
EXTERNAL PLASTER WORK | N/C | N/C | Shree Gopal Ruplal Pawar | 20 | 2024-07-19 | F1 Bldg Part- EXT. PLASTER NORTH SIDE-100% | 66671 | 1 | 0 | 66671 | 12000.78 | 2024-09-05 13:08 | 100% COMPLETION | 100 | North Face External Plaster 30% at F1 Building | 229 | 2024-09-05 | 140749 | 2024-12-24 10:33 | -74078 | Shree Gopal Ruplal Pawar
EXTERNAL PLASTER WORK | N/C | N/C | Shree Gopal Ruplal Pawar | 20 | 2024-07-19 | F1 Bldg Part- EXT. ELEC. & FIRE DUCT | 37039 | 1 | 0 | 37039 | 6667.02 | 2024-12-09 15:53 | 100% COMPLETION | 100 | F1 Bldg Part- EXT. ELEC. & FIRE DUCT S EXTERNAL PLASTER WORK-100% | 654 | 2024-12-09 | 37039 | 2024-12-24 10:34 | 0 | Shree Gopal Ruplal Pawar
BBM WORK | N/C | N/C | MANGAL ENTERPRISES | 21 | 2024-07-19 | F1 Bldg Part- BBM WORK TOP TERRACE FLOOR | 45457 | 1 | 0 | 45457 | 0 | 2024-11-23 17:22 | 100% COMPLETION | 100 | AGAINST BIll no 12 | 543 | 2024-11-23 | 45457 | 2024-12-24 10:30 | 0 | MANGAL ENTERPRISES
EXTERNAL PLASTER WORK | N/C | N/C | MANGAL ENTERPRISES | 21 | 2024-07-19 | F1 Bldg Part- EXT. PLASTER LIFT SCAFF & PLASTER | 64819 | 1 | 0 | 64819 | 0 | 2024-12-09 16:23 | 100% COMPLETION | 100 | LIFT SCAFF & PLASTER | 656 | 2024-12-09 | 64819 | 2024-12-24 10:30 | 0 | MANGAL ENTERPRISES
BBM WORK | N/C | N/C | MANGAL ENTERPRISES | 21 | 2024-07-19 | F1 Bldg Part- BBM WORK THIRD FLOOR | 151524 | 1 | 0 | 151524 | 0 | 2024-09-20 11:57 | 100% COMPLETION | 100 | Work Complition Against Bill no 09 Dt 19-09-2024 | 308 | 2024-09-20 | 151524 | 2024-12-24 10:30 | 0 | MANGAL ENTERPRISES
INTERNAL PLASTER- | N/C | N/C | MANGAL ENTERPRISES | 21 | 2024-07-19 | F1 Bldg Part- INT.PLASTER THIRD FLOOR | 71553 | 1 | 0 | 71553 | 0 | 2024-10-05 19:11 | 100% COMPLETION | 100 | AGAINST BILL NO 7 | 397 | 2024-10-05 | 71553 | 2024-12-24 10:30 | 0 | HARSHAD GOPAL PAWAR
INTERNAL PLASTER- | N/C | N/C | MANGAL ENTERPRISES | 21 | 2024-07-19 | F1 Bldg Part- INT.PLASTER SECOND FLOOR | 67344 | 1 | 0 | 67344 | 0 | 2024-08-05 17:05 | 100% COMPLETION | 100 | F1 Second Floor Internal Plaster | 99 | 2024-08-05 | 67344 | 2024-08-06 15:07 | 0 | HARSHAD GOPAL PAWAR
EXTERNAL PLASTER WORK | N/C | N/C | MANGAL ENTERPRISES | 21 | 2024-07-19 | F1 Bldg Part- EXT. PLASTER SOUTH SIDE-60% | 137044.9907 | 1 | 0 | 137044.9907 | 0 | 2025-01-03 10:40 | 100% COMPLETION | 100 | F1 Bldg Part- EXT. PLASTER SOUTH SIDE-40% DONE | 825 | 2025-01-03 | 221224.99 | 2025-01-06 14:46 | -84179.9993 | HARSHAD GOPAL PAWAR
INTERNAL PLASTER- | N/C | N/C | MANGAL ENTERPRISES | 21 | 2024-07-19 | F1 Bldg Part- INT.PLASTER PASSAGE L.G,1ST,2ND,3RD FLOOR | 84180 | 1 | 0 | 84180 | 0 | 2025-01-03 10:42 | 100% COMPLETION | 100 | F1 Bldg Part- INT.PLASTER PASSAGE L.G,1ST,2ND,3RD FLOOR-DONE | 825 | 2025-01-03 | 221224.99 | 2025-01-06 14:46 | -137044.99 | HARSHAD GOPAL PAWAR
SAFETY NET FIXING | N/C | N/C | MARUTI SHAKTI SAFETY NET SERVICES | 22 | 2024-07-22 | SAFETY NET FIXING & REMOVING | 645 | 2.25 | 0 | 1451.25 | 0 | 2025-01-03 11:11 | 100% COMPLETION | 100 | F1 BLDG OHWT,CHALAN-146 | 828 | 2025-01-03 | 28081.5 | 2025-01-06 14:47 | -26630.25 | MARUTI SHAKTI SAFETY NET SERVICES
SAFETY NET REMOVING WORK | N/C | N/C | MARUTI SHAKTI SAFETY NET SERVICES | 22 | 2024-07-22 | SAFETY NET FIXING & REMOVING | 1291 | 1.25 | 0 | 1613.75 | 0 | 2025-01-03 11:11 | 100% COMPLETION | 100 | F1 BLDG OHWT,CHALAN-146 | 828 | 2025-01-03 | 28081.5 | 2025-01-06 14:47 | -26467.75 | MARUTI SHAKTI SAFETY NET SERVICES
SAFETY NET FIXING | N/C | N/C | MARUTI SHAKTI SAFETY NET SERVICES | 22 | 2024-07-22 | SAFETY NET FIXING & REMOVING | 9684 | 2.25 | 0 | 21789 | 0 | 2025-01-03 11:15 | 100% COMPLETION | 100 | F1 BLDG OHWT,CHALAN-307 | 828 | 2025-01-03 | 28081.5 | 2025-01-06 14:47 | -6292.5 | MARUTI SHAKTI SAFETY NET SERVICES
SAFETY NET REMOVING WORK | N/C | N/C | MARUTI SHAKTI SAFETY NET SERVICES | 22 | 2024-07-22 | SAFETY NET FIXING & REMOVING | 2582 | 1.25 | 0 | 3227.5 | 0 | 2025-01-03 11:15 | 100% COMPLETION | 100 | F1 BLDG OHWT,CHALAN-307 | 828 | 2025-01-03 | 28081.5 | 2025-01-06 14:47 | -24854 | MARUTI SHAKTI SAFETY NET SERVICES
SAFETY NET FIXING | N/C | N/C | MARUTI SHAKTI SAFETY NET SERVICES | 22 | 2024-07-22 | SAFETY NET FIXING & REMOVING | 7747 | 2.25 | 0 | 17430.75 | 0 | 2025-01-03 11:21 | 100% COMPLETION | 100 | E1 BLDG SAFETY NET OUTER SIDE FIXING, CHALAN-362 | 829 | 2025-01-03 | 24869.75 | 2025-01-06 14:47 | -7439 | MARUTI SHAKTI SAFETY NET SERVICES
SAFETY NET CLEANING WORK | N/C | N/C | MARUTI SHAKTI SAFETY NET SERVICES | 22 | 2024-07-22 | SAFETY NET FIXING & REMOVING | 4519 | 0.5 | 0 | 2259.5 | 0 | 2025-01-03 11:21 | 100% COMPLETION | 100 | SAFETY NET CLEANING, CHALAN-361 | 829 | 2025-01-03 | 24869.75 | 2025-01-06 14:47 | -22610.25 | MARUTI SHAKTI SAFETY NET SERVICES
SAFETY NET FIXING | N/C | N/C | MARUTI SHAKTI SAFETY NET SERVICES | 22 | 2024-07-22 | SAFETY NET FIXING & REMOVING | 2302 | 2.25 | 0 | 5179.5 | 0 | 2025-01-03 11:23 | 100% COMPLETION | 100 | E1 BLDG SAFETY NET DUCT FIXING, CHALAN-362 | 829 | 2025-01-03 | 24869.75 | 2025-01-06 14:47 | -19690.25 | MARUTI SHAKTI SAFETY NET SERVICES
SAFETY NET FIXING | N/C | N/C | MARUTI SHAKTI SAFETY NET SERVICES | 22 | 2024-07-22 | SAFETY NET FIXING & REMOVING | 3497 | 2.25 | 0 | 7868.25 | 0 | 2025-01-19 15:03 | 100% COMPLETION | 100 | Against Bill no 718 | 962 | 2025-01-19 | 16556.75 | 2025-01-20 14:55 | -8688.5 | MARUTI SHAKTI SAFETY NET SERVICES
SAFETY NET CLEANING WORK | N/C | N/C | MARUTI SHAKTI SAFETY NET SERVICES | 22 | 2024-07-22 | SAFETY NET FIXING & REMOVING | 17377 | 0.5 | 0 | 8688.5 | 0 | 2025-01-19 15:03 | 100% COMPLETION | 100 | Against Bill no 718 | 962 | 2025-01-19 | 16556.75 | 2025-01-20 14:55 | -7868.25 | MARUTI SHAKTI SAFETY NET SERVICES
SAFETY NET FIXING | N/C | N/C | MARUTI SHAKTI SAFETY NET SERVICES | 22 | 2024-07-22 | SAFETY NET FIXING & REMOVING | 15494 | 2.25 | 0 | 34861.5 | 0 | 2024-07-26 17:49 | 100% COMPLETION | 100 | F1 Building External front face & Back side | 81 | 2024-07-26 | 52615.25 | 2024-07-26 19:11 | -17753.75 | MARUTI SHAKTI SAFETY NET SERVICES
SAFETY NET REMOVING WORK | N/C | N/C | MARUTI SHAKTI SAFETY NET SERVICES | 22 | 2024-07-22 | SAFETY NET FIXING & REMOVING | 14203 | 1.25 | 0 | 17753.75 | 0 | 2024-07-26 17:49 | 100% COMPLETION | 100 | F1 Building External front face & Back side | 81 | 2024-07-26 | 52615.25 | 2024-07-26 19:11 | -34861.5 | MARUTI SHAKTI SAFETY NET SERVICES
SAFETY NET FIXING | N/C | N/C | MARUTI SHAKTI SAFETY NET SERVICES | 22 | 2024-07-22 | SAFETY NET FIXING & REMOVING | 2582 | 2.25 | 0 | 5809.5 | 0 | 2024-10-14 19:36 | 100% COMPLETION | 100 | 10 x 6=4 NOS | 447 | 2024-10-14 | 17914.5 | 2024-12-24 10:51 | -12105 | MARUTI SHAKTI SAFETY NET SERVICES
SAFETY NET REMOVING WORK | N/C | N/C | MARUTI SHAKTI SAFETY NET SERVICES | 22 | 2024-07-22 | SAFETY NET FIXING & REMOVING | 9684 | 1.25 | 0 | 12105 | 0 | 2024-10-14 19:36 | 100% COMPLETION | 100 | 1)10x6=15 nos | 447 | 2024-10-14 | 17914.5 | 2024-12-24 10:51 | -5809.5 | MARUTI SHAKTI SAFETY NET SERVICES
SAFETY NET FIXING | N/C | N/C | MARUTI SHAKTI SAFETY NET SERVICES | 22 | 2024-07-22 | SAFETY NET FIXING & REMOVING | 645 | 2.25 | 0 | 1451.25 | 0 | 2024-08-19 11:13 | 100% COMPLETION | 100 | G1 Building Front Side Net Fixing work | 156 | 2024-08-19 | 11787.5 | 2024-09-04 16:32 | -10336.25 | MARUTI SHAKTI SAFETY NET SERVICES
SAFETY NET REMOVING WORK | N/C | N/C | MARUTI SHAKTI SAFETY NET SERVICES | 22 | 2024-07-22 | SAFETY NET FIXING & REMOVING | 5915 | 1.25 | 0 | 7393.75 | 0 | 2024-08-19 11:13 | 100% COMPLETION | 100 | Work Done At G1 Building Front and Back side Podium Face | 156 | 2024-08-19 | 11787.5 | 2024-09-04 16:32 | -4393.75 | MARUTI SHAKTI SAFETY NET SERVICES
SAFETY NET CLEANING WORK | N/C | N/C | MARUTI SHAKTI SAFETY NET SERVICES | 22 | 2024-07-22 | SAFETY NET FIXING & REMOVING | 5885 | 0.5 | 0 | 2942.5 | 0 | 2024-08-19 11:13 | 100% COMPLETION | 100 | F1 Building Front Side & G1 Side Cleaning Work | 156 | 2024-08-19 | 11787.5 | 2024-09-04 16:32 | -8845 | MARUTI SHAKTI SAFETY NET SERVICES
Curtain wall facade with 115mm x 67mm | N/C | N/C | POTDAR CREATION | 23 | 2024-07-24 | Mat.1.Glass Glazing 15% ADV | 203.64 | 311.5 | 0 | 63433.86 | 11418.1 | 2024-08-08 14:01 | 100% COMPLETION | 100 | Advance against work order | 128 | 2024-08-08 | 70571.17 | 2024-09-04 16:37 | -7137.31 | POTDAR CREATION
Curtain wall facade with 45mm x 45mm - 3.700Kg - per 12ft | N/C | N/C | POTDAR CREATION | 23 | 2024-07-24 | Mat.1.Glass Glazing 15% ADV | 33.43 | 213.5 | 0 | 7137.305 | 1284.72 | 2024-08-08 14:01 | 100% COMPLETION | 100 | Advance against work order | 128 | 2024-08-08 | 70571.17 | 2024-09-04 16:37 | -63433.865 | POTDAR CREATION
Supply of Trimix Machine & labour | N/C | N/C | Santosh Awale | 25 | 2024-08-03 | UP TO 1st Slab & Above Coln E1building 1st slab levelling by | 13281 | 5 | 0 | 66405 | 0 | 2024-08-06 18:37 | 100% COMPLETION | 100 | E1 Building 1st Slab top finishing with Flotar and Tar Brush | 103 | 2024-08-06 | 66405 | 2024-08-07 18:54 | 0 | Santosh Awale
CONSTRUCTION QUALITY MONITORING | N/C | N/C | CQRA PVT. LTD. | 27 | 2024-08-05 | SITE SAFETY & QUALITY SITE SAFETY & QUALITY MONITORING | 1 | 70000 | 0 | 70000 | 12600 | 2024-08-05 16:51 | 100% COMPLETION | 100 | QA-QC Service | 97 | 2024-08-05 | 70000 | 2024-08-06 15:11 | 0 | CQRA PVT. LTD.
CONSTRUCTION QUALITY MONITORING | N/C | N/C | CQRA PVT. LTD. | 27 | 2024-08-05 | SITE SAFETY & QUALITY SITE SAFETY & QUALITY MONITORING | 1 | 70000 | 0 | 70000 | 12600 | 2025-02-04 15:23 | 100% COMPLETION | 100 | CONSTRUCTION QUALITY MONITORING-JAN 2025 | 1064 | 2025-02-04 | 70000 | 2025-02-05 14:30 | 0 | CQRA PVT. LTD.
CONSTRUCTION QUALITY MONITORING | N/C | N/C | CQRA PVT. LTD. | 27 | 2024-08-05 | SITE SAFETY & QUALITY SITE SAFETY & QUALITY MONITORING | 1 | 70000 | 0 | 70000 | 12600 | 2025-01-06 15:06 | 100% COMPLETION | 100 | Against Bill no 699 | 852 | 2025-01-06 | 70000 | 2025-01-09 10:18 | 0 | CQRA PVT. LTD.
SITE SAFETY MONITORING | N/C | N/C | CQRA PVT. LTD. | 28 | 2024-08-05 | SITE SAFETY & QUALITY SITE SAFETY & QUALITY MONITORING | 1 | 98000 | 0 | 98000 | 17640 | 2025-01-06 15:05 | 100% COMPLETION | 100 | Against Bill no 697 | 851 | 2025-01-06 | 98000 | 2025-01-09 10:18 | 0 | CQRA PVT. LTD.
SITE SAFETY MONITORING | N/C | N/C | CQRA PVT. LTD. | 28 | 2024-08-05 | SITE SAFETY & QUALITY SITE SAFETY & QUALITY MONITORING | 1 | 98000 | 0 | 98000 | 17640 | 2025-02-04 15:23 | 100% COMPLETION | 100 | MONITORING S SITE SAFETY MONITORING-JAN 2025 | 1065 | 2025-02-04 | 98000 | 2025-02-05 14:30 | 0 | CQRA PVT. LTD.
SITE SAFETY MONITORING | N/C | N/C | CQRA PVT. LTD. | 28 | 2024-08-05 | SITE SAFETY & QUALITY SITE SAFETY & QUALITY MONITORING | 1 | 98000 | 0 | 98000 | 17640 | 2024-08-05 16:53 | 100% COMPLETION | 100 | For the Month of July 2024 | 98 | 2024-08-05 | 98000 | 2024-08-06 15:11 | 0 | CQRA PVT. LTD.
Chamber 1.5 x 1.5 ft Electrical | N/C | N/C | SOMNATH KALYAN TAPKIR | 29 | 2024-08-05 | DEVELOPMENT UG Plumbing & Electrical Line & Chambers | 15 | 1200 | 0 | 18000 | 0 | 2024-08-06 18:45 | 100% COMPLETION | 100 | Work done at Lower Ground Floor of F1 Building & Drive Way | 104 | 2024-08-06 | 47861 | 2024-08-07 18:44 | -29861 | SOMNATH KALYAN TAPKIR
Chamber 2 X 2 ft Drainage | N/C | N/C | SOMNATH KALYAN TAPKIR | 29 | 2024-08-05 | DEVELOPMENT UG Plumbing & Electrical Line & Chambers | 10 | 1650 | 0 | 16500 | 0 | 2024-08-06 18:45 | 100% COMPLETION | 100 | Work done at Lower Ground Floor of F1 Building & Drive Way | 104 | 2024-08-06 | 47861 | 2024-08-07 18:44 | -31361 | SOMNATH KALYAN TAPKIR
PVC Line 8 inch | N/C | N/C | SOMNATH KALYAN TAPKIR | 29 | 2024-08-05 | DEVELOPMENT UG Plumbing & Electrical Line & Chambers | 272 | 8 | 0 | 2176 | 0 | 2024-08-06 18:45 | 100% COMPLETION | 100 | Work Done in front of F1 Building shop Passage area at Lower Ground Floor | 104 | 2024-08-06 | 47861 | 2024-08-07 18:44 | -45685 | SOMNATH KALYAN TAPKIR
RCC line 12-inch Strom Water Line | N/C | N/C | SOMNATH KALYAN TAPKIR | 29 | 2024-08-05 | DEVELOPMENT UG Plumbing & Electrical Line & Chambers | 63 | 55 | 0 | 3465 | 0 | 2024-08-06 18:45 | 100% COMPLETION | 100 | work done at F1 Shop front Driveway Storm water line | 104 | 2024-08-06 | 47861 | 2024-08-07 18:44 | -44396 | SOMNATH KALYAN TAPKIR
RCC line 8-inch Drainage Line | N/C | N/C | SOMNATH KALYAN TAPKIR | 29 | 2024-08-05 | DEVELOPMENT UG Plumbing & Electrical Line & Chambers | 139 | 30 | 0 | 4170 | 0 | 2024-08-06 18:45 | 100% COMPLETION | 100 | work done at F1 Shop front Driveway Storm water line | 104 | 2024-08-06 | 47861 | 2024-08-07 18:44 | -43691 | SOMNATH KALYAN TAPKIR
Round Chamber Extension above 5' | N/C | N/C | SOMNATH KALYAN TAPKIR | 29 | 2024-08-05 | DEVELOPMENT UG Plumbing & Electrical Line & Chambers | 1.5 | 300 | 0 | 450 | 0 | 2024-08-06 18:45 | 100% COMPLETION | 100 | Developed for Stormwater Line near Visawa for Lvel Difference | 104 | 2024-08-06 | 47861 | 2024-08-07 18:44 | -47411 | SOMNATH KALYAN TAPKIR
Round Chamber Making up to 5ft Height | N/C | N/C | SOMNATH KALYAN TAPKIR | 29 | 2024-08-05 | DEVELOPMENT UG Plumbing & Electrical Line & Chambers | 1 | 3100 | 0 | 3100 | 0 | 2024-08-06 18:45 | 100% COMPLETION | 100 | Developed for Stormwater Line near Visawa for Lvel Difference | 104 | 2024-08-06 | 47861 | 2024-08-07 18:44 | -44761 | SOMNATH KALYAN TAPKIR
Chamber 2 x 3 ft Drainage | N/C | N/C | SOMNATH KALYAN TAPKIR | 29 | 2024-08-05 | DEVELOPMENT UG Plumbing & Electrical Line & Chambers | 5 | 2100 | 0 | 10500 | 0 | 2024-08-16 11:02 | 100% COMPLETION | 100 | Work Done At E1 Building Drainage Line. | 152 | 2024-08-16 | 22985 | 2024-09-04 16:32 | -12485 | SOMNATH KALYAN TAPKIR
RCC line 12-inch Strom Water Line | N/C | N/C | SOMNATH KALYAN TAPKIR | 29 | 2024-08-05 | DEVELOPMENT UG Plumbing & Electrical Line & Chambers | 227 | 55 | 0 | 12485 | 0 | 2024-08-16 11:02 | 100% COMPLETION | 100 | Work Done at Drainage line at E1 Building | 152 | 2024-08-16 | 22985 | 2024-09-04 16:32 | -10500 | SOMNATH KALYAN TAPKIR
IPS WATERPROOFING ONLY LABOUR | N/C | N/C | SHREE SWAMI SAMARTHA CONSTRUCTION | 3 | 2024-06-08 | Waterproofing INDENT NO-1138/IPS WATERPROOFING F1 PASS | 1398 | 10 | 0 | 13980 | 0 | 2024-06-08 12:52 | 100% COMPLETION | 100 | WORK COMPLETED | 10 | 2024-06-08 | 17492 | 2024-07-26 19:08 | -3512 | SHREE SWAMI SAMARTHA CONSTRUCTION
WATER PROOFING BRCKBAT & FINISHING ONLY LABOUR | N/C | N/C | SHREE SWAMI SAMARTHA CONSTRUCTION | 3 | 2024-06-08 | Waterproofing INDENT NO-1138/IPS WATERPROOFING F1 PASS | 219.5 | 16 | 0 | 3512 | 0 | 2024-06-08 12:52 | 100% COMPLETION | 100 | WORK COMPLETED | 10 | 2024-06-08 | 17492 | 2024-07-26 19:08 | -13980 | SHREE SWAMI SAMARTHA CONSTRUCTION
Electrical Helper | N/C | N/C | SUYASH ENTERPRISES | 30 | 2024-08-20 | DEVELOPMENT Electrical Maintenance Work | 1 | 500 | 0 | 500 | 0 | 2024-09-06 11:14 | 100% COMPLETION | 100 | Against Bill no 4 DPR No 002 | 236 | 2024-09-06 | 1500 | 2024-12-20 14:19 | -1000 | SUYASH ENTERPRISES
Electrician Skilled | N/C | N/C | SUYASH ENTERPRISES | 30 | 2024-08-20 | DEVELOPMENT Electrical Maintenance Work | 1 | 1000 | 0 | 1000 | 0 | 2024-09-06 11:14 | 100% COMPLETION | 100 | Against Bill no 4 DPR No 002 | 236 | 2024-09-06 | 1500 | 2024-12-20 14:19 | -500 | SUYASH ENTERPRISES
Electrical Helper | N/C | N/C | SUYASH ENTERPRISES | 30 | 2024-08-20 | DEVELOPMENT Electrical Maintenance Work | 2 | 500 | 0 | 1000 | 0 | 2024-09-06 12:03 | 100% COMPLETION | 100 | Bill Against Electrical Maintenance Work as per DPR no 3 | 237 | 2024-09-06 | 2000 | 2024-12-20 14:19 | -1000 | SUYASH ENTERPRISES
Electrician Skilled | N/C | N/C | SUYASH ENTERPRISES | 30 | 2024-08-20 | DEVELOPMENT Electrical Maintenance Work | 1 | 1000 | 0 | 1000 | 0 | 2024-09-06 12:03 | 100% COMPLETION | 100 | Bill Against Electrical Maintenance Work as per DPR no 3 | 237 | 2024-09-06 | 2000 | 2024-12-20 14:19 | -1000 | SUYASH ENTERPRISES
Electrical Helper | N/C | N/C | SUYASH ENTERPRISES | 30 | 2024-08-20 | DEVELOPMENT Electrical Maintenance Work | 1 | 500 | 0 | 500 | 0 | 2024-09-06 12:11 | 100% COMPLETION | 100 | Bill Against Electrical Maintenance Work as per DPR no 4 | 239 | 2024-09-06 | 2000 | 2024-12-20 14:19 | -1500 | SUYASH ENTERPRISES
Electrician Skilled | N/C | N/C | SUYASH ENTERPRISES | 30 | 2024-08-20 | DEVELOPMENT Electrical Maintenance Work | 1.5 | 1000 | 0 | 1500 | 0 | 2024-09-06 12:11 | 100% COMPLETION | 100 | Bill Against Electrical Maintenance Work as per DPR no 4 | 239 | 2024-09-06 | 2000 | 2024-12-20 14:19 | -500 | SUYASH ENTERPRISES
Electrical Helper | N/C | N/C | SUYASH ENTERPRISES | 30 | 2024-08-20 | DEVELOPMENT Electrical Maintenance Work | 1 | 500 | 0 | 500 | 0 | 2024-09-06 12:15 | 100% COMPLETION | 100 | Bill Against Electrical Maintenance Work as per DPR no 5 | 240 | 2024-09-06 | 1500 | 2024-12-24 10:46 | -1000 | SUYASH ENTERPRISES
Electrician Skilled | N/C | N/C | SUYASH ENTERPRISES | 30 | 2024-08-20 | DEVELOPMENT Electrical Maintenance Work | 1 | 1000 | 0 | 1000 | 0 | 2024-09-06 12:15 | 100% COMPLETION | 100 | Bill Against Electrical Maintenance Work as per DPR no 5 | 240 | 2024-09-06 | 1500 | 2024-12-24 10:46 | -500 | SUYASH ENTERPRISES
Electrical Helper | N/C | N/C | SUYASH ENTERPRISES | 30 | 2024-08-20 | DEVELOPMENT Electrical Maintenance Work | 8.048 | 500 | 0 | 4024 | 0 | 2024-09-06 12:28 | 100% COMPLETION | 100 | Bill Against Supply & Installation of MCCB 100A 4 pole with spreader link AND 85 AMP 4pole Contactor with Addon | 241 | 2024-09-06 | 16024 | 2024-12-24 10:46 | -12000 | SUYASH ENTERPRISES
Electrician Skilled | N/C | N/C | SUYASH ENTERPRISES | 30 | 2024-08-20 | DEVELOPMENT Electrical Maintenance Work | 12 | 1000 | 0 | 12000 | 0 | 2024-09-06 12:28 | 100% COMPLETION | 100 | Bill Against Supply & Installation of MCCB 100A 4 pole with spreader link AND 85 AMP 4pole Contactor with Addon | 241 | 2024-09-06 | 16024 | 2024-12-24 10:46 | -4024 | SUYASH ENTERPRISES
Electrician Skilled | N/C | N/C | SUYASH ENTERPRISES | 30 | 2024-08-20 | DEVELOPMENT Electrical Maintenance Work | 7.936 | 1000 | 0 | 7936 | 0 | 2024-09-06 12:39 | 100% COMPLETION | 100 | Bill Against Supply of additional 85 AMP 4pole Contactor with Addon | 242 | 2024-09-06 | 7936 | 2024-12-24 10:46 | 0 | SUYASH ENTERPRISES
Electrical Helper | N/C | N/C | SUYASH ENTERPRISES | 30 | 2024-08-20 | DEVELOPMENT Electrical Maintenance Work | 2.1 | 500 | 0 | 1050 | 0 | 2024-09-06 12:50 | 100% COMPLETION | 100 | Providing Electrical technician for Fixing Flood Light at F1, G1 Elevation Face | 245 | 2024-09-06 | 1050 | 2024-12-24 10:46 | 0 | SUYASH ENTERPRISES
Electrical Helper | N/C | N/C | SUYASH ENTERPRISES | 30 | 2024-08-20 | DEVELOPMENT Electrical Maintenance Work | 4 | 500 | 0 | 2000 | 0 | 2024-09-06 13:09 | 100% COMPLETION | 100 | Installation and Maintenance of 1) 160 Amp 4 pole MCCB 2) Laying of 95 sq.mm. x 3.5 Core armad cable 5 mtr 3) Termination of 95 sqmm Armad cable 2 nos 4) Installation of Indicator at Pump Room Pannel 3 nos 5) Installation of Connector at -3 nos | 246 | 2024-09-06 | 2000 | 2024-12-24 10:48 | 0 | SUYASH ENTERPRISES
Electrical Helper | N/C | N/C | SUYASH ENTERPRISES | 30 | 2024-08-20 | DEVELOPMENT Electrical Maintenance Work | 3 | 500 | 0 | 1500 | 0 | 2024-09-06 13:13 | 100% COMPLETION | 100 | DG power Supply Not Working problem verify DG phase sequence change, STP Changeover Supply check Club house Rellay Wire Replaced | 247 | 2024-09-06 | 1500 | 2024-12-24 10:48 | 0 | SUYASH ENTERPRISES
Electrical Helper | N/C | N/C | SUYASH ENTERPRISES | 30 | 2024-08-20 | DEVELOPMENT Electrical Maintenance Work | 2.52 | 500 | 0 | 1260 | 0 | 2024-09-06 13:55 | 100% COMPLETION | 100 | Supply & Installation of Voltage Monitor Relay 3Pole | 248 | 2024-09-06 | 3260 | 2024-12-24 10:48 | -2000 | SUYASH ENTERPRISES
Electrician Skilled | N/C | N/C | SUYASH ENTERPRISES | 30 | 2024-08-20 | DEVELOPMENT Electrical Maintenance Work | 2 | 1000 | 0 | 2000 | 0 | 2024-09-06 13:55 | 100% COMPLETION | 100 | Supply & Installation of Voltage Monitor Relay 3Pole | 248 | 2024-09-06 | 3260 | 2024-12-24 10:48 | -1260 | SUYASH ENTERPRISES
Carpentry Work | N/C | N/C | SAMPATLAL SOHANLAL SHARMA | 31 | 2024-08-23 | F1 BLDG SALES OFFICE FURNITURE INTERNAL WORK | 289.0255 | 340 | 0 | 98268.67 | 0 | 2024-09-04 16:56 | 100% COMPLETION | 100 | Work Done at New Sales Office interior work | 222 | 2024-09-04 | 115863.67 | 2024-12-24 17:58 | -17595 | SAMPATLAL SOHANLAL SHARMA
Furniture dismantle work | N/C | N/C | SAMPATLAL SOHANLAL SHARMA | 31 | 2024-08-23 | F1 BLDG SALES OFFICE FURNITURE INTERNAL WORK | 0.85 | 20000 | 0 | 17000 | 0 | 2024-09-04 16:56 | 100% COMPLETION | 100 | Work Done at New Sales Office interior work | 222 | 2024-09-04 | 115863.67 | 2024-12-24 17:58 | -98863.67 | SAMPATLAL SOHANLAL SHARMA
Wooden Door Fixing Work | N/C | N/C | SAMPATLAL SOHANLAL SHARMA | 31 | 2024-08-23 | F1 BLDG SALES OFFICE FURNITURE INTERNAL WORK | 1.7 | 350 | 0 | 595 | 0 | 2024-09-04 16:56 | 100% COMPLETION | 100 | Work Done at New Sales Office interior work | 222 | 2024-09-04 | 115863.67 | 2024-12-24 17:58 | -115268.67 | SAMPATLAL SOHANLAL SHARMA
Brick Pattern Cladding Work | N/C | N/C | DEVA SUBHASH CHAVAN | 32 | 2024-08-24 | VISAWA BUETYFICATION Tiling WORK | 62.97 | 25 | 0 | 1574.25 | 0 | 2024-09-03 18:05 | 100% COMPLETION | 100 | Work Done For VISAWA Buetyfication | 213 | 2024-09-03 | 57021.85 | 2024-09-04 17:03 | -55447.6 | DEVA SUBHASH CHAVAN
Edge Polish & Champer for Granite | N/C | N/C | DEVA SUBHASH CHAVAN | 32 | 2024-08-24 | VISAWA BUETYFICATION Tiling WORK | 137.54 | 15 | 0 | 2063.1 | 0 | 2024-09-03 18:05 | 100% COMPLETION | 100 | Work Done For VISAWA Buetyfication | 213 | 2024-09-03 | 57021.85 | 2024-09-04 17:03 | -54958.75 | DEVA SUBHASH CHAVAN
Granite Flooring Fixing | N/C | N/C | DEVA SUBHASH CHAVAN | 32 | 2024-08-24 | VISAWA BUETYFICATION Tiling WORK | 69.98 | 45 | 0 | 3149.1 | 0 | 2024-09-03 18:05 | 100% COMPLETION | 100 | Work Done For VISAWA Buetyfication | 213 | 2024-09-03 | 57021.85 | 2024-09-04 17:03 | -53872.75 | DEVA SUBHASH CHAVAN
Granite Round Cutting and Fixing | N/C | N/C | DEVA SUBHASH CHAVAN | 32 | 2024-08-24 | VISAWA BUETYFICATION Tiling WORK | 247.45 | 65 | 0 | 16084.25 | 0 | 2024-09-03 18:05 | 100% COMPLETION | 100 | Work Done For VISAWA Buetyfication | 213 | 2024-09-03 | 57021.85 | 2024-09-04 17:03 | -40937.6 | DEVA SUBHASH CHAVAN
Granite Round Staircase cutting and Fixing | N/C | N/C | DEVA SUBHASH CHAVAN | 32 | 2024-08-24 | VISAWA BUETYFICATION Tiling WORK | 290.86 | 55 | 0 | 15997.3 | 0 | 2024-09-03 18:05 | 100% COMPLETION | 100 | Work Done For VISAWA Buetyfication | 213 | 2024-09-03 | 57021.85 | 2024-09-04 17:03 | -41024.55 | DEVA SUBHASH CHAVAN
Granite Skirting Work | N/C | N/C | DEVA SUBHASH CHAVAN | 32 | 2024-08-24 | VISAWA BUETYFICATION Tiling WORK | 178.62 | 25 | 0 | 4465.5 | 0 | 2024-09-03 18:05 | 100% COMPLETION | 100 | Work Done For VISAWA Buetyfication | 213 | 2024-09-03 | 57021.85 | 2024-09-04 17:03 | -52556.35 | DEVA SUBHASH CHAVAN
Moulding for Granite Dubble top and Bottom | N/C | N/C | DEVA SUBHASH CHAVAN | 32 | 2024-08-24 | VISAWA BUETYFICATION Tiling WORK | 210.59 | 65 | 0 | 13688.35 | 0 | 2024-09-03 18:05 | 100% COMPLETION | 100 | Work Done For VISAWA Buetyfication | 213 | 2024-09-03 | 57021.85 | 2024-09-04 17:03 | -43333.5 | DEVA SUBHASH CHAVAN
WATER TANKER 5000 LTR | N/C | N/C | SWARA WATER SUPPLIERS | 33 | 2024-08-27 | Labour Camp WATER TANKER 5000 LTR | 46 | 550 | 0 | 25300 | 0 | 2024-08-29 12:37 | 100% COMPLETION | 100 | Against Bill no 1899 | 191 | 2024-08-29 | 25300 | 2024-08-30 14:13 | 0 | SWARA WATER SUPPLIERS
WATER TANKER 5000 LTR | N/C | N/C | SWARA WATER SUPPLIERS | 33 | 2024-08-27 | Labour Camp WATER TANKER 5000 LTR | 16 | 550 | 0 | 8800 | 0 | 2024-08-29 12:50 | 100% COMPLETION | 100 | Tanker Trip provided | 192 | 2024-08-29 | 8800 | 2024-09-02 15:22 | 0 | SWARA WATER SUPPLIERS
DRINKING WATER 10000 LTR | N/C | N/C | SWARA WATER SUPPLIERS | 33 | 2024-08-27 | Labour Camp WATER TANKER 5000 LTR | 1 | 2500 | 0 | 2500 | 0 | 2024-08-29 13:53 | 100% COMPLETION | 100 | PROVIDING DRINKING WATER FOR SWIMMING POOL. | 194 | 2024-08-29 | 2500 | 2024-08-30 14:14 | 0 | SWARA WATER SUPPLIERS
WATER TANKER 5000 LTR | N/C | N/C | SWARA WATER SUPPLIERS | 33 | 2024-08-27 | Labour Camp WATER TANKER 5000 LTR | 44 | 550 | 0 | 24200 | 0 | 2024-10-14 19:32 | 100% COMPLETION | 100 | AGAINST BILL NO 1954 FOR SEP-2024 | 445 | 2024-10-14 | 24200 | 2024-12-20 14:20 | 0 | SWARA WATER SUPPLIERS
WATER TANKER 5000 LTR | N/C | N/C | SWARA WATER SUPPLIERS | 33 | 2024-08-27 | Labour Camp WATER TANKER 5000 LTR | 25 | 550 | 0 | 13750 | 0 | 2024-10-14 19:34 | 100% COMPLETION | 100 | AGAINST BILL NO 1955 FOR SEP-2024 | 446 | 2024-10-14 | 13750 | 2024-12-20 14:20 | 0 | SWARA WATER SUPPLIERS
WATER TANKER 5000 LTR | N/C | N/C | SWARA WATER SUPPLIERS | 33 | 2024-08-27 | Labour Camp WATER TANKER 5000 LTR | 46 | 550 | 0 | 25300 | 0 | 2024-09-19 17:01 | 100% COMPLETION | 100 | Providing Water Tanker at Labour Camp for Aug -24 | 303 | 2024-09-19 | 25300 | 2024-12-20 14:19 | 0 | SWARA WATER SUPPLIERS
WATER TANKER 5000 LTR | N/C | N/C | SWARA WATER SUPPLIERS | 33 | 2024-08-27 | Labour Camp WATER TANKER 5000 LTR | 21 | 550 | 0 | 11550 | 0 | 2024-09-19 17:03 | 100% COMPLETION | 100 | Providing Water Tanker at Labour Camp for Aug -24 | 306 | 2024-09-19 | 11550 | 2024-12-20 14:20 | 0 | SWARA WATER SUPPLIERS
WATER TANKER 5000 LTR | N/C | N/C | SWARA WATER SUPPLIERS | 33 | 2024-08-27 | Labour Camp WATER TANKER 5000 LTR | 68 | 550 | 0 | 37400 | 0 | 2025-02-04 17:44 | 100% COMPLETION | 100 | Labour Camp WATER TANKER 5000 LTR-1 JAN TO 31 JAN=68 TRIP | 1075 | 2025-02-04 | 37400 | 2025-02-05 14:34 | 0 | SWARA WATER SUPPLIERS
WATER TANKER 5000 LTR | N/C | N/C | SWARA WATER SUPPLIERS | 33 | 2024-08-27 | Labour Camp WATER TANKER 5000 LTR | 57 | 550 | 0 | 31350 | 0 | 2025-01-19 15:31 | 100% COMPLETION | 100 | Against Bill 6 | 973 | 2025-01-19 | 31350 | 2025-01-20 14:57 | 0 | SWARA WATER SUPPLIERS
WATER TANKER 5000 LTR | N/C | N/C | SWARA WATER SUPPLIERS | 33 | 2024-08-27 | Labour Camp WATER TANKER 5000 LTR | 12 | 550 | 0 | 6600 | 0 | 2025-01-19 15:36 | 100% COMPLETION | 100 | against Bill no 7 | 974 | 2025-01-19 | 6600 | 2025-01-20 14:57 | 0 | SWARA WATER SUPPLIERS
WATER TANKER 5000 LTR | N/C | N/C | SWARA WATER SUPPLIERS | 33 | 2024-08-27 | Labour Camp WATER TANKER 5000 LTR | 1.4546 | 550 | 0 | 800.03 | 0 | 2025-01-19 15:44 | 100% COMPLETION | 100 | against bill no 8 | 978 | 2025-01-19 | 800.03 | 2025-01-20 14:57 | 0 | SWARA WATER SUPPLIERS
WATER TANKER 5000 LTR | N/C | N/C | SWARA WATER SUPPLIERS | 33 | 2024-08-27 | Labour Camp WATER TANKER 5000 LTR | 21 | 550 | 0 | 11550 | 0 | 2024-11-25 14:29 | 100% COMPLETION | 100 | Labour camp water supply against bill no 1973 | 545 | 2024-11-25 | 11550 | 2024-12-20 14:20 | 0 | SWARA WATER SUPPLIERS
DRINKING WATER 10000 LTR | N/C | N/C | SWARA WATER SUPPLIERS | 33 | 2024-08-27 | Labour Camp WATER TANKER 5000 LTR | 2 | 2500 | 0 | 5000 | 0 | 2024-11-25 14:31 | 100% COMPLETION | 100 | Ostia Club House Swimming Pool Water Top up against Bill no 1984 | 546 | 2024-11-25 | 5000 | 2024-12-20 14:20 | 0 | SWARA WATER SUPPLIERS
WATER TANKER 5000 LTR | N/C | N/C | SWARA WATER SUPPLIERS | 33 | 2024-08-27 | Labour Camp WATER TANKER 5000 LTR | 1 | 550 | 0 | 550 | 0 | 2024-11-25 14:34 | 100% COMPLETION | 100 | labour camp water supply against bill no 1988 | 547 | 2024-11-25 | 550 | 2024-12-20 14:20 | 0 | SWARA WATER SUPPLIERS
DRINKING WATER 10000 LTR | N/C | N/C | SWARA WATER SUPPLIERS | 33 | 2024-08-27 | Labour Camp WATER TANKER 5000 LTR | 1 | 2500 | 0 | 2500 | 0 | 2024-12-21 17:59 | 100% COMPLETION | 100 | For Ostia Swimming Pool against ch no 9386 | 751 | 2024-12-21 | 2500 | 2024-12-26 12:27 | 0 | SWARA WATER SUPPLIERS
WATER TANKER 5000 LTR | N/C | N/C | SWARA WATER SUPPLIERS | 33 | 2024-08-27 | Labour Camp WATER TANKER 5000 LTR | 18 | 550 | 0 | 9900 | 0 | 2024-12-21 17:59 | 100% COMPLETION | 100 | Against Bill no 2001 for labour camp | 752 | 2024-12-21 | 9900 | 2024-12-26 12:27 | 0 | SWARA WATER SUPPLIERS
WATER TANKER 5000 LTR | N/C | N/C | SWARA WATER SUPPLIERS | 33 | 2024-08-27 | Labour Camp WATER TANKER 5000 LTR | 47 | 550 | 0 | 25850 | 0 | 2024-12-21 18:00 | 100% COMPLETION | 100 | against bill no 2000 for Labour camp | 753 | 2024-12-21 | 25850 | 2024-12-26 12:27 | 0 | SWARA WATER SUPPLIERS
AC FITTING CHARGES | N/C | N/C | YOGIRAJ RAMKRISHNA PATIL | 34 | 2024-09-03 | SALES OFFICE AC MAINTAINACE WORK | 3 | 1450 | 0 | 4350 | 0 | 2024-09-05 15:51 | 100% COMPLETION | 100 | New Sales Office Maintenance Work | 231 | 2024-09-05 | 58750 | 2024-12-20 14:25 | -54400 | YOGIRAJ RAMKRISHNA PATIL
AC Gas Charging 1 Tonne | N/C | N/C | YOGIRAJ RAMKRISHNA PATIL | 34 | 2024-09-03 | SALES OFFICE AC MAINTAINACE WORK | 2 | 1800 | 0 | 3600 | 0 | 2024-09-05 15:51 | 100% COMPLETION | 100 | New Sales Office Maintenance Work | 231 | 2024-09-05 | 58750 | 2024-12-20 14:25 | -55150 | YOGIRAJ RAMKRISHNA PATIL
AC Gas Charging for 2 Tonne Cap. | N/C | N/C | YOGIRAJ RAMKRISHNA PATIL | 34 | 2024-09-03 | SALES OFFICE AC MAINTAINACE WORK | 1 | 2200 | 0 | 2200 | 0 | 2024-09-05 15:51 | 100% COMPLETION | 100 | New Sales Office Maintenance Work | 231 | 2024-09-05 | 58750 | 2024-12-20 14:25 | -56550 | YOGIRAJ RAMKRISHNA PATIL
AC Maintenance Charges | N/C | N/C | YOGIRAJ RAMKRISHNA PATIL | 34 | 2024-09-03 | SALES OFFICE AC MAINTAINACE WORK | 1 | 7000 | 0 | 7000 | 0 | 2024-09-05 15:51 | 100% COMPLETION | 100 | New Sales Office Maintenance Work | 231 | 2024-09-05 | 58750 | 2024-12-20 14:25 | -51750 | YOGIRAJ RAMKRISHNA PATIL
AIR CONDITIONER REMOVING | N/C | N/C | YOGIRAJ RAMKRISHNA PATIL | 34 | 2024-09-03 | SALES OFFICE AC MAINTAINACE WORK | 3 | 500 | 0 | 1500 | 0 | 2024-09-05 15:51 | 100% COMPLETION | 100 | New Sales Office Maintenance Work | 231 | 2024-09-05 | 58750 | 2024-12-20 14:25 | -57250 | YOGIRAJ RAMKRISHNA PATIL
Installation Of Coper Piping for 2 Tonne | N/C | N/C | YOGIRAJ RAMKRISHNA PATIL | 34 | 2024-09-03 | SALES OFFICE AC MAINTAINACE WORK | 18 | 1000 | 0 | 18000 | 0 | 2024-09-05 15:51 | 100% COMPLETION | 100 | New Sales Office Maintenance Work | 231 | 2024-09-05 | 58750 | 2024-12-20 14:25 | -40750 | YOGIRAJ RAMKRISHNA PATIL
Installation of Copper Piping for 1 Tonne Unit | N/C | N/C | YOGIRAJ RAMKRISHNA PATIL | 34 | 2024-09-03 | SALES OFFICE AC MAINTAINACE WORK | 22 | 800 | 0 | 17600 | 0 | 2024-09-05 15:51 | 100% COMPLETION | 100 | New Sales Office Maintenance Work | 231 | 2024-09-05 | 58750 | 2024-12-20 14:25 | -41150 | YOGIRAJ RAMKRISHNA PATIL
POWDER COATING FOR INDOOR AND OUTDOOR UNIT | N/C | N/C | YOGIRAJ RAMKRISHNA PATIL | 34 | 2024-09-03 | SALES OFFICE AC MAINTAINACE WORK | 3 | 1500 | 0 | 4500 | 0 | 2024-09-05 15:51 | 100% COMPLETION | 100 | New Sales Office Maintenance Work | 231 | 2024-09-05 | 58750 | 2024-12-20 14:25 | -54250 | YOGIRAJ RAMKRISHNA PATIL
Providing & Fixing 10mm Toughened Glass For Door Shutter | N/C | N/C | 24 ALUMINIUM | 35 | 2024-09-04 | SALES OFFICE Toughened Glass Work | 93.9 | 305 | 0 | 28639.5 | 0 | 2024-09-05 12:19 | 100% COMPLETION | 100 | Executed By Sandesh Jadhav Labour Agency at New Sales Office | 227 | 2024-09-05 | 114620.2 | 2024-12-20 14:31 | -85980.7 | TIRUPATI ENTERPRISES
Providing & Fixing 12mm Toughened Glass For Partition | N/C | N/C | 24 ALUMINIUM | 35 | 2024-09-04 | SALES OFFICE Toughened Glass Work | 52.5 | 305 | 0 | 16012.5 | 0 | 2024-09-05 12:19 | 100% COMPLETION | 100 | Executed By Sandesh Jadhav Labour Agency at New Sales Office | 227 | 2024-09-05 | 114620.2 | 2024-12-20 14:31 | -98607.7 | TIRUPATI ENTERPRISES
Providing & Fixing Floor Machin, SS Handle, And Accessories | N/C | N/C | 24 ALUMINIUM | 35 | 2024-09-04 | SALES OFFICE Toughened Glass Work | 4 | 10000 | 0 | 40000 | 0 | 2024-09-05 12:19 | 100% COMPLETION | 100 | Executed By Sandesh Jadhav Labour Agency at New Sales Office | 227 | 2024-09-05 | 114620.2 | 2024-12-20 14:31 | -74620.2 | TIRUPATI ENTERPRISES
Providing and Fixing Aluminum Louvers For Ventilator | N/C | N/C | 24 ALUMINIUM | 35 | 2024-09-04 | SALES OFFICE Toughened Glass Work | 3.6 | 190 | 0 | 684 | 0 | 2024-09-05 12:19 | 100% COMPLETION | 100 | Executed By Sandesh Jadhav Labour Agency at New Sales Office | 227 | 2024-09-05 | 114620.2 | 2024-12-20 14:31 | -113936.2 | TIRUPATI ENTERPRISES
Providing Labors for Fixing 12mm Glass | N/C | N/C | 24 ALUMINIUM | 35 | 2024-09-04 | SALES OFFICE Toughened Glass Work | 325.38 | 90 | 0 | 29284.2 | 0 | 2024-09-05 12:19 | 100% COMPLETION | 100 | Executed By Sandesh Jadhav Labour Agency at New Sales Office | 227 | 2024-09-05 | 114620.2 | 2024-12-20 14:31 | -85336 | TIRUPATI ENTERPRISES
Providing & Fixing 10mm Toughened Glass For Door Shutter | N/C | N/C | 24 ALUMINIUM | 35 | 2024-09-04 | SALES OFFICE Toughened Glass Work | 140.85 | 305 | 0 | 42959.25 | 7732.66 | 2024-09-05 12:45 | 100% COMPLETION | 100 | Executed By Sandesh Jadhav 24 ALUMINIUM at New Sales Office | 228 | 2024-09-05 | 128004 | 2024-12-20 14:30 | -85044.75 | 24 ALUMINIUM
Providing & Fixing 12mm Toughened Glass For Partition | N/C | N/C | 24 ALUMINIUM | 35 | 2024-09-04 | SALES OFFICE Toughened Glass Work | 78.75 | 305 | 0 | 24018.75 | 4323.38 | 2024-09-05 12:45 | 100% COMPLETION | 100 | Executed By Sandesh Jadhav 24 ALUMINIUM at New Sales Office | 228 | 2024-09-05 | 128004 | 2024-12-20 14:30 | -103985.25 | 24 ALUMINIUM
Providing & Fixing Floor Machin, SS Handle, And Accessories | N/C | N/C | 24 ALUMINIUM | 35 | 2024-09-04 | SALES OFFICE Toughened Glass Work | 6 | 10000 | 0 | 60000 | 10800 | 2024-09-05 12:45 | 100% COMPLETION | 100 | Executed By Sandesh Jadhav 24 ALUMINIUM at New Sales Office | 228 | 2024-09-05 | 128004 | 2024-12-20 14:30 | -68004 | 24 ALUMINIUM
Providing and Fixing Aluminum Louvers For Ventilator | N/C | N/C | 24 ALUMINIUM | 35 | 2024-09-04 | SALES OFFICE Toughened Glass Work | 5.4 | 190 | 0 | 1026 | 184.68 | 2024-09-05 12:45 | 100% COMPLETION | 100 | Executed By Sandesh Jadhav 24 ALUMINIUM at New Sales Office | 228 | 2024-09-05 | 128004 | 2024-12-20 14:30 | -126978 | 24 ALUMINIUM
RCC PARAPET WALL ON LABOUR RATE | N/C | N/C | SAKSHI CONSTRUCTION AND DEVELOPERS | 38 | 2024-09-19 | G1 BLDG TERRACE RCC PARAPET PARDI | 1198.8 | 120 | 0 | 143856 | 0 | 2024-10-05 19:52 | 100% COMPLETION | 100 | AGAINST BILL No 19 | 401 | 2024-10-05 | 143856 | 2024-12-20 14:22 | 0 | SAKSHI CONSTRUCTION AND DEVELOPERS
Sweeper Toilet Clener | N/C | N/C | PRAKASH BUGLE | 4 | 2024-07-04 | Labour Camp Sweeper Service For Labour Camp | 1 | 3500 | 0 | 3500 | 0 | 2025-02-05 18:37 | 100% COMPLETION | 100 | Sweeper Service For Dec 2024 | 1116 | 2025-02-05 | 3500 | 1900-01-01 | 0 | PRAKASH BUGLE
Sweeper Toilet Clener | N/C | N/C | PRAKASH BUGLE | 4 | 2024-07-04 | Labour Camp Sweeper Service For Labour Camp | 1 | 3500 | 0 | 3500 | 0 | 2025-02-05 18:41 | 100% COMPLETION | 100 | Sweeper Service for Labour camp for Jan 2025 | 1117 | 2025-02-05 | 3500 | 1900-01-01 | 0 | PRAKASH BUGLE
Sweeper Toilet Clener | N/C | N/C | PRAKASH BUGLE | 4 | 2024-07-04 | Labour Camp Sweeper Service For Labour Camp | 1 | 3500 | 0 | 3500 | 0 | 2024-07-04 17:39 | 100% COMPLETION | 100 | for Month of June 2024 | 44 | 2024-07-04 | 3500 | 2024-07-04 17:56 | 0 | PRAKASH BUGLE
Sweeper Toilet Clener | N/C | N/C | PRAKASH BUGLE | 4 | 2024-07-04 | Labour Camp Sweeper Service For Labour Camp | 1 | 3500 | 0 | 3500 | 0 | 2024-08-05 17:16 | 100% COMPLETION | 100 | For THE MONTH OF July 2024 | 100 | 2024-08-05 | 3500 | 2024-08-06 15:07 | 0 | PRAKASH BUGLE
Sweeper Toilet Clener | N/C | N/C | PRAKASH BUGLE | 4 | 2024-07-04 | Labour Camp Sweeper Service For Labour Camp | 1 | 3500 | 0 | 3500 | 0 | 2024-11-25 14:26 | 100% COMPLETION | 100 | For the Month of OCT 2024 Bill no 15 | 544 | 2024-11-25 | 3500 | 2024-12-20 14:14 | 0 | PRAKASH BUGLE
Mosquito Managment Services | N/C | N/C | Aarya Hygiene | 41 | 2024-09-20 | Labour Camp Mosquito Managment Services | 4 | 900 | 0 | 3600 | 648 | 2024-12-21 18:23 | 100% COMPLETION | 100 | Against bill no 24251155 for Aug, Sep, Oct & Nov 2024 | 745 | 2024-12-21 | 13500 | 2024-12-26 12:49 | -9900 | Aarya Hygiene
Mosquito Managment Services | N/C | N/C | Aarya Hygiene | 41 | 2024-09-20 | Labour Camp Mosquito Managment Services | 11 | 900 | 0 | 9900 | 1782 | 2024-12-21 18:49 | 100% COMPLETION | 100 | Against bill no 24251155 for Aug, Sep, Oct & Nov 2024 | 745 | 2024-12-21 | 13500 | 2024-12-26 12:49 | -3600 | Aarya Hygiene
Mosquito Managment Services | N/C | N/C | Aarya Hygiene | 41 | 2024-09-20 | Labour Camp Mosquito Managment Services | 4 | 900 | 0 | 3600 | 648 | 2025-01-19 15:26 | 100% COMPLETION | 100 | Against Bill no 24251207 | 971 | 2025-01-19 | 3600 | 2025-01-20 14:57 | 0 | Aarya Hygiene
Mosquito Managment Services | N/C | N/C | Aarya Hygiene | 41 | 2024-09-20 | Labour Camp Mosquito Managment Services | 4 | 900 | 0 | 3600 | 648 | 2025-02-05 18:44 | 100% COMPLETION | 100 | Against Bill no 1376 For Dec 2024 | 1118 | 2025-02-05 | 3600 | 1900-01-01 | 0 | Aarya Hygiene
PODIUM GROUTING WORK | N/C | N/C | SUMAN SANTOSH GAIKWAD | 42 | 2024-09-24 | PODIUM PARKING SOCKET GROUTING WORK | 48 | 300 | 0 | 14400 | 0 | 2024-10-11 12:36 | 100% COMPLETION | 100 | podium parking 48 nos of socket grouting work done | 425 | 2024-10-11 | 14400 | 2024-12-24 10:54 | 0 | SUMAN SANTOSH GAIKWAD
PRIMERY INSTALLMENT (AT INCEPTION) | N/C | N/C | ICICI LOMBARD GIC LTD | 44 | 2024-09-24 | E1 BUILDING CONTRACTOR ALL RISK POLICY | 1 | 127669 | 0 | 127669 | 22980.42 | 2024-10-22 11:14 | 100% COMPLETION | 100 | E1 BUILDING CONTRACTOR ALL RISK POLICY, 1ST INSTALLMENT | 518 | 2024-10-22 | 127669 | 2024-12-24 10:44 | 0 | ICICI LOMBARD GIC LTD
Dia 2" Core Cutting Work | N/C | N/C | Shree Sai Service | 45 | 2024-09-25 | F1 Building REBARING AND CORE CUTTING WORK | 26 | 30 | 0 | 780 | 0 | 2024-10-05 19:17 | 100% COMPLETION | 100 | AGAINST BILL NO 176 | 398 | 2024-10-05 | 17495 | 2024-12-24 10:49 | -16715 | Shree Sai Service
Dia 3" Core Cutting Work | N/C | N/C | Shree Sai Service | 45 | 2024-09-25 | F1 Building REBARING AND CORE CUTTING WORK | 19 | 40 | 0 | 760 | 0 | 2024-10-05 19:17 | 100% COMPLETION | 100 | AGAINST BILL NO 176 | 398 | 2024-10-05 | 17495 | 2024-12-24 10:49 | -16735 | Shree Sai Service
Dia 4" Core Cutting Work | N/C | N/C | Shree Sai Service | 45 | 2024-09-25 | F1 Building REBARING AND CORE CUTTING WORK | 161 | 45 | 0 | 7245 | 0 | 2024-10-05 19:17 | 100% COMPLETION | 100 | AGAINST BILL NO 176 | 398 | 2024-10-05 | 17495 | 2024-12-24 10:49 | -10250 | Shree Sai Service
Dia 8" Core Cutting Work | N/C | N/C | Shree Sai Service | 45 | 2024-09-25 | F1 Building REBARING AND CORE CUTTING WORK | 16 | 100 | 0 | 1600 | 0 | 2024-10-05 19:17 | 100% COMPLETION | 100 | AGAINST BILL NO 176 | 398 | 2024-10-05 | 17495 | 2024-12-24 10:49 | -15895 | Shree Sai Service
Rebaring Work Dia 10 mm | N/C | N/C | Shree Sai Service | 45 | 2024-09-25 | F1 Building REBARING AND CORE CUTTING WORK | 66 | 50 | 0 | 3300 | 0 | 2024-10-05 19:17 | 100% COMPLETION | 100 | AGAINST BILL NO 176 | 398 | 2024-10-05 | 17495 | 2024-12-24 10:49 | -14195 | Shree Sai Service
Rebaring Work Dia 12 mm | N/C | N/C | Shree Sai Service | 45 | 2024-09-25 | F1 Building REBARING AND CORE CUTTING WORK | 32 | 60 | 0 | 1920 | 0 | 2024-10-05 19:17 | 100% COMPLETION | 100 | AGAINST BILL NO 176 | 398 | 2024-10-05 | 17495 | 2024-12-24 10:49 | -15575 | Shree Sai Service
Rebaring Work Dia 8mm | N/C | N/C | Shree Sai Service | 45 | 2024-09-25 | F1 Building REBARING AND CORE CUTTING WORK | 42 | 45 | 0 | 1890 | 0 | 2024-10-05 19:17 | 100% COMPLETION | 100 | AGAINST BILL NO 176 | 398 | 2024-10-05 | 17495 | 2024-12-24 10:49 | -15605 | Shree Sai Service
Dia 4" Core Cutting Work | N/C | N/C | Shree Sai Service | 45 | 2024-09-25 | F1 Building REBARING AND CORE CUTTING WORK | 32 | 45 | 0 | 1440 | 0 | 2024-10-05 19:20 | 100% COMPLETION | 100 | AGAINST BILL NO 175 | 399 | 2024-10-05 | 4830 | 2024-12-24 10:49 | -3390 | Shree Sai Service
Rebaring Work Dia 12 mm | N/C | N/C | Shree Sai Service | 45 | 2024-09-25 | F1 Building REBARING AND CORE CUTTING WORK | 52 | 60 | 0 | 3120 | 0 | 2024-10-05 19:20 | 100% COMPLETION | 100 | AGAINST BILL NO 175 | 399 | 2024-10-05 | 4830 | 2024-12-24 10:49 | -1710 | Shree Sai Service
Rebaring Work Dia 8mm | N/C | N/C | Shree Sai Service | 45 | 2024-09-25 | F1 Building REBARING AND CORE CUTTING WORK | 6 | 45 | 0 | 270 | 0 | 2024-10-05 19:20 | 100% COMPLETION | 100 | AGAINST BILL NO 175 | 399 | 2024-10-05 | 4830 | 2024-12-24 10:49 | -4560 | Shree Sai Service
Rebaring Work Dia 10 mm | N/C | N/C | Shree Sai Service | 45 | 2024-09-25 | F1 Building REBARING AND CORE CUTTING WORK | 213 | 50 | 0 | 10650 | 0 | 2024-10-05 19:26 | 100% COMPLETION | 100 | AGAINST BILL NO 177 | 400 | 2024-10-05 | 17700 | 2024-12-24 10:49 | -7050 | Shree Sai Service
Rebaring Work Dia 12 mm | N/C | N/C | Shree Sai Service | 45 | 2024-09-25 | F1 Building REBARING AND CORE CUTTING WORK | 98 | 60 | 0 | 5880 | 0 | 2024-10-05 19:26 | 100% COMPLETION | 100 | AGAINST BILL NO 177 | 400 | 2024-10-05 | 17700 | 2024-12-24 10:49 | -11820 | Shree Sai Service
Rebaring Work Dia 8mm | N/C | N/C | Shree Sai Service | 45 | 2024-09-25 | F1 Building REBARING AND CORE CUTTING WORK | 26 | 45 | 0 | 1170 | 0 | 2024-10-05 19:26 | 100% COMPLETION | 100 | AGAINST BILL NO 177 | 400 | 2024-10-05 | 17700 | 2024-12-24 10:49 | -16530 | Shree Sai Service
M.S STAIRCASE LABOUR RATE | N/C | N/C | S.S. ENTERPRISES | 46 | 2024-10-01 | F1-BLDG MEZZANINE M.S STAIRCASE LABOUR RATE | 9 | 6000 | 0 | 54000 | 0 | 2024-10-10 13:59 | 100% COMPLETION | 100 | for f1bldg 9nos of shop complete and 8 is in progress | 423 | 2024-10-10 | 54000 | 2024-12-24 10:56 | 0 | S.S. ENTERPRISES
CEILING PATRA PUNNING IN GYPSUM FINISH | N/C | N/C | Zoya Enterprises | 48 | 2024-10-05 | F1 BLDG CEILING PUNNING AT LG FLOOR | 1942.9552 | 12 | 0 | 23315.4624 | 1165.78 | 2024-10-15 10:46 | 100% COMPLETION | 100 | Against Bill no 38 | 448 | 2024-10-15 | 530038.16 | 2024-12-24 10:51 | -506722.6976 | Zoya Enterprises
CEILING PATRA PUNNING IN GYPSUM FINISH | N/C | N/C | Zoya Enterprises | 48 | 2024-10-05 | F1 BLDG CEILING PUNNING AT UG AND MEZZ. FLOOR | 1942.9552 | 12 | 0 | 23315.4624 | 1165.78 | 2024-10-15 10:46 | 100% COMPLETION | 100 | Against Bill no 38 | 448 | 2024-10-15 | 530038.16 | 2024-12-24 10:51 | -506722.6976 | Zoya Enterprises
CEILING PATRA PUNNING IN GYPSUM FINISH | N/C | N/C | Zoya Enterprises | 48 | 2024-10-05 | F1 BLDG CEILING PUNNING AT 1ST FLOOR | 2266.781 | 12 | 0 | 27201.372 | 1360.06 | 2024-10-15 10:46 | 100% COMPLETION | 100 | Against Bill no 38 | 448 | 2024-10-15 | 530038.16 | 2024-12-24 10:51 | -502836.788 | Zoya Enterprises
CEILING PATRA PUNNING IN GYPSUM FINISH | N/C | N/C | Zoya Enterprises | 48 | 2024-10-05 | F1 BLDG CEILING PUNNING AT 2ND FLOOR | 2266.781 | 12 | 0 | 27201.372 | 1360.06 | 2024-10-15 10:46 | 100% COMPLETION | 100 | Against Bill no 38 | 448 | 2024-10-15 | 530038.16 | 2024-12-24 10:51 | -502836.788 | Zoya Enterprises
WALL IN GYPSUM FINISH | N/C | N/C | Zoya Enterprises | 48 | 2024-10-05 | F1 BLDG WALL GYPSUM AT LG FLOOR | 4054.863 | 23 | 0 | 93261.849 | 4663.1 | 2024-10-15 10:46 | 100% COMPLETION | 100 | Against Bill no 38 | 448 | 2024-10-15 | 530038.16 | 2024-12-24 10:51 | -436776.311 | Zoya Enterprises
WALL IN GYPSUM FINISH | N/C | N/C | Zoya Enterprises | 48 | 2024-10-05 | F1 BLDG WALL GYPSUM AT UPPER GROUND and MEZZ. FLOOR | 5406.484 | 23 | 0 | 124349.132 | 6217.46 | 2024-10-15 10:46 | 100% COMPLETION | 100 | Against Bill no 38 | 448 | 2024-10-15 | 530038.16 | 2024-12-24 10:51 | -405689.028 | Zoya Enterprises
WALL IN GYPSUM FINISH | N/C | N/C | Zoya Enterprises | 48 | 2024-10-05 | F1 BLDG WALL GYPSUM AT 1ST FLOOR | 4595.5114 | 23 | 0 | 105696.7622 | 5284.84 | 2024-10-15 10:46 | 100% COMPLETION | 100 | Against Bill no 38 | 448 | 2024-10-15 | 530038.16 | 2024-12-24 10:51 | -424341.3978 | Zoya Enterprises
WALL IN GYPSUM FINISH | N/C | N/C | Zoya Enterprises | 48 | 2024-10-05 | F1 BLDG WALL GYPSUM AT 2ND FLOOR | 4595.5114 | 23 | 0 | 105696.7622 | 5284.84 | 2024-10-15 10:46 | 100% COMPLETION | 100 | Against Bill no 38 | 448 | 2024-10-15 | 530038.16 | 2024-12-24 10:51 | -424341.3978 | Zoya Enterprises
CEILING PATRA PUNNING IN GYPSUM FINISH | N/C | N/C | Zoya Enterprises | 48 | 2024-10-05 | F1 BLDG CEILING PUNNING AT 3RD FLOOR | 2590.6069 | 12 | 0 | 31087.2828 | 1554.36 | 2025-01-20 12:13 | 100% COMPLETION | 100 | F1 Building Against Bill no 69 | 989 | 2025-01-20 | 186523.69 | 2025-01-22 13:47 | -155436.4072 | Zoya Enterprises
WALL IN GYPSUM FINISH | N/C | N/C | Zoya Enterprises | 48 | 2024-10-05 | F1 BLDG WALL GYPSUM AT 3RD FLOOR | 6758.1049 | 23 | 0 | 155436.4127 | 7771.82 | 2025-01-20 12:13 | 100% COMPLETION | 100 | Against Bill no 69 | 989 | 2025-01-20 | 186523.69 | 2025-01-22 13:47 | -31087.2773 | Zoya Enterprises
CEILING PATRA PUNNING IN GYPSUM FINISH | N/C | N/C | Ubaidurrahman Khan | 49 | 2024-10-05 | F1 BLDG CEILING GYPSUM PUNNING AT UG AND MEZZA. FLOOR | 1295.3034 | 12 | 0 | 15543.6408 | 0 | 2024-10-15 10:56 | 100% COMPLETION | 100 | Against Bill no 01 | 449 | 2024-10-15 | 275640.58 | 2024-12-24 10:45 | -260096.9392 | Ubaidurrahman Khan
CEILING PATRA PUNNING IN GYPSUM FINISH | N/C | N/C | Ubaidurrahman Khan | 49 | 2024-10-05 | F1 BLDG CEILING GYPSUM PUNNING AT 1ST FLOOR | 1511.1874 | 12 | 0 | 18134.2488 | 0 | 2024-10-15 10:56 | 100% COMPLETION | 100 | Against Bill no 01 | 449 | 2024-10-15 | 275640.58 | 2024-12-24 10:45 | -257506.3312 | Ubaidurrahman Khan
CEILING PATRA PUNNING IN GYPSUM FINISH | N/C | N/C | Ubaidurrahman Khan | 49 | 2024-10-05 | F1 BLDG CEILING GYPSUM PUNNING AT 2ND FLOOR | 1511.1874 | 12 | 0 | 18134.2488 | 0 | 2024-10-15 10:56 | 100% COMPLETION | 100 | Against Bill no 01 | 449 | 2024-10-15 | 275640.58 | 2024-12-24 10:45 | -257506.3312 | Ubaidurrahman Khan
WALL IN GYPSUM FINISH | N/C | N/C | Ubaidurrahman Khan | 49 | 2024-10-05 | F1 BLDG WALL GYPSUM AT UG AND MEZZ.FLOOR | 3604.3226 | 23 | 0 | 82899.4198 | 0 | 2024-10-15 10:56 | 100% COMPLETION | 100 | Against Bill no 01 | 449 | 2024-10-15 | 275640.58 | 2024-12-24 10:45 | -192741.1602 | Ubaidurrahman Khan
WALL IN GYPSUM FINISH | N/C | N/C | Ubaidurrahman Khan | 49 | 2024-10-05 | F1 BLDG WALL GYPSUM AT 1ST FLOOR | 3063.6742 | 23 | 0 | 70464.5066 | 0 | 2024-10-15 10:56 | 100% COMPLETION | 100 | Against Bill no 01 | 449 | 2024-10-15 | 275640.58 | 2024-12-24 10:45 | -205176.0734 | Ubaidurrahman Khan
WALL IN GYPSUM FINISH | N/C | N/C | Ubaidurrahman Khan | 49 | 2024-10-05 | F1 BLDG WALL GYPSUM AT 2ND FLOOR | 3063.6742 | 23 | 0 | 70464.5066 | 0 | 2024-10-15 10:56 | 100% COMPLETION | 100 | Against Bill no 01 | 449 | 2024-10-15 | 275640.58 | 2024-12-24 10:45 | -205176.0734 | Ubaidurrahman Khan
CEILING PATRA PUNNING IN GYPSUM FINISH | N/C | N/C | Ubaidurrahman Khan | 49 | 2024-10-05 | F1 BLDG CEILING GYPSUM PUNNING AT 3RD FLOOR | 1727.0713 | 12 | 0 | 20724.8556 | 0 | 2025-02-06 18:10 | 100% COMPLETION | 100 | F1 BLDG CEILING GYPSUM PUNNING AT 3RD FLOOR | 1119 | 2025-02-06 | 124349.14 | 1900-01-01 | -103624.2844 | Ubaidurrahman Khan
WALL IN GYPSUM FINISH | N/C | N/C | Ubaidurrahman Khan | 49 | 2024-10-05 | F1 BLDG WALL GYPSUM AT 3RD FLOOR | 4505.4033 | 23 | 0 | 103624.2759 | 0 | 2025-02-06 18:10 | 100% COMPLETION | 100 | F1 BLDG WALL GYPSUM AT 3RD FLOOR | 1119 | 2025-02-06 | 124349.14 | 1900-01-01 | -20724.8641 | Ubaidurrahman Khan
Watchmen | N/C | N/C | GURUKRUPA ENTERPRISES | 5 | 2024-07-04 | DEVELOPMENT Security Service For Ostia Project | 1 | 13500 | 0 | 13500 | 0 | 2025-02-06 18:14 | 100% COMPLETION | 100 | DEVELOPMENT Security Service For Ostia Project-F1 BLDG MAIN ROAD FRONT PRIMISES GUARD | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | GURUKRUPA ENTERPRISES
Watchmen | N/C | N/C | GURUKRUPA ENTERPRISES | 5 | 2024-07-04 | DEVELOPMENT Security Service For Ostia Project | 1 | 13500 | 0 | 13500 | 0 | 2025-02-06 18:16 | 100% COMPLETION | 100 | DEVELOPMENT Security Service For Ostia Project-H1 BLDG UPPER PARKING RAMP ENTRY SECURITY GUARD | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | GURUKRUPA ENTERPRISES
Watchmen | N/C | N/C | GURUKRUPA ENTERPRISES | 5 | 2024-07-04 | DEVELOPMENT Security Service For Ostia Project | 2 | 13500 | 0 | 27000 | 0 | 2024-08-05 15:13 | 100% COMPLETION | 100 | 1 watchman For Day Ship & one for night Ship | 94 | 2024-08-05 | 27000 | 2024-08-06 15:12 | 0 | GURUKRUPA ENTERPRISES
Watchmen | N/C | N/C | GURUKRUPA ENTERPRISES | 5 | 2024-07-04 | DEVELOPMENT Security Service For Ostia Project | 2 | 13500 | 0 | 27000 | 0 | 2024-09-05 11:33 | 100% COMPLETION | 100 | H1-G1 Entrance Gate at Ramp, Against Bill No 2024-25/87 | 225 | 2024-09-05 | 27000 | 2024-12-20 14:10 | 0 | GURUKRUPA ENTERPRISES
Watchmen | N/C | N/C | GURUKRUPA ENTERPRISES | 5 | 2024-07-04 | DEVELOPMENT Security Service For Ostia Project | 2 | 13500 | 0 | 27000 | 0 | 2024-09-05 11:36 | 100% COMPLETION | 100 | F1 Building Front Primises Day & Night, Against Bill no 87, or the Month Of Aug-24 | 226 | 2024-09-05 | 27000 | 2024-12-20 14:11 | 0 | GURUKRUPA ENTERPRISES
Watchmen | N/C | N/C | GURUKRUPA ENTERPRISES | 5 | 2024-07-04 | DEVELOPMENT Security Service For Ostia Project | 1.33 | 13500 | 0 | 17955 | 0 | 2024-07-05 15:10 | 100% COMPLETION | 100 |  | 45 | 2024-07-05 | 17955 | 2024-07-05 16:47 | 0 | GURUKRUPA ENTERPRISES
Watchmen | N/C | N/C | GURUKRUPA ENTERPRISES | 5 | 2024-07-04 | DEVELOPMENT Security Service For Ostia Project | 2 | 13500 | 0 | 27000 | 0 | 2025-01-06 15:37 | 100% COMPLETION | 100 | Against Bill no 178 | 856 | 2025-01-06 | 27000 | 2025-01-09 10:19 | 0 | GURUKRUPA ENTERPRISES
Watchmen | N/C | N/C | GURUKRUPA ENTERPRISES | 5 | 2024-07-04 | DEVELOPMENT Security Service For Ostia Project | 2 | 13500 | 0 | 27000 | 0 | 2025-01-06 15:38 | 100% COMPLETION | 100 | Against Bill no 183 | 855 | 2025-01-06 | 27000 | 2025-01-09 10:18 | 0 | GURUKRUPA ENTERPRISES
Watchmen | N/C | N/C | GURUKRUPA ENTERPRISES | 5 | 2024-07-04 | DEVELOPMENT Security Service For Ostia Project | 2 | 13500 | 0 | 27000 | 0 | 2024-12-09 16:45 | 100% COMPLETION | 100 | Security Service For Ostia Project-NOV 2024 | 659 | 2024-12-09 | 27000 | 2024-12-20 14:11 | 0 | GURUKRUPA ENTERPRISES
Watchmen | N/C | N/C | GURUKRUPA ENTERPRISES | 5 | 2024-07-04 | DEVELOPMENT Security Service For Ostia Project | 2 | 13500 | 0 | 27000 | 0 | 2024-12-09 16:55 | 100% COMPLETION | 100 | Security Service For Ostia Project -NOV 2024 F1 FRONT PRIMISES | 660 | 2024-12-09 | 27000 | 2024-12-20 14:11 | 0 | GURUKRUPA ENTERPRISES
FLOORING TILE FIXING 800 X 800 | N/C | N/C | DEVA SUBHASH CHAVAN | 50 | 2024-10-07 | F1 BLDG 1ST FLOOR VITRIFIED FLOORING 800 x 800 FIXING WORK | 5860.7907 | 23 | 0 | 134798.1861 | 0 | 2024-12-09 15:42 | 100% COMPLETION | 100 | F1 BLDG 1ST FLOOR VITRIFIED FLOORING 800 x 800 FIXING WORK | 653 | 2024-12-09 | 189359.34 | 2024-12-24 10:35 | -54561.1539 | DEVA SUBHASH CHAVAN
SKIRTING FIXING WORK | N/C | N/C | DEVA SUBHASH CHAVAN | 50 | 2024-10-07 | F1 BLDG 1ST FLOOR SKIRTING FIXING WORK | 2005.9254 | 16 | 0 | 32094.8064 | 0 | 2024-12-09 15:42 | 100% COMPLETION | 100 | F1 BLDG 1ST FLOOR SKIRTING FIXING WORK | 653 | 2024-12-09 | 189359.34 | 2024-12-24 10:35 | -157264.5336 | DEVA SUBHASH CHAVAN
TOILET FLOORING FIXING | N/C | N/C | DEVA SUBHASH CHAVAN | 50 | 2024-10-07 | F1 BLDG 1ST FLOOR TOILET FLOORING | 37.4439 | 600 | 0 | 22466.34 | 0 | 2024-12-09 15:42 | 100% COMPLETION | 100 | F1 BLDG 1ST FLOOR TOILET FLOORING | 653 | 2024-12-09 | 189359.34 | 2024-12-24 10:35 | -166893 | DEVA SUBHASH CHAVAN
GRANITE UMBRA FIXING WORK | N/C | N/C | DEVA SUBHASH CHAVAN | 50 | 2024-10-07 | F1 BLDG UG AND MEZZ. FLOOR GRANITE UMBRA PATTI FIXING WORK | 213.9654 | 50 | 0 | 10698.27 | 0 | 2025-01-20 11:52 | 100% COMPLETION | 100 | F1 Building Tiling Work Against Bill no 3 | 988 | 2025-01-20 | 82911.59 | 2025-01-20 14:59 | -72213.32 | DEVA SUBHASH CHAVAN
GRANITE UMBRA FIXING WORK | N/C | N/C | DEVA SUBHASH CHAVAN | 50 | 2024-10-07 | F1 BLDG 1ST FLOOR GRANITE UMBRA PATTI FIXING WORK | 320.9481 | 50 | 0 | 16047.405 | 0 | 2025-01-20 11:52 | 100% COMPLETION | 100 | F1 Building Tiling Work Against Bill no 3 | 988 | 2025-01-20 | 82911.59 | 2025-01-20 14:59 | -66864.185 | DEVA SUBHASH CHAVAN
DADO TILE FIXING | N/C | N/C | DEVA SUBHASH CHAVAN | 50 | 2024-10-07 | F1 BLDG 2ND AND 3RD FLOOR DADO TILE | 3303.8771 | 17 | 0 | 56165.9107 | 0 | 2025-01-20 11:52 | 100% COMPLETION | 100 | F1 Building Tiling Work Against Bill no 3 | 988 | 2025-01-20 | 82911.59 | 2025-01-20 14:59 | -26745.6793 | DEVA SUBHASH CHAVAN
CEILING PATRA PUNNING IN GYPSUM FINISH | N/C | N/C | LAVANYA ENTERPRISES | 51 | 2024-10-07 | G1 BLDG CEILING GYPSUM WORK AT 3RD FLOOR | 2600.4544 | 12 | 0 | 31205.4528 | 0 | 2025-01-19 13:48 | 100% COMPLETION | 100 | Against Bill no G1-03 | 954 | 2025-01-19 | 59290.36 | 2025-01-20 14:53 | -28084.9072 | LAVANYA ENTERPRISES
CEILING PATRA PUNNING IN GYPSUM FINISH | N/C | N/C | LAVANYA ENTERPRISES | 51 | 2024-10-07 | G1 BLDG CEILING GYPSUM AT LOBBY AND PASSAGE | 2340.409 | 12 | 0 | 28084.908 | 0 | 2025-01-19 13:48 | 100% COMPLETION | 100 | Against Bill no G1-03 | 954 | 2025-01-19 | 59290.36 | 2025-01-20 14:53 | -31205.452 | LAVANYA ENTERPRISES
WALL IN GYPSUM FINISH | N/C | N/C | LAVANYA ENTERPRISES | 51 | 2024-10-07 | G1 BLDG WALL GYPSUM AT UG AND MEZZ. FLOOR | 5427.0354 | 23 | 0 | 124821.8142 | 0 | 2024-12-09 16:32 | 100% COMPLETION | 100 | G1 BLDG WALL GYPSUM AT UG AND MEZZ. FLOOR-100% | 657 | 2024-12-09 | 280849.08 | 2024-12-23 10:25 | -156027.2658 | LAVANYA ENTERPRISES
WALL IN GYPSUM FINISH | N/C | N/C | LAVANYA ENTERPRISES | 51 | 2024-10-07 | G1 BLDG WALL GYPSUM AT 3RD FLOOR | 6783.7942 | 23 | 0 | 156027.2666 | 0 | 2024-12-09 16:32 | 100% COMPLETION | 100 | G1 BLDG WALL GYPSUM AT 3RD FLOOR-100% | 657 | 2024-12-09 | 280849.08 | 2024-12-23 10:25 | -124821.8134 | LAVANYA ENTERPRISES
RCC PARAPET WALL ON LABOUR RATE | N/C | N/C | MOHAN SHRIKANT RAM | 52 | 2024-10-10 | F1- BLDG PARAPET WALL ON LABOUR RATE | 1770 | 120 | 0 | 212400 | 0 | 2024-10-17 11:28 | 100% COMPLETION | 100 | AGAINST BILL no12 | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | MOHAN SHRIKANT RAM
AT ALUMINIUM SECTION DELIVERY | N/C | N/C | SSD SERVICES | 53 | 2024-10-14 | G1 BLDG ALU WORK (EXT)- MATERIAL RECIVED AT SITE-100% | 1 | 76409.0702 | 0 | 76409.0702 | 13753.64 | 2024-12-09 14:54 | 100% COMPLETION | 100 | MATERIAL RECEVIED AT SITE | 649 | 2024-12-09 | 76409.07 | 2024-12-24 10:40 | 0.0002 | SSD SERVICES
5mm T. Glass With Alu. Sec 100mm x 50mm | N/C | N/C | SSD SERVICES | 53 | 2024-10-14 | G1 BLDG ALU WORK (EXT) 5mm T. Glass -MAT. RCVD & UG FLR | 1 | 47234.7 | 0 | 47234.7 | 8502.24 | 2024-12-09 15:05 | 100% COMPLETION | 100 | GLASS MATERIAL RCVD | 650 | 2024-12-09 | 47234.7 | 2024-12-24 10:40 | 0 | SSD SERVICES
10mm GLASS DOOR With Fitting | N/C | N/C | SSD SERVICES | 53 | 2024-10-14 | G1 BLDG ALU WORK (INT) 10MM GLASS DOOR-1ST & 2ND FLOOR - 60% | 2 | 40844.1211 | 0 | 81688.2422 | 14703.88 | 2025-02-04 16:02 | 100% COMPLETION | 100 | G1 BLDG ALU WORK (INT) 10MM GLASS DOOR-1ST & 2ND FLOOR | 1068 | 2025-02-04 | 81688.24 | 2025-02-05 14:33 | 0.0022 | SSD SERVICES
10mm GLASS DOOR With Fitting | N/C | N/C | SSD SERVICES | 53 | 2024-10-14 | G1 BLDG ALU WORK (INT) 10MM GLASS DOOR - 3RD FLOOR - 40% | 1 | 54458.8282 | 0 | 54458.8282 | 9802.58 | 2025-02-04 16:06 | 100% COMPLETION | 100 | G1 BLDG ALU WORK (INT) 10MM GLASS DOOR - 3RD FLOOR - 40% | 1069 | 2025-02-04 | 54458.83 | 2025-02-05 14:33 | -0.0018 | SSD SERVICES
12mm Partition With Fitting | N/C | N/C | SSD SERVICES | 53 | 2024-10-14 | G1 BLDG ALU WORK (INT) 12MM PARTITION -1ST & 2ND FLOOR - 60% | 2 | 37926.6839 | 0 | 75853.3678 | 13653.6 | 2025-02-04 16:08 | 100% COMPLETION | 100 | G1 BLDG ALU WORK (INT) 12MM PARTITION -1ST & 2ND FLOOR - 60% | 1070 | 2025-02-04 | 75853.37 | 2025-02-05 14:33 | -0.0022 | SSD SERVICES
12mm Partition With Fitting | N/C | N/C | SSD SERVICES | 53 | 2024-10-14 | G1 BLDG ALU WORK (INT) 12MM PARTITION -3RD FLOOR - 40% | 1 | 50568.9119 | 0 | 50568.9119 | 9102.4 | 2025-02-04 16:14 | 100% COMPLETION | 100 | G1 BLDG ALU WORK (INT) 12MM PARTITION -3RD FLOOR - 40% | 1071 | 2025-02-04 | 50568.91 | 2025-02-05 14:33 | 0.0019 | SSD SERVICES
2 track slidding window | N/C | N/C | SSD SERVICES | 53 | 2024-10-14 | G1 BLDG ALU WORK (EXT)-2 TRACK SD WIN. UG ,MEZZ,1ST & 2ND FL | 2 | 8752.3117 | 0 | 17504.6234 | 3150.84 | 2025-02-04 16:16 | 100% COMPLETION | 100 | G1 BLDG ALU WORK (EXT)-2 TRACK SD WIN. UG ,MEZZ,1ST & 2ND FL | 1072 | 2025-02-04 | 53486.35 | 2025-02-05 14:33 | -35981.7266 | SSD SERVICES
2 track slidding window | N/C | N/C | SSD SERVICES | 53 | 2024-10-14 | G1 BLDG ALU WORK (EXT)-2 TRACK SD WIN. 3RD FLOOR - 40% | 1 | 11669.7489 | 0 | 11669.7489 | 2100.56 | 2025-02-04 16:16 | 100% COMPLETION | 100 | G1 BLDG ALU WORK (EXT)-2 TRACK SD WIN. 3RD FLOOR | 1072 | 2025-02-04 | 53486.35 | 2025-02-05 14:33 | -41816.6011 | SSD SERVICES
2 track slidding window | N/C | N/C | SSD SERVICES | 53 | 2024-10-14 | G1 BLDG ALU WORK (INT)-2 TRACK SD WIN. 1ST & 2ND FLOOR-60% | 2 | 7293.5931 | 0 | 14587.1862 | 2625.7 | 2025-02-04 16:16 | 100% COMPLETION | 100 | G1 BLDG ALU WORK (INT)-2 TRACK SD WIN. 1ST & 2ND FLOOR | 1072 | 2025-02-04 | 53486.35 | 2025-02-05 14:33 | -38899.1638 | SSD SERVICES
2 track slidding window | N/C | N/C | SSD SERVICES | 53 | 2024-10-14 | G1 BLDG ALU WORK (INT)-2 TRACK SD WIN. 3RD FLOOR- 40% | 1 | 9724.7908 | 0 | 9724.7908 | 1750.46 | 2025-02-04 16:16 | 100% COMPLETION | 100 | G1 BLDG ALU WORK (INT)-2 TRACK SD WIN. 3RD FLOOR | 1072 | 2025-02-04 | 53486.35 | 2025-02-05 14:33 | -43761.5592 | SSD SERVICES
COMPRESSIVE STRENGTH TESTING | N/C | N/C | Construction Excellence Testing & Research Ser.LLP | 59 | 2024-10-22 | E1 BLDG 4TH SLAB MATERIAL TESTING FOR CUBE AND REINFORCEM | 3 | 100 | 0 | 300 | 54 | 2024-12-21 18:17 | 100% COMPLETION | 100 | Against Bill no 4475 | 747 | 2024-12-21 | 300 | 2024-12-26 12:46 | 0 | Construction Excellence Testing & Research Ser.LLP
COMPRESSIVE STRENGTH TESTING | N/C | N/C | Construction Excellence Testing & Research Ser.LLP | 59 | 2024-10-22 | E1 BLDG 4TH SLAB MATERIAL TESTING FOR CUBE AND REINFORCEM | 3 | 100 | 0 | 300 | 54 | 2024-12-21 18:19 | 100% COMPLETION | 100 | Against Bill no 4665 4th Slab Part-2 | 746 | 2024-12-21 | 300 | 2024-12-26 12:46 | 0 | Construction Excellence Testing & Research Ser.LLP
10 mm Reinforcement Steel Testing | N/C | N/C | Construction Excellence Testing & Research Ser.LLP | 59 | 2024-10-22 | E1 BLDG 5TH SLAB MATERIAL TESTING FOR CUBE AND REINFORCEM | 3 | 450 | 0 | 1350 | 243 | 2024-12-21 18:04 | 100% COMPLETION | 100 | Against Bill no 4518 | 748 | 2024-12-21 | 9000 | 2024-12-26 12:46 | -7650 | Construction Excellence Testing & Research Ser.LLP
12mm Reinforcement Steel Testing | N/C | N/C | Construction Excellence Testing & Research Ser.LLP | 59 | 2024-10-22 | E1 BLDG 5TH SLAB MATERIAL TESTING FOR CUBE AND REINFORCEM | 3 | 450 | 0 | 1350 | 243 | 2024-12-21 18:04 | 100% COMPLETION | 100 | Against Bill no 4518 | 748 | 2024-12-21 | 9000 | 2024-12-26 12:46 | -7650 | Construction Excellence Testing & Research Ser.LLP
16mm Reinforcement Steel Testing | N/C | N/C | Construction Excellence Testing & Research Ser.LLP | 59 | 2024-10-22 | E1 BLDG 5TH SLAB MATERIAL TESTING FOR CUBE AND REINFORCEM | 3 | 550 | 0 | 1650 | 297 | 2024-12-21 18:04 | 100% COMPLETION | 100 | Against Bill no 4518 | 748 | 2024-12-21 | 9000 | 2024-12-26 12:46 | -7350 | Construction Excellence Testing & Research Ser.LLP
20mm Reinforcement Steel Testing | N/C | N/C | Construction Excellence Testing & Research Ser.LLP | 59 | 2024-10-22 | E1 BLDG 5TH SLAB MATERIAL TESTING FOR CUBE AND REINFORCEM | 3 | 550 | 0 | 1650 | 297 | 2024-12-21 18:04 | 100% COMPLETION | 100 | Against Bill no 4518 | 748 | 2024-12-21 | 9000 | 2024-12-26 12:46 | -7350 | Construction Excellence Testing & Research Ser.LLP
25mm Reinforcement Steel Testing | N/C | N/C | Construction Excellence Testing & Research Ser.LLP | 59 | 2024-10-22 | E1 BLDG 5TH SLAB MATERIAL TESTING FOR CUBE AND REINFORCEM | 3 | 550 | 0 | 1650 | 297 | 2024-12-21 18:04 | 100% COMPLETION | 100 | Against Bill no 4518 | 748 | 2024-12-21 | 9000 | 2024-12-26 12:46 | -7350 | Construction Excellence Testing & Research Ser.LLP
8MM Reinforcement Steel Testing | N/C | N/C | Construction Excellence Testing & Research Ser.LLP | 59 | 2024-10-22 | E1 BLDG 5TH SLAB MATERIAL TESTING FOR CUBE AND REINFORCEM | 3 | 450 | 0 | 1350 | 243 | 2024-12-21 18:04 | 100% COMPLETION | 100 | Against Bill no 4518 | 748 | 2024-12-21 | 9000 | 2024-12-26 12:46 | -7650 | Construction Excellence Testing & Research Ser.LLP
TRACTOR | N/C | N/C | SANGRAM LAND DEVELOPERS | 6 | 2024-07-05 | MACHINARY MACHINARY Required For Devlopment Work | 1 | 2500 | 0 | 2500 | 450 | 2024-12-21 18:39 | 100% COMPLETION | 100 | Against Bill no 38 | 744 | 2024-12-21 | 96600 | 2024-12-26 12:50 | -94100 | SANGRAM LAND DEVELOPERS
JCB BUCKET | N/C | N/C | SANGRAM LAND DEVELOPERS | 6 | 2024-07-05 | MACHINARY MACHINARY Required For Devlopment Work | 39 | 900 | 0 | 35100 | 6318 | 2024-12-21 18:39 | 100% COMPLETION | 100 | Against Bill no 38 | 744 | 2024-12-21 | 96600 | 2024-12-26 12:50 | -61500 | SANGRAM LAND DEVELOPERS
POKLAND SANY 850- BREAKER | N/C | N/C | SANGRAM LAND DEVELOPERS | 6 | 2024-07-05 | MACHINARY MACHINARY Required For Devlopment Work | 10 | 2300 | 0 | 23000 | 4140 | 2024-12-21 18:39 | 100% COMPLETION | 100 | Against Bill no 38 | 744 | 2024-12-21 | 96600 | 2024-12-26 12:50 | -73600 | SANGRAM LAND DEVELOPERS
POKLAND SANY 850- BUCKET | N/C | N/C | SANGRAM LAND DEVELOPERS | 6 | 2024-07-05 | MACHINARY MACHINARY Required For Devlopment Work | 18 | 2000 | 0 | 36000 | 6480 | 2024-12-21 18:39 | 100% COMPLETION | 100 | Against Bill no 38 | 744 | 2024-12-21 | 96600 | 2024-12-26 12:50 | -60600 | SANGRAM LAND DEVELOPERS
BOBCAT on Hours | N/C | N/C | SANGRAM LAND DEVELOPERS | 6 | 2024-07-05 | MACHINARY MACHINARY Required For Devlopment Work | 10 | 900 | 0 | 9000 | 1620 | 2024-10-14 18:52 | 100% COMPLETION | 100 | Against Bill no 29 | 443 | 2024-10-14 | 25200 | 2024-12-20 14:14 | -16200 | SANGRAM LAND DEVELOPERS
JCB BUCKET | N/C | N/C | SANGRAM LAND DEVELOPERS | 6 | 2024-07-05 | MACHINARY MACHINARY Required For Devlopment Work | 18 | 900 | 0 | 16200 | 2916 | 2024-10-14 18:52 | 100% COMPLETION | 100 | Against Bill no 29 | 443 | 2024-10-14 | 25200 | 2024-12-20 14:14 | -9000 | SANGRAM LAND DEVELOPERS
BOBCAT on Hours | N/C | N/C | SANGRAM LAND DEVELOPERS | 6 | 2024-07-05 | MACHINARY MACHINARY Required For Devlopment Work | 18.5 | 900 | 0 | 16650 | 2997 | 2024-07-20 18:20 | 100% COMPLETION | 100 | chalan no 1210,1211,1212,1220 | 89 | 2024-07-31 | 161200 | 2024-07-31 18:48 | -144550 | SANGRAM LAND DEVELOPERS
JCB BUCKET | N/C | N/C | SANGRAM LAND DEVELOPERS | 6 | 2024-07-05 | MACHINARY MACHINARY Required For Devlopment Work | 137 | 900 | 0 | 123300 | 22194 | 2024-07-20 18:20 | 100% COMPLETION | 100 | Ch no 1208,2151,2153,2154,2155,2156,1408,1409,1410,2162,1255,1411,1412,1413,2168,2167,1253,1251,1252,1254,1256 | 89 | 2024-07-31 | 161200 | 2024-07-31 18:48 | -37900 | SANGRAM LAND DEVELOPERS
TRACTOR | N/C | N/C | SANGRAM LAND DEVELOPERS | 6 | 2024-07-05 | MACHINARY MACHINARY Required For Devlopment Work | 8.5 | 2500 | 0 | 21250 | 3825 | 2024-07-20 18:20 | 100% COMPLETION | 100 | ch no 2151,2153,2154,2155,2156,1409,1410,1411 | 89 | 2024-07-31 | 161200 | 2024-07-31 18:48 | -139950 | SANGRAM LAND DEVELOPERS
JCB BUCKET | N/C | N/C | SANGRAM LAND DEVELOPERS | 6 | 2024-07-05 | MACHINARY MACHINARY Required For Devlopment Work | 48.5 | 900 | 0 | 43650 | 7857 | 2024-08-05 15:41 | 100% COMPLETION | 100 |  | 96 | 2024-08-05 | 47400 | 2024-08-06 15:10 | -3750 | SANGRAM LAND DEVELOPERS
TRACTOR | N/C | N/C | SANGRAM LAND DEVELOPERS | 6 | 2024-07-05 | MACHINARY MACHINARY Required For Devlopment Work | 1.5 | 2500 | 0 | 3750 | 675 | 2024-08-05 15:41 | 100% COMPLETION | 100 |  | 96 | 2024-08-05 | 47400 | 2024-08-06 15:10 | -43650 | SANGRAM LAND DEVELOPERS
TRACTOR | N/C | N/C | SANGRAM LAND DEVELOPERS | 6 | 2024-07-05 | MACHINARY MACHINARY Required For Devlopment Work | 3.5 | 2500 | 0 | 8750 | 1575 | 2025-01-19 14:01 | 100% COMPLETION | 100 | Against Bill no 44 | 956 | 2025-01-19 | 65000 | 2025-01-20 14:54 | -56250 | SANGRAM LAND DEVELOPERS
JCB BUCKET | N/C | N/C | SANGRAM LAND DEVELOPERS | 6 | 2024-07-05 | MACHINARY MACHINARY Required For Devlopment Work | 34 | 900 | 0 | 30600 | 5508 | 2025-01-19 14:01 | 100% COMPLETION | 100 | Against Bill no 44 | 956 | 2025-01-19 | 65000 | 2025-01-20 14:54 | -34400 | SANGRAM LAND DEVELOPERS
BOBCAT on Hours | N/C | N/C | SANGRAM LAND DEVELOPERS | 6 | 2024-07-05 | MACHINARY MACHINARY Required For Devlopment Work | 28.5 | 900 | 0 | 25650 | 4617 | 2025-01-19 14:01 | 100% COMPLETION | 100 | Against Bill no 44 | 956 | 2025-01-19 | 65000 | 2025-01-20 14:54 | -39350 | SANGRAM LAND DEVELOPERS
BOBCAT on Hours | N/C | N/C | SANGRAM LAND DEVELOPERS | 6 | 2024-07-05 | MACHINARY MACHINARY Required For Devlopment Work | 46 | 900 | 0 | 41400 | 7452 | 2025-01-07 10:43 | 100% COMPLETION | 100 | BOBCAT FOR 13/10/2024 TO 23/10/2024-46 HRS | 870 | 2025-01-07 | 221400 | 2025-01-09 12:45 | -180000 | SANGRAM LAND DEVELOPERS
BOBCAT on Hours | N/C | N/C | SANGRAM LAND DEVELOPERS | 6 | 2024-07-05 | MACHINARY MACHINARY Required For Devlopment Work | 200 | 900 | 0 | 180000 | 32400 | 2025-01-07 10:43 | 100% COMPLETION | 100 | BOBCAT FOR 25/10/2024 TO 16/12/2024-200 HRS | 870 | 2025-01-07 | 221400 | 2025-01-09 12:45 | -41400 | SANGRAM LAND DEVELOPERS
TRACTOR | N/C | N/C | SANGRAM LAND DEVELOPERS | 6 | 2024-07-05 | MACHINARY MACHINARY Required For Devlopment Work | 1 | 2500 | 0 | 2500 | 450 | 2024-09-20 10:57 | 100% COMPLETION | 100 | Work Complition against bill no 22/2024-25 | 311 | 2024-09-20 | 52450 | 2024-12-20 14:14 | -49950 | SANGRAM LAND DEVELOPERS
JCB BUCKET | N/C | N/C | SANGRAM LAND DEVELOPERS | 6 | 2024-07-05 | MACHINARY MACHINARY Required For Devlopment Work | 30 | 900 | 0 | 27000 | 4860 | 2024-09-20 10:57 | 100% COMPLETION | 100 | Work Complition against bill no 22/2024-25 | 311 | 2024-09-20 | 52450 | 2024-12-20 14:14 | -25450 | SANGRAM LAND DEVELOPERS
BOBCAT on Hours | N/C | N/C | SANGRAM LAND DEVELOPERS | 6 | 2024-07-05 | MACHINARY MACHINARY Required For Devlopment Work | 25.5 | 900 | 0 | 22950 | 4131 | 2024-09-20 16:43 | 100% COMPLETION | 100 |  | 311 | 2024-09-20 | 52450 | 2024-12-20 14:14 | -29500 | SANGRAM LAND DEVELOPERS
GI TOP COVER FOR SHUTTER | N/C | N/C | GOPAL PRABHU KAMBLE | 61 | 2024-11-16 | F1 BUILDING UPPER GROUND SHOP MS ROLLING SHUTTER LAB AND MAT | 170 | 160 | 0 | 27200 | 0 | 2024-11-23 17:01 | 100% COMPLETION | 100 | F1 Building Upper Parking Rolling Shutter | 541 | 2024-11-23 | 400560 | 2024-12-24 10:43 | -373360 | GOPAL PRABHU KAMBLE
MS GEAR SET FOR SHUTTER WITH MS HANDLE | N/C | N/C | GOPAL PRABHU KAMBLE | 61 | 2024-11-16 | F1 BUILDING UPPER GROUND SHOP MS ROLLING SHUTTER LAB AND MAT | 17 | 7500 | 0 | 127500 | 0 | 2024-11-23 17:01 | 100% COMPLETION | 100 | F1 Building Upper Parking Rolling Shutter | 541 | 2024-11-23 | 400560 | 2024-12-24 10:43 | -273060 | GOPAL PRABHU KAMBLE
MS GRID PATTTI MAKING CHARGES | N/C | N/C | GOPAL PRABHU KAMBLE | 61 | 2024-11-16 | F1 BUILDING UPPER GROUND SHOP MS ROLLING SHUTTER LAB AND MAT | 323 | 50 | 0 | 16150 | 0 | 2024-11-23 17:01 | 100% COMPLETION | 100 | F1 Building Upper Parking Rolling Shutter | 541 | 2024-11-23 | 400560 | 2024-12-24 10:43 | -384410 | GOPAL PRABHU KAMBLE
MS ROLLING SHUTTER (20 Guage) | N/C | N/C | GOPAL PRABHU KAMBLE | 61 | 2024-11-16 | F1 BUILDING UPPER GROUND SHOP MS ROLLING SHUTTER LAB AND MAT | 1482 | 155 | 0 | 229710 | 0 | 2024-11-23 17:01 | 100% COMPLETION | 100 | F1 Building Upper Parking Rolling Shutter | 541 | 2024-11-23 | 400560 | 2024-12-24 10:43 | -170850 | GOPAL PRABHU KAMBLE
TRACTOR WITH LABOUR | N/C | N/C | MANU S RATHOD | 62 | 2024-11-20 | DEVELOPMENT Rabit Shifting Work | 6 | 700 | 0 | 4200 | 0 | 2024-11-23 17:19 | 100% COMPLETION | 100 | H1 Old Sales Office Pantry Debris Shifting work Bill no 18 | 542 | 2024-11-23 | 4200 | 2024-12-24 10:42 | 0 | MANU S RATHOD
Hand Breaker With Oprator | N/C | N/C | BALAJI ENTERPRISES | 63 | 2024-11-20 | DEVELOPMENT Hiring Hand Breaker and Oprator | 7 | 1200 | 0 | 8400 | 0 | 2024-11-25 14:41 | 100% COMPLETION | 100 | Against Bill no 71 for H1 Building Old Sales office Pantry Structure Breaking work | 548 | 2024-11-25 | 8400 | 2024-12-24 10:41 | 0 | BALAJI ENTERPRISES
RCC WORK-LABOUR | N/C | N/C | SAKSHI CONSTRUCTION AND DEVELOPERS | 64 | 2024-11-24 | E1 BLDG RCC : 5TH SLAB - SHUTT.,REINF. & CAST. OF SLAB | 2571.9451 | 164 | 0 | 421798.9964 | 0 | 2024-12-09 16:11 | 100% COMPLETION | 100 | 5TH SLAB - SHUTT.,REINF. & CAST. OF SLAB | 655 | 2024-12-09 | 421799 | 2024-12-24 10:31 | -0.0036 | SAKSHI CONSTRUCTION AND DEVELOPERS
RCC WORK-LABOUR | N/C | N/C | SAKSHI CONSTRUCTION AND DEVELOPERS | 64 | 2024-11-24 | E1 BLDG RCC : 6TH SLAB - SHUTT.,REINF. & CAST. OF SLAB | 2571.9451 | 164 | 0 | 421798.9964 | 0 | 2025-01-03 10:32 | 100% COMPLETION | 100 | E1 BLDG RCC : 6TH SLAB - SHUTT.,REINF. & CAST. OF SLAB-DONE | 824 | 2025-01-03 | 421799 | 2025-01-06 14:46 | -0.0036 | SNEHA ENTERPRISES
RCC WORK-LABOUR | N/C | N/C | SAKSHI CONSTRUCTION AND DEVELOPERS | 64 | 2024-11-24 | E1 BLDG RCC : 7TH SLAB - SHUTT.,REINF. & CAST. OF SLAB | 2679.1098 | 164 | 0 | 439374.0072 | 0 | 2025-02-04 17:31 | 100% COMPLETION | 100 | E1 BLDG RCC : 7TH SLAB - SHUTT.,REINF. & CAST. OF SLAB | 1073 | 2025-02-04 | 439374.01 | 2025-02-05 14:34 | -0.0028 | SNEHA ENTERPRISES
RCC WORK-LABOUR | N/C | N/C | Shri Swami Samarth Construction & Developers | 65 | 2024-11-24 | E1 BLDG RCC : 7TH SLAB - SHUTT.,REINF. & CAST. OF SLAB | 6251.2561 | 164 | 0 | 1025206.0004 | 184537.08 | 2025-02-04 17:23 | 100% COMPLETION | 100 | E1 BLDG RCC : 7TH SLAB - SHUTT.,REINF. & CAST. OF SLAB | 1093 | 2025-02-05 | 1025206 | 1900-01-01 | 0.0004 | Shri Swami Samarth Construction & Developers
RCC WORK-LABOUR | N/C | N/C | Shri Swami Samarth Construction & Developers | 65 | 2024-11-24 | E1 BLDG RCC : 6TH SLAB - SHUTT.,REINF. & CAST. OF SLAB | 6001.2073 | 164 | 0 | 984197.9972 | 177155.64 | 2025-01-19 15:57 | 100% COMPLETION | 100 | 6th slab Casting Completed | 985 | 2025-01-19 | 984198 | 2025-01-20 14:58 | -0.0028 | Shri Swami Samarth Construction & Developers
RCC WORK-LABOUR | N/C | N/C | Shri Swami Samarth Construction & Developers | 65 | 2024-11-24 | E1 BLDG RCC : 5TH SLAB - SHUTT.,REINF. & CAST. OF SLAB | 6001.2073 | 164 | 0 | 984197.9972 | 177155.64 | 2024-12-21 18:13 | 100% COMPLETION | 100 | Against Bill no 73 | 749 | 2024-12-21 | 984198 | 2024-12-26 12:28 | -0.0028 | Shri Swami Samarth Construction & Developers
10mm GLASS DOOR With Fitting | N/C | N/C | SUNIL GUPTA | 66 | 2024-12-06 | G1 BLDG ALU WORK (INT) 10MM GLASS DOOR-1ST & 2ND FLOOR - 60% | 2 | 17504.6233 | 0 | 35009.2466 | 0 | 2025-02-04 17:38 | 100% COMPLETION | 100 | G1 BLDG ALU WORK (INT) 10MM GLASS DOOR-1ST & 2ND FLOOR - 60% | 1074 | 2025-02-04 | 67517.84 | 2025-02-05 14:34 | -32508.5934 | SUNIL GUPTA
12mm Partition With Fitting | N/C | N/C | SUNIL GUPTA | 66 | 2024-12-06 | G1 BLDG ALU WORK (INT) 12MM PARTITION -1ST & 2ND FLOOR - 60% | 2 | 16254.2931 | 0 | 32508.5862 | 0 | 2025-02-04 17:38 | 100% COMPLETION | 100 | G1 BLDG ALU WORK (INT) 12MM PARTITION -1ST & 2ND FLOOR - 60% | 1074 | 2025-02-04 | 67517.84 | 2025-02-05 14:34 | -35009.2538 | SUNIL GUPTA
ELECTRICAL WORK. | N/C | N/C | RAMKISAN RAOSAHEB KHOTKAR | 67 | 2024-12-07 | F1 BLDG ELECTRICAL WORK-LABOUR | 1.25 | 20000 | 0 | 25000 | 0 | 2025-01-21 17:11 | 100% COMPLETION | 100 | F1 BLDG ELECTRICAL WORK-LABOUR | 0 | 1900-01-01 | 0 | 1900-01-01 | 0 | RAMKISAN RAOSAHEB KHOTKAR
ELECTRICAL WORK. | N/C | N/C | RAMKISAN RAOSAHEB KHOTKAR | 67 | 2024-12-07 | F1 BLDG ELECTRICAL WORK-LABOUR | 1.25 | 20000 | 0 | 25000 | 0 | 2025-01-20 16:26 | 100% COMPLETION | 100 | against bill no 2 | 997 | 2025-01-20 | 25000 | 2025-01-22 13:51 | 0 | RAMKISAN RAOSAHEB KHOTKAR
ELECTRICAL WORK. | N/C | N/C | RAMKISAN RAOSAHEB KHOTKAR | 67 | 2024-12-07 | F1 BLDG ELECTRICAL WORK-LABOUR | 1 | 20000 | 0 | 20000 | 0 | 2024-12-09 15:17 | 100% COMPLETION | 100 | F1 BLDG ELECTRICAL WORK-LABOUR | 651 | 2024-12-09 | 20000 | 2024-12-24 10:39 | 0 | RAMKISAN RAOSAHEB KHOTKAR
Rebaring Work Dia 10 mm | N/C | N/C | Shree Sai Service | 69 | 2024-12-10 | F1-G1 BUILDING BAR REBARING WORK | 97 | 50 | 0 | 4850 | 0 | 2024-12-21 10:26 | 100% COMPLETION | 100 | F1-G1 BUILDING BAR REBARING WORK | 732 | 2024-12-21 | 4850 | 2024-12-26 12:53 | 0 | Shree Sai Service
Rebaring Work Dia 8mm | N/C | N/C | Shree Sai Service | 69 | 2024-12-10 | F1-G1 BUILDING BAR REBARING WORK | 806 | 40 | 0 | 32240 | 0 | 2024-12-21 10:26 | 100% COMPLETION | 100 | F1-G1 BUILDING BAR REBARING WORK, CHALAN-1122,1123 | 733 | 2024-12-21 | 32240 | 2024-12-26 12:53 | 0 | Shree Sai Service
Rebaring Work Dia 8mm | N/C | N/C | Shree Sai Service | 69 | 2024-12-10 | F1-G1 BUILDING BAR REBARING WORK | 743 | 40 | 0 | 29720 | 0 | 2024-12-21 10:31 | 100% COMPLETION | 100 | F1-G1 BUILDING BAR REBARING WORK, CHALAN-1125,1126 | 734 | 2024-12-21 | 29720 | 2024-12-26 12:53 | 0 | Shree Sai Service
MINI POCLAIN BREAKER | N/C | N/C | SAI COMPACTOR SERVICE | 7 | 2024-07-05 | MACHINARY MACHINARY Required For Devlopment Work | 4 | 1400 | 0 | 5600 | 0 | 2024-12-09 17:04 | 100% COMPLETION | 100 | MINI POCLAIN BREAKER CHALAN-1587 | 661 | 2024-12-09 | 66400 | 2024-12-20 14:13 | -60800 | SAI COMPACTOR SERVICE
MINI POCLAIN BUCKET | N/C | N/C | SAI COMPACTOR SERVICE | 7 | 2024-07-05 | MACHINARY MACHINARY Required For Devlopment Work | 47 | 1200 | 0 | 56400 | 0 | 2024-12-09 17:04 | 100% COMPLETION | 100 | MINI POCLAIN BUCKET-1586,1587,1588,1858,1859,1862,1863,1864 | 661 | 2024-12-09 | 66400 | 2024-12-20 14:13 | -10000 | SAI COMPACTOR SERVICE
Fare Charges Transportation - | N/C | N/C | SAI COMPACTOR SERVICE | 7 | 2024-07-05 | MACHINARY MACHINARY Required For Devlopment Work | 2 | 1000 | 0 | 2000 | 0 | 2024-12-09 17:16 | 100% COMPLETION | 100 | BOTH SIDE TRANSPORTATION | 661 | 2024-12-09 | 66400 | 2024-12-20 14:13 | -64400 | SAI COMPACTOR SERVICE
MINI POCLAIN BUCKET | N/C | N/C | SAI COMPACTOR SERVICE | 7 | 2024-07-05 | MACHINARY MACHINARY Required For Devlopment Work | 2 | 1200 | 0 | 2400 | 0 | 2024-12-09 17:19 | 100% COMPLETION | 100 |  | 661 | 2024-12-09 | 66400 | 2024-12-20 14:13 | -64000 | SAI COMPACTOR SERVICE
MINI POCLAIN BUCKET | N/C | N/C | SAI COMPACTOR SERVICE | 7 | 2024-07-05 | MACHINARY MACHINARY Required For Devlopment Work | 34.3334 | 1200 | 0 | 41200.08 | 7416.02 | 2024-12-27 18:34 | 100% COMPLETION | 100 | F1 BLDG PARKING FLOOR DRAINAGE LINE EXCAVATION WORK | 787 | 2024-12-27 | 43200.08 | 2025-01-03 12:30 | -2000 | NAGESHWAR INFRA
Fare Charges Transportation - | N/C | N/C | SAI COMPACTOR SERVICE | 7 | 2024-07-05 | MACHINARY MACHINARY Required For Devlopment Work | 2 | 1000 | 0 | 2000 | 240 | 2024-12-27 18:34 | 100% COMPLETION | 100 |  | 787 | 2024-12-27 | 43200.08 | 2025-01-03 12:30 | -41200.08 | NAGESHWAR INFRA
MINI POCLAIN BUCKET | N/C | N/C | SAI COMPACTOR SERVICE | 7 | 2024-07-05 | MACHINARY MACHINARY Required For Devlopment Work | 5 | 1200 | 0 | 6000 | 0 | 2024-07-30 12:19 | 100% COMPLETION | 100 | Challan no 1561,1402 used for F1 Building Shop Front Electrical Line & Rainwater Trench Excavation work. | 92 | 2024-08-05 | 6000 | 2024-08-06 15:06 | 0 | SAI COMPACTOR SERVICE
MINI ROLLER COMPACTOR | N/C | N/C | SAI COMPACTOR SERVICE | 7 | 2024-07-05 | MACHINARY MACHINARY Required For Devlopment Work | 2 | 3500 | 0 | 7000 | 0 | 2024-07-30 12:19 | 100% COMPLETION | 100 | Challan No 1457, 1458 used for F1 & G1 Building shop front murum compaction work | 85 | 2024-07-30 | 7000 | 2024-07-30 16:47 | 0 | SAI COMPACTOR SERVICE
MINI ROLLER COMPACTOR | N/C | N/C | SAI COMPACTOR SERVICE | 7 | 2024-07-05 | MACHINARY MACHINARY Required For Devlopment Work | 7 | 3500 | 0 | 24500 | 0 | 2024-07-06 17:33 | 100% COMPLETION | 100 | Challan No 1268,1269,1276,1392,1393,1291,1294 | 46 | 2024-07-06 | 24500 | 2024-07-06 18:43 | 0 | SAI COMPACTOR SERVICE
MINI POCLAIN BREAKER | N/C | N/C | SAI COMPACTOR SERVICE | 7 | 2024-07-05 | MACHINARY MACHINARY Required For Devlopment Work | 7 | 1400 | 0 | 9800 | 0 | 2024-07-06 18:30 | 100% COMPLETION | 100 | Challan No 1401,1404 | 47 | 2024-07-06 | 41600 | 2024-07-06 18:45 | -31800 | SAI COMPACTOR SERVICE
MINI POCLAIN BUCKET | N/C | N/C | SAI COMPACTOR SERVICE | 7 | 2024-07-05 | MACHINARY MACHINARY Required For Devlopment Work | 26.5 | 1200 | 0 | 31800 | 0 | 2024-07-06 18:30 | 100% COMPLETION | 100 | Challan no1401,1404,1386,1387,1398 | 47 | 2024-07-06 | 41600 | 2024-07-06 18:45 | -9800 | SAI COMPACTOR SERVICE
MINI ROLLER COMPACTOR | N/C | N/C | SAI COMPACTOR SERVICE | 7 | 2024-07-05 | MACHINARY MACHINARY Required For Devlopment Work | 3 | 3500 | 0 | 10500 | 0 | 2025-02-05 18:33 | 100% COMPLETION | 100 | Against Bill no 726 | 1115 | 2025-02-05 | 11000 | 1900-01-01 | -500 | SAI COMPACTOR SERVICE
Fare Charges Transportation - | N/C | N/C | SAI COMPACTOR SERVICE | 7 | 2024-07-05 | MACHINARY MACHINARY Required For Devlopment Work | 0.5 | 1000 | 0 | 500 | 60 | 2025-02-05 18:33 | 100% COMPLETION | 100 | Against Bill no 726 | 1115 | 2025-02-05 | 11000 | 1900-01-01 | -10500 | SAI COMPACTOR SERVICE
MINI POCLAIN BREAKER | N/C | N/C | SAI COMPACTOR SERVICE | 7 | 2024-07-05 | MACHINARY MACHINARY Required For Devlopment Work | 6 | 1400 | 0 | 8400 | 0 | 2024-08-19 11:37 | 100% COMPLETION | 100 | Excavation & breaking Work Near Podium for E1 Drainage Line Plumbing work | 158 | 2024-08-19 | 13200 | 2024-09-04 16:31 | -4800 | SAI COMPACTOR SERVICE
MINI POCLAIN BUCKET | N/C | N/C | SAI COMPACTOR SERVICE | 7 | 2024-07-05 | MACHINARY MACHINARY Required For Devlopment Work | 4 | 1200 | 0 | 4800 | 0 | 2024-08-19 11:37 | 100% COMPLETION | 100 | Excavation & breaking Work Near Podium for E1 Drainage Line Plumbing work | 158 | 2024-08-19 | 13200 | 2024-09-04 16:31 | -8400 | SAI COMPACTOR SERVICE
Patra (Tin sheet) Fixing | N/C | N/C | S.S. ENTERPRISES | 70 | 2024-12-18 | M.S SHEET FABRICATION WORK FOR STORE IN E1-BLDG | 1036 | 10 | 0 | 10360 | 0 | 2024-12-21 10:47 | 100% COMPLETION | 100 | M.S SHEET FABRICATION WORK FOR STORE IN E1-BLDG | 737 | 2024-12-21 | 27794 | 2024-12-26 12:50 | -17434 | S.S. ENTERPRISES
Patra (Tin sheet) Fixing | N/C | N/C | S.S. ENTERPRISES | 70 | 2024-12-18 | M.S SHEET FABRICATION WORK FOR CEMENT GODOWN IN E1-BLDG | 505 | 10 | 0 | 5050 | 0 | 2024-12-21 10:47 | 100% COMPLETION | 100 | M.S SHEET FABRICATION WORK FOR CEMENT GODOWN IN E1-BLDG | 737 | 2024-12-21 | 27794 | 2024-12-26 12:50 | -22744 | S.S. ENTERPRISES
Patra (Tin sheet) Removing work | N/C | N/C | S.S. ENTERPRISES | 70 | 2024-12-18 | H1 & G1 BLDG B/W RAMP SIDE SHED REMOVING WORK. | 1032 | 12 | 0 | 12384 | 0 | 2024-12-21 10:47 | 100% COMPLETION | 100 | H1 & G1 BLDG B/W RAMP SIDE SHED REMOVING WORK. S Patra | 737 | 2024-12-21 | 27794 | 2024-12-26 12:50 | -15410 | S.S. ENTERPRISES
OHWT MS Cover (Labour + Material) | N/C | N/C | S.S. ENTERPRISES | 71 | 2024-12-18 | F1 BLDG OHW TANK MS COVER & M.S RAILING (M+L) | 4 | 2325 | 0 | 9300 | 0 | 2024-12-21 10:50 | 100% COMPLETION | 100 | F1 BLDG OHW TANK MS COVER & M.S RAILING (M+L) | 739 | 2024-12-21 | 39550 | 2024-12-26 12:50 | -30250 | S.S. ENTERPRISES
OHWT MS Railing (Mat. + Lab.) | N/C | N/C | S.S. ENTERPRISES | 71 | 2024-12-18 | F1 BLDG OHW TANK MS COVER & M.S RAILING (M+L) | 275 | 110 | 0 | 30250 | 0 | 2024-12-21 10:50 | 100% COMPLETION | 100 | F1 BLDG OHW TANK MS COVER & M.S RAILING (M+L) | 739 | 2024-12-21 | 39550 | 2024-12-26 12:50 | -9300 | S.S. ENTERPRISES
OHWT MS Cover (Labour + Material) | N/C | N/C | S.S. ENTERPRISES | 71 | 2024-12-18 | G1 BLDG OHW TANK MS COVER & M.S RAILING (M+L) | 2 | 2325 | 0 | 4650 | 0 | 2024-12-21 10:50 | 100% COMPLETION | 100 | G1 BLDG OHW TANK MS COVER & M.S RAILING (M+L) | 738 | 2024-12-21 | 32920 | 2024-12-26 12:50 | -28270 | S.S. ENTERPRISES
OHWT MS Railing (Mat. + Lab.) | N/C | N/C | S.S. ENTERPRISES | 71 | 2024-12-18 | G1 BLDG OHW TANK MS COVER & M.S RAILING (M+L) | 257 | 110 | 0 | 28270 | 0 | 2024-12-21 10:50 | 100% COMPLETION | 100 | G1 BLDG OHW TANK MS COVER & M.S RAILING (M+L) | 738 | 2024-12-21 | 32920 | 2024-12-26 12:50 | -4650 | S.S. ENTERPRISES
PARKING YELLOW PAINT | N/C | N/C | Mohammed Sameer Mohammed Shakhur Shaikh | 72 | 2024-12-18 | PODIUM PARKING INDENTIFICATION-YELLW MARK PAINT (M+L) | 1860 | 15 | 0 | 27900 | 0 | 2024-12-21 10:34 | 100% COMPLETION | 100 | PODIUM PARKING YELLOW PAINT MARK | 735 | 2024-12-21 | 27900 | 2024-12-26 12:52 | 0 | Mohammed Sameer Mohammed Shakhur Shaikh
Chamber 1.5 x 1.5 ft Drainage | N/C | N/C | SOMNATH KALYAN TAPKIR | 73 | 2024-12-21 | E1 BLDG Under Ground Plumbing Labour | 3 | 1300 | 0 | 3900 | 0 | 2025-01-06 15:55 | 100% COMPLETION | 100 | Against Bill no 03 | 861 | 2025-01-06 | 10014 | 2025-01-09 10:21 | -6114 | SOMNATH KALYAN TAPKIR
Chamber 1.5 x 1.5 ft Electrical | N/C | N/C | SOMNATH KALYAN TAPKIR | 73 | 2024-12-21 | E1 BLDG Under Ground Plumbing Labour | 2 | 1200 | 0 | 2400 | 0 | 2025-01-06 15:55 | 100% COMPLETION | 100 | Against Bill no 03 | 861 | 2025-01-06 | 10014 | 2025-01-09 10:21 | -7614 | SOMNATH KALYAN TAPKIR
Chamber 2 X 2 ft Drainage | N/C | N/C | SOMNATH KALYAN TAPKIR | 73 | 2024-12-21 | E1 BLDG Under Ground Plumbing Labour | 2 | 1650 | 0 | 3300 | 0 | 2025-01-06 15:55 | 100% COMPLETION | 100 | Against Bill no 03 | 861 | 2025-01-06 | 10014 | 2025-01-09 10:21 | -6714 | SOMNATH KALYAN TAPKIR
PVC Line 6 inch | N/C | N/C | SOMNATH KALYAN TAPKIR | 73 | 2024-12-21 | E1 BLDG Under Ground Plumbing Labour | 23 | 8 | 0 | 184 | 0 | 2025-01-06 15:55 | 100% COMPLETION | 100 | Against Bill no 03 | 861 | 2025-01-06 | 10014 | 2025-01-09 10:21 | -9830 | SOMNATH KALYAN TAPKIR
PVC Line 8 inch | N/C | N/C | SOMNATH KALYAN TAPKIR | 73 | 2024-12-21 | E1 BLDG Under Ground Plumbing Labour | 23 | 10 | 0 | 230 | 0 | 2025-01-06 15:55 | 100% COMPLETION | 100 | Against Bill no 03 | 861 | 2025-01-06 | 10014 | 2025-01-09 10:21 | -9784 | SOMNATH KALYAN TAPKIR
Chamber 2 X 2 ft Drainage | N/C | N/C | SOMNATH KALYAN TAPKIR | 73 | 2024-12-21 | E1 BLDG Under Ground Plumbing Labour | 2 | 1650 | 0 | 3300 | 0 | 2025-01-03 11:58 | 100% COMPLETION | 100 | Against Bill no 1 | 830 | 2025-01-03 | 54608 | 2025-01-06 14:48 | -51308 | SOMNATH KALYAN TAPKIR
Chamber 2 x 3 ft Drainage | N/C | N/C | SOMNATH KALYAN TAPKIR | 73 | 2024-12-21 | E1 BLDG Under Ground Plumbing Labour | 9 | 2100 | 0 | 18900 | 0 | 2025-01-03 11:58 | 100% COMPLETION | 100 | Against Bill no 1 | 830 | 2025-01-03 | 54608 | 2025-01-06 14:48 | -35708 | SOMNATH KALYAN TAPKIR
Chamber 2 x 3 ft Electrical | N/C | N/C | SOMNATH KALYAN TAPKIR | 73 | 2024-12-21 | E1 BLDG Under Ground Plumbing Labour | 4 | 1900 | 0 | 7600 | 0 | 2025-01-03 11:58 | 100% COMPLETION | 100 | Against Bill no 1 | 830 | 2025-01-03 | 54608 | 2025-01-06 14:48 | -47008 | SOMNATH KALYAN TAPKIR
PVC Line 6 inch | N/C | N/C | SOMNATH KALYAN TAPKIR | 73 | 2024-12-21 | E1 BLDG Under Ground Plumbing Labour | 56 | 8 | 0 | 448 | 0 | 2025-01-03 11:58 | 100% COMPLETION | 100 |  | 830 | 2025-01-03 | 54608 | 2025-01-06 14:48 | -54160 | SOMNATH KALYAN TAPKIR
PVC Line 8 inch | N/C | N/C | SOMNATH KALYAN TAPKIR | 73 | 2024-12-21 | E1 BLDG Under Ground Plumbing Labour | 269 | 10 | 0 | 2690 | 0 | 2025-01-03 11:58 | 100% COMPLETION | 100 | Against Bill no 1 | 830 | 2025-01-03 | 54608 | 2025-01-06 14:48 | -51918 | SOMNATH KALYAN TAPKIR
RCC line 10-inch Drainage Line | N/C | N/C | SOMNATH KALYAN TAPKIR | 73 | 2024-12-21 | E1 BLDG Under Ground Plumbing Labour | 250 | 52 | 0 | 13000 | 0 | 2025-01-03 11:58 | 100% COMPLETION | 100 | Against Bill no 1 | 830 | 2025-01-03 | 54608 | 2025-01-06 14:48 | -41608 | SOMNATH KALYAN TAPKIR
RCC line 12-inch Drainage Line | N/C | N/C | SOMNATH KALYAN TAPKIR | 73 | 2024-12-21 | E1 BLDG Under Ground Plumbing Labour | 132 | 55 | 0 | 7260 | 0 | 2025-01-03 11:58 | 100% COMPLETION | 100 | Against Bill no 1 | 830 | 2025-01-03 | 54608 | 2025-01-06 14:48 | -47348 | SOMNATH KALYAN TAPKIR
RCC line 8-inch Drainage Line | N/C | N/C | SOMNATH KALYAN TAPKIR | 73 | 2024-12-21 | E1 BLDG Under Ground Plumbing Labour | 47 | 30 | 0 | 1410 | 0 | 2025-01-03 11:58 | 100% COMPLETION | 100 | Against Bill no 1 | 830 | 2025-01-03 | 54608 | 2025-01-06 14:48 | -53198 | SOMNATH KALYAN TAPKIR
Chamber 2 X 2 ft Drainage | N/C | N/C | SOMNATH KALYAN TAPKIR | 73 | 2024-12-21 | E1 BLDG Under Ground Plumbing Labour | 2 | 1650 | 0 | 3300 | 0 | 2025-01-03 12:23 | 100% COMPLETION | 100 | Against Bill no 2 Rainwater Inlet / Outlet chamber | 831 | 2025-01-03 | 10300 | 2025-01-06 14:48 | -7000 | SOMNATH KALYAN TAPKIR
Rainwater Harvesting Chamber Making | N/C | N/C | SOMNATH KALYAN TAPKIR | 73 | 2024-12-21 | E1 BLDG Under Ground Plumbing Labour | 1 | 7000 | 0 | 7000 | 0 | 2025-01-03 12:23 | 100% COMPLETION | 100 | Against Bill no 2 Rainwater Inlet / Outlet chamber | 831 | 2025-01-03 | 10300 | 2025-01-06 14:48 | -3300 | SOMNATH KALYAN TAPKIR
SLAB PIPING MATERIAL | N/C | N/C | SUYASH ELECTRIC COMPANY | 75 | 2024-12-25 | E1 Building Electrical Work 7th, 8th and 9th Floor | 3 | 82292.47 | 0 | 246877.41 | 44437.94 | 2025-01-21 17:07 | 100% COMPLETION | 100 | E1 Building Electrical Work 7th, 8th and 9th Floor-done | 1001 | 2025-01-21 | 246877.41 | 2025-01-22 13:51 | 0 | SUYASH ELECTRIC COMPANY
SLAB PIPING LABOUR | N/C | N/C | SUYASH ELECTRIC COMPANY | 75 | 2024-12-25 | E1 Building Electrical Work 7th, 8th and 9th Floor | 3 | 31050 | 0 | 93150 | 0 | 2025-01-21 17:09 | 100% COMPLETION | 100 | E1 Building Electrical Work 7th, 8th and 9th Floor-done | 1002 | 2025-01-21 | 93150 | 2025-01-22 13:51 | 0 | SUYASH ENTERPRISES
SLAB PIPING MATERIAL | N/C | N/C | SUYASH ELECTRIC COMPANY | 75 | 2024-12-25 | E1 Building Electrical work1ST, 2ND AND 3RD FLOOR | 3 | 82292.47 | 0 | 246877.41 | 44437.94 | 2024-12-27 18:04 | 100% COMPLETION | 100 | Against Bill no 88 | 785 | 2024-12-27 | 493754.82 | 2025-01-01 11:00 | -246877.41 | SUYASH ELECTRIC COMPANY
SLAB PIPING MATERIAL | N/C | N/C | SUYASH ELECTRIC COMPANY | 75 | 2024-12-25 | E1 Building Electrical Work 4th,5th and 6th Floor | 3 | 82292.47 | 0 | 246877.41 | 44437.94 | 2024-12-27 18:04 | 100% COMPLETION | 100 | Against Bill no 88 | 785 | 2024-12-27 | 493754.82 | 2025-01-01 11:00 | -246877.41 | SUYASH ELECTRIC COMPANY
SLAB PIPING LABOUR | N/C | N/C | SUYASH ELECTRIC COMPANY | 75 | 2024-12-25 | E1 Building Electrical work1ST, 2ND AND 3RD FLOOR | 3 | 31050 | 0 | 93150 | 0 | 2024-12-27 18:14 | 100% COMPLETION | 100 |  | 786 | 2024-12-27 | 186300 | 2025-01-01 11:02 | -93150 | SUYASH ENTERPRISES
SLAB PIPING LABOUR | N/C | N/C | SUYASH ELECTRIC COMPANY | 75 | 2024-12-25 | E1 Building Electrical Work 4th,5th and 6th Floor | 3 | 31050 | 0 | 93150 | 0 | 2024-12-27 18:14 | 100% COMPLETION | 100 |  | 786 | 2024-12-27 | 186300 | 2025-01-01 11:02 | -93150 | SUYASH ENTERPRISES
Gardener | N/C | N/C | SWARA MANPOWER SERVICES | 76 | 2024-12-26 | DEVELPEMENT-HOUSE KEEPING & GARDEN MAINTANANCE WORK (M+L) | 1 | 2000 | 0 | 2000 | 0 | 2025-01-19 13:37 | 100% COMPLETION | 100 | against bill NO 105 | 953 | 2025-01-19 | 19500 | 2025-01-20 15:25 | -17500 | SWARA MANPOWER SERVICES
Gardening Material | N/C | N/C | SWARA MANPOWER SERVICES | 76 | 2024-12-26 | DEVELPEMENT-HOUSE KEEPING & GARDEN MAINTANANCE WORK (M+L) | 1 | 1500 | 0 | 1500 | 0 | 2025-01-19 13:37 | 100% COMPLETION | 100 | against bill NO 105 | 953 | 2025-01-19 | 19500 | 2025-01-20 15:25 | -18000 | SWARA MANPOWER SERVICES
House Keeping Material (Club house) | N/C | N/C | SWARA MANPOWER SERVICES | 76 | 2024-12-26 | DEVELPEMENT-HOUSE KEEPING & GARDEN MAINTANANCE WORK (M+L) | 1 | 1500 | 0 | 1500 | 0 | 2025-01-19 13:37 | 100% COMPLETION | 100 | against bill NO 105 | 953 | 2025-01-19 | 19500 | 2025-01-20 15:25 | -18000 | SWARA MANPOWER SERVICES
Jents (Club house-House Keeping) | N/C | N/C | SWARA MANPOWER SERVICES | 76 | 2024-12-26 | DEVELPEMENT-HOUSE KEEPING & GARDEN MAINTANANCE WORK (M+L) | 1 | 14500 | 0 | 14500 | 0 | 2025-01-19 13:37 | 100% COMPLETION | 100 | against bill NO 105 | 953 | 2025-01-19 | 19500 | 2025-01-20 15:25 | -5000 | SWARA MANPOWER SERVICES
1/8-Digital print (F/B Printing) | N/C | N/C | KASHINATH CHANDRAKANT MESTRY | 77 | 2024-12-27 | DESTINATION OSTIA SITE - SAFETY SIGNAGE BOARD | 90 | 14.44 | 0 | 1299.6 | 0 | 2025-02-05 16:24 | 100% COMPLETION | 100 | AGAINST BILL no 336 | 1102 | 2025-02-05 | 9425.6 | 1900-01-01 | -8126 | KASHINATH CHANDRAKANT MESTRY
A4-ECO WITH 5MM FOAM SHEET | N/C | N/C | KASHINATH CHANDRAKANT MESTRY | 77 | 2024-12-27 | DESTINATION OSTIA SITE - SAFETY SIGNAGE BOARD | 3 | 80 | 0 | 240 | 0 | 2025-02-05 16:24 | 100% COMPLETION | 100 |  | 1102 | 2025-02-05 | 9425.6 | 1900-01-01 | -9185.6 | KASHINATH CHANDRAKANT MESTRY
FLEX BOARD FOR SAFETY-11'0'' X 1'6'' | N/C | N/C | KASHINATH CHANDRAKANT MESTRY | 77 | 2024-12-27 | DESTINATION OSTIA SITE - SAFETY SIGNAGE BOARD | 1 | 250 | 0 | 250 | 0 | 2025-02-05 16:24 | 100% COMPLETION | 100 |  | 1102 | 2025-02-05 | 9425.6 | 1900-01-01 | -9175.6 | KASHINATH CHANDRAKANT MESTRY
FLEX BOARD FOR SAFETY-2'0'' X 3'0'' | N/C | N/C | KASHINATH CHANDRAKANT MESTRY | 77 | 2024-12-27 | DESTINATION OSTIA SITE - SAFETY SIGNAGE BOARD | 50 | 130 | 0 | 6500 | 0 | 2025-02-05 16:24 | 100% COMPLETION | 100 |  | 1102 | 2025-02-05 | 9425.6 | 1900-01-01 | -2925.6 | KASHINATH CHANDRAKANT MESTRY
FLEX BOARD FOR SAFETY-8'0'' X 2'0'' | N/C | N/C | KASHINATH CHANDRAKANT MESTRY | 77 | 2024-12-27 | DESTINATION OSTIA SITE - SAFETY SIGNAGE BOARD | 2 | 200 | 0 | 400 | 0 | 2025-02-05 16:24 | 100% COMPLETION | 100 |  | 1102 | 2025-02-05 | 9425.6 | 1900-01-01 | -9025.6 | KASHINATH CHANDRAKANT MESTRY
FLEX BOARD SAFETY PARK-6'0'' X 8'0'' | N/C | N/C | KASHINATH CHANDRAKANT MESTRY | 77 | 2024-12-27 | DESTINATION OSTIA SITE - SAFETY SIGNAGE BOARD | 1 | 576 | 0 | 576 | 0 | 2025-02-05 16:24 | 100% COMPLETION | 100 |  | 1102 | 2025-02-05 | 9425.6 | 1900-01-01 | -8849.6 | KASHINATH CHANDRAKANT MESTRY
SAFETY FIRST Vny Foam Board 12'' x 18'' | N/C | N/C | KASHINATH CHANDRAKANT MESTRY | 77 | 2024-12-27 | DESTINATION OSTIA SITE - SAFETY SIGNAGE BOARD | 1 | 160 | 0 | 160 | 0 | 2025-02-05 16:24 | 100% COMPLETION | 100 |  | 1102 | 2025-02-05 | 9425.6 | 1900-01-01 | -9265.6 | KASHINATH CHANDRAKANT MESTRY
FC (Developement & House Keeping) | N/C | N/C | SWARA MANPOWER SERVICES | 78 | 2024-12-27 | OSTIA SITE - SALES OFFICE HOUSE KEEPING WORK | 11.1828 | 375 | 0 | 4193.55 | 0 | 2025-01-19 15:20 | 100% COMPLETION | 100 | Against Bill no 110 | 969 | 2025-01-19 | 4193.55 | 2025-01-20 15:25 | 0 | SWARA MANPOWER SERVICES
4_END OF INSTALLATION 10% | N/C | N/C | Schindler India Private Limited | 79 | 2024-12-28 | G1 BLDG LIFT SCHINDLER 8PASS JOB NO 1182068 | 1 | 113813 | 0 | 113813 | 20486.34 | 2024-12-28 15:39 | 100% COMPLETION | 100 | Against Bill no CI2700454364 | 788 | 2024-12-28 | 113813 | 2025-01-03 12:31 | 0 | Schindler India Private Limited
Swimming Pool cleaning work | N/C | N/C | ANOSH WAGHMARE | 8 | 2024-07-06 | HOUSE KEEPING SWIMMING POOL MAINTENANCE WORK | 1 | 8500 | 0 | 8500 | 0 | 2025-01-06 15:53 | 100% COMPLETION | 100 | Against Bill no 12 | 860 | 2025-01-06 | 8500 | 2025-01-09 10:21 | 0 | ANOSH WAGHMARE
Swimming Pool cleaning work | N/C | N/C | ANOSH WAGHMARE | 8 | 2024-07-06 | HOUSE KEEPING SWIMMING POOL MAINTENANCE WORK | 1 | 8500 | 0 | 8500 | 0 | 2025-02-04 15:21 | 100% COMPLETION | 100 | HOUSE KEEPING SWIMMING POOL MAINTENANCE WORK-JAN 2025 | 1063 | 2025-02-04 | 8500 | 2025-02-05 14:29 | 0 | ANOSH WAGHMARE
Swimming Pool cleaning work | N/C | N/C | ANOSH WAGHMARE | 8 | 2024-07-06 | HOUSE KEEPING SWIMMING POOL MAINTENANCE WORK | 1 | 8500 | 0 | 8500 | 0 | 2024-08-05 10:55 | 100% COMPLETION | 100 | Bill For July 2024 | 93 | 2024-08-05 | 8500 | 2024-08-06 15:18 | 0 | ANOSH WAGHMARE
Swimming Pool cleaning work | N/C | N/C | ANOSH WAGHMARE | 8 | 2024-07-06 | HOUSE KEEPING SWIMMING POOL MAINTENANCE WORK | 1 | 8500 | 0 | 8500 | 0 | 2024-10-05 19:01 | 100% COMPLETION | 100 | AGAINST BILL NO 9 FOR SEPT 24 | 396 | 2024-10-05 | 8500 | 2024-12-20 14:13 | 0 | ANOSH WAGHMARE
Swimming Pool cleaning work | N/C | N/C | ANOSH WAGHMARE | 8 | 2024-07-06 | HOUSE KEEPING SWIMMING POOL MAINTENANCE WORK | 1 | 8500 | 0 | 8500 | 0 | 2024-09-09 14:28 | 100% COMPLETION | 100 | Work Done For The Month of Aug 2024 | 258 | 2024-09-09 | 8500 | 2024-12-20 14:12 | 0 | ANOSH WAGHMARE
Swimming Pool cleaning work | N/C | N/C | ANOSH WAGHMARE | 8 | 2024-07-06 | HOUSE KEEPING SWIMMING POOL MAINTENANCE WORK | 1 | 8500 | 0 | 8500 | 0 | 2024-12-09 16:42 | 100% COMPLETION | 100 | Swimming Pool cleaning work-FOR NOV 2024 | 658 | 2024-12-09 | 8500 | 2024-12-20 14:13 | 0 | ANOSH WAGHMARE
4_END OF INSTALLATION-10% | N/C | N/C | Schindler India Private Limited | 80 | 2024-12-28 | F1 BUILDING LIFT-1 8PASS JOB NO 11820671 | 1 | 118898.306 | 0 | 118898.306 | 21401.7 | 2025-01-07 09:58 | 100% COMPLETION | 100 | Against Bill no C12700454537 | 867 | 2025-01-07 | 118898.31 | 2025-01-09 10:22 | -0.004 | Schindler India Private Limited
PAVING BLOCK FIXING | N/C | N/C | YANKAPPA RATHODAM | 81 | 2025-01-03 | PODIUM PAVING BLOCK FIXING | 624 | 12 | 0 | 7488 | 0 | 2025-01-19 16:22 | 100% COMPLETION | 100 | Against Bill no 2 | 986 | 2025-01-19 | 19296 | 2025-01-20 14:58 | -11808 | YANKAPPA RATHODAM
PAVING BLOCK FIXING | N/C | N/C | YANKAPPA RATHODAM | 81 | 2025-01-03 | PODIUM PAVING BLOCK FIXING | 984 | 12 | 0 | 11808 | 0 | 2025-01-19 16:22 | 100% COMPLETION | 100 | Against Bill no 2 | 986 | 2025-01-19 | 19296 | 2025-01-20 14:58 | -7488 | YANKAPPA RATHODAM
PAVING BLOCK FIXING | N/C | N/C | YANKAPPA RATHODAM | 81 | 2025-01-03 | PODIUM PAVING BLOCK FIXING | 3876 | 12 | 0 | 46512 | 0 | 2025-01-06 15:50 | 100% COMPLETION | 100 | Against Bill no 1 | 859 | 2025-01-06 | 46512 | 2025-01-09 10:21 | 0 | YANKAPPA RATHODAM
10' X 18" Flex Printing | N/C | N/C | KASHINATH CHANDRAKANT MESTRY | 82 | 2025-01-04 | SITE SAFETY BOARD AND FLEX FOR SAFETY PARK | 1 | 400 | 0 | 400 | 0 | 2025-01-06 15:42 | 100% COMPLETION | 100 | Against Bill 363 | 858 | 2025-01-06 | 16397 | 2025-01-09 10:20 | -15997 | KASHINATH CHANDRAKANT MESTRY
2.5 x 1 ft Vinyl Board Printing | N/C | N/C | KASHINATH CHANDRAKANT MESTRY | 82 | 2025-01-04 | SITE SAFETY BOARD AND FLEX FOR SAFETY PARK | 23 | 270 | 0 | 6210 | 0 | 2025-01-06 15:42 | 100% COMPLETION | 100 | Against Bill 363 | 858 | 2025-01-06 | 16397 | 2025-01-09 10:20 | -10187 | KASHINATH CHANDRAKANT MESTRY
3 x 2 ft Flex Printing with Wooden Frame | N/C | N/C | KASHINATH CHANDRAKANT MESTRY | 82 | 2025-01-04 | SITE SAFETY BOARD AND FLEX FOR SAFETY PARK | 20 | 200 | 0 | 4000 | 0 | 2025-01-06 15:42 | 100% COMPLETION | 100 | Against Bill 363 | 858 | 2025-01-06 | 16397 | 2025-01-09 10:20 | -12397 | KASHINATH CHANDRAKANT MESTRY
5 x 5 ft Flex Printing with wooden frame | N/C | N/C | KASHINATH CHANDRAKANT MESTRY | 82 | 2025-01-04 | SITE SAFETY BOARD AND FLEX FOR SAFETY PARK | 1 | 875 | 0 | 875 | 0 | 2025-01-06 15:42 | 100% COMPLETION | 100 | Against Bill 363 | 858 | 2025-01-06 | 16397 | 2025-01-09 10:20 | -15522 | KASHINATH CHANDRAKANT MESTRY
6 x 4 ft Flex Printing with wooden frame | N/C | N/C | KASHINATH CHANDRAKANT MESTRY | 82 | 2025-01-04 | SITE SAFETY BOARD AND FLEX FOR SAFETY PARK | 2 | 816 | 0 | 1632 | 0 | 2025-01-06 15:42 | 100% COMPLETION | 100 | Against Bill 363 | 858 | 2025-01-06 | 16397 | 2025-01-09 10:20 | -14765 | KASHINATH CHANDRAKANT MESTRY
72" X 12" Vinyl Foam Board Printing | N/C | N/C | KASHINATH CHANDRAKANT MESTRY | 82 | 2025-01-04 | SITE SAFETY BOARD AND FLEX FOR SAFETY PARK | 1 | 1080 | 0 | 1080 | 0 | 2025-01-06 15:42 | 100% COMPLETION | 100 | Against Bill 363 | 858 | 2025-01-06 | 16397 | 2025-01-09 10:20 | -15317 | KASHINATH CHANDRAKANT MESTRY
Name Plate 3mm Vinyl Foam Board | N/C | N/C | KASHINATH CHANDRAKANT MESTRY | 82 | 2025-01-04 | SITE SAFETY BOARD AND FLEX FOR SAFETY PARK | 15 | 100 | 0 | 1500 | 0 | 2025-01-06 15:42 | 100% COMPLETION | 100 | Against Bill 363 | 858 | 2025-01-06 | 16397 | 2025-01-09 10:20 | -14897 | KASHINATH CHANDRAKANT MESTRY
Transport | N/C | N/C | KASHINATH CHANDRAKANT MESTRY | 82 | 2025-01-04 | SITE SAFETY BOARD AND FLEX FOR SAFETY PARK | 1 | 700 | 0 | 700 | 0 | 2025-01-06 15:42 | 100% COMPLETION | 100 | Against Bill 363 | 858 | 2025-01-06 | 16397 | 2025-01-09 10:20 | -15697 | KASHINATH CHANDRAKANT MESTRY
FC | N/C | N/C | OSTIA PROJECT | 84 | 2025-01-04 | DEPT LABOUR CURING WORK & OTHER SITE MISC.WORK | 12.5 | 375 | 0 | 4687.5 | 0 | 2025-01-07 10:35 | 100% COMPLETION | 100 | CURING,CLEANING OF E1,G1 & F1 BLDG-FOR DEC 2024 | 869 | 2025-01-07 | 12287.5 | 2025-01-09 12:45 | -7600 | BALAJI ENTERPRISES
MC | N/C | N/C | OSTIA PROJECT | 84 | 2025-01-04 | DEPT LABOUR CURING WORK & OTHER SITE MISC.WORK | 16 | 475 | 0 | 7600 | 0 | 2025-01-07 10:35 | 100% COMPLETION | 100 | CURING,CLEANING OF E1,G1 & F1 BLDG-FOR DEC 2024 | 869 | 2025-01-07 | 12287.5 | 2025-01-09 12:45 | -4687.5 | BALAJI ENTERPRISES
MC | N/C | N/C | OSTIA PROJECT | 84 | 2025-01-04 | DEPT LABOUR CURING WORK & OTHER SITE MISC.WORK | 10 | 475 | 0 | 4750 | 0 | 2025-01-07 10:54 | 100% COMPLETION | 100 | DEPARTMENTAL WORK-CURING,CLEANING OF E1,G1 & F1 BLDG FOR MONTH DEC-2024 | 871 | 2025-01-07 | 4750 | 2025-01-09 12:47 | 0 | DATTA RAMA DUBBE
MC | N/C | N/C | OSTIA PROJECT | 84 | 2025-01-04 | DEPT LABOUR CURING WORK & OTHER SITE MISC.WORK | 30 | 475 | 0 | 14250 | 0 | 2025-01-07 13:18 | 100% COMPLETION | 100 | DEPARTMENTAL WORK-CURING,CLEANING OF E1,G1 & F1 BLDG FOR MONTH DEC-2024 | 890 | 2025-01-07 | 14250 | 2025-01-09 12:47 | 0 | Prabhuji Kadam
MC | N/C | N/C | OSTIA PROJECT | 84 | 2025-01-04 | DEPT LABOUR CURING WORK & OTHER SITE MISC.WORK | 38.5 | 475 | 0 | 18287.5 | 0 | 2025-01-07 13:20 | 100% COMPLETION | 100 | DEPARTMENTAL WORK-CURING,CLEANING OF E1,G1 & F1 BLDG FOR MONTH DEC-2024 | 891 | 2025-01-07 | 18287.5 | 2025-01-09 12:47 | 0 | Chetan Ingale
FC | N/C | N/C | OSTIA PROJECT | 84 | 2025-01-04 | DEPT LABOUR CURING WORK & OTHER SITE MISC.WORK | 12 | 375 | 0 | 4500 | 0 | 2025-02-04 15:51 | 100% COMPLETION | 100 | DEPT LABOUR CURING WORK & OTHER SITE MISC.WORK-JAN 2025 | 1066 | 2025-02-04 | 10200 | 2025-02-05 14:30 | -5700 | BALAJI ENTERPRISES
MC | N/C | N/C | OSTIA PROJECT | 84 | 2025-01-04 | DEPT LABOUR CURING WORK & OTHER SITE MISC.WORK | 12 | 475 | 0 | 5700 | 0 | 2025-02-04 15:51 | 100% COMPLETION | 100 | DEPT LABOUR CURING WORK & OTHER SITE MISC.WORK-JAN 2025 | 1066 | 2025-02-04 | 10200 | 2025-02-05 14:30 | -4500 | BALAJI ENTERPRISES
MC | N/C | N/C | OSTIA PROJECT | 84 | 2025-01-04 | DEPT LABOUR CURING WORK & OTHER SITE MISC.WORK | 36 | 475 | 0 | 17100 | 0 | 2025-02-04 15:52 | 100% COMPLETION | 100 | DEPT LABOUR CURING WORK & OTHER SITE MISC.WORK-JAN 2025 | 1067 | 2025-02-04 | 17100 | 2025-02-05 14:31 | 0 | Chetan Ingale
100mm Dia GI Pipe "C" Class (6 MTR Long) | N/C | N/C | ENDUMATI FIRE SERVICES | 85 | 2025-01-06 | FIRE FIGHTING SYSTEM Fire Fighting System Work | 54 | 1288 | 0 | 69552 | 12519.36 | 2025-01-20 10:37 | 100% COMPLETION | 100 | Against Bill No EFS/2024-25/183 For F1 and G1 Bldg | 987 | 2025-01-20 | 784704 | 2025-01-20 14:58 | -715152 | ENDUMATI FIRE SERVICES
150mm Dia GI Pipe "C" Class (6 MTR Long) | N/C | N/C | ENDUMATI FIRE SERVICES | 85 | 2025-01-06 | FIRE FIGHTING SYSTEM Fire Fighting System Work | 180 | 1898 | 0 | 341640 | 61495.2 | 2025-01-20 10:37 | 100% COMPLETION | 100 | Against Bill No EFS/2024-25/183 For F1 and G1 Bldg | 987 | 2025-01-20 | 784704 | 2025-01-20 14:58 | -443064 | ENDUMATI FIRE SERVICES
25 mm Dia GI Pipe "C" Class (6 MTR Long) | N/C | N/C | ENDUMATI FIRE SERVICES | 85 | 2025-01-06 | FIRE FIGHTING SYSTEM Fire Fighting System Work | 198 | 262 | 0 | 51876 | 9337.68 | 2025-01-20 10:37 | 100% COMPLETION | 100 | Against Bill No EFS/2024-25/183 For F1 and G1 Bldg | 987 | 2025-01-20 | 784704 | 2025-01-20 14:58 | -732828 | ENDUMATI FIRE SERVICES
32 mm Dia GI Pipe "C" Class (6 MTR Long) | N/C | N/C | ENDUMATI FIRE SERVICES | 85 | 2025-01-06 | FIRE FIGHTING SYSTEM Fire Fighting System Work | 156 | 326 | 0 | 50856 | 9154.08 | 2025-01-20 10:37 | 100% COMPLETION | 100 | Against Bill No EFS/2024-25/183 For F1 and G1 Bldg | 987 | 2025-01-20 | 784704 | 2025-01-20 14:58 | -733848 | ENDUMATI FIRE SERVICES
40mm Dia GI Pipe "C" Class (6 MTR Long) | N/C | N/C | ENDUMATI FIRE SERVICES | 85 | 2025-01-06 | FIRE FIGHTING SYSTEM Fire Fighting System Work | 102 | 410 | 0 | 41820 | 7527.6 | 2025-01-20 10:37 | 100% COMPLETION | 100 | Against Bill No EFS/2024-25/183 For F1 and G1 Bldg | 987 | 2025-01-20 | 784704 | 2025-01-20 14:58 | -742884 | ENDUMATI FIRE SERVICES
65 mm Dia GI Pipe "C" Class (6 MTR Long) | N/C | N/C | ENDUMATI FIRE SERVICES | 85 | 2025-01-06 | FIRE FIGHTING SYSTEM Fire Fighting System Work | 54 | 620 | 0 | 33480 | 6026.4 | 2025-01-20 10:37 | 100% COMPLETION | 100 | Against Bill No EFS/2024-25/183 For F1 and G1 Bldg | 987 | 2025-01-20 | 784704 | 2025-01-20 14:58 | -751224 | ENDUMATI FIRE SERVICES
80mm Dia GI Pipe "C" Class (6 MTR Long) | N/C | N/C | ENDUMATI FIRE SERVICES | 85 | 2025-01-06 | FIRE FIGHTING SYSTEM Fire Fighting System Work | 216 | 905 | 0 | 195480 | 35186.4 | 2025-01-20 10:37 | 100% COMPLETION | 100 | Against Bill No EFS/2024-25/183 For F1 and G1 Bldg | 987 | 2025-01-20 | 784704 | 2025-01-20 14:58 | -589224 | ENDUMATI FIRE SERVICES
BBM WORK-125MM (UPTO BEAM BOTT.) | N/C | N/C | BALAJI ENTERPRISES | 86 | 2025-01-10 | F1 BLDG METER ROOM BBM & PLASTER WORK | 330 | 22 | 0 | 7260 | 0 | 2025-01-20 15:59 | 100% COMPLETION | 100 | Against Bill no1 | 996 | 2025-01-20 | 23820 | 2025-01-22 13:50 | -16560 | BALAJI ENTERPRISES
single coat plaster | N/C | N/C | BALAJI ENTERPRISES | 86 | 2025-01-10 | F1 BLDG METER ROOM BBM & PLASTER WORK | 690 | 24 | 0 | 16560 | 0 | 2025-01-20 15:59 | 100% COMPLETION | 100 | Against Bill no1 | 996 | 2025-01-20 | 23820 | 2025-01-22 13:50 | -7260 | BALAJI ENTERPRISES
MC-LABOUR | N/C | N/C | SOMNATH KALYAN TAPKIR | 88 | 2025-01-13 | H1 & E1 PODIUM-PLUMBING WORK IN DEPARTMENT | 1 | 500 | 0 | 500 | 0 | 2025-02-05 15:27 | 100% COMPLETION | 100 | H1 BLDG TOP TERRACE OUTLET FOR WASHING, F1202 DRAINAGE LINE REMOVING, D BLDG SOLAR LINE CHECKING | 1097 | 2025-02-05 | 2500 | 1900-01-01 | -2000 | SOMNATH KALYAN TAPKIR
SKILLED (MASON) | N/C | N/C | SOMNATH KALYAN TAPKIR | 88 | 2025-01-13 | H1 & E1 PODIUM-PLUMBING WORK IN DEPARTMENT | 2 | 1000 | 0 | 2000 | 0 | 2025-02-05 15:27 | 100% COMPLETION | 100 | H1 BLDG TOP TERRACE OUTLET FOR WASHING, F1202 DRAINAGE LINE REMOVING, D BLDG SOLAR LINE CHECKING | 1097 | 2025-02-05 | 2500 | 1900-01-01 | -500 | SOMNATH KALYAN TAPKIR
ELEVATION BBM PIN | N/C | N/C | MANGAL ENTERPRISES | 89 | 2025-01-15 | F1 BLDG ELEVATION PIN BBM WORK | 328 | 70 | 0 | 22960 | 0 | 2025-01-19 14:59 | 100% COMPLETION | 100 | against bill no 1 | 960 | 2025-01-19 | 22960 | 2025-01-20 14:54 | 0 | MANGAL ENTERPRISES
CONCRETE MIX DESIGN FOR M 30 Grade | N/C | N/C | Durocrete Engineering Services Pvt. Ltd. | 9 | 2024-07-10 | CONCRETE MIX DESIGN | 1 | 6000 | 0 | 6000 | 1080 | 2024-08-26 11:27 | 100% COMPLETION | 100 | Mix Design for M30 Grade of Concrete Received | 178 | 2024-08-26 | 15750 | 2024-08-30 14:21 | -9750 | Durocrete Engineering Services Pvt. Ltd.
Testing Of Material For Mix Design | N/C | N/C | Durocrete Engineering Services Pvt. Ltd. | 9 | 2024-07-10 | CONCRETE MIX DESIGN | 1 | 3750 | 0 | 3750 | 675 | 2024-08-26 11:27 | 100% COMPLETION | 100 | MTC received For Crush Sand and Metal | 178 | 2024-08-26 | 15750 | 2024-08-30 14:21 | -12000 | Durocrete Engineering Services Pvt. Ltd.
Conven. Mix Design M25 (With Admixture) | N/C | N/C | Durocrete Engineering Services Pvt. Ltd. | 9 | 2024-07-10 | CONCRETE MIX DESIGN | 1 | 6000 | 0 | 6000 | 1080 | 2024-08-26 | 100% COMPLETION | 100 |  | 178 | 2024-08-26 | 15750 | 2024-08-30 14:21 | -9750 | Durocrete Engineering Services Pvt. Ltd.
H Frame Scaffolding | N/C | N/C | ARJUN CHOUDHARY | 90 | 2025-01-19 | F1 Bldg ELEVATION H FRAME SCAFFOLDING WORK | 6048 | 12 | 0 | 72576 | 0 | 2025-01-20 12:46 | 100% COMPLETION | 100 | F1 Bldg ELEVATION H FRAME SCAFFOLDING | 991 | 2025-01-20 | 72576 | 2025-01-22 13:50 | 0 | ARJUN CHOUDHARY
Terracotta BRICK CLADDING WORK | N/C | N/C | GOVING PRASAD YADAV | 91 | 2025-01-19 | G1 ELEVATION TERRACOTTA CLADDING WORK labour | 388.97 | 90 | 0 | 35007.3 | 0 | 2025-01-20 12:41 | 100% COMPLETION | 100 | Against Bill no 1 | 990 | 2025-01-20 | 35007.3 | 2025-01-22 13:49 | 0 | GOVING PRASAD YADAV
12mm REBARING with Hilti RE 500 V4 | N/C | N/C | SAMARTH ENTERPRISES | 93 | 2025-01-27 | F1 AXIS BANK SHOP 18 REBARING AND FASTNER | 24 | 270 | 0 | 6480 | 1166.4 | 2025-02-05 18:30 | 100% COMPLETION | 100 | AGAINST BILL no SE/24-25/286 | 1114 | 2025-02-05 | 38490 | 1900-01-01 | -32010 | SAMARTH ENTERPRISES
16mm REBARING with Hilti RE 500 V4 | N/C | N/C | SAMARTH ENTERPRISES | 93 | 2025-01-27 | F1 AXIS BANK SHOP 18 REBARING AND FASTNER | 11 | 570 | 0 | 6270 | 1128.6 | 2025-02-05 18:30 | 100% COMPLETION | 100 | AGAINST BILL no SE/24-25/286 | 1114 | 2025-02-05 | 38490 | 1900-01-01 | -32220 | SAMARTH ENTERPRISES
FASTNER 16mm X 260mm with Hilti RE 500 V4 | N/C | N/C | SAMARTH ENTERPRISES | 93 | 2025-01-27 | F1 AXIS BANK SHOP 18 REBARING AND FASTNER | 22 | 1170 | 0 | 25740 | 4633.2 | 2025-02-05 18:30 | 100% COMPLETION | 100 | AGAINST BILL no SE/24-25/286 | 1114 | 2025-02-05 | 38490 | 1900-01-01 | -12750 | SAMARTH ENTERPRISES
ELECTRICAL WORK. | N/C | N/C | SHRAVAN ELECTRICALS | 94 | 2025-02-03 | F1 BLDG SLAB & WALL PIPING (MAT)-LGF,MEZZ,1ST,2ND,3RD FLOOR | 5 | 73117.57 | 0 | 365587.85 | 65805.82 | 2025-02-05 18:18 | 100% COMPLETION | 100 | Against Bill no 256 | 1112 | 2025-02-05 | 365587.85 | 1900-01-01 | 0 | SHRAVAN ELECTRICALS
ELECTRICAL WORK. | N/C | N/C | NIKITA S. KAKDE | 95 | 2025-02-03 | F1 BLDG SLAB & WALL PIPING (LAB)-LGF,MEZZ,1ST,2ND,3RD FLOOR | 5 | 27043.49 | 0 | 135217.45 | 0 | 2025-02-05 17:34 | 100% COMPLETION | 100 | Against Bill no 2 | 1110 | 2025-02-05 | 135217.45 | 1900-01-01 | 0 | NIKITA S. KAKDE
ELECTRICAL WORK. | N/C | N/C | SHRAVAN ELECTRICALS | 96 | 2025-02-03 | G1 BLDG SLAB & WALL PIPING (MAT)-LGF,MEZZ,1ST,2ND,3RD FLOOR | 5 | 12961.02 | 0 | 64805.1 | 11664.92 | 2025-02-05 18:25 | 100% COMPLETION | 100 | Against Bill no 256 | 1113 | 2025-02-05 | 64805.1 | 1900-01-01 | 0 | SHRAVAN ELECTRICALS
ELECTRICAL WORK. | N/C | N/C | NIKITA S. KAKDE | 97 | 2025-02-03 | G1 BLDG SLAB & WALL PIPING (LAB)-LGF,MEZZ,1ST,2ND,3RD FLOOR | 5 | 4553.87 | 0 | 22769.35 | 0 | 2025-02-05 17:29 | 100% COMPLETION | 100 | Against Bill no 1 | 1108 | 2025-02-05 | 22769.35 | 1900-01-01 | 0 | NIKITA S. KAKDE
TOILET DOOR Wooden SHUTTER FIXING | N/C | N/C | Audumbar D Kangane | 98 | 2025-02-04 | 2) F1 BLDG UG FLOOR Door Fixing Work | 19 | 426.56 | 0 | 8104.64 | 0 | 2025-02-05 15:21 | 100% COMPLETION | 100 | F1 BLDG UG FLOOR Door Fixing Work | 1103 | 2025-02-05 | 24313.92 | 1900-01-01 | -16209.28 | Audumbar D Kangane
TOILET DOOR Wooden SHUTTER FIXING | N/C | N/C | Audumbar D Kangane | 98 | 2025-02-04 | 3) F1 BLDG 1ST FLOOR Door Fixing Work | 19 | 426.56 | 0 | 8104.64 | 0 | 2025-02-05 15:21 | 100% COMPLETION | 100 | F1 BLDG 1ST FLOOR Door Fixing Work | 1103 | 2025-02-05 | 24313.92 | 1900-01-01 | -16209.28 | Audumbar D Kangane
TOILET DOOR Wooden SHUTTER FIXING | N/C | N/C | Audumbar D Kangane | 98 | 2025-02-04 | 4) F1 BLDG 2ND FLOOR Door Fixing Work | 19 | 426.56 | 0 | 8104.64 | 0 | 2025-02-05 15:21 | 100% COMPLETION | 100 | F1 BLDG 2ND FLOOR Door Fixing Work | 1103 | 2025-02-05 | 24313.92 | 1900-01-01 | -16209.28 | Audumbar D Kangane